## Studies
study_id | title | phase | therapeutic_area | indication | portfolio | program | region | study_status | target_enrollment | actual_enrollment | enrollment_plan_percent | planned_fpi_date | planned_lpo_date | countries_count | sites_count | planned_velocity_per_week | actual_velocity_per_week | performance_status | study_stage | project_description | project_priority | project_status | partnership_type | activity_planning_status | project_id | asset_name | asset_number | launch_strategy | temp_budget_id | study_lifecycle_state | priority_study | priority_from | priority_to | not_part_of_uq_objectives | study_short_name | study_description | primary_indication | primary_subject_population | fso_model | fso_model_vendor | study_type | study_designation | business_area | funding_source | demographic_plan_in_scope | sponsor_company | study_sponsor | eligible_for_outsourcing | study_creation_date | country_list | asset_lead | sdl_name | clinical_scientist | medical_director | clinical_development_lead | org_therapy_area | csi_planned | csi_actual | cpa_planned | cpa_actual | fpa_planned | fpa_actual | fsa_planned | fsa_actual | fsfv_planned | fsfv_actual | lsfv_planned | lsfv_actual | lslv_planned | lslv_actual | dbl_planned | dbl_actual | sac_planned | sac_actual | rc_planned | rc_actual | epe_forecast_future_gbp | epe_forecast_this_year_gbp
ST-2024-007 | Efficacy of an Asian Culture-tailored Lung Health (ACT) Intervention on Lung Cancer Screening and Smoking Cessation in Asian Americans | PHASE_II | Oncology | Smoking Cessation | Oncology Portfolio | CRX-255 | Europe | PLANNED | 50 | 0 |  | 2027-01-18 | 2029-07-18 | 6 | 22 | 0.4 | 0 |  | Start-Up | This two-arm stratified randomized clinical trial is to test a counseling and educational program designed to improve lung health through smoking cessation for Chinese and Korean American smokers at high risk for lung cancer. Participants will be randomized into one of two groups: Group A: ACT Lung | High | Active | Commercial | Completed | PRJ-0006 | CRX-255 | ASS-0006 | US First | BUD-0006 | Pre-Activation | TRUE | 2027-01-18 | 2029-07-18 | FALSE | Efficacy of an Asian Culture-tailored Lung Health | This two-arm stratified randomized clinical trial is to test a counseling and educational program designed to improve lung health through smoking cessation for Chinese and Korean American smokers at high risk for lung cancer. Participants will be randomized into one of two groups: Group A: ACT Lung Health Intervention versus Group B: Standard Care. Randomization means a participant is placed into a study group by chance. The research study procedures include screening for eligibility, questionnaires, and saliva tests. It is expected participation in this study will last about 6 months. About 50 participants are expected to take part in this research study. The National Cancer Institute is providing funding for this trial. | Smoking Cessation | Geriatric (65+) | In-House |  | Interventional | Fast Track | Gene Therapy | Licensing Agreement | FALSE | ClinVita Sciences | ClinVita Sciences | FALSE | 2026-07-22 | Chile, Australia, Argentina, India, Japan, Brazil | Dr. Jennifer Harris | Dr. Michelle Taylor | Dr. Michelle Thomas | Dr. William Martin | Dr. David Davis | Oncology & Hematology | 2026-11-19 |  | 2026-11-04 |  | 2026-09-20 |  | 2026-10-20 |  | 2027-01-18 |  | 2029-04-19 |  | 2029-07-18 |  | 2029-09-18 |  | 2029-12-18 |  | 2030-02-18 |  | 7052872 | 1634609
ST-2024-008 | Complete Functional Assessment of Intermediate Coronary Artery Stenosis Before and After Transcatheter Aortic Valve Implantation (TAVI) in Patients With Severe Symptomatic Aortic Valve Stenosis | PHASE_II | Cardiovascular | Coronary Artery Stenosis | Cardiovascular Portfolio | VRD-698 | LATAM | RECRUITING | 50 | 41 | 83.67 | 2021-09-29 | 2025-09-30 | 3 | 10 | 0.2 | 0.2 | AT_RISK | Enrolling | Prospective, single center, open-label study to 1. compare coronary flow reserve (CFR), index of microvascular resistance (IMR), fractional flow reserve (FFR) and resting full cycle ratio (RFR) values before TAVI and 6 months after TAVI 2. correlate testing of microcirculatory function (IMR) with m | High | Active | Consortium | Planned | PRJ-0007 | VRD-698 | ASS-0007 | US & EU Simultaneous | BUD-0007 | Enrollment | TRUE | 2021-09-29 | 2025-09-30 | FALSE | Complete Functional Assessment of Intermediate Cor | Prospective, single center, open-label study to 1. compare coronary flow reserve (CFR), index of microvascular resistance (IMR), fractional flow reserve (FFR) and resting full cycle ratio (RFR) values before TAVI and 6 months after TAVI 2. correlate testing of microcirculatory function (IMR) with measurements of functional testing (FFR and RFR) before and six months after TAVI 3. correlate functional testing (FFR and RFR) with computed tomography (CT) derived fractional flow reserve (CT-FFR) before and six months after TAVI. | Coronary Artery Stenosis | All Ages | Hybrid | Syneos Health | Interventional | Fast Track | Small Molecule | Licensing Agreement | FALSE | Veridon Therapeutics | Veridon Therapeutics | TRUE | 2021-04-02 | China, Belgium, Poland | Dr. Christopher Garcia | Dr. Amanda Garcia | Dr. Robert Moore | Dr. Nicole Garcia | Dr. Michelle Johnson | Cardiovascular & Metabolism | 2021-07-31 | 2021-07-31 | 2021-07-16 | 2021-07-21 | 2021-06-01 | 2021-05-25 | 2021-07-01 | 2021-06-27 | 2021-09-29 | 2021-09-30 | 2025-07-02 |  | 2025-09-30 |  | 2025-11-30 |  | 2026-02-28 |  | 2026-04-30 |  | 8719046 | 3705680
ST-2024-009 | Prasugrel Monotherapy Reduced Dose in Acute and Chronic Coronary Syndrome Patients After Percutaneous Coronary Intervention | PHASE_IV | Cardiovascular | Coronary Arterial Disease (CAD) | Cardiovascular Portfolio | GEN-887 | APAC | RECRUITING | 300 | 14 | 77.78 | 2025-11-13 | 2029-06-13 | 5 | 12 | 1.6 | 0.4 | OFF_TRACK | Enrolling | Rationale: Dual antiplatelet therapy, consisting of aspirin and a P2Y12-inhibitor, reduces the risk of stent-related and non-stent-related ischemic events after percutaneous coronary intervention (PCI). However, this therapy is also associated with a higher risk of bleeding. Given the advances in st | Medium | Active | Commercial | Planned | PRJ-0008 | GEN-887 | ASS-0008 | Global | BUD-0008 | Enrollment | FALSE |  |  | FALSE | Prasugrel Monotherapy Reduced Dose in Acute and Ch | Rationale: Dual antiplatelet therapy, consisting of aspirin and a P2Y12-inhibitor, reduces the risk of stent-related and non-stent-related ischemic events after percutaneous coronary intervention (PCI). However, this therapy is also associated with a higher risk of bleeding. Given the advances in stent technology and pharmacology, it may be possible to treat patients undergoing PCI with low dose prasugrel as single antiplatelet therapy, regardless of medical history, age or body weight. Objective: Assess the feasibility and safety of a single antiplatelet strategy with a reduced dose of prasugrel 5 mg after PCI in acute and chronic coronary syndrome patients (ACS and CCS). Study design: Open-label, single-centre, randomized controlled trial. Study population: Patients undergoing successful PCI due to acute or chronic coronary syndrome. Intervention: A once-daily reduced dose of 5 mg prasugrel for 6 months in CCS patients and for 12 months in ACS patients, preceded by a loading dose of 60 mg prasugrel after PCI, administered without concomitant use of aspirin. Main study parameters/endpoints: The primary endpoint is Net Adverse Clinical Events (NACE), a composite of all-cause death, myocardial infarction, definite stent thrombosis, ischemic stroke, clinically relevant non-major bleeding or major bleeding defined as Bleeding Academic Research Consortium type 2, 3 or 5. | Coronary Arterial Disease (CAD) | Adults (18-75) | Full Service Outsourcing (FSO) | PRA Health Sciences | Interventional | Breakthrough Therapy | Gene Therapy | Partnership | FALSE | MedPath Sciences | MedPath Sciences | TRUE | 2025-05-17 | Sweden, Mexico, Colombia, Taiwan, Mexico | Dr. Christopher Thompson | Dr. Robert Thomas | Dr. James Martin | Dr. Emily Anderson | Dr. Stephanie Williams | Cardiovascular & Metabolism | 2025-09-14 | 2025-09-23 | 2025-08-30 | 2025-09-03 | 2025-07-16 | 2025-07-08 | 2025-08-15 | 2025-08-20 | 2025-11-13 | 2025-11-21 | 2029-03-15 |  | 2029-06-13 |  | 2029-08-13 |  | 2029-11-13 |  | 2030-01-13 |  | 12628175 | 4407667
ST-2024-013 | Validating the Accuracy of Novel, Non-contrast, Cardiac Magnetic resOnaNce Imaging in Defining Myocardial FIbRosis in Patients With End-stage Renal Disease on haeModialysis: the CONFIRM Study | PHASE_II | Cardiovascular | End Stage Kidney Disease | Cardiovascular Portfolio | APX-463 | APAC | PLANNED | 9 | 0 |  | 2026-12-18 | 2029-09-18 | 4 | 8 | 0.1 | 0 |  | Start-Up | Native T1 mapping is a novel, non-contrast, cardiac MRI technique that characterises myocardial tissue by exploiting the different water content of tissues. It correlates well with histo-pathological levels of myocardial fibrosis in diseases of pressure overload such as aortic stenosis. There is gro | Medium | Active | Investigator-Initiated | Planned | PRJ-0012 | APX-463 | ASS-0012 | US & EU Simultaneous | BUD-0012 | Pre-Activation | FALSE |  |  | FALSE | Validating the Accuracy of Novel, Non-contrast, Ca | Native T1 mapping is a novel, non-contrast, cardiac MRI technique that characterises myocardial tissue by exploiting the different water content of tissues. It correlates well with histo-pathological levels of myocardial fibrosis in diseases of pressure overload such as aortic stenosis. There is growing evidence to demonstrate the potential of native T1 mapping as an imaging biomarker of myocardial fibrosis in patients with ESRD; myocardial native T1 values are higher in patients with ESRD than controls, and associate with measures of myocardial strain and circulating markers of cardiac dysfunction. Although native T1 times are affected by water content of tissues, our group has shown that native T1 times are not influenced by clinical changes in fluid status in HD patients and that the inter-study reproducibility and intra- and inter-observer variability of native T1 are outstanding. Native T1 mapping is a promising, non-invasive imaging biomarker of myocardial fibrosis in patients with advanced renal disease. It is essential that the technique is validated against histology before further use in clinical studies. The aim of this study is to directly assess the relationship between native T1 mapping and levels of MF examined at post-mortem in haemodialysis patients. | End Stage Kidney Disease | Pediatric (2-17) | Hybrid | Parexel | Interventional | Breakthrough Therapy | Biologics | Internal R&D | FALSE | OmniPath Pharma | OmniPath Pharma | TRUE | 2026-06-21 | Brazil, Spain, Mexico, Sweden | Dr. David Harris | Dr. David Taylor | Dr. Emily White | Dr. Sarah Brown | Dr. Christopher Harris | Cardiovascular & Metabolism | 2026-10-19 |  | 2026-10-04 |  | 2026-08-20 |  | 2026-09-19 |  | 2026-12-18 |  | 2029-06-20 |  | 2029-09-18 |  | 2029-11-18 |  | 2030-02-18 |  | 2030-04-18 |  | 5773196 | 2496247
ST-2024-011 | Point-of-care Echocardiogram (POCUS) Guided Resuscitation Versus Conventional Goal- Directed Therapy in the Management of Cirrhosis With Severe Sepsis or Septic Shock: A Randomised Controlled Trial | PHASE_II | Cardiovascular | Cirrhosis, Liver | Cardiovascular Portfolio | MED-892 | MEA | RECRUITING | 140 | 5 | 71.43 | 2026-01-01 | 2028-12-30 | 4 | 17 | 0.9 | 0.2 | OFF_TRACK | Enrolling | * Patients with cirrhosis requiring intensive care for severe sepsis carry a risk of high mortality due to altered hemodynamics with reduced effective arterial volume, portal hypertension, presence of ascites, and risk of complications like acute variceal bleeding (AVB), acute kidney injury (AKI) an | High | Active | Consortium | In Progress | PRJ-0010 | MED-892 | ASS-0010 | EU First | BUD-0010 | Enrollment | TRUE | 2026-01-01 | 2028-12-30 | FALSE | Point-of-care Echocardiogram (POCUS) Guided Resusc | * Patients with cirrhosis requiring intensive care for severe sepsis carry a risk of high mortality due to altered hemodynamics with reduced effective arterial volume, portal hypertension, presence of ascites, and risk of complications like acute variceal bleeding (AVB), acute kidney injury (AKI) and circulatory failure(3-5). The main principles for management of severe sepsis include early recognition, control of the source of infection, appropriate and timely administration of antimicrobial agents, and resuscitation with intravenous fluids +/- vasoactive drugs, if needed (6). * Due to portal hypertension, these patients have a hyperdynamic circulation, increased capillary permeability, splanchnic arteriolar vasodilation, and may have latent cirrhotic cardiomyopathy (CCM) (7). Hence assessment of volume status and cardiac reserve using conventional central venous pressure (CVP) or mean arterial pressure (MAP) remains difficult (8). Although inferior vena cava (IVC) dynamics and IVC collapsibility index are reasonable accurate for ventilated patients, their use in spontaneously breathing subjects or those with tense ascites are not defined(9). Even measures like passive leg raising and Valsalva manoeuvre are difficult to perform in cirrhotic patients with tense ascites. * Early goal directed therapy (EGDT) improved outcomes in a randomized trial in patients with severe sepsis(10). Thereafter EGDT was incorporated into the 6-hour resuscitation bundle of the surviving sepsis campaign guidelines, but did not incorporate patients with cirrhosis(11-13). Following the early EGDT trials, studies focussed choice of resuscitation fluid i.e., albumin versus normal saline or balanced salt solution (BSS), concerns about potential risks of volume overload and pulmonary edema and lack of generalisability in subsequent trials showed that there was no associated survival benefit with an aggressive fluid protocol(14, 15). In the ALBIOS study, 1818 patients with severe sepsis or sept | Cirrhosis, Liver | Adults (18-75) | Hybrid | Parexel | Interventional | Priority Review | Gene Therapy | Partnership | TRUE | PharmaNova Inc | PharmaNova Inc | TRUE | 2025-07-05 | Brazil, United Kingdom, Colombia, Spain | Dr. Michelle Thomas | Dr. Lisa Garcia | Dr. Charles Anderson | Dr. Jessica Jones | Dr. Jennifer Smith | Cardiovascular & Metabolism | 2025-11-02 | 2025-11-11 | 2025-10-18 | 2025-10-18 | 2025-09-03 | 2025-08-24 | 2025-10-03 | 2025-09-29 | 2026-01-01 | 2025-12-26 | 2028-10-01 |  | 2028-12-30 |  | 2029-02-28 |  | 2029-05-30 |  | 2029-07-30 |  | 13290277 | 2567561
ST-2024-019 | Immune System, Inflammation, Migraine - The Role of Cytokines and Regulatory T Lymphocytes in Migraine Pathophysiology | PHASE_II | Neurology | Migraine Disorders | Neurology Portfolio | PHX-851 | MEA | PLANNED | 396 | 0 |  | 2027-01-18 | 2029-03-18 | 6 | 26 | 3.5 | 0 |  | Start-Up | Migraine is the 6th most frequent disease (14% of the population) and the second leading cause of disability worldwide. From puberty and onward, migraine is 2 to 3 times more frequent in women, which also suffer from more severe attacks. Migraine is also up to twice as prevalent in patients sufferin | Low | Active | Consortium | Completed | PRJ-0018 | PHX-851 | ASS-0018 | Global | BUD-0018 | Pre-Activation | FALSE |  |  | FALSE | Immune System, Inflammation, Migraine - The Role o | Migraine is the 6th most frequent disease (14% of the population) and the second leading cause of disability worldwide. From puberty and onward, migraine is 2 to 3 times more frequent in women, which also suffer from more severe attacks. Migraine is also up to twice as prevalent in patients suffering from autoimmune or inflammatory diseases such as multiple sclerosis (MS), rheumatoid arthritis (RA), Crohn disease (CD), systemic lupus erythematosus (SLE) and endometriosis, whereas patients with long standing type 1 diabetes mellitus (T1DM) - an autoimmune but non inflammatory disease - seem to be less affected compared to the general population. Despite the identification of the role of peptides such as CGRP in migraine pathophysiology and the development of targetted anti-CGRP treatments, many patients remain unresponsive and the mechanisms behind migraine are still unclear. The trigemino-vascular system is involved in the perception of migraine pain. Migraine occurs with trigemino-cervical neuron sensitization, leading to peptide secretion (such as CGRP, PACAP-38 and VIP), which induce neurogenic inflammation that is responsible for vasodilation, capillary leakage, oedema and further sensitization of the trigemino-vascular system, leading to amplified perception of migraine pain. CGRP, PACAP-38 and VIP infusions all induce migraine attacks in migraine patients, and only mild or no headache in healthy volunteers. Sex hormones, prolactin and insulin are also involved in migraine pathophysiology, and the immune system, through cytokine production and immune cell dysregulations seems to also play a role in the pathogenesis of migraine. Both are closely related as sex hormone levels may have an influence on the levels of certain immune cell subtypes. Several pro-inflammatory cytokines (tumor necrosis factor (TNF)-alpha, interferon (IFN)-gamma and interleukin (IL)-6) were shown to be elevated in migraine patients but also inflammatory diseases such as MS and endometri | Migraine Disorders | Adults (18+) | Hybrid | Covance | Interventional | Standard | Gene Therapy | Internal R&D | TRUE | OmniPath Pharma | OmniPath Pharma | TRUE | 2026-07-22 | Poland, Australia, Sweden, Taiwan, New Zealand, France | Dr. Christopher Thomas | Dr. Lisa Anderson | Dr. William Miller | Dr. Sarah Smith | Dr. Michael Johnson | Neuroscience & Rare Disease | 2026-11-19 |  | 2026-11-04 |  | 2026-09-20 |  | 2026-10-20 |  | 2027-01-18 |  | 2028-12-18 |  | 2029-03-18 |  | 2029-05-18 |  | 2029-08-18 |  | 2029-10-18 |  | 9757117 | 3810803
ST-2024-017 | E-Tailored Pain Management Support for Dementia Family Caregivers | PHASE_II | Neurology | Care Giving Burden | Neurology Portfolio | VRD-384 | MEA | RECRUITING | 60 | 9 | 64.29 | 2025-05-22 | 2028-04-22 | 3 | 9 | 0.4 | 0.2 | OFF_TRACK | Enrolling | This randomized controlled trial will assess the feasibility, usability, and preliminary efficacy of the Pain Control Enhancement App (PACE-app), a web-based intervention designed to support family caregivers of persons with dementia in managing pain. The trial will also explore mechanisms through w | Medium | Active | Academic | Planned | PRJ-0016 | VRD-384 | ASS-0016 | EU First | BUD-0016 | Enrollment | FALSE |  |  | FALSE | E-Tailored Pain Management Support for Dementia Fa | This randomized controlled trial will assess the feasibility, usability, and preliminary efficacy of the Pain Control Enhancement App (PACE-app), a web-based intervention designed to support family caregivers of persons with dementia in managing pain. The trial will also explore mechanisms through which the PACE-app may affect caregiver and care recipient outcomes. Uncontrolled pain is common in people with dementia and presents unique challenges for caregivers, particularly those with limited access to specialized healthcare services. Family caregivers often lack adequate knowledge, skills, and support to manage pain effectively, contributing to suboptimal outcomes for both caregivers and care recipients. The PACE-app provides tailored, technology-based pain management support that includes: Screening of caregiver-specific challenges in pain management; Personalized pain management strategies based on the screening results; Communication tools to facilitate interactions with healthcare providers; A digital pain diary for tracking care recipients' pain experiences. A total of 60 family caregivers of people with dementia and chronic pain will be randomized 1:1 to either the PACE-app intervention group or a usual-care control group. Participants in the intervention arm will use the app for 1 month and complete outcome assessments at baseline, 1 month (post-intervention), and 2 months (follow-up). Participants in the control arm will continue their usual caregiving practices and complete assessments on the same schedule. Primary outcomes include feasibility (recruitment, retention, adherence to study protocol) and acceptability (measured by app usage analytics and qualitative interviews). Secondary outcomes include changes in caregiver self-efficacy in pain management, adherence to prescribed pain treatments, caregiver burden, stress, depression, and communication with healthcare providers. The study will also examine potential mediators (caregiver knowledge, c | Care Giving Burden | Adults (18-75) | Full Service Outsourcing (FSO) | Syneos Health | Interventional | Standard | Small Molecule | Partnership | TRUE | Veridon Therapeutics | Veridon Therapeutics | TRUE | 2024-11-23 | Denmark, Germany, Switzerland | Dr. Sarah Brown | Dr. Stephanie Garcia | Dr. Jennifer Anderson | Dr. Michelle Garcia | Dr. Christopher Thomas | Neuroscience & Rare Disease | 2025-03-23 | 2025-05-12 | 2025-03-08 | 2025-05-01 | 2025-01-22 | 2025-02-26 | 2025-02-21 | 2025-04-04 | 2025-05-22 | 2025-07-02 | 2028-01-23 |  | 2028-04-22 |  | 2028-06-22 |  | 2028-09-22 |  | 2028-11-22 |  | 5593137 | 2071249
ST-2025-021 | Autoreactive Anti-Ro/SSA IgE To Determine Primary SjögRen's Syndrome's Disease Activity | PHASE_II | Immunology | Primary Sjögren's Syndrome | Immunology Portfolio | GEN-769 | APAC | RECRUITING | 185 | 185 | 102.21 | 2018-03-27 | 2020-12-27 | 5 | 25 | 1.3 | 0.4 | ON_TRACK | Enrolling | Primary Sjögren's syndrome (pSS) can affect various organs, sometimes leads to life-threatening conditions and is always responsible for a decreased quality of life. Its evolution is chronic, with flares and relapses, and the need for reliable biomarkers to be carried out routinely is major in patie | High | Active | Commercial | In Progress | PRJ-0020 | GEN-769 | ASS-0020 | US & EU Simultaneous | BUD-0020 | Enrollment | TRUE | 2018-03-27 | 2020-12-27 | FALSE | Autoreactive Anti-Ro/SSA IgE To Determine Primary | Primary Sjögren's syndrome (pSS) can affect various organs, sometimes leads to life-threatening conditions and is always responsible for a decreased quality of life. Its evolution is chronic, with flares and relapses, and the need for reliable biomarkers to be carried out routinely is major in patients' follow-up. Because of the existence of autoreactive immunoglobulins E (IgE) in autoimmune diseases, the recently described role for anti-Ro/SSA antibodies in inducing interferon alpha (IFNα) signaling and the specific pharmacologic properties of IgE, anti-Ro/SSA IgE should be an interesting biomarker to determine pSS's activity. The aim of the study is to evaluate whether the proportion of anti-Ro/SSA IgE positive patients is higher in patients with active disease (i.e. Eular Sjögren Syndrome Disease Activity Index≥ 5). All consecutive patients with pSS (new or already known diagnosis) will be included, Anti-Ro/SSA IgE titers will be determined, the disease's features will be collected (including Eular Sjögren Syndrome Disease Activity Index/Eular Sjogren's Syndrome Patient Reported Index). | Primary Sjögren's Syndrome | Geriatric (65+) | Full Service Outsourcing (FSO) | PPD | Interventional | Fast Track | Gene Therapy | Licensing Agreement | FALSE | OmniPath Pharma | OmniPath Pharma | TRUE | 2017-09-28 | Chile, Switzerland, Turkey, Japan, Canada | Dr. Nicole Brown | Dr. Amanda Thompson | Dr. James Wilson | Dr. Jennifer Johnson | Dr. Robert Taylor | Immunology & Inflammation | 2018-01-26 | 2018-01-25 | 2018-01-11 | 2018-01-19 | 2017-11-27 | 2017-11-26 | 2017-12-27 | 2018-01-01 | 2018-03-27 | 2018-04-03 | 2020-09-28 |  | 2020-12-27 |  | 2021-02-27 |  | 2021-05-27 |  | 2021-07-27 |  | 4163229 | 918867
ST-2025-022 | Study on the Safety of Administering Isoniazid to Systemic Lupus Erythematosus Patients to Prevent Tuberculosis | PHASE_II | Immunology | Tuberculosis | Immunology Portfolio | APX-521 | North America | RECRUITING | 60 | 60 | 96.55 | 2022-08-15 | 2025-12-01 | 6 | 23 | 0.3 | 0.3 | ON_TRACK | Enrolling | Systemic Lupus Erythematosus (SLE) is a prototypical systemic autoimmune disease characterized by heterogeneity, multisystem involvement, and production of multiple autoantibodies. Clinical features can vary, from mild skin and joint involvement to severe and life-threatening conditions. The course | Medium | Active | Commercial | Completed | PRJ-0021 | APX-521 | ASS-0021 | Global | BUD-0021 | Enrollment | FALSE |  |  | FALSE | Study on the Safety of Administering Isoniazid to | Systemic Lupus Erythematosus (SLE) is a prototypical systemic autoimmune disease characterized by heterogeneity, multisystem involvement, and production of multiple autoantibodies. Clinical features can vary, from mild skin and joint involvement to severe and life-threatening conditions. The course of lupus is highly variable in the form of relapses and remissions, with mild and severe forms that can be life-threatening. Treatments for SLE includes steroids and immunosuppressants to control disease activity. Patients with lupus are more susceptible to infections, in addition to being immunocompromised, and due to the administration of corticosteroid and cytotoxic drugs. The presence of these infections is a cause of death in lupus disease in addition to the activity of the disease itself, especially in Asia-Pacific countries. One infection that often occurs in lupus is Tuberculosis (TB). Tuberculosis is still a problem especially in the Asian region, and Indonesia ranks 2nd with the most cases after India according to World Health Organization in 2019. TB infection is found in 10-11.4% of SLE patients in Asia. The incidence of TB in SLE is reported to range from 150/100,000 patients per year in Turkey to 2,450/100,000 patients per year in India. The annual risk of TB in SLE patients is higher than the normal population. Registry data at Hasan Sadikin Hospital Bandung showed that 11.4% or 93 out of 813 SLE patients were infected with TB after being diagnosed with SLE. Risk factors for increased TB infection in SLE patients, in addition to SLE disease activity itself (SLEDAI score \>12), renal involvement, lymphopenia, and cumulative dose of steroids used by the patient, are also due to long duration of illness and previous history of TB. Tuberculosis is also one of the infections that cause death in SLE patients. Mortality from TB in Asian countries ranged from 5-31%. A study in the Philippines found that 14.8% of SLE patients with TB died, those who died had dis | Tuberculosis | Adults (18+) | In-House |  | Interventional | Fast Track | Biologics | Internal R&D | FALSE | ApexBio Research | ApexBio Research | FALSE | 2022-02-16 | Japan, Italy, Saudi Arabia, Singapore, Belgium, China | Dr. Sarah Harris | Dr. Stephanie Thompson | Dr. Stephanie Wilson | Dr. James Martin | Dr. James Taylor | Immunology & Inflammation | 2022-06-16 | 2022-06-10 | 2022-06-01 | 2022-05-23 | 2022-04-17 | 2022-04-25 | 2022-05-17 | 2022-05-18 | 2022-08-15 | 2022-08-16 | 2025-09-02 |  | 2025-12-01 |  | 2026-02-01 |  | 2026-05-01 |  | 2026-07-01 |  | 12730931 | 3719737
ST-2025-025 | Clinical Study on Evaluating the Efficacy and Safety of IM19 CAR-T Cell Therapy in Patients With Refractory Systemic Lupus Erythematosus | PHASE_II | Immunology | Refractory Systemic Lupus Erythematosus | Immunology Portfolio | MED-158 | MEA | PLANNED | 6 | 0 |  | 2026-09-18 | 2029-06-18 | 8 | 37 | 0 | 0 |  | Start-Up | The study is a single-arm, open-label clinical trial intended to recruit 6 refractory SLE subjects who meet the inclusion and exclusion criteria. The subjects will receive IM19 CAR-T cell infusion therapy at a dose of 1×10\^6/kg or 1×10\^8 CAR-T cells . The primary endpoint is to evaluate the improv | Medium | Active | Consortium | Planned | PRJ-0024 | MED-158 | ASS-0024 | US & EU Simultaneous | BUD-0024 | Pre-Activation | FALSE |  |  | TRUE | Clinical Study on Evaluating the Efficacy and Safe | The study is a single-arm, open-label clinical trial intended to recruit 6 refractory SLE subjects who meet the inclusion and exclusion criteria. The subjects will receive IM19 CAR-T cell infusion therapy at a dose of 1×10\^6/kg or 1×10\^8 CAR-T cells . The primary endpoint is to evaluate the improvement in SLE disease activity (SLEDAI-2K) at 90 days and the occurrence of adverse events related to IM19 CAR-T cell infusion within 28 days post-infusion. Additionally, the long-term efficacy was evaluated, including the improvement of SLEDAI-2K score and achieving lupus low disease activity (LLDAS) at day 180 and day 360, and renal response at day 180 and day 360. The persistence and duration of IM19 CAR-T cells in the peripheral blood of subjects will also be evaluated. The study plan includes five phases: screening phase, cell collection phase, lymphodepletion pretreatment phase, cell infusion phase, and follow-up phase. | Refractory Systemic Lupus Erythematosus | Geriatric (65+) | Hybrid | Covance | Interventional | Fast Track | Small Molecule | Partnership | FALSE | MedPath Sciences | MedPath Sciences | TRUE | 2026-03-22 | Germany, Denmark, Switzerland, Spain, South Africa, Singapore, Mexico, Mexico | Dr. Thomas Garcia | Dr. Emily Harris | Dr. Sarah Martin | Dr. Lisa Smith | Dr. Lisa Davis | Immunology & Inflammation | 2026-07-20 |  | 2026-07-05 |  | 2026-05-21 |  | 2026-06-20 |  | 2026-09-18 |  | 2029-03-20 |  | 2029-06-18 |  | 2029-08-18 |  | 2029-11-18 |  | 2030-01-18 |  | 3934747 | 1336434
ST-2025-031 | A Randomized, Double-Blind, Placebo-controlled, Single- and Multiple-ascending Dose Study to Evaluate the Safety, Tolerability, Pharmacokinetics, Immunogenicity, Pharmacodynamics and Clinical Activity | PHASE_I | Respiratory | Chronic Obstructive Pulmonary Disease (COPD) | Respiratory Portfolio | APX-570 | Europe | PLANNED | 68 | 0 |  | 2027-01-18 | 2029-11-18 | 8 | 34 | 0.5 | 0 |  | Start-Up | The study consists of two parts: * Part A (single dose in HVs in sequential ascending dose cohorts, SAD in HVs part) * Part B (two repeated doses in patients with COPD, MAD in patients part) | High | Active | Investigator-Initiated | In Progress | PRJ-0030 | APX-570 | ASS-0030 | US & EU Simultaneous | BUD-0030 | Pre-Activation | TRUE | 2027-01-18 | 2029-11-18 | FALSE | A Randomized, Double-Blind, Placebo-controlled, Si | The study consists of two parts: * Part A (single dose in HVs in sequential ascending dose cohorts, SAD in HVs part) * Part B (two repeated doses in patients with COPD, MAD in patients part) | Chronic Obstructive Pulmonary Disease (COPD) | Geriatric (65+) | In-House |  | Interventional | Fast Track | Biologics | Partnership | FALSE | Stellara Inc | Stellara Inc | FALSE | 2026-07-22 | South Korea, Colombia, Argentina, Taiwan, Belgium, Poland, Mexico, Singapore | Dr. Charles Williams | Dr. Sarah Smith | Dr. Jennifer Davis | Dr. Emily Brown | Dr. Nicole Martin | Respiratory & Allergy | 2026-11-19 |  | 2026-11-04 |  | 2026-09-20 |  | 2026-10-20 |  | 2027-01-18 |  | 2029-08-20 |  | 2029-11-18 |  | 2030-01-18 |  | 2030-04-18 |  | 2030-06-18 |  | 2549425 | 720633
ST-2025-030 | Expanded Studies of Risk Factors for Pulmonary-, Liver-, and Cardiovascular Disease in the SCAPIS 2 Stockholm Reexamination | PHASE_II | Respiratory | Coronary Artery Disease | Respiratory Portfolio | ZPH-863 | LATAM | RECRUITING | 1400 | 942 | 67.01 | 2024-04-08 | 2026-08-30 | 8 | 25 | 11.2 | 8.6 | OFF_TRACK | Enrolling | The Swedish CArdioPulmonary bioImage Study (SCAPIS) is a unique, large-scale national research initiative involving 30,000 randomly selected individuals aged 50-64, recruited between 2014 and 2018. The study is a collaborative effort among six university hospitals across Sweden. A follow-up study, S | Low | Active | Consortium | In Progress | PRJ-0029 | ZPH-863 | ASS-0029 | Global | BUD-0029 | Enrollment | FALSE |  |  | FALSE | Expanded Studies of Risk Factors for Pulmonary-, L | The Swedish CArdioPulmonary bioImage Study (SCAPIS) is a unique, large-scale national research initiative involving 30,000 randomly selected individuals aged 50-64, recruited between 2014 and 2018. The study is a collaborative effort among six university hospitals across Sweden. A follow-up study, SCAPIS 2, is conducted for half of the original participants. In Stockholm, 2,500 individuals will be re-examined at Danderyd University Hospital and Karolinska Institutet. SCAPIS 2 includes a core set of examinations involving blood sampling, questionnaires, and imaging. In addition to these, complementary local investigations are conducted to enable more detailed research questions. This protocol describes the additional studies conducted in the Stockholm cohort: EXTENDED SAMPLING: Saliva and Blood Samples with Blood Cell Isolation Additional blood samples will be collected to isolate blood cells for detailed immune system profiling, red blood cell function nd for lipid profiles and inflammatory markers. Saliva samples will be analyzed for inflammatory markers and microbial composition. EXTENDED QUESTIONNAIRES: Dyspnea, Sleep, Respiratory Infections, and Dental Health Participants will complete detailed questionnaires covering recent food, drink, and medication intake; oral hygiene; breathing and lung function; sleep quality and daytime somnolence; and history of respiratory infections, including COVID-19. EXTENDED IMAGING AND PHYSIOLOGICAL MEASUREMENTS: These investigations will be conducted during a separate visit, coordinated with the main study, and take approximately one hour. 1. Cardiac Ultrasound and Abdominal Aortic Measurements: cardiac structure and function, as well as the diameter of major arteries (e.g., the thoracic and abdominal aorta). 2. Liver Elastography: An ultrasound-based technique used to assess liver stiffness and fat content. 3. Vascular Stiffness: Blood pressure cuff-based pulse wave analysis with automated stiffness calculation. Photopleth | Coronary Artery Disease | Adults (18-75) | In-House |  | Interventional | Breakthrough Therapy | Gene Therapy | Licensing Agreement | FALSE | Nexagen Pharmaceuticals | Nexagen Pharmaceuticals | FALSE | 2023-10-11 | Colombia, Israel, Spain, Netherlands, France, Saudi Arabia, Taiwan, New Zealand | Dr. Stephanie Wilson | Dr. Thomas Brown | Dr. Charles White | Dr. David Thomas | Dr. Amanda Williams | Respiratory & Allergy | 2024-02-08 | 2024-02-06 | 2024-01-24 | 2024-01-18 | 2023-12-10 | 2023-12-02 | 2024-01-09 | 2024-01-07 | 2024-04-08 | 2024-04-13 | 2026-06-01 |  | 2026-08-30 |  | 2026-10-30 |  | 2027-01-30 |  | 2027-03-30 |  | 11826821 | 4868689
ST-2025-036 | Canadian Observational Study Evaluating the Long-term IMPACT of CFTR (Can-IMPACT CF) | PHASE_II | Rare Disease | Cystic Fibrosis | Rare Disease Portfolio | VRD-673 | Europe | RECRUITING | 500 | 413 | 95.15 | 2021-11-01 | 2027-12-31 | 6 | 22 | 1.6 | 1.7 | ON_TRACK | Enrolling | This observational study intends to investigate health trends and data in cystic fibrosis patients all across Canada that are receiving modulator treatment so researchers can determine if CFTR treatments are effective over a long period of time and if so, which treatments work best for each individu | Low | Active | Commercial | Planned | PRJ-0035 | VRD-673 | ASS-0035 | US First | BUD-0035 | Enrollment | FALSE |  |  | FALSE | Canadian Observational Study Evaluating the Long-t | This observational study intends to investigate health trends and data in cystic fibrosis patients all across Canada that are receiving modulator treatment so researchers can determine if CFTR treatments are effective over a long period of time and if so, which treatments work best for each individual. The study will collect clinical data from routine standard of care, patient reported outcomes via survey data and samples for a biobank. | Cystic Fibrosis | Pediatric (2-17) | Hybrid | Covance | Interventional | Priority Review | Gene Therapy | Internal R&D | FALSE | Stellara Inc | Stellara Inc | TRUE | 2021-05-05 | Denmark, India, Australia, Norway, Mexico, Netherlands | Dr. Nicole Davis | Dr. William Jackson | Dr. Sarah Brown | Dr. Sarah Taylor | Dr. William Moore | Neuroscience & Rare Disease | 2021-09-02 | 2021-08-23 | 2021-08-18 | 2021-08-16 | 2021-07-04 | 2021-07-08 | 2021-08-03 | 2021-07-30 | 2021-11-01 | 2021-10-28 | 2027-10-02 |  | 2027-12-31 |  | 2028-02-28 |  | 2028-05-31 |  | 2028-07-31 |  | 4552366 | 1242169
ST-2025-037 | Exploration and Study on the Identification of Various Pulmonary Diseases Using Volatile Organic Compounds Biomarkers in Human Exhaled Breath | PHASE_II | Rare Disease | Lung Cancer | Rare Disease Portfolio | GEN-899 | LATAM | PLANNED | 10000 | 0 |  | 2026-08-18 | 2028-02-18 | 8 | 24 | 128.2 | 0 |  | Start-Up | This is a prospective, cross-sectional, observational cohort study aimed at recruiting 10,000 participants with multiple pulmonary disease, including lung cancer, lung infection, chronic obstructive pulmonary disease (COPD), bronchitis, pulmonary fibrosis, pulmonary embolism, pulmonary arterial hype | Medium | Active | Commercial | Completed | PRJ-0036 | GEN-899 | ASS-0036 | Global | BUD-0036 | Pre-Activation | FALSE |  |  | FALSE | Exploration and Study on the Identification of Var | This is a prospective, cross-sectional, observational cohort study aimed at recruiting 10,000 participants with multiple pulmonary disease, including lung cancer, lung infection, chronic obstructive pulmonary disease (COPD), bronchitis, pulmonary fibrosis, pulmonary embolism, pulmonary arterial hypertension, tuberculosis, lung abscess, emphysema, radioactive lung injury, cystic fibrosis of the lung, Bronchial Asthma, Bronchiectasis, interstitial lung disease (ILD), preserved ratio impaired spirometry (PRISm) etc . Exhaled breath samples from these participants will be collected and analyzed using Gas chromatography-mass spectrometry(GC-MS) and micro Gas Chromatography-photoionisation detector (μGC-PID) system. Upon obtaining the μGC-PID results, a comprehensive evaluation of the diagnostic capabilities of exhaled breath samples in differentiating various pulmonary diseases will be performed, leveraging clinical diagnostic results, CT examination data, and clinical data. | Lung Cancer | Adults (18+) | Full Service Outsourcing (FSO) | PPD | Interventional | Breakthrough Therapy | Small Molecule | Licensing Agreement | FALSE | Stellara Inc | Stellara Inc | TRUE | 2026-02-19 | Argentina, India, Australia, Mexico, Taiwan, Poland, Canada, Saudi Arabia | Dr. Sarah Thomas | Dr. Christopher Harris | Dr. Daniel Johnson | Dr. Charles White | Dr. James Miller | Neuroscience & Rare Disease | 2026-06-19 |  | 2026-06-04 |  | 2026-04-20 |  | 2026-05-20 |  | 2026-08-18 |  | 2027-11-20 |  | 2028-02-18 |  | 2028-04-18 |  | 2028-07-18 |  | 2028-09-18 |  | 9095006 | 3333547
ST-2024-002 | Phase I/II First-In-Human Open-label Trial to Assess Safety and Efficacy of STX-241 in Participants With Locally Advanced or Metastatic Non-small Cell Lung Cancer (NSCLC) Resistant to EGFR Tyrosine Ki | PHASE_I | Oncology | Non-small Cell Lung Cancer (NSCLC) | Oncology Portfolio | ZPH-505 | LATAM | RECRUITING | 171 | 58 | 78.38 | 2024-09-17 | 2028-05-17 | 5 | 16 | 0.9 | 0.6 | OFF_TRACK | Enrolling | The goal of this First-In-Human (FIH) Phase I/II trial is to establish the safety profile, determine the Recommended Phase II Dose (RP2D), explore the pharmacokinetic (PK) exposure and pharmacodynamic (PD) properties as well as assess the efficacy of STX-241/PFL-241, a mutant selective Central Nervo | High | Active | Investigator-Initiated | In Progress | PRJ-0001 | ZPH-505 | ASS-0001 | US First | BUD-0001 | Enrollment | TRUE | 2024-09-17 | 2028-05-17 | FALSE | Phase I/II First-In-Human Open-label Trial to Asse | The goal of this First-In-Human (FIH) Phase I/II trial is to establish the safety profile, determine the Recommended Phase II Dose (RP2D), explore the pharmacokinetic (PK) exposure and pharmacodynamic (PD) properties as well as assess the efficacy of STX-241/PFL-241, a mutant selective Central Nervous System (CNS)-penetrant fourth generation EGFR TKI, in participants with locally advanced or metastatic NSCLC that progressed during or following third generation EGFR TKI such as osimertinib due to C797X double acquired (secondary) mutations. | Non-small Cell Lung Cancer (NSCLC) | Geriatric (65+) | Hybrid | IQVIA | Interventional | Priority Review | Pharmaceuticals | Internal R&D | TRUE | OmniPath Pharma | OmniPath Pharma | TRUE | 2024-03-21 | Belgium, Australia, Netherlands, Japan, Mexico | Dr. Robert Garcia | Dr. Stephanie Williams | Dr. Charles Jackson | Dr. Christopher Thompson | Dr. William Moore | Oncology & Hematology | 2024-07-19 | 2024-08-24 | 2024-07-04 | 2024-08-15 | 2024-05-20 | 2024-06-25 | 2024-06-19 | 2024-08-03 | 2024-09-17 | 2024-11-03 | 2028-02-17 |  | 2028-05-17 |  | 2028-07-17 |  | 2028-10-17 |  | 2028-12-17 |  | 4559701 | 2198150
ST-2024-003 | Hemithoracic Irradiation With Proton Therapy in Malignant Pleural Mesothelioma | PHASE_II | Oncology | Malignant Pleural Mesothelioma | Oncology Portfolio | OMP-770 | LATAM | RECRUITING | 148 | 49 | 106.52 | 2024-03-28 | 2029-09-30 | 6 | 30 | 0.5 | 0.4 | ON_TRACK | Enrolling | Study design: Randomised phase III clinical trial for patients with unilateral MPM. Primary endpoint: Progression free survival (PFS) and overall survival (OS), defined as the time from randomisation to the date of progression and death from any cause. Secondary Endpoints: Safety and Tolerability, | Low | Active | Academic | Completed | PRJ-0002 | OMP-770 | ASS-0002 | Global | BUD-0002 | Enrollment | FALSE |  |  | FALSE | Hemithoracic Irradiation With Proton Therapy in Ma | Study design: Randomised phase III clinical trial for patients with unilateral MPM. Primary endpoint: Progression free survival (PFS) and overall survival (OS), defined as the time from randomisation to the date of progression and death from any cause. Secondary Endpoints: Safety and Tolerability, Health related Quality of Life (QOL): EuroQoL EQ-5D-3L, Locoregional Control. Randomisation and stratification: 1:1 randomisation. Patients with be stratified for histology (epithelioid versus non-epithelioid), potential PBT centre (UCLH or The Christie) , laterality (left or right sided) and time since diagnosis (\<1 year or \> 1 year) Treatment: Experimental Arm: Patients in the experimental arm will receive PBT to the hemithorax to a dose of 50Gy in 25 fractions with a boost to 60Gy for the visible tumour (gross tumour volume-GTV). Treatment is given daily Monday-Friday over 5 weeks. Following completion of treatment in the experimental arm patients will have 2 years of follow-up from time of randomisation at the local recruiting/referring centre. Control Arm: The patients in the control arm would be under standard of care surveillance i.e. "watch and wait", with no treatment or other intervention. Patients will have 2 years of follow-up from time of randomisation at the local recruiting/referring centre. If the disease progresses, the patient will receive SOC treatment i.e. immunotherapy with nivolumab and ipilimumab, or chemotherapy at the clinician's discretion. Statistical analysis plan: The sample size is 148 patients (74 patients per arm). This is to detect a OS hazard ratio of 0.58, equivalent to an improvement in 2-year OS from 30% to 50%, with 85% power and 5% two-sided alpha. Recruitment to complete in 3 years across 20 UK centres with 2 years of additional follow-up and up to 5% dropout. Interim analyses for OS efficacy will be performed when 50, 75 and 110 patients have been randomised at around 1.5, 2.0 and 2.5 years respectively. Using a fixed-se | Malignant Pleural Mesothelioma | Geriatric (65+) | Full Service Outsourcing (FSO) | PRA Health Sciences | Interventional | Fast Track | Pharmaceuticals | Government Grant | FALSE | ApexBio Research | ApexBio Research | TRUE | 2023-09-30 | South Africa, Norway, Taiwan, Spain, Australia, Japan | Dr. Lisa Miller | Dr. Robert Smith | Dr. Sarah Davis | Dr. Nicole Williams | Dr. Christopher White | Oncology & Hematology | 2024-01-28 | 2024-02-06 | 2024-01-13 | 2024-01-08 | 2023-11-29 | 2023-12-01 | 2023-12-29 | 2024-01-06 | 2024-03-28 | 2024-03-27 | 2029-07-02 |  | 2029-09-30 |  | 2029-11-30 |  | 2030-02-28 |  | 2030-04-30 |  | 12044891 | 3151460
ST-2024-004 | A Prospective Study to Evaluate the Efficacy and Safety of MZL-IPI Risk-adapted Targeted Therapy in Patients With Untreated Marginal Zone B-cell Lymphoma | PHASE_II | Oncology | Marginal Zone Lymphoma(MZL) | Oncology Portfolio | GEN-330 | LATAM | RECRUITING | 145 | 26 | 76.47 | 2025-01-23 | 2028-12-31 | 7 | 27 | 0.7 | 0.3 | OFF_TRACK | Enrolling | Marginal zone lymphoma (MZL) is a common type of indolent lymphoma that originates from the marginal zone of lymphoid follicles. This study aims to evaluate targeted therapy based on the prognostic risk stratification of MZL-IPI in newly diagnosed MZL cases requiring systemic treatment, and provides | Medium | Active | Consortium | In Progress | PRJ-0003 | GEN-330 | ASS-0003 | US & EU Simultaneous | BUD-0003 | Enrollment | FALSE |  |  | TRUE | A Prospective Study to Evaluate the Efficacy and S | Marginal zone lymphoma (MZL) is a common type of indolent lymphoma that originates from the marginal zone of lymphoid follicles. This study aims to evaluate targeted therapy based on the prognostic risk stratification of MZL-IPI in newly diagnosed MZL cases requiring systemic treatment, and provides a basis for precision treatment of MZL. | Marginal Zone Lymphoma(MZL) | Adults (18-75) | In-House |  | Interventional | Priority Review | Biologics | Licensing Agreement | TRUE | PharmaNova Inc | PharmaNova Inc | FALSE | 2024-07-27 | Italy, Singapore, Chile, United Kingdom, Japan, New Zealand, Belgium | Dr. Daniel Jones | Dr. Michael Wilson | Dr. Stephanie Taylor | Dr. Daniel Wilson | Dr. James Anderson | Oncology & Hematology | 2024-11-24 | 2024-11-14 | 2024-11-09 | 2024-11-02 | 2024-09-25 | 2024-09-30 | 2024-10-25 | 2024-11-04 | 2025-01-23 | 2025-02-01 | 2028-10-02 |  | 2028-12-31 |  | 2029-02-28 |  | 2029-05-31 |  | 2029-07-31 |  | 11413424 | 4013620
ST-2024-005 | A Prospective Clinical Study of Hanlikang and BTK Inhibitors in the Treatment of Newly Diagnosed Mantle Cell Lymphoma | PHASE_II | Oncology | Newly Diagnosed Mantle Cell Lymphoma | Oncology Portfolio | PHX-873 | North America | RECRUITING | 100 | 71 | 75.53 | 2022-08-12 | 2026-12-30 | 6 | 20 | 0.4 | 0.4 | OFF_TRACK | Enrolling | An open-label, single-arm, multicenter, prospective clinical study of Hanlikang and BTK inhibitors in the treatment of newly diagnosed mantle cell lymphoma | Medium | Active | Investigator-Initiated | Completed | PRJ-0004 | PHX-873 | ASS-0004 | EU First | BUD-0004 | Enrollment | FALSE |  |  | FALSE | A Prospective Clinical Study of Hanlikang and BTK | An open-label, single-arm, multicenter, prospective clinical study of Hanlikang and BTK inhibitors in the treatment of newly diagnosed mantle cell lymphoma | Newly Diagnosed Mantle Cell Lymphoma | Adults (18-75) | Hybrid | Syneos Health | Interventional | Priority Review | Pharmaceuticals | Internal R&D | TRUE | Astellion Biosciences | Astellion Biosciences | TRUE | 2022-02-13 | New Zealand, Denmark, Germany, Belgium, Taiwan, Mexico | Dr. Jessica Miller | Dr. Robert Wilson | Dr. Jessica Taylor | Dr. Emily Smith | Dr. Nicole White | Oncology & Hematology | 2022-06-13 | 2022-06-22 | 2022-05-29 | 2022-05-24 | 2022-04-14 | 2022-04-08 | 2022-05-14 | 2022-05-05 | 2022-08-12 | 2022-08-04 | 2026-10-01 |  | 2026-12-30 |  | 2027-02-28 |  | 2027-05-30 |  | 2027-07-30 |  | 15516017 | 5780085
ST-2024-006 | A Phase 2 Study of EIK1001 in Combination With Pembrolizumab and Chemotherapy in Patients With Stage 4 Non-Small Cell Lung Cancer | PHASE_II | Oncology | NSCLC | Oncology Portfolio | NXG-810 | Europe | RECRUITING | 70 | 55 | 77.94 | 2024-02-06 | 2025-11-06 | 4 | 17 | 0.8 | 0.5 | OFF_TRACK | Enrolling | This is a multicenter open-label phase 2 trial that aim to assess the safety, tolerability, and efficacy of EIK1001 in combination with standard of care in participants with both confirmed stage 4 squamous and non-squamous NSCLC who have not received prior systemic therapy for the advanced disease. | Medium | Active | Academic | Completed | PRJ-0005 | NXG-810 | ASS-0005 | US & EU Simultaneous | BUD-0005 | Enrollment | FALSE |  |  | FALSE | A Phase 2 Study of EIK1001 in Combination With Pem | This is a multicenter open-label phase 2 trial that aim to assess the safety, tolerability, and efficacy of EIK1001 in combination with standard of care in participants with both confirmed stage 4 squamous and non-squamous NSCLC who have not received prior systemic therapy for the advanced disease. The study includes dose finding and evaluates adverse events and efficacy. | NSCLC | Pediatric (2-17) | In-House |  | Interventional | Fast Track | Pharmaceuticals | Partnership | FALSE | Nexagen Pharmaceuticals | Nexagen Pharmaceuticals | FALSE | 2023-08-10 | Italy, Netherlands, United Kingdom, South Africa | Dr. Jennifer Garcia | Dr. Amanda Thompson | Dr. Lisa Brown | Dr. David Jones | Dr. Lisa Martin | Oncology & Hematology | 2023-12-08 | 2023-12-14 | 2023-11-23 | 2023-11-28 | 2023-10-09 | 2023-10-04 | 2023-11-08 | 2023-11-10 | 2024-02-06 | 2024-02-13 | 2025-08-08 |  | 2025-11-06 |  | 2026-01-06 |  | 2026-04-06 |  | 2026-06-06 |  | 9739961 | 3993914
ST-2024-010 | Responders and Non-responders in the Management of Heart Failure - Significance of Genetic Influence and Identification of Novel Informative Biomarkers | PHASE_II | Cardiovascular | Heart Failure | Cardiovascular Portfolio | APX-926 | APAC | RECRUITING | 5000 | 2480 | 85.91 | 2021-02-17 | 2030-12-31 | 3 | 6 | 9.7 | 9.1 | AT_RISK | Enrolling | The national heart failure quality registry SwedeHF started in 2003. It is the world's largest continuous HF registry enrolling clinician-judged HF (regardless of LVEF) at time of hospital or clinical visit. Eighty variables are entered into an electronic database managed by the Uppsala Clinical Res | Medium | Active | Investigator-Initiated | Completed | PRJ-0009 | APX-926 | ASS-0009 | EU First | BUD-0009 | Enrollment | FALSE |  |  | FALSE | Responders and Non-responders in the Management of | The national heart failure quality registry SwedeHF started in 2003. It is the world's largest continuous HF registry enrolling clinician-judged HF (regardless of LVEF) at time of hospital or clinical visit. Eighty variables are entered into an electronic database managed by the Uppsala Clinical Research Center (UCR). There are \>140,000 registrations from \>110,000 unique patients from 70 hospitals in Sweden. University hospitals in Sweden with access to central biobanking will collect a high-quality biobank linked to SwedeHF consisting of blood plasma, whole blood and urine enabling genetic, proteomic and metabolomic analyses as well as analyses of different biomarkers of interest for HF patients. This will provide unique opportunities for future research within the national SwedeHF registry. | Heart Failure | All Ages | In-House |  | Interventional | Breakthrough Therapy | Small Molecule | Government Grant | FALSE | ClinVita Sciences | ClinVita Sciences | FALSE | 2020-08-21 | United Kingdom, Australia, Turkey | Dr. Emily Brown | Dr. Lisa Thompson | Dr. James Johnson | Dr. James Davis | Dr. Sarah Martin | Cardiovascular & Metabolism | 2020-12-19 | 2020-12-17 | 2020-12-04 | 2020-12-10 | 2020-10-20 | 2020-10-26 | 2020-11-19 | 2020-11-14 | 2021-02-17 | 2021-02-18 | 2030-10-02 |  | 2030-12-31 |  | 2031-02-28 |  | 2031-05-31 |  | 2031-07-31 |  | 9860610 | 4157629
ST-2024-012 | Pacemaker Implantation in Patients With Heart Failure With Preserved Ejection Fraction, Chronotropic Incompetence and Small Ventricular Volume. The SHOP-HF Trial | PHASE_II | Cardiovascular | Heart Failure With Preserved Ejection Fraction | Cardiovascular Portfolio | CRX-750 | North America | RECRUITING | 30 | 17 | 73.91 | 2025-06-17 | 2026-12-17 | 6 | 28 | 0.4 | 0.3 | OFF_TRACK | Enrolling | This study is designed as a multicenter, prospective, controlled, randomized, two-arms, cross-over, two parallel cohorts, efficacy Clinical research with CE-marked medical device . The crossover trial will be performed in a blind fashion, so each participant will be evaluated during both blinded pac | Low | Active | Investigator-Initiated | Completed | PRJ-0011 | CRX-750 | ASS-0011 | EU First | BUD-0011 | Enrollment | FALSE |  |  | FALSE | Pacemaker Implantation in Patients With Heart Fail | This study is designed as a multicenter, prospective, controlled, randomized, two-arms, cross-over, two parallel cohorts, efficacy Clinical research with CE-marked medical device . The crossover trial will be performed in a blind fashion, so each participant will be evaluated during both blinded pacing-on and pacing-off phases, each of which will last 3 months. The population includes patients with the diagnosis of stable HFpEF according to criteria of the European Society of Cardiology and New York Heart Association (NYHA) functional class II-III/IV, left ventricular hypertrophy with small ventricular volume, sinus rhythm with low basal heart rate and chronotropic incompetence (CI). All patients will undergo pacemaker implantation, and computer-generated randomization sequence previously designed will be used to allocate participants (in a 1:1 ratio) to receive: (a) programming of the pacemaker with pacing On followed by pacing Off in two periods of 3 months; or (b) programming of the pacemaker with pacing Off followed by pacing On in two periods of 3 months. The study will be conducted in three centers in Spain. Discounting the time due to staggered entry, the total duration of a patient's follow-up will be 7 months. | Heart Failure With Preserved Ejection Fraction | Adults (18-75) | Full Service Outsourcing (FSO) | IQVIA | Interventional | Fast Track | Pharmaceuticals | Partnership | TRUE | PharmaNova Inc | PharmaNova Inc | TRUE | 2024-12-19 | Japan, Switzerland, Turkey, India, Norway, France | Dr. Charles Johnson | Dr. Jennifer Miller | Dr. Lisa Davis | Dr. David Wilson | Dr. Stephanie Thompson | Cardiovascular & Metabolism | 2025-04-18 | 2025-04-09 | 2025-04-03 | 2025-03-30 | 2025-02-17 | 2025-02-13 | 2025-03-19 | 2025-03-16 | 2025-06-17 | 2025-06-08 | 2026-09-18 |  | 2026-12-17 |  | 2027-02-17 |  | 2027-05-17 |  | 2027-07-17 |  | 9288796 | 2392219
ST-2024-014 | Walking and Thinking - Brain Activity During Complex Walking in Atypical Parkinsonian Syndromes | PHASE_II | Neurology | Gait Disorders, Neurologic | Neurology Portfolio | NXG-793 | APAC | RECRUITING | 30 | 10 | 90.91 | 2025-03-14 | 2027-12-31 | 8 | 20 | 0.2 | 0.1 | AT_RISK | Enrolling | Every-day life means being part of a complex environment and performing complex tasks that usually involve a combination of motor and cognitive skills. However, the process of aging or the sequelae of neurological diseases such as atypical Parkinson's disease (APD) compromises motor-cognitive intera | Medium | Active | Investigator-Initiated | Completed | PRJ-0013 | NXG-793 | ASS-0013 | Global | BUD-0013 | Enrollment | FALSE |  |  | FALSE | Walking and Thinking - Brain Activity During Compl | Every-day life means being part of a complex environment and performing complex tasks that usually involve a combination of motor and cognitive skills. However, the process of aging or the sequelae of neurological diseases such as atypical Parkinson's disease (APD) compromises motor-cognitive interaction necessary for an independent lifestyle. While motor-cognitive performance has been identified as an important goal for sustained health across different clinical populations, little is known about underlying brain function leading to these difficulties and how to best target these motor-cognitive difficulties in the context of rehabilitation and exercise interventions. The challenge of improving treatments of motor-cognitive difficulties (such as dual-tasking and navigation) is daunting, and an important step is arriving at a method that accurately portrays these impairments in an ecologically valid state. The investigators aim therefore to explore brain function during complex walking in healthy and APD by investigating the effects of age and neurological disease on motor-cognitive performance and its neural correlates during three conditions of complex walking (dual-task walking, navigation and a combination of both) using non-invasive measures of brain activity (functional near infrared spectrometry, fNIRS) and advanced gait analysis in real time in older healthy adults and people with APD. | Gait Disorders, Neurologic | Adults (18-75) | In-House |  | Interventional | Fast Track | Biologics | Licensing Agreement | TRUE | Stellara Inc | Stellara Inc | FALSE | 2024-09-15 | United States, South Korea, Mexico, Saudi Arabia, United Kingdom, Germany, Canada, Turkey | Dr. Jennifer Garcia | Dr. Lisa Wilson | Dr. David Brown | Dr. Jennifer Johnson | Dr. Michelle Harris | Neuroscience & Rare Disease | 2025-01-13 | 2025-02-22 | 2024-12-29 | 2025-02-17 | 2024-11-14 | 2024-12-19 | 2024-12-14 | 2025-02-04 | 2025-03-14 | 2025-04-25 | 2027-10-02 |  | 2027-12-31 |  | 2028-02-28 |  | 2028-05-31 |  | 2028-07-31 |  | 18439477 | 4871997
ST-2024-015 | Modification of Threat Interpretation Bias to Reduce Anxiety in Neurodegenerative Movement Disorders (Aim 3) | PHASE_II | Neurology | Huntington Disease | Neurology Portfolio | CRX-271 | North America | RECRUITING | 136 | 15 | 88.24 | 2025-11-20 | 2028-02-20 | 7 | 28 | 1.2 | 0.5 | AT_RISK | Enrolling | The investigators will conduct a pilot randomized controlled trial of the MindTrails-Movement CBM-I app in patients with Huntington's disease and Parkinson's disease (N=136). Participants randomly assigned to the intervention group (N=68) will be asked to download the MindTrails-Movement mobile app | Low | Active | Commercial | Planned | PRJ-0014 | CRX-271 | ASS-0014 | US First | BUD-0014 | Enrollment | FALSE |  |  | TRUE | Modification of Threat Interpretation Bias to Redu | The investigators will conduct a pilot randomized controlled trial of the MindTrails-Movement CBM-I app in patients with Huntington's disease and Parkinson's disease (N=136). Participants randomly assigned to the intervention group (N=68) will be asked to download the MindTrails-Movement mobile app and to complete daily CBM-I training sessions and nightly surveys, in addition to surveys at baseline and every 2 weeks for the duration of the 6-week intervention and at 4-week follow-up (week 10). Participants assigned to the waitlist control group will download a control version of the app without CBM-I training sessions. They will be asked to complete surveys in the app at baseline and every 2 weeks for the duration of the 6-week intervention and at 4-week follow-up (week 10). After 10 weeks, they will be offered the opportunity to access the version of MindTrails-Movement with CBM-I training content. | Huntington Disease | Adults (18+) | Full Service Outsourcing (FSO) | ICON plc | Interventional | Standard | Pharmaceuticals | Licensing Agreement | TRUE | Genetika Therapeutics | Genetika Therapeutics | TRUE | 2025-05-24 | Netherlands, Brazil, Italy, Taiwan, Turkey, Saudi Arabia, New Zealand | Dr. James Jackson | Dr. Daniel Williams | Dr. Emily Wilson | Dr. Robert Williams | Dr. Charles Anderson | Neuroscience & Rare Disease | 2025-09-21 | 2025-10-31 | 2025-09-06 | 2025-10-15 | 2025-07-23 | 2025-08-20 | 2025-08-22 | 2025-09-23 | 2025-11-20 | 2025-12-18 | 2027-11-22 |  | 2028-02-20 |  | 2028-04-20 |  | 2028-07-20 |  | 2028-09-20 |  | 12037286 | 5148503
ST-2024-016 | Strength-Endurance Circuit Training in Parkinson's Disease: Effects on Disease Severity, Physical Performance, Blood Biomarkers and Quality of Life. | PHASE_II | Neurology | Parkinson Disease, Idiopathic | Neurology Portfolio | APX-563 | LATAM | RECRUITING | 90 | 45 | 88.24 | 2025-03-03 | 2027-07-03 | 7 | 22 | 0.7 | 0.7 | AT_RISK | Enrolling | The goal of this clinical trial is to determine whether adding strength training to aerobic training has a comparable or greater effect on the clinical status of Parkinson's disease patients than a standalone aerobic training. \- Does combined strength-endurance circuit training provide added benef | Medium | Active | Academic | In Progress | PRJ-0015 | APX-563 | ASS-0015 | Global | BUD-0015 | Enrollment | FALSE |  |  | FALSE | Strength-Endurance Circuit Training in Parkinson's | The goal of this clinical trial is to determine whether adding strength training to aerobic training has a comparable or greater effect on the clinical status of Parkinson's disease patients than a standalone aerobic training. \- Does combined strength-endurance circuit training provide added benefits to physical performance, disease severity, blood biomarkers, and quality of life in PD patients compared to standalone aerobic training? Participants will: * undergo outcome measurements before and after the 12-week intervention and a 3-month follow-up measurement, * visit the clinic twice a week for 1-hour training sessions. * selected patients will be given a smartwatch with a pedometer that will count their average number of steps before, during and after the training period | Parkinson Disease, Idiopathic | Adults (18-75) | In-House |  | Interventional | Breakthrough Therapy | Small Molecule | Internal R&D | FALSE | Nexagen Pharmaceuticals | Nexagen Pharmaceuticals | FALSE | 2024-09-04 | United States, Brazil, Canada, Belgium, India, Turkey, Australia | Dr. Michelle Thompson | Dr. Michelle Jones | Dr. Emily Johnson | Dr. Christopher Thomas | Dr. Robert Jones | Neuroscience & Rare Disease | 2025-01-02 | 2025-02-26 | 2024-12-18 | 2025-02-04 | 2024-11-03 | 2024-12-19 | 2024-12-03 | 2025-01-20 | 2025-03-03 | 2025-04-17 | 2027-04-04 |  | 2027-07-03 |  | 2027-09-03 |  | 2027-12-03 |  | 2028-02-03 |  | 9437981 | 2740256
ST-2024-018 | Feasibility Study for a Randomised Control Trial for the Acceptability of Exoskeleton Assisted Walking Compared to Standard Exercise Training for Persons With Mobility Issues Due to Multiple Sclerosis | PHASE_II | Neurology | Multiple Sclerosis | Neurology Portfolio | OMP-574 | MEA | RECRUITING | 24 | 24 | 104.35 | 2022-06-23 | 2024-10-30 | 3 | 15 | 0.2 | 0.1 | ON_TRACK | Enrolling | Multiple sclerosis (MS) is a chronic, inflammatory disease of the central nervous system. Lack of physical activity is common in people with MS (pwMS). This can lead to several comorbid conditions such as obesity, metabolic syndrome, osteoporosis, hypertension, diabetes and worse prognosis. An incre | Medium | Active | Consortium | In Progress | PRJ-0017 | OMP-574 | ASS-0017 | Global | BUD-0017 | Enrollment | FALSE |  |  | FALSE | Feasibility Study for a Randomised Control Trial f | Multiple sclerosis (MS) is a chronic, inflammatory disease of the central nervous system. Lack of physical activity is common in people with MS (pwMS). This can lead to several comorbid conditions such as obesity, metabolic syndrome, osteoporosis, hypertension, diabetes and worse prognosis. An increasing number of studies suggest that physical exercise can play an important role in managing symptoms, preventing complications and comorbidities in pwMS, and may possibly be neuroprotective. However, doing exercise can be very challenging for pwMS who have moderate/severe mobility disability and who have problems with walking. In this project, the investigators will explore the use of a powered Exoskeleton as an exercise tool for people with moderate to severe difficulty walking due to MS. Powered Exoskeletons are wearable robots that offer opportunity to persons with lower limb weakness to stand and walk. The Exoskeleton-assisted training provides active training with potentially much less intervention needed from therapists. However, it is not clear whether pwMS can walk with a powered Exoskeleton at speeds and intensities sufficient to positively affect health and fitness outcomes. Thus, in this study, the investigators aim to explore whether using an Exoskeleton will enable people with MS to exercise at a moderate intensity and whether people with MS find this acceptable and safe to do on a regular basis. The investigators will also explore whether training with an Exoskeleton can improve walking. The investigators will train 12 patients with MS to walk with an Exoskeleton twice a week for 8 weeks. The investigators will compare the effects with another group of 12 patients who will do exercises with a fitness instructor twice a week for 8 weeks. The investigators will study whether walking with Exoskeleton is better than fitness training in terms of fitness outcomes, walking and cognitive, psychological factors. | Multiple Sclerosis | Geriatric (65+) | In-House |  | Interventional | Priority Review | Small Molecule | Licensing Agreement | TRUE | ApexBio Research | ApexBio Research | FALSE | 2021-12-25 | Spain, South Africa, Switzerland | Dr. Michael Miller | Dr. Robert Smith | Dr. Robert Jones | Dr. Christopher Moore | Dr. Jessica Jackson | Neuroscience & Rare Disease | 2022-04-24 | 2022-05-01 | 2022-04-09 | 2022-04-09 | 2022-02-23 | 2022-03-03 | 2022-03-25 | 2022-03-22 | 2022-06-23 | 2022-06-18 | 2024-08-01 |  | 2024-10-30 |  | 2024-12-30 |  | 2025-03-30 |  | 2025-05-30 |  | 16565577 | 7700984
ST-2024-020 | A Single-center Clinical Study Evaluating the Safety and Efficacy of CD19 Universal CAR-γδT Cells in Active Systemic Lupus Erythematosus | PHASE_I | Immunology | Systemic Lupus Erythematosus | Immunology Portfolio | VRD-975 | North America | RECRUITING | 15 | 12 | 85.71 | 2024-01-12 | 2026-09-12 | 4 | 17 | 0.1 | 0.1 | AT_RISK | Enrolling | The prognosis of patients with active systemic lupus erythematosus (SLE) remains poor, due to two major therapeutic obstacles: (1) current treatment strategies including glucocorticoids, immunosuppressive agents, biological agents, are still difficult to achieve disease control, making the disease c | Medium | Active | Investigator-Initiated | In Progress | PRJ-0019 | VRD-975 | ASS-0019 | Global | BUD-0019 | Enrollment | FALSE |  |  | TRUE | A Single-center Clinical Study Evaluating the Safe | The prognosis of patients with active systemic lupus erythematosus (SLE) remains poor, due to two major therapeutic obstacles: (1) current treatment strategies including glucocorticoids, immunosuppressive agents, biological agents, are still difficult to achieve disease control, making the disease condition of some patients continue to be active or even worse; (2) some patients are unable to wean themselves off glucocorticoid and face the risk of numerous adverse effects caused by long-term glucocorticoid dependence, such as glucocorticoid-related diabetes, femoral head necrosis, hypertension, stress ulcers, and infection, etc. Therefore, there is a strong unmet clinical need for more effective treatment for patients suffering from active SLE. Several preclinical studies have shown the efficacy of CAR-T cell treatment in SLE. The aim of this study is to investigate the safety, tolerability, preliminary efficacy, pharmacokinetics (PK), and pharmacodynamics (PD) of CD19 Universal CAR-γδT cells therapy in active SLE. Patients with active SLE will be invited to participate in the study, to receive CD19 Universal CAR-γδT cells intravenous infusion and follow-up visits of up to 2 years after enrollment. | Systemic Lupus Erythematosus | Adults (18-75) | In-House |  | Interventional | Breakthrough Therapy | Small Molecule | Licensing Agreement | TRUE | MedPath Sciences | MedPath Sciences | FALSE | 2023-07-16 | Chile, Turkey, Denmark, Saudi Arabia | Dr. Robert Smith | Dr. Stephanie Johnson | Dr. Sarah Martin | Dr. Daniel Johnson | Dr. Stephanie Thompson | Immunology & Inflammation | 2023-11-13 | 2023-11-10 | 2023-10-29 | 2023-10-29 | 2023-09-14 | 2023-09-09 | 2023-10-14 | 2023-10-13 | 2024-01-12 | 2024-01-21 | 2026-06-14 |  | 2026-09-12 |  | 2026-11-12 |  | 2027-02-12 |  | 2027-04-12 |  | 4848213 | 2503712
ST-2025-023 | Prospective Registry of Patients With Systemic Lupus Erythematosus of the Argentinian Society of Rheumatology | PHASE_II | Immunology | SLE | Immunology Portfolio | APX-126 | North America | RECRUITING | 1500 | 1270 | 87.86 | 2022-04-01 | 2027-04-01 | 6 | 15 | 5.7 | 5.9 | AT_RISK | Enrolling | A longitudinal and multicenter cohort study of patients with systemic lupus erythematosus (SLE) is planned, with a follow-up of for 5 years. The data will be obtained from the clinical history of each patient. The responsible for data collection will always be a physician with experience in the mana | Medium | Active | Academic | Planned | PRJ-0022 | APX-126 | ASS-0022 | Global | BUD-0022 | Enrollment | FALSE |  |  | TRUE | Prospective Registry of Patients With Systemic Lup | A longitudinal and multicenter cohort study of patients with systemic lupus erythematosus (SLE) is planned, with a follow-up of for 5 years. The data will be obtained from the clinical history of each patient. The responsible for data collection will always be a physician with experience in the management of patients with SLE and who has received training for data loading. The data will be collected through the an electronic case report form (eCRF) specially designed for this record and which in turn will facilitate the control of the data and the generation of inquiries to the researchers. STUDY VARIABLES Baseline visit: Sociodemographic data Classification criteria American College of Rheumatology (ACR 1982/1997), Systemic Lupus International Collaborating Clinics (SLICC 2012) and/or European League Against Rheumatism / American College of Rheumatology (EULAR / ACR 2019) History of SLE Access to specialized care Current clinical manifestations Activity and damage Scores Current treatments Patient-Reported Outcomes (PROs): Self-reported quality of life questionnaires EQ-5R; physician global assessment (PGA) and the patient Comorbidities Vaccination Habits Obstetric history Associated antiphospholipid syndrome Hospitalizations for adverse event, infections, or lupus activity Annual clinical follow-up visits Clinical follow-up of the patient Changes in clinical manifestations Changes in treatments Use of health services; hospitalizations; high cost treatments Activity and damage scores PROs Annual global and SLE-related mortality STUDY ENDPOINTS * Number of patients who achieved complete clinical remission or low disease activity status (LDAS) * Impact on the quality of life and working life measured by PROs and PGA * Mortality annual and global during the follow up period * Change in disease activity and damage scores * Health care resources used reported as number of hospitalizations, emergency visits and need of high cost treatment * Accessibility to high c | SLE | All Ages | In-House |  | Interventional | Priority Review | Small Molecule | Internal R&D | FALSE | TrialSync Pharma | TrialSync Pharma | FALSE | 2021-10-03 | Colombia, Switzerland, China, Germany, Chile, Sweden | Dr. Sarah Harris | Dr. Thomas Jones | Dr. David Johnson | Dr. Jessica Taylor | Dr. Sarah Williams | Immunology & Inflammation | 2022-01-31 | 2022-02-22 | 2022-01-16 | 2022-01-26 | 2021-12-02 | 2021-12-24 | 2022-01-01 | 2022-01-05 | 2022-04-01 | 2022-04-21 | 2027-01-01 |  | 2027-04-01 |  | 2027-06-01 |  | 2027-09-01 |  | 2027-11-01 |  | 6068360 | 1509810
ST-2025-024 | Systemic Proteomic Analysis of Plasma Exosomes to Explore the Immunomodulation Reflected to Sjogren's Syndrome and Dry Eye Syndrome | PHASE_II | Immunology | Dry Eye Syndrome (DES) | Immunology Portfolio | PHX-287 | LATAM | RECRUITING | 220 | 135 | 72.97 | 2025-01-16 | 2026-12-31 | 5 | 19 | 2.2 | 1.8 | OFF_TRACK | Enrolling | Background: A 2015 survey in Taiwan revealed that the prevalence of Dry Eye Syndrome (DES) is 4.87%, with 4.8% of these cases likely to develop into Sjögren's Syndrome (SJS). An American study indicated that 11.6% of DES cases could be diagnosed as SJS, and SJS patients showed significantly more sev | Medium | Active | Investigator-Initiated | In Progress | PRJ-0023 | PHX-287 | ASS-0023 | EU First | BUD-0023 | Enrollment | FALSE |  |  | TRUE | Systemic Proteomic Analysis of Plasma Exosomes to | Background: A 2015 survey in Taiwan revealed that the prevalence of Dry Eye Syndrome (DES) is 4.87%, with 4.8% of these cases likely to develop into Sjögren's Syndrome (SJS). An American study indicated that 11.6% of DES cases could be diagnosed as SJS, and SJS patients showed significantly more severe conjunctival and corneal staining, Schirmer's test results, clinical symptoms, anti-nuclear antibody, and rheumatoid factor compared to non-SJS patients. Various autoimmune diseases (such as SJS, SLE, RA, SSc, AS, etc.) also affect the severity of dry eye symptoms. Recent studies have employed exosome proteomics to investigate cell-to-cell communication, molecular mechanisms of diseases, and the development of new diagnostic markers and therapeutic targets. While these studies have significant research value for understanding disease mechanisms, diagnosis, and treatment, few have specifically focused on the impact of exosome proteomics in SJS and DES. Objective: By analyzing the differential proteins in exosomes, this study aims to understand the pathological mechanisms of SJS and DES, identify potential diagnostic and therapeutic methods, and advance the diagnosis and treatment of these diseases. Methods: This study will develope on previous research projects conducted at Taipei Veterans General Hospital (TBDESJS，V112C-190) and the National Science and Technology Council (ACUDES). TBDESJS focused on evaluating the use of a herbal tea TBDESJS for relieving dry eye and mouth symptoms in DES and SJS patients, and ACUDES explored the immediate and long-term effects of acupuncture on treating dry eye and mouth symptoms in DES and SJS patients by using the GB20 (Fengchi) and BL2 (Zanzhu) acupuncture points. 1. TBDESJS Study: Included 30 DES patients, 60 SJS patients, and 10 healthy controls (NHC) to evaluate the efficacy of the Traditional Chinese Medicine (TCM) herbal tea in improving dry eye and mouth symptoms. 2. ACUDES Study: Included 50 DES patients, 50 SJS patient | Dry Eye Syndrome (DES) | Pediatric (2-17) | In-House |  | Interventional | Priority Review | Gene Therapy | Government Grant | TRUE | Stellara Inc | Stellara Inc | FALSE | 2024-07-20 | United States, Italy, New Zealand, United Kingdom, Mexico | Dr. Daniel Harris | Dr. Christopher Harris | Dr. Robert Taylor | Dr. Michael White | Dr. Charles Davis | Immunology & Inflammation | 2024-11-17 | 2024-11-22 | 2024-11-02 | 2024-11-01 | 2024-09-18 | 2024-09-17 | 2024-10-18 | 2024-10-08 | 2025-01-16 | 2025-01-10 | 2026-10-02 |  | 2026-12-31 |  | 2027-02-28 |  | 2027-05-31 |  | 2027-07-31 |  | 16092692 | 3059123
ST-2025-026 | Hyperpolarized 129Xe MR Imaging of Lung Function in Healthy Volunteers and Subjects With Pulmonary Disease | PHASE_I | Respiratory | Asthma | Respiratory Portfolio | MED-384 | North America | RECRUITING | 260 | 148 | 69.48 | 2020-11-02 | 2028-10-26 | 6 | 22 | 0.6 | 0.5 | OFF_TRACK | Enrolling | This is an unblinded, open-label study with \~160 subjects with diagnosed pulmonary disease and \~100 healthy controls. Subjects to be enrolled will include males and females 18-80 years old. Evaluation will be on an outpatient basis. Imaging will be done on a single day and will involve administrat | High | Active | Academic | Completed | PRJ-0025 | MED-384 | ASS-0025 | EU First | BUD-0025 | Enrollment | TRUE | 2020-11-02 | 2028-10-26 | FALSE | Hyperpolarized 129Xe MR Imaging of Lung Function i | This is an unblinded, open-label study with \~160 subjects with diagnosed pulmonary disease and \~100 healthy controls. Subjects to be enrolled will include males and females 18-80 years old. Evaluation will be on an outpatient basis. Imaging will be done on a single day and will involve administration of up to four 1-liter doses of HP 129Xe plus one 129Xe calibration dose (\~300-400mL HP 129Xe). In addition to 129Xe MRI, a series of anatomical conventional 1H MR images will be collected including a localizer scan, breath-hold spin echo image, and breath-hold steady-state free precession image to highlight the vasculature. All subjects will be evaluated at one center: The University of Kansas Medical Center, KS USA. | Asthma | Adults (18-75) | In-House |  | Interventional | Breakthrough Therapy | Pharmaceuticals | Government Grant | TRUE | ApexBio Research | ApexBio Research | FALSE | 2020-05-06 | Chile, Singapore, Turkey, Belgium, Argentina, United States | Dr. Charles Thompson | Dr. Thomas Garcia | Dr. Christopher Smith | Dr. Michael Martin | Dr. Michael Miller | Respiratory & Allergy | 2020-09-03 | 2020-08-28 | 2020-08-19 | 2020-08-15 | 2020-07-05 | 2020-07-04 | 2020-08-04 | 2020-08-06 | 2020-11-02 | 2020-10-29 | 2028-07-28 |  | 2028-10-26 |  | 2028-12-26 |  | 2029-03-26 |  | 2029-05-26 |  | 4577129 | 2439889
ST-2025-027 | Mechanistic Trial of Dupilumab in Adults With House Dust Mite-associated Asthma Using an Aeroallergen Challenge Chamber | PHASE_II | Respiratory | Asthma, Allergic | Respiratory Portfolio | MED-515 | North America | RECRUITING | 88 | 86 | 101.18 | 2023-03-29 | 2026-08-29 | 8 | 33 | 0.5 | 0.5 | ON_TRACK | Enrolling | (i)Intervention #1: HDM exposures in the ACC This trial utilizes exposures to House dust mites (HDM) in the Aeroallergen Challenge Chamber (ACC) as a two-pronged tool for (i) precision phenotyping of HDM+PARC+AA+ persons to identify those with the adaptive and maladaptive phenotypes and (ii) assessm | Medium | Active | Commercial | Completed | PRJ-0026 | MED-515 | ASS-0026 | Global | BUD-0026 | Enrollment | FALSE |  |  | FALSE | Mechanistic Trial of Dupilumab in Adults With Hous | (i)Intervention #1: HDM exposures in the ACC This trial utilizes exposures to House dust mites (HDM) in the Aeroallergen Challenge Chamber (ACC) as a two-pronged tool for (i) precision phenotyping of HDM+PARC+AA+ persons to identify those with the adaptive and maladaptive phenotypes and (ii) assessment of symptoms intermittently throughout the clinical trial to monitor effects of dupilumab/placebo on symptom severity . (ii) Participants classifying to the adaptive and maladaptive phenotypes are then randomized to 18-weeks dupilumab vs. placebo, with ACC HDM visits during this phase. | Asthma, Allergic | Adults (18+) | Full Service Outsourcing (FSO) | Covance | Interventional | Breakthrough Therapy | Biologics | Internal R&D | FALSE | Stellara Inc | Stellara Inc | TRUE | 2022-09-30 | Colombia, South Korea, Chile, Saudi Arabia, Turkey, Mexico, Australia, Japan | Dr. Thomas Brown | Dr. Sarah Jones | Dr. David Garcia | Dr. Michael Moore | Dr. William Johnson | Respiratory & Allergy | 2023-01-28 | 2023-01-30 | 2023-01-13 | 2023-01-08 | 2022-11-29 | 2022-12-07 | 2022-12-29 | 2023-01-03 | 2023-03-29 | 2023-04-08 | 2026-05-31 |  | 2026-08-29 |  | 2026-10-29 |  | 2027-01-29 |  | 2027-03-29 |  | 6543924 | 1792770
ST-2025-028 | Improving Chronic Disease Outcomes Across the Lifespan by Addressing Structural Racism | PHASE_II | Respiratory | Hyperlipidemias | Respiratory Portfolio | VRD-853 | North America | RECRUITING | 68000 | 6573 | 98.87 | 2025-10-08 | 2028-09-30 | 3 | 7 | 438.7 | 163.4 | ON_TRACK | Enrolling | With a multidisciplinary team of social determinants of health (SDOH), implementation, antiracism, community-engaged, and practice-based researchers, the investigators will apply an antiracism framework to an existing evidence-based SDOH screening and referral system and develop a holistic implement | Low | Active | Investigator-Initiated | Planned | PRJ-0027 | VRD-853 | ASS-0027 | EU First | BUD-0027 | Enrollment | FALSE |  |  | FALSE | Improving Chronic Disease Outcomes Across the Life | With a multidisciplinary team of social determinants of health (SDOH), implementation, antiracism, community-engaged, and practice-based researchers, the investigators will apply an antiracism framework to an existing evidence-based SDOH screening and referral system and develop a holistic implementation toolkit aimed at reducing bias and mitigating unequal treatment for families of color. The investigators will first conduct qualitative interviews with adult patients and caregivers to understand their experiences with racism and discrimination within the context of their experiences with screening and referral for SDOH; the investigators will then share their findings with stakeholders (e.g., clinic directors, community agency leaders, health system leaders, Medicaid leaders) and elicit their ideas on how best to address these issues within the systems they lead. Subsequently, the investigators will refine the WE CARE implementation protocol using this stakeholder input with the guidance of antiracism and implementation experts. The investigators will then implement the refined WE CARE protocol in family medicine clinics since adverse SDOH impact the whole family unit; it will also allow them to examine WE CARE's impact on improving health outcomes for racialized groups across the life course. The investigators will conduct a hybrid effectiveness-implementation study with a stepped wedge cluster RCT design in three large family medicine clinics (including 2 health centers) that serve racially/ethnically diverse low-income families from Worcester, Massachusetts. The specific aims are to: * Aim 1: Refine the WE CARE implementation protocol using an antiracism lens and community engagement approach to: (a) conduct key informant interviews with families to identify racism and discrimination related barriers to SDOH screening/referral; (b) present these barriers to systems-level stakeholders to elicit input on strategies to address patient concerns; and 3) create an an | Hyperlipidemias | All Ages | Hybrid | PPD | Interventional | Breakthrough Therapy | Biologics | Internal R&D | FALSE | ApexBio Research | ApexBio Research | TRUE | 2025-04-11 | Poland, Netherlands, Saudi Arabia | Dr. Michelle Brown | Dr. James Johnson | Dr. Emily Moore | Dr. Jessica Brown | Dr. Daniel White | Respiratory & Allergy | 2025-08-09 | 2025-08-03 | 2025-07-25 | 2025-07-16 | 2025-06-10 | 2025-06-20 | 2025-07-10 | 2025-07-07 | 2025-10-08 | 2025-09-30 | 2028-07-02 |  | 2028-09-30 |  | 2028-11-30 |  | 2029-02-28 |  | 2029-04-30 |  | 3770776 | 1682104
ST-2025-029 | A Multicenter, Single-group Phase II Clinical Study to Evaluate the Long-term Safety, Pharmacodynamics and Efficacy of Multiple Subcutaneous Injections of SHR-1703 in Eosinophilic Asthma Patients | PHASE_II | Respiratory | Eosinophilic Asthma Patients | Respiratory Portfolio | PHX-501 | MEA | RECRUITING | 200 | 122 | 63.87 | 2024-07-19 | 2026-09-19 | 6 | 13 | 1.8 | 1.2 | OFF_TRACK | Enrolling | The purpose of this study is to evaluation the long-term Safety, Pharmacodynamics and Efficacy of SHR-1703 in Eosinophilic Asthma Patients | Medium | Active | Investigator-Initiated | In Progress | PRJ-0028 | PHX-501 | ASS-0028 | US First | BUD-0028 | Enrollment | FALSE |  |  | FALSE | A Multicenter, Single-group Phase II Clinical Stud | The purpose of this study is to evaluation the long-term Safety, Pharmacodynamics and Efficacy of SHR-1703 in Eosinophilic Asthma Patients | Eosinophilic Asthma Patients | Pediatric (2-17) | Hybrid | IQVIA | Interventional | Priority Review | Biologics | Partnership | TRUE | Genetika Therapeutics | Genetika Therapeutics | TRUE | 2024-01-21 | United Kingdom, Chile, New Zealand, Norway, Japan, Sweden | Dr. Emily Williams | Dr. Amanda Taylor | Dr. James Davis | Dr. Jessica Garcia | Dr. Michelle Brown | Respiratory & Allergy | 2024-05-20 | 2024-05-31 | 2024-05-05 | 2024-05-18 | 2024-03-21 | 2024-04-10 | 2024-04-20 | 2024-05-07 | 2024-07-19 | 2024-07-28 | 2026-06-21 |  | 2026-09-19 |  | 2026-11-19 |  | 2027-02-19 |  | 2027-04-19 |  | 6451776 | 2747002
ST-2025-032 | Identifying the Causes and Risk Factors of Pulmonary Exacerbations in Cystic Fibrosis | PHASE_II | Rare Disease | Cystic Fibrosis (CF) | Rare Disease Portfolio | PHX-540 | APAC | RECRUITING | 300 | 28 | 90.32 | 2025-05-16 | 2029-12-31 | 4 | 8 | 1.2 | 0.5 | AT_RISK | Enrolling | Participants will be recruited by staff within the care of UK CF centres. Initial discussions will occur either during routine outpatient reviews, telephone consultations or during admissions. Consent will take place prior to any other procedures. There will be four separate cohorts of participant | Medium | Active | Academic | Planned | PRJ-0031 | PHX-540 | ASS-0031 | EU First | BUD-0031 | Enrollment | FALSE |  |  | FALSE | Identifying the Causes and Risk Factors of Pulmona | Participants will be recruited by staff within the care of UK CF centres. Initial discussions will occur either during routine outpatient reviews, telephone consultations or during admissions. Consent will take place prior to any other procedures. There will be four separate cohorts of participant 1. Group A participants will be 200 adults with CF (16 years or older) attending a UK adult CF centre taking part in the study 2. Group B participants will be 100 additional adults with CF attending one of the five core CF adult centres: Manchester, Leeds, Newcastle, Cardiff, Liverpool. 3. There will be a pilot study to test the practicalities of running the same protocol in a paediatric population. This will consist of up to 25 children with CF (5-16 years) attending a paediatric clinic in one of the five core centres. 4. In addition, the investigators will recruit up to 40 healthy volunteers to provide samples on a single occasion as controls. Group A participants will have a single in-person visit, at the start of the study. Clinical data, including lung function (spirometry), venous blood draw, sweat chloride, saliva sample and finger-prick dried blood spot sample, sputum, nasal liquid sample and urine sample and demographic data will be collected. The study will run for 12 months. Home sampling kit, consisting of 13 home sampling boxes and 3 additional exacerbation boxes, will be provided for participants to collect in-home sampling for the first 6 months fortnightly. The 3 additional exacerbation boxes will be provided for posting additional set of samples when unwell. There will be questionnaires to complete to remotely monitor the adherence to the protocol. Study app ("Watson") will be set up to provide reminders and aid study adherence and timely return of samples. Group B will only be offered at 5 specialist CF centres (Manchester, Cardiff, Newcastle, Leeds, Liverpool). This follows the same format as Group A but includes additional face to face visits at 1 a | Cystic Fibrosis (CF) | All Ages | Full Service Outsourcing (FSO) | Covance | Interventional | Priority Review | Biologics | Government Grant | FALSE | Astellion Biosciences | Astellion Biosciences | TRUE | 2024-11-17 | Singapore, Spain, New Zealand, China | Dr. William Brown | Dr. Lisa Wilson | Dr. Robert Brown | Dr. David Moore | Dr. Daniel Garcia | Neuroscience & Rare Disease | 2025-03-17 | 2025-03-23 | 2025-03-02 | 2025-03-08 | 2025-01-16 | 2025-01-24 | 2025-02-15 | 2025-02-23 | 2025-05-16 | 2025-05-22 | 2029-10-02 |  | 2029-12-31 |  | 2030-02-28 |  | 2030-05-31 |  | 2030-07-31 |  | 10959892 | 4729821
ST-2025-033 | The Effect of Intensive Hippotherapy on the Psychomotoric Development of Children With Spinal Muscular Atrophy | PHASE_II | Rare Disease | Spinal Muscular Atrophy | Rare Disease Portfolio | APX-588 | North America | RECRUITING | 16 | 13 | 86.67 | 2022-04-22 | 2025-10-22 | 4 | 15 | 0.1 | 0.1 | AT_RISK | Enrolling | Spinal muscular atrophy is rare neuromuscular disease, it is caused by gene mutation survival motor neuron 1 (SMN1). This gene encodes survival motor neuron(SMN) protein. This protein is most important to survive alfa-motoric neurons in spinal cord. When this protein doesn´t work, no signals go from | Medium | Active | Commercial | Completed | PRJ-0032 | APX-588 | ASS-0032 | US First | BUD-0032 | Enrollment | FALSE |  |  | FALSE | The Effect of Intensive Hippotherapy on the Psycho | Spinal muscular atrophy is rare neuromuscular disease, it is caused by gene mutation survival motor neuron 1 (SMN1). This gene encodes survival motor neuron(SMN) protein. This protein is most important to survive alfa-motoric neurons in spinal cord. When this protein doesn´t work, no signals go from brain to skeletal muscles and fazic muscles of body. In the end weakening breathing muscles and internal organs muscles. The first treatment is pharmacological treatment. There is a lot of research about medicament treatment, the famous treatment in Czech Republic is medicine Spinraze and from year 2020 medicine Zongelsma. This, however, more often puts more difficulty on complex rehabilitation. An empirical observation has found out that complex rehabilitation has positive effect on progress of disease and on self-sufficiency of people and children with SMA. Physiotherapy is one of the recommended rehabilitation types. The use of rehabilitation procedures is common in clinical practice. In a 2016 study, 105 adults with SMA were asked how many of them used physiotherapy. A total of 86% of respondents received these services, yet the authors of the article conclude that further research is needed to understand the impact of physiotherapy in SMA. Nevertheless, there is a lot of discussion if physiotherapy is really good for people and children with SMA. Some research shows us, that physiotherapy doesn´t worsen this disease. Researchers showed that strength training 3 times a week does not show side effects in children under 10 years of age, in some cases trends in improving muscle strength and motor functions have been observed. Because in physiotherapy therapists work primarily with muscles, and a lot of activity can cause fatigue of skeletal muscles and worsen their function. But from clinical work scientists know that the effect of physiotherapy is extensive. There is a research on mice which shows the effect of physiotherapy on the strength activities and the aerobi | Spinal Muscular Atrophy | All Ages | In-House |  | Interventional | Breakthrough Therapy | Pharmaceuticals | Government Grant | FALSE | Veridon Therapeutics | Veridon Therapeutics | FALSE | 2021-10-24 | India, Taiwan, Belgium, France | Dr. Nicole Thompson | Dr. Lisa Johnson | Dr. Nicole Wilson | Dr. Stephanie Anderson | Dr. Thomas Jones | Neuroscience & Rare Disease | 2022-02-21 | 2022-02-28 | 2022-02-06 | 2022-02-07 | 2021-12-23 | 2021-12-25 | 2022-01-22 | 2022-01-15 | 2022-04-22 | 2022-04-26 | 2025-07-24 |  | 2025-10-22 |  | 2025-12-22 |  | 2026-03-22 |  | 2026-05-22 |  | 4496223 | 1339009
ST-2025-034 | KB407-02 A Phase 1 Study of Inhaled KB407, a Replication-Defective, Non-Integrating Vector Expressing Human Cystic Fibrosis Transmembrane Conductance Regulator, for the Treatment of Cystic Fibrosis | PHASE_I | Rare Disease | Cystic Fibrosis | Rare Disease Portfolio | ZPH-190 | North America | RECRUITING | 20 | 17 | 94.44 | 2023-06-30 | 2026-11-30 | 3 | 15 | 0.1 | 0.1 | AT_RISK | Enrolling | This study will evaluate safety and tolerability of ascending doses of nebulized KB407 in adults with cystic fibrosis. | Medium | Active | Commercial | Planned | PRJ-0033 | ZPH-190 | ASS-0033 | Global | BUD-0033 | Enrollment | FALSE |  |  | FALSE | KB407-02 A Phase 1 Study of Inhaled KB407, a Repli | This study will evaluate safety and tolerability of ascending doses of nebulized KB407 in adults with cystic fibrosis. | Cystic Fibrosis | Pediatric (2-17) | In-House |  | Interventional | Priority Review | Pharmaceuticals | Government Grant | FALSE | PharmaNova Inc | PharmaNova Inc | FALSE | 2023-01-01 | Switzerland, France, Singapore | Dr. David Jones | Dr. Jessica Johnson | Dr. Charles Anderson | Dr. Jennifer Wilson | Dr. Robert Taylor | Neuroscience & Rare Disease | 2023-05-01 | 2023-06-13 | 2023-04-16 | 2023-05-30 | 2023-03-02 | 2023-04-06 | 2023-04-01 | 2023-05-23 | 2023-06-30 | 2023-08-15 | 2026-09-01 |  | 2026-11-30 |  | 2027-01-30 |  | 2027-04-30 |  | 2027-06-30 |  | 4619807 | 2146375
ST-2025-035 | Analysis of Mobility in the Bath for Infants Affected With Spinal Muscular Atrophy | PHASE_II | Rare Disease | Infantile Spinal Muscular Atrophy | Rare Disease Portfolio | CRX-889 | APAC | RECRUITING | 15 | 9 | 100 | 2025-06-26 | 2027-03-26 | 8 | 28 | 0.2 | 0.2 | ON_TRACK | Enrolling | This is a multicenter research project coordinated by the Child Neuromuscular Unit at Raymond Poincaré Hospital. Additionally, two other pediatric neurology departments, part of the national neuromuscular network FILNEMUS (https://www.filnemus.fr/), will participate in the study: Necker Children's H | Medium | Active | Consortium | In Progress | PRJ-0034 | CRX-889 | ASS-0034 | EU First | BUD-0034 | Enrollment | FALSE |  |  | FALSE | Analysis of Mobility in the Bath for Infants Affec | This is a multicenter research project coordinated by the Child Neuromuscular Unit at Raymond Poincaré Hospital. Additionally, two other pediatric neurology departments, part of the national neuromuscular network FILNEMUS (https://www.filnemus.fr/), will participate in the study: Necker Children's Hospital and Armand Trousseau Hospital. The study's population will include all infants diagnosed with spinal muscular atrophy (SMA), specifically SMA type 1, who have onset before 6 months of age and have been evaluated by the French Therapeutic Commission. Participation in the study will be contingent on parental or guardian consent during follow-up visits. Spinal muscular atrophy is a genetic neurodegenerative condition that affects spinal motor neurons, causing motor and respiratory paralysis and ultimately leading to death. As groundbreaking therapies emerge, there's an increasing need to refine the methods used to assess motor function, especially in infants with severe hypotonia due to SMA type 1. Traditional reference scales used on examination tables are limited in their accuracy because of gravitational effects. Consequently, there's growing interest in evaluating these children's motor skills in water to detect movements unburdened by gravity. Pediatric neurologists in France (SFNP) have already acknowledged the potential value of parental video recordings during infant baths. However, the lack of standardization in recording conditions, coupled with the subjective nature of video interpretations, underscores the necessity for a more standardized and quantifiable approach. Herein lies the application of our proposed evaluation utilizing inertial sensors. Utilizing inertial sensors to detect subtle movements can highlight still-active yet minimally functional motor neurons. Such detection can be pivotal in identifying children who, despite severe motor skill limitations in traditional settings, still possess developmental potential. Our study seeks to leverage | Infantile Spinal Muscular Atrophy | Adults (18+) | Full Service Outsourcing (FSO) | Parexel | Interventional | Breakthrough Therapy | Gene Therapy | Licensing Agreement | TRUE | BioMed Corp | BioMed Corp | TRUE | 2024-12-28 | Mexico, Netherlands, Brazil, Singapore, Germany, India, Colombia, Norway | Dr. Robert Smith | Dr. Thomas Wilson | Dr. David Thompson | Dr. Christopher White | Dr. Sarah Harris | Neuroscience & Rare Disease | 2025-04-27 | 2025-05-22 | 2025-04-12 | 2025-05-02 | 2025-02-26 | 2025-03-30 | 2025-03-28 | 2025-04-27 | 2025-06-26 | 2025-07-20 | 2026-12-26 |  | 2027-03-26 |  | 2027-05-26 |  | 2027-08-26 |  | 2027-10-26 |  | 15328463 | 5983667

## Enrollment Timeline
id | study_id | period_date | planned_cumulative | actual_cumulative | forecast_cumulative | enrolled_this_period | below_plan_flag
5631 | ST-2024-002 | 2024-09-01 | 3 | 2 | 2 | 2 | TRUE
5632 | ST-2024-002 | 2024-10-01 | 4 | 3 | 3 | 1 | TRUE
5633 | ST-2024-002 | 2024-11-01 | 5 | 4 | 4 | 1 | TRUE
5634 | ST-2024-002 | 2024-12-01 | 6 | 5 | 5 | 1 | TRUE
5635 | ST-2024-002 | 2025-01-01 | 7 | 5 | 5 | 0 | TRUE
5636 | ST-2024-002 | 2025-02-01 | 8 | 6 | 6 | 1 | TRUE
5637 | ST-2024-002 | 2025-03-01 | 10 | 8 | 8 | 2 | TRUE
5638 | ST-2024-002 | 2025-04-01 | 12 | 9 | 9 | 1 | TRUE
5639 | ST-2024-002 | 2025-05-01 | 14 | 11 | 11 | 2 | TRUE
5640 | ST-2024-002 | 2025-06-01 | 16 | 13 | 13 | 2 | TRUE
5641 | ST-2024-002 | 2025-07-01 | 19 | 16 | 16 | 3 | TRUE
5642 | ST-2024-002 | 2025-08-01 | 22 | 18 | 18 | 2 | TRUE
5643 | ST-2024-002 | 2025-09-01 | 26 | 20 | 20 | 2 | TRUE
5644 | ST-2024-002 | 2025-10-01 | 30 | 24 | 24 | 4 | TRUE
5645 | ST-2024-002 | 2025-11-01 | 35 | 27 | 28 | 3 | TRUE
5646 | ST-2024-002 | 2025-12-01 | 40 | 34 | 35 | 7 | TRUE
5647 | ST-2024-002 | 2026-01-01 | 46 | 39 | 40 | 5 | TRUE
5648 | ST-2024-002 | 2026-02-01 | 53 | 42 | 43 | 3 | TRUE
5649 | ST-2024-002 | 2026-03-01 | 59 | 49 | 50 | 7 | TRUE
5650 | ST-2024-002 | 2026-04-01 | 66 | 54 | 56 | 5 | TRUE
5651 | ST-2024-002 | 2026-05-01 | 74 | 58 | 60 | 4 | TRUE
5652 | ST-2024-002 | 2026-06-01 | 81 |  | 72 |  | FALSE
5653 | ST-2024-002 | 2026-07-01 | 89 |  | 80 |  | FALSE
5654 | ST-2024-002 | 2026-08-01 | 96 |  | 86 |  | FALSE
5655 | ST-2024-002 | 2026-09-01 | 104 |  | 93 |  | FALSE
5656 | ST-2024-002 | 2026-10-01 | 111 |  | 99 |  | FALSE
5657 | ST-2024-002 | 2026-11-01 | 117 |  | 105 |  | FALSE
5658 | ST-2024-002 | 2026-12-01 | 124 |  | 111 |  | FALSE
5659 | ST-2024-002 | 2027-01-01 | 130 |  | 117 |  | FALSE
5660 | ST-2024-002 | 2027-02-01 | 135 |  | 121 |  | FALSE
5661 | ST-2024-002 | 2027-03-01 | 140 |  | 126 |  | FALSE
5662 | ST-2024-002 | 2027-04-01 | 144 |  | 129 |  | FALSE
5663 | ST-2024-002 | 2027-05-01 | 148 |  | 133 |  | FALSE
5664 | ST-2024-002 | 2027-06-01 | 151 |  | 135 |  | FALSE
5665 | ST-2024-002 | 2027-07-01 | 154 |  | 138 |  | FALSE
5666 | ST-2024-002 | 2027-08-01 | 156 |  | 140 |  | FALSE
5667 | ST-2024-002 | 2027-09-01 | 158 |  | 142 |  | FALSE
5668 | ST-2024-002 | 2027-10-01 | 160 |  | 144 |  | FALSE
5669 | ST-2024-002 | 2027-11-01 | 162 |  | 145 |  | FALSE
5670 | ST-2024-002 | 2027-12-01 | 163 |  | 146 |  | FALSE
5671 | ST-2024-002 | 2028-01-01 | 164 |  | 147 |  | FALSE
5672 | ST-2024-002 | 2028-02-01 | 165 |  | 148 |  | FALSE
5673 | ST-2024-002 | 2028-03-01 | 166 |  | 149 |  | FALSE
5674 | ST-2024-002 | 2028-04-01 | 167 |  | 150 |  | FALSE
5675 | ST-2024-002 | 2028-05-01 | 167 |  | 150 |  | FALSE
5676 | ST-2024-002 | 2028-06-01 | 167 |  | 150 |  | FALSE
5677 | ST-2024-002 | 2028-07-01 | 167 |  | 150 |  | FALSE
5678 | ST-2024-002 | 2028-08-01 | 167 |  | 150 |  | FALSE
5679 | ST-2024-003 | 2024-03-01 | 2 | 2 | 2 | 2 | FALSE
5680 | ST-2024-003 | 2024-04-01 | 3 | 3 | 3 | 1 | FALSE
5681 | ST-2024-003 | 2024-05-01 | 3 | 3 | 3 | 0 | FALSE
5682 | ST-2024-003 | 2024-06-01 | 4 | 4 | 4 | 1 | FALSE
5683 | ST-2024-003 | 2024-07-01 | 4 | 4 | 4 | 0 | FALSE
5684 | ST-2024-003 | 2024-08-01 | 5 | 4 | 4 | 0 | TRUE
5685 | ST-2024-003 | 2024-09-01 | 5 | 5 | 5 | 1 | FALSE
5686 | ST-2024-003 | 2024-10-01 | 6 | 6 | 6 | 1 | FALSE
5687 | ST-2024-003 | 2024-11-01 | 7 | 7 | 7 | 1 | FALSE
5688 | ST-2024-003 | 2024-12-01 | 8 | 8 | 8 | 1 | FALSE
5689 | ST-2024-003 | 2025-01-01 | 9 | 9 | 9 | 1 | FALSE
5690 | ST-2024-003 | 2025-02-01 | 10 | 9 | 9 | 0 | TRUE
5691 | ST-2024-003 | 2025-03-01 | 11 | 11 | 11 | 2 | FALSE
5692 | ST-2024-003 | 2025-04-01 | 13 | 13 | 13 | 2 | FALSE
5693 | ST-2024-003 | 2025-05-01 | 14 | 14 | 14 | 1 | FALSE
5694 | ST-2024-003 | 2025-06-01 | 16 | 16 | 16 | 2 | FALSE
5695 | ST-2024-003 | 2025-07-01 | 18 | 19 | 19 | 3 | FALSE
5696 | ST-2024-003 | 2025-08-01 | 20 | 19 | 19 | 0 | TRUE
5697 | ST-2024-003 | 2025-09-01 | 22 | 21 | 21 | 2 | TRUE
5698 | ST-2024-003 | 2025-10-01 | 24 | 24 | 24 | 3 | FALSE
5699 | ST-2024-003 | 2025-11-01 | 27 | 27 | 28 | 3 | FALSE
5700 | ST-2024-003 | 2025-12-01 | 29 | 30 | 31 | 3 | FALSE
5701 | ST-2024-003 | 2026-01-01 | 32 | 32 | 33 | 2 | FALSE
5702 | ST-2024-003 | 2026-02-01 | 36 | 38 | 39 | 6 | FALSE
5703 | ST-2024-003 | 2026-03-01 | 39 | 39 | 40 | 1 | FALSE
5704 | ST-2024-003 | 2026-04-01 | 42 | 44 | 45 | 5 | FALSE
5705 | ST-2024-003 | 2026-05-01 | 46 | 49 | 50 | 5 | FALSE
5706 | ST-2024-003 | 2026-06-01 | 50 |  | 52 |  | FALSE
5707 | ST-2024-003 | 2026-07-01 | 54 |  | 56 |  | FALSE
5708 | ST-2024-003 | 2026-08-01 | 58 |  | 60 |  | FALSE
5709 | ST-2024-003 | 2026-09-01 | 63 |  | 66 |  | FALSE
5710 | ST-2024-003 | 2026-10-01 | 67 |  | 70 |  | FALSE
5711 | ST-2024-003 | 2026-11-01 | 71 |  | 74 |  | FALSE
5712 | ST-2024-003 | 2026-12-01 | 76 |  | 79 |  | FALSE
5713 | ST-2024-003 | 2027-01-01 | 80 |  | 84 |  | FALSE
5714 | ST-2024-003 | 2027-02-01 | 84 |  | 88 |  | FALSE
5715 | ST-2024-003 | 2027-03-01 | 89 |  | 93 |  | FALSE
5716 | ST-2024-003 | 2027-04-01 | 93 |  | 97 |  | FALSE
5717 | ST-2024-003 | 2027-05-01 | 97 |  | 101 |  | FALSE
5718 | ST-2024-003 | 2027-06-01 | 101 |  | 106 |  | FALSE
5719 | ST-2024-003 | 2027-07-01 | 105 |  | 110 |  | FALSE
5720 | ST-2024-003 | 2027-08-01 | 108 |  | 113 |  | FALSE
5721 | ST-2024-003 | 2027-09-01 | 111 |  | 116 |  | FALSE
5722 | ST-2024-003 | 2027-10-01 | 115 |  | 120 |  | FALSE
5723 | ST-2024-003 | 2027-11-01 | 118 |  | 123 |  | FALSE
5724 | ST-2024-003 | 2027-12-01 | 120 |  | 126 |  | FALSE
5725 | ST-2024-003 | 2028-01-01 | 123 |  | 129 |  | FALSE
5726 | ST-2024-003 | 2028-02-01 | 125 |  | 131 |  | FALSE
5727 | ST-2024-003 | 2028-03-01 | 127 |  | 133 |  | FALSE
5728 | ST-2024-003 | 2028-04-01 | 129 |  | 135 |  | FALSE
5729 | ST-2024-003 | 2028-05-01 | 131 |  | 137 |  | FALSE
5730 | ST-2024-003 | 2028-06-01 | 133 |  | 139 |  | FALSE
5731 | ST-2024-003 | 2028-07-01 | 134 |  | 140 |  | FALSE
5732 | ST-2024-003 | 2028-08-01 | 136 |  | 142 |  | FALSE
5733 | ST-2024-003 | 2028-09-01 | 137 |  | 143 |  | FALSE
5734 | ST-2024-003 | 2028-10-01 | 138 |  | 144 |  | FALSE
5735 | ST-2024-003 | 2028-11-01 | 139 |  | 145 |  | FALSE
5736 | ST-2024-003 | 2028-12-01 | 140 |  | 147 |  | FALSE
5737 | ST-2024-003 | 2029-01-01 | 141 |  | 148 |  | FALSE
5738 | ST-2024-003 | 2029-02-01 | 142 |  | 148 |  | FALSE
5739 | ST-2024-003 | 2029-03-01 | 142 |  | 148 |  | FALSE
5740 | ST-2024-003 | 2029-04-01 | 143 |  | 148 |  | FALSE
5741 | ST-2024-003 | 2029-05-01 | 143 |  | 148 |  | FALSE
5742 | ST-2024-003 | 2029-06-01 | 144 |  | 148 |  | FALSE
5743 | ST-2024-003 | 2029-07-01 | 144 |  | 148 |  | FALSE
5744 | ST-2024-003 | 2029-08-01 | 145 |  | 148 |  | FALSE
5745 | ST-2024-003 | 2029-09-01 | 145 |  | 148 |  | FALSE
5746 | ST-2024-003 | 2029-10-01 | 145 |  | 148 |  | FALSE
5747 | ST-2024-003 | 2029-11-01 | 145 |  | 148 |  | FALSE
5748 | ST-2024-003 | 2029-12-01 | 145 |  | 148 |  | FALSE
5749 | ST-2024-004 | 2025-01-01 | 3 | 2 | 2 | 2 | TRUE
5750 | ST-2024-004 | 2025-02-01 | 3 | 2 | 2 | 0 | TRUE
5751 | ST-2024-004 | 2025-03-01 | 4 | 3 | 3 | 1 | TRUE
5752 | ST-2024-004 | 2025-04-01 | 4 | 3 | 3 | 0 | TRUE
5753 | ST-2024-004 | 2025-05-01 | 5 | 4 | 4 | 1 | TRUE
5754 | ST-2024-004 | 2025-06-01 | 6 | 4 | 4 | 0 | TRUE
5755 | ST-2024-004 | 2025-07-01 | 8 | 6 | 6 | 2 | TRUE
5756 | ST-2024-004 | 2025-08-01 | 9 | 6 | 6 | 0 | TRUE
5757 | ST-2024-004 | 2025-09-01 | 10 | 7 | 7 | 1 | TRUE
5758 | ST-2024-004 | 2025-10-01 | 12 | 9 | 9 | 2 | TRUE
5759 | ST-2024-004 | 2025-11-01 | 14 | 11 | 11 | 2 | TRUE
5760 | ST-2024-004 | 2025-12-01 | 17 | 13 | 13 | 2 | TRUE
5761 | ST-2024-004 | 2026-01-01 | 19 | 15 | 15 | 2 | TRUE
5762 | ST-2024-004 | 2026-02-01 | 23 | 17 | 17 | 2 | TRUE
5763 | ST-2024-004 | 2026-03-01 | 26 | 19 | 19 | 2 | TRUE
5764 | ST-2024-004 | 2026-04-01 | 30 | 24 | 24 | 5 | TRUE
5765 | ST-2024-004 | 2026-05-01 | 34 | 26 | 27 | 2 | TRUE
5766 | ST-2024-004 | 2026-06-01 | 38 |  | 34 |  | FALSE
5767 | ST-2024-004 | 2026-07-01 | 43 |  | 38 |  | FALSE
5768 | ST-2024-004 | 2026-08-01 | 49 |  | 44 |  | FALSE
5769 | ST-2024-004 | 2026-09-01 | 54 |  | 48 |  | FALSE
5770 | ST-2024-004 | 2026-10-01 | 60 |  | 54 |  | FALSE
5771 | ST-2024-004 | 2026-11-01 | 66 |  | 59 |  | FALSE
5772 | ST-2024-004 | 2026-12-01 | 72 |  | 64 |  | FALSE
5773 | ST-2024-004 | 2027-01-01 | 78 |  | 70 |  | FALSE
5774 | ST-2024-004 | 2027-02-01 | 84 |  | 75 |  | FALSE
5775 | ST-2024-004 | 2027-03-01 | 90 |  | 81 |  | FALSE
5776 | ST-2024-004 | 2027-04-01 | 95 |  | 85 |  | FALSE
5777 | ST-2024-004 | 2027-05-01 | 101 |  | 90 |  | FALSE
5778 | ST-2024-004 | 2027-06-01 | 106 |  | 95 |  | FALSE
5779 | ST-2024-004 | 2027-07-01 | 110 |  | 99 |  | FALSE
5780 | ST-2024-004 | 2027-08-01 | 114 |  | 102 |  | FALSE
5781 | ST-2024-004 | 2027-09-01 | 118 |  | 106 |  | FALSE
5782 | ST-2024-004 | 2027-10-01 | 121 |  | 108 |  | FALSE
5783 | ST-2024-004 | 2027-11-01 | 125 |  | 112 |  | FALSE
5784 | ST-2024-004 | 2027-12-01 | 127 |  | 114 |  | FALSE
5785 | ST-2024-004 | 2028-01-01 | 130 |  | 117 |  | FALSE
5786 | ST-2024-004 | 2028-02-01 | 132 |  | 118 |  | FALSE
5787 | ST-2024-004 | 2028-03-01 | 134 |  | 120 |  | FALSE
5788 | ST-2024-004 | 2028-04-01 | 135 |  | 121 |  | FALSE
5789 | ST-2024-004 | 2028-05-01 | 136 |  | 122 |  | FALSE
5790 | ST-2024-004 | 2028-06-01 | 138 |  | 124 |  | FALSE
5791 | ST-2024-004 | 2028-07-01 | 139 |  | 125 |  | FALSE
5792 | ST-2024-004 | 2028-08-01 | 140 |  | 126 |  | FALSE
5793 | ST-2024-004 | 2028-09-01 | 140 |  | 126 |  | FALSE
5794 | ST-2024-004 | 2028-10-01 | 141 |  | 126 |  | FALSE
5795 | ST-2024-004 | 2028-11-01 | 141 |  | 126 |  | FALSE
5796 | ST-2024-004 | 2028-12-01 | 142 |  | 127 |  | FALSE
5797 | ST-2024-004 | 2029-01-01 | 142 |  | 127 |  | FALSE
5798 | ST-2024-004 | 2029-02-01 | 142 |  | 127 |  | FALSE
5799 | ST-2024-004 | 2029-03-01 | 142 |  | 127 |  | FALSE
5800 | ST-2024-005 | 2022-08-01 | 2 | 1 | 1 | 1 | TRUE
5801 | ST-2024-005 | 2022-09-01 | 2 | 1 | 1 | 0 | TRUE
5802 | ST-2024-005 | 2022-10-01 | 2 | 1 | 1 | 0 | TRUE
5803 | ST-2024-005 | 2022-11-01 | 3 | 2 | 2 | 1 | TRUE
5804 | ST-2024-005 | 2022-12-01 | 3 | 2 | 2 | 0 | TRUE
5805 | ST-2024-005 | 2023-01-01 | 4 | 3 | 3 | 1 | TRUE
5806 | ST-2024-005 | 2023-02-01 | 5 | 3 | 3 | 0 | TRUE
5807 | ST-2024-005 | 2023-03-01 | 5 | 3 | 3 | 0 | TRUE
5808 | ST-2024-005 | 2023-04-01 | 6 | 4 | 4 | 1 | TRUE
5809 | ST-2024-005 | 2023-05-01 | 7 | 4 | 4 | 0 | TRUE
5810 | ST-2024-005 | 2023-06-01 | 8 | 6 | 6 | 2 | TRUE
5811 | ST-2024-005 | 2023-07-01 | 10 | 7 | 7 | 1 | TRUE
5812 | ST-2024-005 | 2023-08-01 | 11 | 8 | 8 | 1 | TRUE
5813 | ST-2024-005 | 2023-09-01 | 13 | 9 | 9 | 1 | TRUE
5814 | ST-2024-005 | 2023-10-01 | 14 | 10 | 10 | 1 | TRUE
5815 | ST-2024-005 | 2023-11-01 | 17 | 12 | 12 | 2 | TRUE
5816 | ST-2024-005 | 2023-12-01 | 19 | 13 | 13 | 1 | TRUE
5817 | ST-2024-005 | 2024-01-01 | 21 | 14 | 14 | 1 | TRUE
5818 | ST-2024-005 | 2024-02-01 | 24 | 17 | 17 | 3 | TRUE
5819 | ST-2024-005 | 2024-03-01 | 27 | 20 | 20 | 3 | TRUE
5820 | ST-2024-005 | 2024-04-01 | 30 | 22 | 22 | 2 | TRUE
5821 | ST-2024-005 | 2024-05-01 | 33 | 25 | 26 | 3 | TRUE
5822 | ST-2024-005 | 2024-06-01 | 37 | 28 | 29 | 3 | TRUE
5823 | ST-2024-005 | 2024-07-01 | 40 | 28 | 29 | 0 | TRUE
5824 | ST-2024-005 | 2024-08-01 | 44 | 33 | 34 | 5 | TRUE
5825 | ST-2024-005 | 2024-09-01 | 48 | 34 | 35 | 1 | TRUE
5826 | ST-2024-005 | 2024-10-01 | 51 | 38 | 39 | 4 | TRUE
5827 | ST-2024-005 | 2024-11-01 | 55 | 40 | 41 | 2 | TRUE
5828 | ST-2024-005 | 2024-12-01 | 59 | 43 | 44 | 3 | TRUE
5829 | ST-2024-005 | 2025-01-01 | 62 | 45 | 46 | 2 | TRUE
5830 | ST-2024-005 | 2025-02-01 | 66 | 48 | 49 | 3 | TRUE
5831 | ST-2024-005 | 2025-03-01 | 69 | 50 | 52 | 2 | TRUE
5832 | ST-2024-005 | 2025-04-01 | 72 | 51 | 53 | 1 | TRUE
5833 | ST-2024-005 | 2025-05-01 | 75 | 55 | 57 | 4 | TRUE
5834 | ST-2024-005 | 2025-06-01 | 78 | 55 | 57 | 0 | TRUE
5835 | ST-2024-005 | 2025-07-01 | 80 | 59 | 61 | 4 | TRUE
5836 | ST-2024-005 | 2025-08-01 | 82 | 63 | 65 | 4 | TRUE
5837 | ST-2024-005 | 2025-09-01 | 85 | 62 | 64 | 0 | TRUE
5838 | ST-2024-005 | 2025-10-01 | 86 | 65 | 67 | 3 | TRUE
5839 | ST-2024-005 | 2025-11-01 | 88 | 67 | 69 | 2 | TRUE
5840 | ST-2024-005 | 2025-12-01 | 89 | 68 | 70 | 1 | TRUE
5841 | ST-2024-005 | 2026-01-01 | 91 | 65 | 67 | 0 | TRUE
5842 | ST-2024-005 | 2026-02-01 | 92 | 65 | 67 | 0 | TRUE
5843 | ST-2024-005 | 2026-03-01 | 93 | 66 | 68 | 1 | TRUE
5844 | ST-2024-005 | 2026-04-01 | 94 | 70 | 72 | 4 | TRUE
5845 | ST-2024-005 | 2026-05-01 | 94 | 71 | 73 | 1 | TRUE
5846 | ST-2024-005 | 2026-06-01 | 95 |  | 85 |  | FALSE
5847 | ST-2024-005 | 2026-07-01 | 96 |  | 86 |  | FALSE
5848 | ST-2024-005 | 2026-08-01 | 96 |  | 86 |  | FALSE
5849 | ST-2024-005 | 2026-09-01 | 97 |  | 87 |  | FALSE
5850 | ST-2024-005 | 2026-10-01 | 97 |  | 87 |  | FALSE
5851 | ST-2024-005 | 2026-11-01 | 97 |  | 87 |  | FALSE
5852 | ST-2024-005 | 2026-12-01 | 98 |  | 88 |  | FALSE
5853 | ST-2024-005 | 2027-01-01 | 98 |  | 88 |  | FALSE
5854 | ST-2024-005 | 2027-02-01 | 98 |  | 88 |  | FALSE
5855 | ST-2024-005 | 2027-03-01 | 98 |  | 88 |  | FALSE
5856 | ST-2024-006 | 2024-02-01 | 1 | 0 | 0 | 0 | TRUE
5857 | ST-2024-006 | 2024-03-01 | 2 | 1 | 1 | 1 | TRUE
5858 | ST-2024-006 | 2024-04-01 | 3 | 2 | 2 | 1 | TRUE
5859 | ST-2024-006 | 2024-05-01 | 5 | 4 | 4 | 2 | TRUE
5860 | ST-2024-006 | 2024-06-01 | 7 | 5 | 5 | 1 | TRUE
5861 | ST-2024-006 | 2024-07-01 | 10 | 7 | 7 | 2 | TRUE
5862 | ST-2024-006 | 2024-08-01 | 14 | 10 | 10 | 3 | TRUE
5863 | ST-2024-006 | 2024-09-01 | 19 | 14 | 14 | 4 | TRUE
5864 | ST-2024-006 | 2024-10-01 | 25 | 20 | 20 | 6 | TRUE
5865 | ST-2024-006 | 2024-11-01 | 31 | 25 | 26 | 5 | TRUE
5866 | ST-2024-006 | 2024-12-01 | 38 | 30 | 31 | 5 | TRUE
5867 | ST-2024-006 | 2025-01-01 | 44 | 35 | 36 | 5 | TRUE
5868 | ST-2024-006 | 2025-02-01 | 50 | 40 | 41 | 5 | TRUE
5869 | ST-2024-006 | 2025-03-01 | 55 | 41 | 42 | 1 | TRUE
5870 | ST-2024-006 | 2025-04-01 | 59 | 49 | 50 | 8 | TRUE
5871 | ST-2024-006 | 2025-05-01 | 62 | 49 | 50 | 0 | TRUE
5872 | ST-2024-006 | 2025-06-01 | 64 | 50 | 52 | 1 | TRUE
5873 | ST-2024-006 | 2025-07-01 | 66 | 53 | 55 | 3 | TRUE
5874 | ST-2024-006 | 2025-08-01 | 67 | 51 | 53 | 0 | TRUE
5875 | ST-2024-006 | 2025-09-01 | 68 | 55 | 57 | 4 | TRUE
5876 | ST-2024-006 | 2025-10-01 | 68 | 55 | 57 | 0 | TRUE
5877 | ST-2024-006 | 2025-11-01 | 68 | 54 | 56 | 0 | TRUE
5878 | ST-2024-006 | 2025-12-01 | 68 | 51 | 53 | 0 | TRUE
5879 | ST-2024-006 | 2026-01-01 | 68 | 56 | 58 | 5 | TRUE
5880 | ST-2024-006 | 2026-02-01 | 68 | 53 | 55 | 0 | TRUE
5881 | ST-2024-007 | 2027-01-01 | 1 |  | 0 |  | FALSE
5882 | ST-2024-007 | 2027-02-01 | 1 |  | 0 |  | FALSE
5883 | ST-2024-007 | 2027-03-01 | 1 |  | 0 |  | FALSE
5884 | ST-2024-007 | 2027-04-01 | 2 |  | 1 |  | FALSE
5885 | ST-2024-007 | 2027-05-01 | 3 |  | 2 |  | FALSE
5886 | ST-2024-007 | 2027-06-01 | 4 |  | 3 |  | FALSE
5887 | ST-2024-007 | 2027-07-01 | 5 |  | 4 |  | FALSE
5888 | ST-2024-007 | 2027-08-01 | 6 |  | 5 |  | FALSE
5889 | ST-2024-007 | 2027-09-01 | 8 |  | 7 |  | FALSE
5890 | ST-2024-007 | 2027-10-01 | 10 |  | 9 |  | FALSE
5891 | ST-2024-007 | 2027-11-01 | 12 |  | 10 |  | FALSE
5892 | ST-2024-007 | 2027-12-01 | 15 |  | 13 |  | FALSE
5893 | ST-2024-007 | 2028-01-01 | 18 |  | 16 |  | FALSE
5894 | ST-2024-007 | 2028-02-01 | 21 |  | 18 |  | FALSE
5895 | ST-2024-007 | 2028-03-01 | 25 |  | 22 |  | FALSE
5896 | ST-2024-007 | 2028-04-01 | 28 |  | 25 |  | FALSE
5897 | ST-2024-007 | 2028-05-01 | 31 |  | 27 |  | FALSE
5898 | ST-2024-007 | 2028-06-01 | 34 |  | 30 |  | FALSE
5899 | ST-2024-007 | 2028-07-01 | 37 |  | 33 |  | FALSE
5900 | ST-2024-007 | 2028-08-01 | 39 |  | 35 |  | FALSE
5901 | ST-2024-007 | 2028-09-01 | 41 |  | 36 |  | FALSE
5902 | ST-2024-007 | 2028-10-01 | 43 |  | 38 |  | FALSE
5903 | ST-2024-007 | 2028-11-01 | 44 |  | 39 |  | FALSE
5904 | ST-2024-007 | 2028-12-01 | 45 |  | 40 |  | FALSE
5905 | ST-2024-007 | 2029-01-01 | 46 |  | 41 |  | FALSE
5906 | ST-2024-007 | 2029-02-01 | 47 |  | 42 |  | FALSE
5907 | ST-2024-007 | 2029-03-01 | 48 |  | 43 |  | FALSE
5908 | ST-2024-007 | 2029-04-01 | 48 |  | 43 |  | FALSE
5909 | ST-2024-007 | 2029-05-01 | 48 |  | 43 |  | FALSE
5910 | ST-2024-007 | 2029-06-01 | 49 |  | 44 |  | FALSE
5911 | ST-2024-007 | 2029-07-01 | 49 |  | 44 |  | FALSE
5912 | ST-2024-007 | 2029-08-01 | 49 |  | 44 |  | FALSE
5913 | ST-2024-007 | 2029-09-01 | 49 |  | 44 |  | FALSE
5914 | ST-2024-007 | 2029-10-01 | 49 |  | 44 |  | FALSE
5915 | ST-2024-008 | 2021-09-01 | 1 | 0 | 0 | 0 | TRUE
5916 | ST-2024-008 | 2021-10-01 | 1 | 0 | 0 | 0 | TRUE
5917 | ST-2024-008 | 2021-11-01 | 1 | 0 | 0 | 0 | TRUE
5918 | ST-2024-008 | 2021-12-01 | 1 | 0 | 0 | 0 | TRUE
5919 | ST-2024-008 | 2022-01-01 | 1 | 0 | 0 | 0 | TRUE
5920 | ST-2024-008 | 2022-02-01 | 2 | 1 | 1 | 1 | TRUE
5921 | ST-2024-008 | 2022-03-01 | 2 | 1 | 1 | 0 | TRUE
5922 | ST-2024-008 | 2022-04-01 | 3 | 2 | 2 | 1 | TRUE
5923 | ST-2024-008 | 2022-05-01 | 3 | 2 | 2 | 0 | TRUE
5924 | ST-2024-008 | 2022-06-01 | 4 | 3 | 3 | 1 | TRUE
5925 | ST-2024-008 | 2022-07-01 | 4 | 3 | 3 | 0 | TRUE
5926 | ST-2024-008 | 2022-08-01 | 5 | 4 | 4 | 1 | TRUE
5927 | ST-2024-008 | 2022-09-01 | 6 | 4 | 4 | 0 | TRUE
5928 | ST-2024-008 | 2022-10-01 | 7 | 5 | 5 | 1 | TRUE
5929 | ST-2024-008 | 2022-11-01 | 8 | 7 | 7 | 2 | TRUE
5930 | ST-2024-008 | 2022-12-01 | 9 | 7 | 7 | 0 | TRUE
5931 | ST-2024-008 | 2023-01-01 | 11 | 9 | 9 | 2 | TRUE
5932 | ST-2024-008 | 2023-02-01 | 12 | 9 | 9 | 0 | TRUE
5933 | ST-2024-008 | 2023-03-01 | 14 | 11 | 11 | 2 | TRUE
5934 | ST-2024-008 | 2023-04-01 | 16 | 13 | 13 | 2 | TRUE
5935 | ST-2024-008 | 2023-05-01 | 18 | 14 | 14 | 1 | TRUE
5936 | ST-2024-008 | 2023-06-01 | 19 | 16 | 16 | 2 | TRUE
5937 | ST-2024-008 | 2023-07-01 | 21 | 17 | 17 | 1 | TRUE
5938 | ST-2024-008 | 2023-08-01 | 23 | 18 | 18 | 1 | TRUE
5939 | ST-2024-008 | 2023-09-01 | 26 | 21 | 21 | 3 | TRUE
5940 | ST-2024-008 | 2023-10-01 | 28 | 23 | 23 | 2 | TRUE
5941 | ST-2024-008 | 2023-11-01 | 30 | 24 | 24 | 1 | TRUE
5942 | ST-2024-008 | 2023-12-01 | 31 | 27 | 28 | 3 | TRUE
5943 | ST-2024-008 | 2024-01-01 | 33 | 26 | 27 | 0 | TRUE
5944 | ST-2024-008 | 2024-02-01 | 35 | 30 | 31 | 4 | TRUE
5945 | ST-2024-008 | 2024-03-01 | 37 | 30 | 31 | 0 | TRUE
5946 | ST-2024-008 | 2024-04-01 | 38 | 30 | 31 | 0 | TRUE
5947 | ST-2024-008 | 2024-05-01 | 40 | 33 | 34 | 3 | TRUE
5948 | ST-2024-008 | 2024-06-01 | 41 | 33 | 34 | 0 | TRUE
5949 | ST-2024-008 | 2024-07-01 | 42 | 34 | 35 | 1 | TRUE
5950 | ST-2024-008 | 2024-08-01 | 43 | 37 | 38 | 3 | TRUE
5951 | ST-2024-008 | 2024-09-01 | 44 | 35 | 36 | 0 | TRUE
5952 | ST-2024-008 | 2024-10-01 | 45 | 39 | 40 | 4 | TRUE
5953 | ST-2024-008 | 2024-11-01 | 45 | 37 | 38 | 0 | TRUE
5954 | ST-2024-008 | 2024-12-01 | 46 | 37 | 38 | 0 | TRUE
5955 | ST-2024-008 | 2025-01-01 | 46 | 39 | 40 | 2 | TRUE
5956 | ST-2024-008 | 2025-02-01 | 47 | 38 | 39 | 0 | TRUE
5957 | ST-2024-008 | 2025-03-01 | 47 | 40 | 41 | 2 | TRUE
5958 | ST-2024-008 | 2025-04-01 | 48 | 38 | 39 | 0 | TRUE
5959 | ST-2024-008 | 2025-05-01 | 48 | 42 | 43 | 4 | TRUE
5960 | ST-2024-008 | 2025-06-01 | 48 | 40 | 41 | 0 | TRUE
5961 | ST-2024-008 | 2025-07-01 | 48 | 37 | 38 | 0 | TRUE
5962 | ST-2024-008 | 2025-08-01 | 48 | 39 | 40 | 2 | TRUE
5963 | ST-2024-008 | 2025-09-01 | 49 | 40 | 41 | 1 | TRUE
5964 | ST-2024-008 | 2025-10-01 | 49 | 40 | 41 | 0 | TRUE
5965 | ST-2024-008 | 2025-11-01 | 49 | 41 | 42 | 1 | TRUE
5966 | ST-2024-008 | 2025-12-01 | 49 | 41 | 42 | 0 | TRUE
5967 | ST-2024-009 | 2025-11-01 | 6 | 4 | 4 | 4 | TRUE
5968 | ST-2024-009 | 2025-12-01 | 7 | 6 | 6 | 2 | TRUE
5969 | ST-2024-009 | 2026-01-01 | 9 | 7 | 7 | 1 | TRUE
5970 | ST-2024-009 | 2026-02-01 | 10 | 8 | 8 | 1 | TRUE
5971 | ST-2024-009 | 2026-03-01 | 13 | 10 | 10 | 2 | TRUE
5972 | ST-2024-009 | 2026-04-01 | 15 | 12 | 12 | 2 | TRUE
5973 | ST-2024-009 | 2026-05-01 | 18 | 14 | 14 | 2 | TRUE
5974 | ST-2024-009 | 2026-06-01 | 21 |  | 18 |  | FALSE
5975 | ST-2024-009 | 2026-07-01 | 25 |  | 22 |  | FALSE
5976 | ST-2024-009 | 2026-08-01 | 30 |  | 27 |  | FALSE
5977 | ST-2024-009 | 2026-09-01 | 35 |  | 31 |  | FALSE
5978 | ST-2024-009 | 2026-10-01 | 41 |  | 36 |  | FALSE
5979 | ST-2024-009 | 2026-11-01 | 48 |  | 43 |  | FALSE
5980 | ST-2024-009 | 2026-12-01 | 56 |  | 50 |  | FALSE
5981 | ST-2024-009 | 2027-01-01 | 65 |  | 58 |  | FALSE
5982 | ST-2024-009 | 2027-02-01 | 75 |  | 67 |  | FALSE
5983 | ST-2024-009 | 2027-03-01 | 86 |  | 77 |  | FALSE
5984 | ST-2024-009 | 2027-04-01 | 97 |  | 87 |  | FALSE
5985 | ST-2024-009 | 2027-05-01 | 110 |  | 99 |  | FALSE
5986 | ST-2024-009 | 2027-06-01 | 123 |  | 110 |  | FALSE
5987 | ST-2024-009 | 2027-07-01 | 136 |  | 122 |  | FALSE
5988 | ST-2024-009 | 2027-08-01 | 150 |  | 135 |  | FALSE
5989 | ST-2024-009 | 2027-09-01 | 163 |  | 146 |  | FALSE
5990 | ST-2024-009 | 2027-10-01 | 176 |  | 158 |  | FALSE
5991 | ST-2024-009 | 2027-11-01 | 189 |  | 170 |  | FALSE
5992 | ST-2024-009 | 2027-12-01 | 202 |  | 181 |  | FALSE
5993 | ST-2024-009 | 2028-01-01 | 213 |  | 191 |  | FALSE
5994 | ST-2024-009 | 2028-02-01 | 224 |  | 201 |  | FALSE
5995 | ST-2024-009 | 2028-03-01 | 234 |  | 210 |  | FALSE
5996 | ST-2024-009 | 2028-04-01 | 243 |  | 218 |  | FALSE
5997 | ST-2024-009 | 2028-05-01 | 251 |  | 225 |  | FALSE
5998 | ST-2024-009 | 2028-06-01 | 258 |  | 232 |  | FALSE
5999 | ST-2024-009 | 2028-07-01 | 264 |  | 237 |  | FALSE
6000 | ST-2024-009 | 2028-08-01 | 269 |  | 242 |  | FALSE
6001 | ST-2024-009 | 2028-09-01 | 274 |  | 246 |  | FALSE
6002 | ST-2024-009 | 2028-10-01 | 278 |  | 250 |  | FALSE
6003 | ST-2024-009 | 2028-11-01 | 281 |  | 252 |  | FALSE
6004 | ST-2024-009 | 2028-12-01 | 284 |  | 255 |  | FALSE
6005 | ST-2024-009 | 2029-01-01 | 286 |  | 257 |  | FALSE
6006 | ST-2024-009 | 2029-02-01 | 289 |  | 260 |  | FALSE
6007 | ST-2024-009 | 2029-03-01 | 290 |  | 261 |  | FALSE
6008 | ST-2024-009 | 2029-04-01 | 292 |  | 262 |  | FALSE
6009 | ST-2024-009 | 2029-05-01 | 293 |  | 263 |  | FALSE
6010 | ST-2024-009 | 2029-06-01 | 294 |  | 264 |  | FALSE
6011 | ST-2024-009 | 2029-07-01 | 294 |  | 264 |  | FALSE
6012 | ST-2024-009 | 2029-08-01 | 294 |  | 264 |  | FALSE
6013 | ST-2024-009 | 2029-09-01 | 294 |  | 264 |  | FALSE
6014 | ST-2024-010 | 2021-02-01 | 96 | 81 | 84 | 81 | TRUE
6015 | ST-2024-010 | 2021-03-01 | 102 | 92 | 95 | 11 | TRUE
6016 | ST-2024-010 | 2021-04-01 | 109 | 90 | 93 | 0 | TRUE
6017 | ST-2024-010 | 2021-05-01 | 116 | 105 | 109 | 15 | TRUE
6018 | ST-2024-010 | 2021-06-01 | 124 | 101 | 105 | 0 | TRUE
6019 | ST-2024-010 | 2021-07-01 | 132 | 117 | 121 | 16 | TRUE
6020 | ST-2024-010 | 2021-08-01 | 141 | 124 | 128 | 7 | TRUE
6021 | ST-2024-010 | 2021-09-01 | 151 | 132 | 137 | 8 | TRUE
6022 | ST-2024-010 | 2021-10-01 | 161 | 134 | 139 | 2 | TRUE
6023 | ST-2024-010 | 2021-11-01 | 172 | 144 | 149 | 10 | TRUE
6024 | ST-2024-010 | 2021-12-01 | 183 | 165 | 171 | 21 | TRUE
6025 | ST-2024-010 | 2022-01-01 | 195 | 164 | 170 | 0 | TRUE
6026 | ST-2024-010 | 2022-02-01 | 208 | 186 | 193 | 22 | TRUE
6027 | ST-2024-010 | 2022-03-01 | 222 | 193 | 200 | 7 | TRUE
6028 | ST-2024-010 | 2022-04-01 | 237 | 195 | 202 | 2 | TRUE
6029 | ST-2024-010 | 2022-05-01 | 252 | 221 | 229 | 26 | TRUE
6030 | ST-2024-010 | 2022-06-01 | 269 | 220 | 228 | 0 | TRUE
6031 | ST-2024-010 | 2022-07-01 | 286 | 239 | 248 | 19 | TRUE
6032 | ST-2024-010 | 2022-08-01 | 305 | 263 | 273 | 24 | TRUE
6033 | ST-2024-010 | 2022-09-01 | 324 | 265 | 275 | 2 | TRUE
6034 | ST-2024-010 | 2022-10-01 | 345 | 294 | 305 | 29 | TRUE
6035 | ST-2024-010 | 2022-11-01 | 367 | 330 | 343 | 36 | TRUE
6036 | ST-2024-010 | 2022-12-01 | 391 | 351 | 365 | 21 | TRUE
6037 | ST-2024-010 | 2023-01-01 | 415 | 369 | 383 | 18 | TRUE
6038 | ST-2024-010 | 2023-02-01 | 441 | 372 | 386 | 3 | TRUE
6039 | ST-2024-010 | 2023-03-01 | 469 | 386 | 401 | 14 | TRUE
6040 | ST-2024-010 | 2023-04-01 | 498 | 427 | 444 | 41 | TRUE
6041 | ST-2024-010 | 2023-05-01 | 529 | 449 | 466 | 22 | TRUE
6042 | ST-2024-010 | 2023-06-01 | 561 | 472 | 490 | 23 | TRUE
6043 | ST-2024-010 | 2023-07-01 | 596 | 530 | 551 | 58 | TRUE
6044 | ST-2024-010 | 2023-08-01 | 631 | 559 | 581 | 29 | TRUE
6045 | ST-2024-010 | 2023-09-01 | 669 | 560 | 582 | 1 | TRUE
6046 | ST-2024-010 | 2023-10-01 | 709 | 602 | 626 | 42 | TRUE
6047 | ST-2024-010 | 2023-11-01 | 750 | 681 | 708 | 79 | TRUE
6048 | ST-2024-010 | 2023-12-01 | 794 | 723 | 751 | 42 | TRUE
6049 | ST-2024-010 | 2024-01-01 | 839 | 746 | 775 | 23 | TRUE
6050 | ST-2024-010 | 2024-02-01 | 887 | 785 | 816 | 39 | TRUE
6051 | ST-2024-010 | 2024-03-01 | 937 | 812 | 844 | 27 | TRUE
6052 | ST-2024-010 | 2024-04-01 | 989 | 881 | 916 | 69 | TRUE
6053 | ST-2024-010 | 2024-05-01 | 1043 | 865 | 899 | 0 | TRUE
6054 | ST-2024-010 | 2024-06-01 | 1099 | 994 | 1033 | 129 | TRUE
6055 | ST-2024-010 | 2024-07-01 | 1157 | 945 | 982 | 0 | TRUE
6056 | ST-2024-010 | 2024-08-01 | 1217 | 1055 | 1097 | 110 | TRUE
6057 | ST-2024-010 | 2024-09-01 | 1280 | 1121 | 1165 | 66 | TRUE
6058 | ST-2024-010 | 2024-10-01 | 1344 | 1185 | 1232 | 64 | TRUE
6059 | ST-2024-010 | 2024-11-01 | 1411 | 1151 | 1197 | 0 | TRUE
6060 | ST-2024-010 | 2024-12-01 | 1479 | 1253 | 1303 | 102 | TRUE
6061 | ST-2024-010 | 2025-01-01 | 1550 | 1376 | 1431 | 123 | TRUE
6062 | ST-2024-010 | 2025-02-01 | 1622 | 1380 | 1435 | 4 | TRUE
6063 | ST-2024-010 | 2025-03-01 | 1696 | 1502 | 1562 | 122 | TRUE
6064 | ST-2024-010 | 2025-04-01 | 1771 | 1495 | 1554 | 0 | TRUE
6065 | ST-2024-010 | 2025-05-01 | 1848 | 1542 | 1603 | 47 | TRUE
6066 | ST-2024-010 | 2025-06-01 | 1927 | 1753 | 1823 | 211 | TRUE
6067 | ST-2024-010 | 2025-07-01 | 2006 | 1715 | 1783 | 0 | TRUE
6068 | ST-2024-010 | 2025-08-01 | 2087 | 1894 | 1969 | 179 | TRUE
6069 | ST-2024-010 | 2025-09-01 | 2168 | 1970 | 2048 | 76 | TRUE
6070 | ST-2024-010 | 2025-10-01 | 2250 | 1864 | 1938 | 0 | TRUE
6071 | ST-2024-010 | 2025-11-01 | 2333 | 1964 | 2042 | 100 | TRUE
6072 | ST-2024-010 | 2025-12-01 | 2416 | 1979 | 2058 | 15 | TRUE
6073 | ST-2024-010 | 2026-01-01 | 2500 | 2093 | 2176 | 114 | TRUE
6074 | ST-2024-010 | 2026-02-01 | 2583 | 2315 | 2407 | 222 | TRUE
6075 | ST-2024-010 | 2026-03-01 | 2666 | 2278 | 2369 | 0 | TRUE
6076 | ST-2024-010 | 2026-04-01 | 2749 | 2477 | 2576 | 199 | TRUE
6077 | ST-2024-010 | 2026-05-01 | 2831 | 2432 | 2529 | 0 | TRUE
6078 | ST-2024-010 | 2026-06-01 | 2912 |  | 2697 |  | FALSE
6079 | ST-2024-010 | 2026-07-01 | 2993 |  | 2772 |  | FALSE
6080 | ST-2024-010 | 2026-08-01 | 3072 |  | 2845 |  | FALSE
6081 | ST-2024-010 | 2026-09-01 | 3151 |  | 2918 |  | FALSE
6082 | ST-2024-010 | 2026-10-01 | 3228 |  | 2990 |  | FALSE
6083 | ST-2024-010 | 2026-11-01 | 3303 |  | 3059 |  | FALSE
6084 | ST-2024-010 | 2026-12-01 | 3377 |  | 3128 |  | FALSE
6085 | ST-2024-010 | 2027-01-01 | 3449 |  | 3194 |  | FALSE
6086 | ST-2024-010 | 2027-02-01 | 3520 |  | 3260 |  | FALSE
6087 | ST-2024-010 | 2027-03-01 | 3588 |  | 3323 |  | FALSE
6088 | ST-2024-010 | 2027-04-01 | 3655 |  | 3385 |  | FALSE
6089 | ST-2024-010 | 2027-05-01 | 3719 |  | 3444 |  | FALSE
6090 | ST-2024-010 | 2027-06-01 | 3782 |  | 3503 |  | FALSE
6091 | ST-2024-010 | 2027-07-01 | 3842 |  | 3558 |  | FALSE
6092 | ST-2024-010 | 2027-08-01 | 3900 |  | 3612 |  | FALSE
6093 | ST-2024-010 | 2027-09-01 | 3956 |  | 3664 |  | FALSE
6094 | ST-2024-010 | 2027-10-01 | 4010 |  | 3714 |  | FALSE
6095 | ST-2024-010 | 2027-11-01 | 4062 |  | 3762 |  | FALSE
6096 | ST-2024-010 | 2027-12-01 | 4112 |  | 3808 |  | FALSE
6097 | ST-2024-010 | 2028-01-01 | 4160 |  | 3853 |  | FALSE
6098 | ST-2024-010 | 2028-02-01 | 4205 |  | 3895 |  | FALSE
6099 | ST-2024-010 | 2028-03-01 | 4249 |  | 3935 |  | FALSE
6100 | ST-2024-010 | 2028-04-01 | 4290 |  | 3973 |  | FALSE
6101 | ST-2024-010 | 2028-05-01 | 4330 |  | 4010 |  | FALSE
6102 | ST-2024-010 | 2028-06-01 | 4368 |  | 4046 |  | FALSE
6103 | ST-2024-010 | 2028-07-01 | 4403 |  | 4078 |  | FALSE
6104 | ST-2024-010 | 2028-08-01 | 4438 |  | 4110 |  | FALSE
6105 | ST-2024-010 | 2028-09-01 | 4470 |  | 4140 |  | FALSE
6106 | ST-2024-010 | 2028-10-01 | 4501 |  | 4169 |  | FALSE
6107 | ST-2024-010 | 2028-11-01 | 4530 |  | 4196 |  | FALSE
6108 | ST-2024-010 | 2028-12-01 | 4558 |  | 4222 |  | FALSE
6109 | ST-2024-010 | 2029-01-01 | 4584 |  | 4246 |  | FALSE
6110 | ST-2024-010 | 2029-02-01 | 4608 |  | 4268 |  | FALSE
6111 | ST-2024-010 | 2029-03-01 | 4632 |  | 4290 |  | FALSE
6112 | ST-2024-010 | 2029-04-01 | 4654 |  | 4310 |  | FALSE
6113 | ST-2024-010 | 2029-05-01 | 4675 |  | 4330 |  | FALSE
6114 | ST-2024-010 | 2029-06-01 | 4694 |  | 4348 |  | FALSE
6115 | ST-2024-010 | 2029-07-01 | 4713 |  | 4365 |  | FALSE
6116 | ST-2024-010 | 2029-08-01 | 4730 |  | 4381 |  | FALSE
6117 | ST-2024-010 | 2029-09-01 | 4747 |  | 4397 |  | FALSE
6118 | ST-2024-010 | 2029-10-01 | 4762 |  | 4411 |  | FALSE
6119 | ST-2024-010 | 2029-11-01 | 4777 |  | 4424 |  | FALSE
6120 | ST-2024-010 | 2029-12-01 | 4791 |  | 4437 |  | FALSE
6121 | ST-2024-010 | 2030-01-01 | 4804 |  | 4449 |  | FALSE
6122 | ST-2024-010 | 2030-02-01 | 4816 |  | 4461 |  | FALSE
6123 | ST-2024-010 | 2030-03-01 | 4827 |  | 4471 |  | FALSE
6124 | ST-2024-010 | 2030-04-01 | 4838 |  | 4481 |  | FALSE
6125 | ST-2024-010 | 2030-05-01 | 4848 |  | 4490 |  | FALSE
6126 | ST-2024-010 | 2030-06-01 | 4858 |  | 4499 |  | FALSE
6127 | ST-2024-010 | 2030-07-01 | 4867 |  | 4508 |  | FALSE
6128 | ST-2024-010 | 2030-08-01 | 4875 |  | 4515 |  | FALSE
6129 | ST-2024-010 | 2030-09-01 | 4883 |  | 4523 |  | FALSE
6130 | ST-2024-010 | 2030-10-01 | 4890 |  | 4529 |  | FALSE
6131 | ST-2024-010 | 2030-11-01 | 4897 |  | 4536 |  | FALSE
6132 | ST-2024-010 | 2030-12-01 | 4903 |  | 4541 |  | FALSE
6133 | ST-2024-010 | 2031-01-01 | 4910 |  | 4548 |  | FALSE
6134 | ST-2024-010 | 2031-02-01 | 4910 |  | 4548 |  | FALSE
6135 | ST-2024-010 | 2031-03-01 | 4910 |  | 4548 |  | FALSE
6136 | ST-2024-011 | 2026-01-01 | 3 | 2 | 2 | 2 | TRUE
6137 | ST-2024-011 | 2026-02-01 | 3 | 2 | 2 | 0 | TRUE
6138 | ST-2024-011 | 2026-03-01 | 4 | 2 | 2 | 0 | TRUE
6139 | ST-2024-011 | 2026-04-01 | 5 | 3 | 3 | 1 | TRUE
6140 | ST-2024-011 | 2026-05-01 | 7 | 5 | 5 | 2 | TRUE
6141 | ST-2024-011 | 2026-06-01 | 9 |  | 8 |  | FALSE
6142 | ST-2024-011 | 2026-07-01 | 11 |  | 9 |  | FALSE
6143 | ST-2024-011 | 2026-08-01 | 13 |  | 11 |  | FALSE
6144 | ST-2024-011 | 2026-09-01 | 16 |  | 14 |  | FALSE
6145 | ST-2024-011 | 2026-10-01 | 20 |  | 18 |  | FALSE
6146 | ST-2024-011 | 2026-11-01 | 24 |  | 21 |  | FALSE
6147 | ST-2024-011 | 2026-12-01 | 29 |  | 26 |  | FALSE
6148 | ST-2024-011 | 2027-01-01 | 34 |  | 30 |  | FALSE
6149 | ST-2024-011 | 2027-02-01 | 40 |  | 36 |  | FALSE
6150 | ST-2024-011 | 2027-03-01 | 47 |  | 42 |  | FALSE
6151 | ST-2024-011 | 2027-04-01 | 54 |  | 48 |  | FALSE
6152 | ST-2024-011 | 2027-05-01 | 62 |  | 55 |  | FALSE
6153 | ST-2024-011 | 2027-06-01 | 70 |  | 63 |  | FALSE
6154 | ST-2024-011 | 2027-07-01 | 77 |  | 69 |  | FALSE
6155 | ST-2024-011 | 2027-08-01 | 85 |  | 76 |  | FALSE
6156 | ST-2024-011 | 2027-09-01 | 92 |  | 82 |  | FALSE
6157 | ST-2024-011 | 2027-10-01 | 99 |  | 89 |  | FALSE
6158 | ST-2024-011 | 2027-11-01 | 105 |  | 94 |  | FALSE
6159 | ST-2024-011 | 2027-12-01 | 110 |  | 99 |  | FALSE
6160 | ST-2024-011 | 2028-01-01 | 115 |  | 103 |  | FALSE
6161 | ST-2024-011 | 2028-02-01 | 119 |  | 107 |  | FALSE
6162 | ST-2024-011 | 2028-03-01 | 123 |  | 110 |  | FALSE
6163 | ST-2024-011 | 2028-04-01 | 126 |  | 113 |  | FALSE
6164 | ST-2024-011 | 2028-05-01 | 128 |  | 115 |  | FALSE
6165 | ST-2024-011 | 2028-06-01 | 130 |  | 117 |  | FALSE
6166 | ST-2024-011 | 2028-07-01 | 132 |  | 118 |  | FALSE
6167 | ST-2024-011 | 2028-08-01 | 134 |  | 120 |  | FALSE
6168 | ST-2024-011 | 2028-09-01 | 135 |  | 121 |  | FALSE
6169 | ST-2024-011 | 2028-10-01 | 136 |  | 122 |  | FALSE
6170 | ST-2024-011 | 2028-11-01 | 136 |  | 122 |  | FALSE
6171 | ST-2024-011 | 2028-12-01 | 137 |  | 123 |  | FALSE
6172 | ST-2024-011 | 2029-01-01 | 137 |  | 123 |  | FALSE
6173 | ST-2024-011 | 2029-02-01 | 137 |  | 123 |  | FALSE
6174 | ST-2024-011 | 2029-03-01 | 137 |  | 123 |  | FALSE
6175 | ST-2024-012 | 2025-06-01 | 0 | 0 | 0 | 0 | FALSE
6176 | ST-2024-012 | 2025-07-01 | 1 | 0 | 0 | 0 | TRUE
6177 | ST-2024-012 | 2025-08-01 | 1 | 0 | 0 | 0 | TRUE
6178 | ST-2024-012 | 2025-09-01 | 2 | 1 | 1 | 1 | TRUE
6179 | ST-2024-012 | 2025-10-01 | 4 | 2 | 2 | 1 | TRUE
6180 | ST-2024-012 | 2025-11-01 | 6 | 4 | 4 | 2 | TRUE
6181 | ST-2024-012 | 2025-12-01 | 8 | 5 | 5 | 1 | TRUE
6182 | ST-2024-012 | 2026-01-01 | 11 | 7 | 7 | 2 | TRUE
6183 | ST-2024-012 | 2026-02-01 | 15 | 10 | 10 | 3 | TRUE
6184 | ST-2024-012 | 2026-03-01 | 18 | 13 | 13 | 3 | TRUE
6185 | ST-2024-012 | 2026-04-01 | 21 | 14 | 14 | 1 | TRUE
6186 | ST-2024-012 | 2026-05-01 | 23 | 17 | 17 | 3 | TRUE
6187 | ST-2024-012 | 2026-06-01 | 25 |  | 22 |  | FALSE
6188 | ST-2024-012 | 2026-07-01 | 27 |  | 24 |  | FALSE
6189 | ST-2024-012 | 2026-08-01 | 28 |  | 25 |  | FALSE
6190 | ST-2024-012 | 2026-09-01 | 28 |  | 25 |  | FALSE
6191 | ST-2024-012 | 2026-10-01 | 29 |  | 26 |  | FALSE
6192 | ST-2024-012 | 2026-11-01 | 29 |  | 26 |  | FALSE
6193 | ST-2024-012 | 2026-12-01 | 29 |  | 26 |  | FALSE
6194 | ST-2024-012 | 2027-01-01 | 29 |  | 26 |  | FALSE
6195 | ST-2024-012 | 2027-02-01 | 29 |  | 26 |  | FALSE
6196 | ST-2024-012 | 2027-03-01 | 29 |  | 26 |  | FALSE
6197 | ST-2024-013 | 2026-12-01 | 0 |  | 0 |  | FALSE
6198 | ST-2024-013 | 2027-01-01 | 0 |  | 0 |  | FALSE
6199 | ST-2024-013 | 2027-02-01 | 0 |  | 0 |  | FALSE
6200 | ST-2024-013 | 2027-03-01 | 0 |  | 0 |  | FALSE
6201 | ST-2024-013 | 2027-04-01 | 0 |  | 0 |  | FALSE
6202 | ST-2024-013 | 2027-05-01 | 0 |  | 0 |  | FALSE
6203 | ST-2024-013 | 2027-06-01 | 0 |  | 0 |  | FALSE
6204 | ST-2024-013 | 2027-07-01 | 0 |  | 0 |  | FALSE
6205 | ST-2024-013 | 2027-08-01 | 1 |  | 1 |  | FALSE
6206 | ST-2024-013 | 2027-09-01 | 1 |  | 1 |  | FALSE
6207 | ST-2024-013 | 2027-10-01 | 1 |  | 1 |  | FALSE
6208 | ST-2024-013 | 2027-11-01 | 2 |  | 2 |  | FALSE
6209 | ST-2024-013 | 2027-12-01 | 2 |  | 2 |  | FALSE
6210 | ST-2024-013 | 2028-01-01 | 2 |  | 2 |  | FALSE
6211 | ST-2024-013 | 2028-02-01 | 3 |  | 3 |  | FALSE
6212 | ST-2024-013 | 2028-03-01 | 3 |  | 3 |  | FALSE
6213 | ST-2024-013 | 2028-04-01 | 4 |  | 4 |  | FALSE
6214 | ST-2024-013 | 2028-05-01 | 5 |  | 5 |  | FALSE
6215 | ST-2024-013 | 2028-06-01 | 5 |  | 5 |  | FALSE
6216 | ST-2024-013 | 2028-07-01 | 6 |  | 6 |  | FALSE
6217 | ST-2024-013 | 2028-08-01 | 6 |  | 6 |  | FALSE
6218 | ST-2024-013 | 2028-09-01 | 6 |  | 6 |  | FALSE
6219 | ST-2024-013 | 2028-10-01 | 7 |  | 7 |  | FALSE
6220 | ST-2024-013 | 2028-11-01 | 7 |  | 7 |  | FALSE
6221 | ST-2024-013 | 2028-12-01 | 7 |  | 7 |  | FALSE
6222 | ST-2024-013 | 2029-01-01 | 8 |  | 8 |  | FALSE
6223 | ST-2024-013 | 2029-02-01 | 8 |  | 8 |  | FALSE
6224 | ST-2024-013 | 2029-03-01 | 8 |  | 8 |  | FALSE
6225 | ST-2024-013 | 2029-04-01 | 8 |  | 8 |  | FALSE
6226 | ST-2024-013 | 2029-05-01 | 8 |  | 8 |  | FALSE
6227 | ST-2024-013 | 2029-06-01 | 8 |  | 8 |  | FALSE
6228 | ST-2024-013 | 2029-07-01 | 8 |  | 8 |  | FALSE
6229 | ST-2024-013 | 2029-08-01 | 8 |  | 8 |  | FALSE
6230 | ST-2024-013 | 2029-09-01 | 8 |  | 8 |  | FALSE
6231 | ST-2024-013 | 2029-10-01 | 8 |  | 8 |  | FALSE
6232 | ST-2024-013 | 2029-11-01 | 8 |  | 8 |  | FALSE
6233 | ST-2024-013 | 2029-12-01 | 8 |  | 8 |  | FALSE
6234 | ST-2024-014 | 2025-03-01 | 0 | 0 | 0 | 0 | FALSE
6235 | ST-2024-014 | 2025-04-01 | 0 | 0 | 0 | 0 | FALSE
6236 | ST-2024-014 | 2025-05-01 | 1 | 0 | 0 | 0 | TRUE
6237 | ST-2024-014 | 2025-06-01 | 1 | 0 | 0 | 0 | TRUE
6238 | ST-2024-014 | 2025-07-01 | 1 | 0 | 0 | 0 | TRUE
6239 | ST-2024-014 | 2025-08-01 | 2 | 1 | 1 | 1 | TRUE
6240 | ST-2024-014 | 2025-09-01 | 2 | 2 | 2 | 1 | FALSE
6241 | ST-2024-014 | 2025-10-01 | 3 | 2 | 2 | 0 | TRUE
6242 | ST-2024-014 | 2025-11-01 | 3 | 2 | 2 | 0 | TRUE
6243 | ST-2024-014 | 2025-12-01 | 4 | 3 | 3 | 1 | TRUE
6244 | ST-2024-014 | 2026-01-01 | 5 | 4 | 4 | 1 | TRUE
6245 | ST-2024-014 | 2026-02-01 | 7 | 6 | 6 | 2 | TRUE
6246 | ST-2024-014 | 2026-03-01 | 8 | 7 | 7 | 1 | TRUE
6247 | ST-2024-014 | 2026-04-01 | 9 | 8 | 8 | 1 | TRUE
6248 | ST-2024-014 | 2026-05-01 | 11 | 10 | 10 | 2 | TRUE
6249 | ST-2024-014 | 2026-06-01 | 13 |  | 13 |  | FALSE
6250 | ST-2024-014 | 2026-07-01 | 15 |  | 15 |  | FALSE
6251 | ST-2024-014 | 2026-08-01 | 16 |  | 16 |  | FALSE
6252 | ST-2024-014 | 2026-09-01 | 18 |  | 18 |  | FALSE
6253 | ST-2024-014 | 2026-10-01 | 20 |  | 20 |  | FALSE
6254 | ST-2024-014 | 2026-11-01 | 21 |  | 21 |  | FALSE
6255 | ST-2024-014 | 2026-12-01 | 22 |  | 22 |  | FALSE
6256 | ST-2024-014 | 2027-01-01 | 24 |  | 24 |  | FALSE
6257 | ST-2024-014 | 2027-02-01 | 25 |  | 25 |  | FALSE
6258 | ST-2024-014 | 2027-03-01 | 26 |  | 26 |  | FALSE
6259 | ST-2024-014 | 2027-04-01 | 26 |  | 26 |  | FALSE
6260 | ST-2024-014 | 2027-05-01 | 27 |  | 27 |  | FALSE
6261 | ST-2024-014 | 2027-06-01 | 27 |  | 27 |  | FALSE
6262 | ST-2024-014 | 2027-07-01 | 28 |  | 28 |  | FALSE
6263 | ST-2024-014 | 2027-08-01 | 28 |  | 28 |  | FALSE
6264 | ST-2024-014 | 2027-09-01 | 28 |  | 28 |  | FALSE
6265 | ST-2024-014 | 2027-10-01 | 29 |  | 29 |  | FALSE
6266 | ST-2024-014 | 2027-11-01 | 29 |  | 29 |  | FALSE
6267 | ST-2024-014 | 2027-12-01 | 29 |  | 29 |  | FALSE
6268 | ST-2024-014 | 2028-01-01 | 29 |  | 29 |  | FALSE
6269 | ST-2024-014 | 2028-02-01 | 29 |  | 29 |  | FALSE
6270 | ST-2024-014 | 2028-03-01 | 29 |  | 29 |  | FALSE
6271 | ST-2024-015 | 2025-11-01 | 3 | 2 | 2 | 2 | TRUE
6272 | ST-2024-015 | 2025-12-01 | 4 | 3 | 3 | 1 | TRUE
6273 | ST-2024-015 | 2026-01-01 | 5 | 4 | 4 | 1 | TRUE
6274 | ST-2024-015 | 2026-02-01 | 7 | 6 | 6 | 2 | TRUE
6275 | ST-2024-015 | 2026-03-01 | 10 | 9 | 9 | 3 | TRUE
6276 | ST-2024-015 | 2026-04-01 | 13 | 12 | 12 | 3 | TRUE
6277 | ST-2024-015 | 2026-05-01 | 17 | 15 | 15 | 3 | TRUE
6278 | ST-2024-015 | 2026-06-01 | 22 |  | 22 |  | FALSE
6279 | ST-2024-015 | 2026-07-01 | 28 |  | 28 |  | FALSE
6280 | ST-2024-015 | 2026-08-01 | 35 |  | 36 |  | FALSE
6281 | ST-2024-015 | 2026-09-01 | 43 |  | 44 |  | FALSE
6282 | ST-2024-015 | 2026-10-01 | 53 |  | 54 |  | FALSE
6283 | ST-2024-015 | 2026-11-01 | 62 |  | 64 |  | FALSE
6284 | ST-2024-015 | 2026-12-01 | 73 |  | 75 |  | FALSE
6285 | ST-2024-015 | 2027-01-01 | 82 |  | 84 |  | FALSE
6286 | ST-2024-015 | 2027-02-01 | 92 |  | 95 |  | FALSE
6287 | ST-2024-015 | 2027-03-01 | 100 |  | 103 |  | FALSE
6288 | ST-2024-015 | 2027-04-01 | 107 |  | 110 |  | FALSE
6289 | ST-2024-015 | 2027-05-01 | 113 |  | 116 |  | FALSE
6290 | ST-2024-015 | 2027-06-01 | 118 |  | 121 |  | FALSE
6291 | ST-2024-015 | 2027-07-01 | 122 |  | 126 |  | FALSE
6292 | ST-2024-015 | 2027-08-01 | 125 |  | 129 |  | FALSE
6293 | ST-2024-015 | 2027-09-01 | 128 |  | 132 |  | FALSE
6294 | ST-2024-015 | 2027-10-01 | 130 |  | 134 |  | FALSE
6295 | ST-2024-015 | 2027-11-01 | 131 |  | 135 |  | FALSE
6296 | ST-2024-015 | 2027-12-01 | 132 |  | 136 |  | FALSE
6297 | ST-2024-015 | 2028-01-01 | 133 |  | 136 |  | FALSE
6298 | ST-2024-015 | 2028-02-01 | 133 |  | 136 |  | FALSE
6299 | ST-2024-015 | 2028-03-01 | 133 |  | 136 |  | FALSE
6300 | ST-2024-015 | 2028-04-01 | 133 |  | 136 |  | FALSE
6301 | ST-2024-015 | 2028-05-01 | 133 |  | 136 |  | FALSE
6302 | ST-2024-016 | 2025-03-01 | 2 | 1 | 1 | 1 | TRUE
6303 | ST-2024-016 | 2025-04-01 | 2 | 1 | 1 | 0 | TRUE
6304 | ST-2024-016 | 2025-05-01 | 3 | 2 | 2 | 1 | TRUE
6305 | ST-2024-016 | 2025-06-01 | 4 | 3 | 3 | 1 | TRUE
6306 | ST-2024-016 | 2025-07-01 | 6 | 5 | 5 | 2 | TRUE
6307 | ST-2024-016 | 2025-08-01 | 8 | 7 | 7 | 2 | TRUE
6308 | ST-2024-016 | 2025-09-01 | 10 | 8 | 8 | 1 | TRUE
6309 | ST-2024-016 | 2025-10-01 | 13 | 10 | 10 | 2 | TRUE
6310 | ST-2024-016 | 2025-11-01 | 17 | 14 | 14 | 4 | TRUE
6311 | ST-2024-016 | 2025-12-01 | 21 | 17 | 17 | 3 | TRUE
6312 | ST-2024-016 | 2026-01-01 | 26 | 22 | 22 | 5 | TRUE
6313 | ST-2024-016 | 2026-02-01 | 32 | 27 | 28 | 5 | TRUE
6314 | ST-2024-016 | 2026-03-01 | 38 | 34 | 35 | 7 | TRUE
6315 | ST-2024-016 | 2026-04-01 | 45 | 40 | 41 | 6 | TRUE
6316 | ST-2024-016 | 2026-05-01 | 51 | 45 | 46 | 5 | TRUE
6317 | ST-2024-016 | 2026-06-01 | 57 |  | 53 |  | FALSE
6318 | ST-2024-016 | 2026-07-01 | 63 |  | 58 |  | FALSE
6319 | ST-2024-016 | 2026-08-01 | 68 |  | 63 |  | FALSE
6320 | ST-2024-016 | 2026-09-01 | 72 |  | 67 |  | FALSE
6321 | ST-2024-016 | 2026-10-01 | 76 |  | 70 |  | FALSE
6322 | ST-2024-016 | 2026-11-01 | 79 |  | 73 |  | FALSE
6323 | ST-2024-016 | 2026-12-01 | 81 |  | 75 |  | FALSE
6324 | ST-2024-016 | 2027-01-01 | 83 |  | 77 |  | FALSE
6325 | ST-2024-016 | 2027-02-01 | 85 |  | 79 |  | FALSE
6326 | ST-2024-016 | 2027-03-01 | 86 |  | 80 |  | FALSE
6327 | ST-2024-016 | 2027-04-01 | 87 |  | 81 |  | FALSE
6328 | ST-2024-016 | 2027-05-01 | 87 |  | 81 |  | FALSE
6329 | ST-2024-016 | 2027-06-01 | 88 |  | 82 |  | FALSE
6330 | ST-2024-016 | 2027-07-01 | 88 |  | 82 |  | FALSE
6331 | ST-2024-016 | 2027-08-01 | 88 |  | 82 |  | FALSE
6332 | ST-2024-016 | 2027-09-01 | 88 |  | 82 |  | FALSE
6333 | ST-2024-016 | 2027-10-01 | 88 |  | 82 |  | FALSE
6334 | ST-2024-017 | 2025-05-01 | 1 | 0 | 0 | 0 | TRUE
6335 | ST-2024-017 | 2025-06-01 | 1 | 0 | 0 | 0 | TRUE
6336 | ST-2024-017 | 2025-07-01 | 2 | 1 | 1 | 1 | TRUE
6337 | ST-2024-017 | 2025-08-01 | 2 | 1 | 1 | 0 | TRUE
6338 | ST-2024-017 | 2025-09-01 | 3 | 2 | 2 | 1 | TRUE
6339 | ST-2024-017 | 2025-10-01 | 3 | 1 | 1 | 0 | TRUE
6340 | ST-2024-017 | 2025-11-01 | 4 | 2 | 2 | 1 | TRUE
6341 | ST-2024-017 | 2025-12-01 | 5 | 3 | 3 | 1 | TRUE
6342 | ST-2024-017 | 2026-01-01 | 7 | 4 | 4 | 1 | TRUE
6343 | ST-2024-017 | 2026-02-01 | 8 | 5 | 5 | 1 | TRUE
6344 | ST-2024-017 | 2026-03-01 | 10 | 7 | 7 | 2 | TRUE
6345 | ST-2024-017 | 2026-04-01 | 12 | 8 | 8 | 1 | TRUE
6346 | ST-2024-017 | 2026-05-01 | 14 | 9 | 9 | 1 | TRUE
6347 | ST-2024-017 | 2026-06-01 | 17 |  | 15 |  | FALSE
6348 | ST-2024-017 | 2026-07-01 | 20 |  | 18 |  | FALSE
6349 | ST-2024-017 | 2026-08-01 | 23 |  | 20 |  | FALSE
6350 | ST-2024-017 | 2026-09-01 | 26 |  | 23 |  | FALSE
6351 | ST-2024-017 | 2026-10-01 | 30 |  | 27 |  | FALSE
6352 | ST-2024-017 | 2026-11-01 | 33 |  | 29 |  | FALSE
6353 | ST-2024-017 | 2026-12-01 | 36 |  | 32 |  | FALSE
6354 | ST-2024-017 | 2027-01-01 | 39 |  | 35 |  | FALSE
6355 | ST-2024-017 | 2027-02-01 | 42 |  | 37 |  | FALSE
6356 | ST-2024-017 | 2027-03-01 | 45 |  | 40 |  | FALSE
6357 | ST-2024-017 | 2027-04-01 | 47 |  | 42 |  | FALSE
6358 | ST-2024-017 | 2027-05-01 | 49 |  | 44 |  | FALSE
6359 | ST-2024-017 | 2027-06-01 | 51 |  | 45 |  | FALSE
6360 | ST-2024-017 | 2027-07-01 | 52 |  | 46 |  | FALSE
6361 | ST-2024-017 | 2027-08-01 | 54 |  | 48 |  | FALSE
6362 | ST-2024-017 | 2027-09-01 | 55 |  | 49 |  | FALSE
6363 | ST-2024-017 | 2027-10-01 | 56 |  | 50 |  | FALSE
6364 | ST-2024-017 | 2027-11-01 | 56 |  | 50 |  | FALSE
6365 | ST-2024-017 | 2027-12-01 | 57 |  | 51 |  | FALSE
6366 | ST-2024-017 | 2028-01-01 | 57 |  | 51 |  | FALSE
6367 | ST-2024-017 | 2028-02-01 | 58 |  | 52 |  | FALSE
6368 | ST-2024-017 | 2028-03-01 | 58 |  | 52 |  | FALSE
6369 | ST-2024-017 | 2028-04-01 | 58 |  | 52 |  | FALSE
6370 | ST-2024-017 | 2028-05-01 | 58 |  | 52 |  | FALSE
6371 | ST-2024-017 | 2028-06-01 | 58 |  | 52 |  | FALSE
6372 | ST-2024-017 | 2028-07-01 | 58 |  | 52 |  | FALSE
6373 | ST-2024-018 | 2022-06-01 | 0 | 0 | 0 | 0 | FALSE
6374 | ST-2024-018 | 2022-07-01 | 0 | 0 | 0 | 0 | FALSE
6375 | ST-2024-018 | 2022-08-01 | 0 | 0 | 0 | 0 | FALSE
6376 | ST-2024-018 | 2022-09-01 | 1 | 1 | 1 | 1 | FALSE
6377 | ST-2024-018 | 2022-10-01 | 1 | 1 | 1 | 0 | FALSE
6378 | ST-2024-018 | 2022-11-01 | 2 | 2 | 2 | 1 | FALSE
6379 | ST-2024-018 | 2022-12-01 | 2 | 2 | 2 | 0 | FALSE
6380 | ST-2024-018 | 2023-01-01 | 3 | 3 | 3 | 1 | FALSE
6381 | ST-2024-018 | 2023-02-01 | 4 | 4 | 4 | 1 | FALSE
6382 | ST-2024-018 | 2023-03-01 | 5 | 5 | 5 | 1 | FALSE
6383 | ST-2024-018 | 2023-04-01 | 6 | 6 | 6 | 1 | FALSE
6384 | ST-2024-018 | 2023-05-01 | 8 | 9 | 9 | 3 | FALSE
6385 | ST-2024-018 | 2023-06-01 | 9 | 9 | 9 | 0 | FALSE
6386 | ST-2024-018 | 2023-07-01 | 11 | 11 | 11 | 2 | FALSE
6387 | ST-2024-018 | 2023-08-01 | 12 | 12 | 12 | 1 | FALSE
6388 | ST-2024-018 | 2023-09-01 | 14 | 15 | 15 | 3 | FALSE
6389 | ST-2024-018 | 2023-10-01 | 15 | 16 | 16 | 1 | FALSE
6390 | ST-2024-018 | 2023-11-01 | 17 | 17 | 17 | 1 | FALSE
6391 | ST-2024-018 | 2023-12-01 | 18 | 20 | 20 | 3 | FALSE
6392 | ST-2024-018 | 2024-01-01 | 19 | 21 | 21 | 1 | FALSE
6393 | ST-2024-018 | 2024-02-01 | 20 | 20 | 20 | 0 | FALSE
6394 | ST-2024-018 | 2024-03-01 | 21 | 22 | 22 | 2 | FALSE
6395 | ST-2024-018 | 2024-04-01 | 21 | 23 | 23 | 1 | FALSE
6396 | ST-2024-018 | 2024-05-01 | 22 | 22 | 22 | 0 | FALSE
6397 | ST-2024-018 | 2024-06-01 | 22 | 22 | 22 | 0 | FALSE
6398 | ST-2024-018 | 2024-07-01 | 23 | 23 | 23 | 1 | FALSE
6399 | ST-2024-018 | 2024-08-01 | 23 | 24 | 24 | 1 | FALSE
6400 | ST-2024-018 | 2024-09-01 | 23 | 24 | 24 | 0 | FALSE
6401 | ST-2024-018 | 2024-10-01 | 23 | 24 | 24 | 0 | FALSE
6402 | ST-2024-018 | 2024-11-01 | 23 | 24 | 24 | 0 | FALSE
6403 | ST-2024-018 | 2024-12-01 | 23 | 24 | 24 | 0 | FALSE
6404 | ST-2024-018 | 2025-01-01 | 23 | 24 | 24 | 0 | FALSE
6405 | ST-2024-019 | 2027-01-01 | 9 |  | 8 |  | FALSE
6406 | ST-2024-019 | 2027-02-01 | 12 |  | 11 |  | FALSE
6407 | ST-2024-019 | 2027-03-01 | 17 |  | 16 |  | FALSE
6408 | ST-2024-019 | 2027-04-01 | 23 |  | 22 |  | FALSE
6409 | ST-2024-019 | 2027-05-01 | 31 |  | 29 |  | FALSE
6410 | ST-2024-019 | 2027-06-01 | 41 |  | 39 |  | FALSE
6411 | ST-2024-019 | 2027-07-01 | 53 |  | 51 |  | FALSE
6412 | ST-2024-019 | 2027-08-01 | 69 |  | 66 |  | FALSE
6413 | ST-2024-019 | 2027-09-01 | 89 |  | 85 |  | FALSE
6414 | ST-2024-019 | 2027-10-01 | 112 |  | 107 |  | FALSE
6415 | ST-2024-019 | 2027-11-01 | 138 |  | 132 |  | FALSE
6416 | ST-2024-019 | 2027-12-01 | 167 |  | 160 |  | FALSE
6417 | ST-2024-019 | 2028-01-01 | 198 |  | 190 |  | FALSE
6418 | ST-2024-019 | 2028-02-01 | 228 |  | 219 |  | FALSE
6419 | ST-2024-019 | 2028-03-01 | 257 |  | 247 |  | FALSE
6420 | ST-2024-019 | 2028-04-01 | 283 |  | 272 |  | FALSE
6421 | ST-2024-019 | 2028-05-01 | 306 |  | 294 |  | FALSE
6422 | ST-2024-019 | 2028-06-01 | 326 |  | 314 |  | FALSE
6423 | ST-2024-019 | 2028-07-01 | 342 |  | 329 |  | FALSE
6424 | ST-2024-019 | 2028-08-01 | 354 |  | 341 |  | FALSE
6425 | ST-2024-019 | 2028-09-01 | 364 |  | 350 |  | FALSE
6426 | ST-2024-019 | 2028-10-01 | 372 |  | 358 |  | FALSE
6427 | ST-2024-019 | 2028-11-01 | 378 |  | 364 |  | FALSE
6428 | ST-2024-019 | 2028-12-01 | 383 |  | 368 |  | FALSE
6429 | ST-2024-019 | 2029-01-01 | 386 |  | 371 |  | FALSE
6430 | ST-2024-019 | 2029-02-01 | 388 |  | 373 |  | FALSE
6431 | ST-2024-019 | 2029-03-01 | 388 |  | 373 |  | FALSE
6432 | ST-2024-019 | 2029-04-01 | 388 |  | 373 |  | FALSE
6433 | ST-2024-019 | 2029-05-01 | 388 |  | 373 |  | FALSE
6434 | ST-2024-019 | 2029-06-01 | 388 |  | 373 |  | FALSE
6435 | ST-2024-020 | 2024-01-01 | 0 | 0 | 0 | 0 | FALSE
6436 | ST-2024-020 | 2024-02-01 | 0 | 0 | 0 | 0 | FALSE
6437 | ST-2024-020 | 2024-03-01 | 0 | 0 | 0 | 0 | FALSE
6438 | ST-2024-020 | 2024-04-01 | 0 | 0 | 0 | 0 | FALSE
6439 | ST-2024-020 | 2024-05-01 | 0 | 0 | 0 | 0 | FALSE
6440 | ST-2024-020 | 2024-06-01 | 1 | 0 | 0 | 0 | TRUE
6441 | ST-2024-020 | 2024-07-01 | 1 | 0 | 0 | 0 | TRUE
6442 | ST-2024-020 | 2024-08-01 | 1 | 0 | 0 | 0 | TRUE
6443 | ST-2024-020 | 2024-09-01 | 2 | 1 | 1 | 1 | TRUE
6444 | ST-2024-020 | 2024-10-01 | 2 | 1 | 1 | 0 | TRUE
6445 | ST-2024-020 | 2024-11-01 | 3 | 2 | 2 | 1 | TRUE
6446 | ST-2024-020 | 2024-12-01 | 4 | 3 | 3 | 1 | TRUE
6447 | ST-2024-020 | 2025-01-01 | 4 | 3 | 3 | 0 | TRUE
6448 | ST-2024-020 | 2025-02-01 | 5 | 4 | 4 | 1 | TRUE
6449 | ST-2024-020 | 2025-03-01 | 6 | 5 | 5 | 1 | TRUE
6450 | ST-2024-020 | 2025-04-01 | 7 | 5 | 5 | 0 | TRUE
6451 | ST-2024-020 | 2025-05-01 | 8 | 7 | 7 | 2 | TRUE
6452 | ST-2024-020 | 2025-06-01 | 9 | 8 | 8 | 1 | TRUE
6453 | ST-2024-020 | 2025-07-01 | 10 | 8 | 8 | 0 | TRUE
6454 | ST-2024-020 | 2025-08-01 | 10 | 9 | 9 | 1 | TRUE
6455 | ST-2024-020 | 2025-09-01 | 11 | 9 | 9 | 0 | TRUE
6456 | ST-2024-020 | 2025-10-01 | 12 | 10 | 10 | 1 | TRUE
6457 | ST-2024-020 | 2025-11-01 | 12 | 10 | 10 | 0 | TRUE
6458 | ST-2024-020 | 2025-12-01 | 13 | 11 | 11 | 1 | TRUE
6459 | ST-2024-020 | 2026-01-01 | 13 | 11 | 11 | 0 | TRUE
6460 | ST-2024-020 | 2026-02-01 | 13 | 11 | 11 | 0 | TRUE
6461 | ST-2024-020 | 2026-03-01 | 14 | 12 | 12 | 1 | TRUE
6462 | ST-2024-020 | 2026-04-01 | 14 | 11 | 11 | 0 | TRUE
6463 | ST-2024-020 | 2026-05-01 | 14 | 12 | 12 | 1 | TRUE
6464 | ST-2024-020 | 2026-06-01 | 14 |  | 13 |  | FALSE
6465 | ST-2024-020 | 2026-07-01 | 14 |  | 13 |  | FALSE
6466 | ST-2024-020 | 2026-08-01 | 14 |  | 13 |  | FALSE
6467 | ST-2024-020 | 2026-09-01 | 14 |  | 13 |  | FALSE
6468 | ST-2024-020 | 2026-10-01 | 14 |  | 13 |  | FALSE
6469 | ST-2024-020 | 2026-11-01 | 14 |  | 13 |  | FALSE
6470 | ST-2024-020 | 2026-12-01 | 14 |  | 13 |  | FALSE
6471 | ST-2025-021 | 2018-03-01 | 4 | 4 | 4 | 4 | FALSE
6472 | ST-2025-021 | 2018-04-01 | 5 | 5 | 5 | 1 | FALSE
6473 | ST-2025-021 | 2018-05-01 | 6 | 6 | 6 | 1 | FALSE
6474 | ST-2025-021 | 2018-06-01 | 8 | 7 | 7 | 1 | TRUE
6475 | ST-2025-021 | 2018-07-01 | 10 | 10 | 10 | 3 | FALSE
6476 | ST-2025-021 | 2018-08-01 | 12 | 12 | 12 | 2 | FALSE
6477 | ST-2025-021 | 2018-09-01 | 16 | 17 | 17 | 5 | FALSE
6478 | ST-2025-021 | 2018-10-01 | 19 | 18 | 18 | 1 | TRUE
6479 | ST-2025-021 | 2018-11-01 | 24 | 24 | 24 | 6 | FALSE
6480 | ST-2025-021 | 2018-12-01 | 29 | 30 | 31 | 6 | FALSE
6481 | ST-2025-021 | 2019-01-01 | 36 | 35 | 36 | 5 | TRUE
6482 | ST-2025-021 | 2019-02-01 | 43 | 43 | 44 | 8 | FALSE
6483 | ST-2025-021 | 2019-03-01 | 51 | 53 | 55 | 10 | FALSE
6484 | ST-2025-021 | 2019-04-01 | 61 | 65 | 67 | 12 | FALSE
6485 | ST-2025-021 | 2019-05-01 | 71 | 74 | 76 | 9 | FALSE
6486 | ST-2025-021 | 2019-06-01 | 81 | 80 | 83 | 6 | TRUE
6487 | ST-2025-021 | 2019-07-01 | 92 | 93 | 96 | 13 | FALSE
6488 | ST-2025-021 | 2019-08-01 | 103 | 104 | 108 | 11 | FALSE
6489 | ST-2025-021 | 2019-09-01 | 113 | 121 | 125 | 17 | FALSE
6490 | ST-2025-021 | 2019-10-01 | 123 | 131 | 136 | 10 | FALSE
6491 | ST-2025-021 | 2019-11-01 | 133 | 134 | 139 | 3 | FALSE
6492 | ST-2025-021 | 2019-12-01 | 141 | 149 | 154 | 15 | FALSE
6493 | ST-2025-021 | 2020-01-01 | 148 | 150 | 156 | 1 | FALSE
6494 | ST-2025-021 | 2020-02-01 | 155 | 161 | 167 | 11 | FALSE
6495 | ST-2025-021 | 2020-03-01 | 160 | 162 | 168 | 1 | FALSE
6496 | ST-2025-021 | 2020-04-01 | 165 | 164 | 170 | 2 | TRUE
6497 | ST-2025-021 | 2020-05-01 | 168 | 166 | 172 | 2 | TRUE
6498 | ST-2025-021 | 2020-06-01 | 172 | 173 | 179 | 7 | FALSE
6499 | ST-2025-021 | 2020-07-01 | 174 | 185 | 185 | 12 | FALSE
6500 | ST-2025-021 | 2020-08-01 | 176 | 180 | 185 | 0 | FALSE
6501 | ST-2025-021 | 2020-09-01 | 178 | 185 | 185 | 5 | FALSE
6502 | ST-2025-021 | 2020-10-01 | 179 | 178 | 185 | 0 | TRUE
6503 | ST-2025-021 | 2020-11-01 | 180 | 180 | 185 | 2 | FALSE
6504 | ST-2025-021 | 2020-12-01 | 181 | 185 | 185 | 5 | FALSE
6505 | ST-2025-021 | 2021-01-01 | 181 | 185 | 185 | 0 | FALSE
6506 | ST-2025-021 | 2021-02-01 | 181 | 185 | 185 | 0 | FALSE
6507 | ST-2025-021 | 2021-03-01 | 181 | 185 | 185 | 0 | FALSE
6508 | ST-2025-022 | 2022-08-01 | 1 | 0 | 0 | 0 | TRUE
6509 | ST-2025-022 | 2022-09-01 | 1 | 0 | 0 | 0 | TRUE
6510 | ST-2025-022 | 2022-10-01 | 1 | 1 | 1 | 1 | FALSE
6511 | ST-2025-022 | 2022-11-01 | 2 | 2 | 2 | 1 | FALSE
6512 | ST-2025-022 | 2022-12-01 | 2 | 1 | 1 | 0 | TRUE
6513 | ST-2025-022 | 2023-01-01 | 3 | 3 | 3 | 2 | FALSE
6514 | ST-2025-022 | 2023-02-01 | 4 | 3 | 3 | 0 | TRUE
6515 | ST-2025-022 | 2023-03-01 | 4 | 4 | 4 | 1 | FALSE
6516 | ST-2025-022 | 2023-04-01 | 5 | 5 | 5 | 1 | FALSE
6517 | ST-2025-022 | 2023-05-01 | 7 | 6 | 6 | 1 | TRUE
6518 | ST-2025-022 | 2023-06-01 | 8 | 8 | 8 | 2 | FALSE
6519 | ST-2025-022 | 2023-07-01 | 10 | 9 | 9 | 1 | TRUE
6520 | ST-2025-022 | 2023-08-01 | 11 | 11 | 11 | 2 | FALSE
6521 | ST-2025-022 | 2023-09-01 | 13 | 13 | 13 | 2 | FALSE
6522 | ST-2025-022 | 2023-10-01 | 16 | 16 | 16 | 3 | FALSE
6523 | ST-2025-022 | 2023-11-01 | 18 | 18 | 18 | 2 | FALSE
6524 | ST-2025-022 | 2023-12-01 | 21 | 22 | 22 | 4 | FALSE
6525 | ST-2025-022 | 2024-01-01 | 24 | 24 | 24 | 2 | FALSE
6526 | ST-2025-022 | 2024-02-01 | 27 | 26 | 27 | 2 | TRUE
6527 | ST-2025-022 | 2024-03-01 | 30 | 28 | 29 | 2 | TRUE
6528 | ST-2025-022 | 2024-04-01 | 32 | 34 | 35 | 6 | FALSE
6529 | ST-2025-022 | 2024-05-01 | 35 | 34 | 35 | 0 | TRUE
6530 | ST-2025-022 | 2024-06-01 | 38 | 37 | 38 | 3 | TRUE
6531 | ST-2025-022 | 2024-07-01 | 41 | 42 | 43 | 5 | FALSE
6532 | ST-2025-022 | 2024-08-01 | 43 | 41 | 42 | 0 | TRUE
6533 | ST-2025-022 | 2024-09-01 | 46 | 48 | 49 | 7 | FALSE
6534 | ST-2025-022 | 2024-10-01 | 48 | 46 | 47 | 0 | TRUE
6535 | ST-2025-022 | 2024-11-01 | 49 | 48 | 49 | 2 | TRUE
6536 | ST-2025-022 | 2024-12-01 | 51 | 49 | 50 | 1 | TRUE
6537 | ST-2025-022 | 2025-01-01 | 52 | 54 | 56 | 5 | FALSE
6538 | ST-2025-022 | 2025-02-01 | 54 | 54 | 56 | 0 | FALSE
6539 | ST-2025-022 | 2025-03-01 | 55 | 53 | 55 | 0 | TRUE
6540 | ST-2025-022 | 2025-04-01 | 55 | 57 | 59 | 4 | FALSE
6541 | ST-2025-022 | 2025-05-01 | 56 | 57 | 59 | 0 | FALSE
6542 | ST-2025-022 | 2025-06-01 | 57 | 56 | 58 | 0 | TRUE
6543 | ST-2025-022 | 2025-07-01 | 57 | 59 | 60 | 3 | FALSE
6544 | ST-2025-022 | 2025-08-01 | 58 | 58 | 60 | 0 | FALSE
6545 | ST-2025-022 | 2025-09-01 | 58 | 58 | 60 | 0 | FALSE
6546 | ST-2025-022 | 2025-10-01 | 58 | 56 | 58 | 0 | TRUE
6547 | ST-2025-022 | 2025-11-01 | 58 | 57 | 59 | 1 | TRUE
6548 | ST-2025-022 | 2025-12-01 | 58 | 59 | 60 | 2 | FALSE
6549 | ST-2025-022 | 2026-01-01 | 58 | 58 | 60 | 0 | FALSE
6550 | ST-2025-022 | 2026-02-01 | 58 | 60 | 60 | 2 | FALSE
6551 | ST-2025-022 | 2026-03-01 | 58 | 56 | 58 | 0 | TRUE
6552 | ST-2025-023 | 2022-04-01 | 30 | 27 | 28 | 27 | TRUE
6553 | ST-2025-023 | 2022-05-01 | 34 | 30 | 31 | 3 | TRUE
6554 | ST-2025-023 | 2022-06-01 | 39 | 33 | 34 | 3 | TRUE
6555 | ST-2025-023 | 2022-07-01 | 45 | 39 | 40 | 6 | TRUE
6556 | ST-2025-023 | 2022-08-01 | 51 | 44 | 45 | 5 | TRUE
6557 | ST-2025-023 | 2022-09-01 | 58 | 53 | 55 | 9 | TRUE
6558 | ST-2025-023 | 2022-10-01 | 65 | 57 | 59 | 4 | TRUE
6559 | ST-2025-023 | 2022-11-01 | 74 | 62 | 64 | 5 | TRUE
6560 | ST-2025-023 | 2022-12-01 | 84 | 73 | 75 | 11 | TRUE
6561 | ST-2025-023 | 2023-01-01 | 95 | 84 | 87 | 11 | TRUE
6562 | ST-2025-023 | 2023-02-01 | 107 | 95 | 98 | 11 | TRUE
6563 | ST-2025-023 | 2023-03-01 | 121 | 110 | 114 | 15 | TRUE
6564 | ST-2025-023 | 2023-04-01 | 137 | 129 | 134 | 19 | TRUE
6565 | ST-2025-023 | 2023-05-01 | 154 | 133 | 138 | 4 | TRUE
6566 | ST-2025-023 | 2023-06-01 | 173 | 152 | 158 | 19 | TRUE
6567 | ST-2025-023 | 2023-07-01 | 194 | 180 | 187 | 28 | TRUE
6568 | ST-2025-023 | 2023-08-01 | 218 | 201 | 209 | 21 | TRUE
6569 | ST-2025-023 | 2023-09-01 | 243 | 228 | 237 | 27 | TRUE
6570 | ST-2025-023 | 2023-10-01 | 271 | 254 | 264 | 26 | TRUE
6571 | ST-2025-023 | 2023-11-01 | 302 | 274 | 284 | 20 | TRUE
6572 | ST-2025-023 | 2023-12-01 | 335 | 296 | 307 | 22 | TRUE
6573 | ST-2025-023 | 2024-01-01 | 370 | 317 | 329 | 21 | TRUE
6574 | ST-2025-023 | 2024-02-01 | 408 | 361 | 375 | 44 | TRUE
6575 | ST-2025-023 | 2024-03-01 | 448 | 389 | 404 | 28 | TRUE
6576 | ST-2025-023 | 2024-04-01 | 490 | 437 | 454 | 48 | TRUE
6577 | ST-2025-023 | 2024-05-01 | 534 | 474 | 492 | 37 | TRUE
6578 | ST-2025-023 | 2024-06-01 | 580 | 508 | 528 | 34 | TRUE
6579 | ST-2025-023 | 2024-07-01 | 628 | 570 | 592 | 62 | TRUE
6580 | ST-2025-023 | 2024-08-01 | 676 | 579 | 602 | 9 | TRUE
6581 | ST-2025-023 | 2024-09-01 | 725 | 646 | 671 | 67 | TRUE
6582 | ST-2025-023 | 2024-10-01 | 774 | 685 | 712 | 39 | TRUE
6583 | ST-2025-023 | 2024-11-01 | 823 | 714 | 742 | 29 | TRUE
6584 | ST-2025-023 | 2024-12-01 | 871 | 794 | 825 | 80 | TRUE
6585 | ST-2025-023 | 2025-01-01 | 919 | 788 | 819 | 0 | TRUE
6586 | ST-2025-023 | 2025-02-01 | 965 | 868 | 902 | 80 | TRUE
6587 | ST-2025-023 | 2025-03-01 | 1009 | 955 | 993 | 87 | TRUE
6588 | ST-2025-023 | 2025-04-01 | 1051 | 963 | 1001 | 8 | TRUE
6589 | ST-2025-023 | 2025-05-01 | 1091 | 997 | 1036 | 34 | TRUE
6590 | ST-2025-023 | 2025-06-01 | 1129 | 1039 | 1080 | 42 | TRUE
6591 | ST-2025-023 | 2025-07-01 | 1164 | 1096 | 1139 | 57 | TRUE
6592 | ST-2025-023 | 2025-08-01 | 1197 | 1079 | 1122 | 0 | TRUE
6593 | ST-2025-023 | 2025-09-01 | 1228 | 1122 | 1166 | 43 | TRUE
6594 | ST-2025-023 | 2025-10-01 | 1256 | 1076 | 1119 | 0 | TRUE
6595 | ST-2025-023 | 2025-11-01 | 1281 | 1147 | 1192 | 71 | TRUE
6596 | ST-2025-023 | 2025-12-01 | 1305 | 1118 | 1162 | 0 | TRUE
6597 | ST-2025-023 | 2026-01-01 | 1326 | 1232 | 1281 | 114 | TRUE
6598 | ST-2025-023 | 2026-02-01 | 1345 | 1182 | 1229 | 0 | TRUE
6599 | ST-2025-023 | 2026-03-01 | 1362 | 1290 | 1341 | 108 | TRUE
6600 | ST-2025-023 | 2026-04-01 | 1378 | 1264 | 1314 | 0 | TRUE
6601 | ST-2025-023 | 2026-05-01 | 1392 | 1223 | 1271 | 0 | TRUE
6602 | ST-2025-023 | 2026-06-01 | 1404 |  | 1351 |  | FALSE
6603 | ST-2025-023 | 2026-07-01 | 1415 |  | 1362 |  | FALSE
6604 | ST-2025-023 | 2026-08-01 | 1425 |  | 1372 |  | FALSE
6605 | ST-2025-023 | 2026-09-01 | 1434 |  | 1380 |  | FALSE
6606 | ST-2025-023 | 2026-10-01 | 1441 |  | 1387 |  | FALSE
6607 | ST-2025-023 | 2026-11-01 | 1448 |  | 1394 |  | FALSE
6608 | ST-2025-023 | 2026-12-01 | 1454 |  | 1399 |  | FALSE
6609 | ST-2025-023 | 2027-01-01 | 1460 |  | 1405 |  | FALSE
6610 | ST-2025-023 | 2027-02-01 | 1465 |  | 1410 |  | FALSE
6611 | ST-2025-023 | 2027-03-01 | 1469 |  | 1414 |  | FALSE
6612 | ST-2025-023 | 2027-04-01 | 1473 |  | 1418 |  | FALSE
6613 | ST-2025-023 | 2027-05-01 | 1473 |  | 1418 |  | FALSE
6614 | ST-2025-023 | 2027-06-01 | 1473 |  | 1418 |  | FALSE
6615 | ST-2025-023 | 2027-07-01 | 1473 |  | 1418 |  | FALSE
6616 | ST-2025-024 | 2025-01-01 | 5 | 3 | 3 | 3 | TRUE
6617 | ST-2025-024 | 2025-02-01 | 7 | 5 | 5 | 2 | TRUE
6618 | ST-2025-024 | 2025-03-01 | 10 | 6 | 6 | 1 | TRUE
6619 | ST-2025-024 | 2025-04-01 | 14 | 10 | 10 | 4 | TRUE
6620 | ST-2025-024 | 2025-05-01 | 19 | 13 | 13 | 3 | TRUE
6621 | ST-2025-024 | 2025-06-01 | 26 | 18 | 18 | 5 | TRUE
6622 | ST-2025-024 | 2025-07-01 | 34 | 23 | 23 | 5 | TRUE
6623 | ST-2025-024 | 2025-08-01 | 45 | 31 | 32 | 8 | TRUE
6624 | ST-2025-024 | 2025-09-01 | 59 | 40 | 41 | 9 | TRUE
6625 | ST-2025-024 | 2025-10-01 | 74 | 54 | 56 | 14 | TRUE
6626 | ST-2025-024 | 2025-11-01 | 91 | 68 | 70 | 14 | TRUE
6627 | ST-2025-024 | 2025-12-01 | 110 | 78 | 81 | 10 | TRUE
6628 | ST-2025-024 | 2026-01-01 | 128 | 94 | 97 | 16 | TRUE
6629 | ST-2025-024 | 2026-02-01 | 145 | 107 | 111 | 13 | TRUE
6630 | ST-2025-024 | 2026-03-01 | 160 | 111 | 115 | 4 | TRUE
6631 | ST-2025-024 | 2026-04-01 | 174 | 133 | 138 | 22 | TRUE
6632 | ST-2025-024 | 2026-05-01 | 185 | 135 | 140 | 2 | TRUE
6633 | ST-2025-024 | 2026-06-01 | 193 |  | 173 |  | FALSE
6634 | ST-2025-024 | 2026-07-01 | 200 |  | 180 |  | FALSE
6635 | ST-2025-024 | 2026-08-01 | 205 |  | 184 |  | FALSE
6636 | ST-2025-024 | 2026-09-01 | 209 |  | 188 |  | FALSE
6637 | ST-2025-024 | 2026-10-01 | 212 |  | 190 |  | FALSE
6638 | ST-2025-024 | 2026-11-01 | 214 |  | 192 |  | FALSE
6639 | ST-2025-024 | 2026-12-01 | 216 |  | 194 |  | FALSE
6640 | ST-2025-024 | 2027-01-01 | 216 |  | 194 |  | FALSE
6641 | ST-2025-024 | 2027-02-01 | 216 |  | 194 |  | FALSE
6642 | ST-2025-024 | 2027-03-01 | 216 |  | 194 |  | FALSE
6643 | ST-2025-025 | 2026-09-01 | 0 |  | 0 |  | FALSE
6644 | ST-2025-025 | 2026-10-01 | 0 |  | 0 |  | FALSE
6645 | ST-2025-025 | 2026-11-01 | 0 |  | 0 |  | FALSE
6646 | ST-2025-025 | 2026-12-01 | 0 |  | 0 |  | FALSE
6647 | ST-2025-025 | 2027-01-01 | 0 |  | 0 |  | FALSE
6648 | ST-2025-025 | 2027-02-01 | 0 |  | 0 |  | FALSE
6649 | ST-2025-025 | 2027-03-01 | 0 |  | 0 |  | FALSE
6650 | ST-2025-025 | 2027-04-01 | 0 |  | 0 |  | FALSE
6651 | ST-2025-025 | 2027-05-01 | 0 |  | 0 |  | FALSE
6652 | ST-2025-025 | 2027-06-01 | 1 |  | 1 |  | FALSE
6653 | ST-2025-025 | 2027-07-01 | 1 |  | 1 |  | FALSE
6654 | ST-2025-025 | 2027-08-01 | 1 |  | 1 |  | FALSE
6655 | ST-2025-025 | 2027-09-01 | 1 |  | 1 |  | FALSE
6656 | ST-2025-025 | 2027-10-01 | 2 |  | 2 |  | FALSE
6657 | ST-2025-025 | 2027-11-01 | 2 |  | 2 |  | FALSE
6658 | ST-2025-025 | 2027-12-01 | 2 |  | 2 |  | FALSE
6659 | ST-2025-025 | 2028-01-01 | 3 |  | 3 |  | FALSE
6660 | ST-2025-025 | 2028-02-01 | 3 |  | 3 |  | FALSE
6661 | ST-2025-025 | 2028-03-01 | 3 |  | 3 |  | FALSE
6662 | ST-2025-025 | 2028-04-01 | 4 |  | 4 |  | FALSE
6663 | ST-2025-025 | 2028-05-01 | 4 |  | 4 |  | FALSE
6664 | ST-2025-025 | 2028-06-01 | 4 |  | 4 |  | FALSE
6665 | ST-2025-025 | 2028-07-01 | 4 |  | 4 |  | FALSE
6666 | ST-2025-025 | 2028-08-01 | 5 |  | 5 |  | FALSE
6667 | ST-2025-025 | 2028-09-01 | 5 |  | 5 |  | FALSE
6668 | ST-2025-025 | 2028-10-01 | 5 |  | 5 |  | FALSE
6669 | ST-2025-025 | 2028-11-01 | 5 |  | 5 |  | FALSE
6670 | ST-2025-025 | 2028-12-01 | 5 |  | 5 |  | FALSE
6671 | ST-2025-025 | 2029-01-01 | 5 |  | 5 |  | FALSE
6672 | ST-2025-025 | 2029-02-01 | 5 |  | 5 |  | FALSE
6673 | ST-2025-025 | 2029-03-01 | 5 |  | 5 |  | FALSE
6674 | ST-2025-025 | 2029-04-01 | 5 |  | 5 |  | FALSE
6675 | ST-2025-025 | 2029-05-01 | 5 |  | 5 |  | FALSE
6676 | ST-2025-025 | 2029-06-01 | 5 |  | 5 |  | FALSE
6677 | ST-2025-025 | 2029-07-01 | 5 |  | 5 |  | FALSE
6678 | ST-2025-025 | 2029-08-01 | 5 |  | 5 |  | FALSE
6679 | ST-2025-025 | 2029-09-01 | 5 |  | 5 |  | FALSE
6680 | ST-2025-026 | 2020-11-01 | 5 | 3 | 3 | 3 | TRUE
6681 | ST-2025-026 | 2020-12-01 | 5 | 3 | 3 | 0 | TRUE
6682 | ST-2025-026 | 2021-01-01 | 5 | 3 | 3 | 0 | TRUE
6683 | ST-2025-026 | 2021-02-01 | 6 | 3 | 3 | 0 | TRUE
6684 | ST-2025-026 | 2021-03-01 | 6 | 3 | 3 | 0 | TRUE
6685 | ST-2025-026 | 2021-04-01 | 7 | 4 | 4 | 1 | TRUE
6686 | ST-2025-026 | 2021-05-01 | 8 | 5 | 5 | 1 | TRUE
6687 | ST-2025-026 | 2021-06-01 | 8 | 5 | 5 | 0 | TRUE
6688 | ST-2025-026 | 2021-07-01 | 9 | 5 | 5 | 0 | TRUE
6689 | ST-2025-026 | 2021-08-01 | 10 | 6 | 6 | 1 | TRUE
6690 | ST-2025-026 | 2021-09-01 | 11 | 7 | 7 | 1 | TRUE
6691 | ST-2025-026 | 2021-10-01 | 12 | 7 | 7 | 0 | TRUE
6692 | ST-2025-026 | 2021-11-01 | 13 | 8 | 8 | 1 | TRUE
6693 | ST-2025-026 | 2021-12-01 | 14 | 9 | 9 | 1 | TRUE
6694 | ST-2025-026 | 2022-01-01 | 15 | 10 | 10 | 1 | TRUE
6695 | ST-2025-026 | 2022-02-01 | 16 | 10 | 10 | 0 | TRUE
6696 | ST-2025-026 | 2022-03-01 | 18 | 12 | 12 | 2 | TRUE
6697 | ST-2025-026 | 2022-04-01 | 19 | 13 | 13 | 1 | TRUE
6698 | ST-2025-026 | 2022-05-01 | 20 | 12 | 12 | 0 | TRUE
6699 | ST-2025-026 | 2022-06-01 | 22 | 15 | 15 | 3 | TRUE
6700 | ST-2025-026 | 2022-07-01 | 24 | 15 | 15 | 0 | TRUE
6701 | ST-2025-026 | 2022-08-01 | 26 | 18 | 18 | 3 | TRUE
6702 | ST-2025-026 | 2022-09-01 | 28 | 18 | 18 | 0 | TRUE
6703 | ST-2025-026 | 2022-10-01 | 30 | 19 | 19 | 1 | TRUE
6704 | ST-2025-026 | 2022-11-01 | 32 | 21 | 21 | 2 | TRUE
6705 | ST-2025-026 | 2022-12-01 | 35 | 22 | 22 | 1 | TRUE
6706 | ST-2025-026 | 2023-01-01 | 37 | 24 | 24 | 2 | TRUE
6707 | ST-2025-026 | 2023-02-01 | 40 | 26 | 27 | 2 | TRUE
6708 | ST-2025-026 | 2023-03-01 | 43 | 27 | 28 | 1 | TRUE
6709 | ST-2025-026 | 2023-04-01 | 46 | 31 | 32 | 4 | TRUE
6710 | ST-2025-026 | 2023-05-01 | 49 | 32 | 33 | 1 | TRUE
6711 | ST-2025-026 | 2023-06-01 | 53 | 36 | 37 | 4 | TRUE
6712 | ST-2025-026 | 2023-07-01 | 56 | 36 | 37 | 0 | TRUE
6713 | ST-2025-026 | 2023-08-01 | 60 | 37 | 38 | 1 | TRUE
6714 | ST-2025-026 | 2023-09-01 | 64 | 44 | 45 | 7 | TRUE
6715 | ST-2025-026 | 2023-10-01 | 68 | 44 | 45 | 0 | TRUE
6716 | ST-2025-026 | 2023-11-01 | 72 | 47 | 48 | 3 | TRUE
6717 | ST-2025-026 | 2023-12-01 | 76 | 50 | 52 | 3 | TRUE
6718 | ST-2025-026 | 2024-01-01 | 81 | 51 | 53 | 1 | TRUE
6719 | ST-2025-026 | 2024-02-01 | 86 | 56 | 58 | 5 | TRUE
6720 | ST-2025-026 | 2024-03-01 | 91 | 58 | 60 | 2 | TRUE
6721 | ST-2025-026 | 2024-04-01 | 95 | 61 | 63 | 3 | TRUE
6722 | ST-2025-026 | 2024-05-01 | 101 | 67 | 69 | 6 | TRUE
6723 | ST-2025-026 | 2024-06-01 | 106 | 70 | 72 | 3 | TRUE
6724 | ST-2025-026 | 2024-07-01 | 111 | 72 | 74 | 2 | TRUE
6725 | ST-2025-026 | 2024-08-01 | 116 | 78 | 81 | 6 | TRUE
6726 | ST-2025-026 | 2024-09-01 | 121 | 77 | 80 | 0 | TRUE
6727 | ST-2025-026 | 2024-10-01 | 127 | 87 | 90 | 10 | TRUE
6728 | ST-2025-026 | 2024-11-01 | 132 | 82 | 85 | 0 | TRUE
6729 | ST-2025-026 | 2024-12-01 | 138 | 95 | 98 | 13 | TRUE
6730 | ST-2025-026 | 2025-01-01 | 143 | 97 | 100 | 2 | TRUE
6731 | ST-2025-026 | 2025-02-01 | 148 | 96 | 99 | 0 | TRUE
6732 | ST-2025-026 | 2025-03-01 | 153 | 100 | 104 | 4 | TRUE
6733 | ST-2025-026 | 2025-04-01 | 158 | 103 | 107 | 3 | TRUE
6734 | ST-2025-026 | 2025-05-01 | 164 | 107 | 111 | 4 | TRUE
6735 | ST-2025-026 | 2025-06-01 | 168 | 114 | 118 | 7 | TRUE
6736 | ST-2025-026 | 2025-07-01 | 173 | 113 | 117 | 0 | TRUE
6737 | ST-2025-026 | 2025-08-01 | 178 | 115 | 119 | 2 | TRUE
6738 | ST-2025-026 | 2025-09-01 | 183 | 127 | 132 | 12 | TRUE
6739 | ST-2025-026 | 2025-10-01 | 187 | 117 | 121 | 0 | TRUE
6740 | ST-2025-026 | 2025-11-01 | 191 | 131 | 136 | 14 | TRUE
6741 | ST-2025-026 | 2025-12-01 | 195 | 136 | 141 | 5 | TRUE
6742 | ST-2025-026 | 2026-01-01 | 199 | 126 | 131 | 0 | TRUE
6743 | ST-2025-026 | 2026-02-01 | 203 | 140 | 145 | 14 | TRUE
6744 | ST-2025-026 | 2026-03-01 | 206 | 131 | 136 | 0 | TRUE
6745 | ST-2025-026 | 2026-04-01 | 210 | 143 | 148 | 12 | TRUE
6746 | ST-2025-026 | 2026-05-01 | 213 | 148 | 153 | 5 | TRUE
6747 | ST-2025-026 | 2026-06-01 | 216 |  | 194 |  | FALSE
6748 | ST-2025-026 | 2026-07-01 | 219 |  | 197 |  | FALSE
6749 | ST-2025-026 | 2026-08-01 | 222 |  | 199 |  | FALSE
6750 | ST-2025-026 | 2026-09-01 | 224 |  | 201 |  | FALSE
6751 | ST-2025-026 | 2026-10-01 | 227 |  | 204 |  | FALSE
6752 | ST-2025-026 | 2026-11-01 | 229 |  | 206 |  | FALSE
6753 | ST-2025-026 | 2026-12-01 | 231 |  | 207 |  | FALSE
6754 | ST-2025-026 | 2027-01-01 | 233 |  | 209 |  | FALSE
6755 | ST-2025-026 | 2027-02-01 | 235 |  | 211 |  | FALSE
6756 | ST-2025-026 | 2027-03-01 | 237 |  | 213 |  | FALSE
6757 | ST-2025-026 | 2027-04-01 | 239 |  | 215 |  | FALSE
6758 | ST-2025-026 | 2027-05-01 | 240 |  | 216 |  | FALSE
6759 | ST-2025-026 | 2027-06-01 | 241 |  | 216 |  | FALSE
6760 | ST-2025-026 | 2027-07-01 | 243 |  | 218 |  | FALSE
6761 | ST-2025-026 | 2027-08-01 | 244 |  | 219 |  | FALSE
6762 | ST-2025-026 | 2027-09-01 | 245 |  | 220 |  | FALSE
6763 | ST-2025-026 | 2027-10-01 | 246 |  | 221 |  | FALSE
6764 | ST-2025-026 | 2027-11-01 | 247 |  | 222 |  | FALSE
6765 | ST-2025-026 | 2027-12-01 | 248 |  | 223 |  | FALSE
6766 | ST-2025-026 | 2028-01-01 | 249 |  | 224 |  | FALSE
6767 | ST-2025-026 | 2028-02-01 | 250 |  | 225 |  | FALSE
6768 | ST-2025-026 | 2028-03-01 | 251 |  | 225 |  | FALSE
6769 | ST-2025-026 | 2028-04-01 | 251 |  | 225 |  | FALSE
6770 | ST-2025-026 | 2028-05-01 | 252 |  | 226 |  | FALSE
6771 | ST-2025-026 | 2028-06-01 | 253 |  | 227 |  | FALSE
6772 | ST-2025-026 | 2028-07-01 | 253 |  | 227 |  | FALSE
6773 | ST-2025-026 | 2028-08-01 | 254 |  | 228 |  | FALSE
6774 | ST-2025-026 | 2028-09-01 | 254 |  | 228 |  | FALSE
6775 | ST-2025-026 | 2028-10-01 | 254 |  | 228 |  | FALSE
6776 | ST-2025-026 | 2028-11-01 | 255 |  | 229 |  | FALSE
6777 | ST-2025-026 | 2028-12-01 | 255 |  | 229 |  | FALSE
6778 | ST-2025-026 | 2029-01-01 | 255 |  | 229 |  | FALSE
6779 | ST-2025-027 | 2023-03-01 | 1 | 0 | 0 | 0 | TRUE
6780 | ST-2025-027 | 2023-04-01 | 2 | 1 | 1 | 1 | TRUE
6781 | ST-2025-027 | 2023-05-01 | 2 | 1 | 1 | 0 | TRUE
6782 | ST-2025-027 | 2023-06-01 | 3 | 3 | 3 | 2 | FALSE
6783 | ST-2025-027 | 2023-07-01 | 3 | 2 | 2 | 0 | TRUE
6784 | ST-2025-027 | 2023-08-01 | 4 | 4 | 4 | 2 | FALSE
6785 | ST-2025-027 | 2023-09-01 | 5 | 4 | 4 | 0 | TRUE
6786 | ST-2025-027 | 2023-10-01 | 6 | 5 | 5 | 1 | TRUE
6787 | ST-2025-027 | 2023-11-01 | 8 | 7 | 7 | 2 | TRUE
6788 | ST-2025-027 | 2023-12-01 | 9 | 9 | 9 | 2 | FALSE
6789 | ST-2025-027 | 2024-01-01 | 11 | 11 | 11 | 2 | FALSE
6790 | ST-2025-027 | 2024-02-01 | 13 | 12 | 12 | 1 | TRUE
6791 | ST-2025-027 | 2024-03-01 | 15 | 14 | 14 | 2 | TRUE
6792 | ST-2025-027 | 2024-04-01 | 18 | 16 | 16 | 2 | TRUE
6793 | ST-2025-027 | 2024-05-01 | 21 | 20 | 20 | 4 | TRUE
6794 | ST-2025-027 | 2024-06-01 | 24 | 22 | 22 | 2 | TRUE
6795 | ST-2025-027 | 2024-07-01 | 28 | 28 | 29 | 6 | FALSE
6796 | ST-2025-027 | 2024-08-01 | 31 | 31 | 32 | 3 | FALSE
6797 | ST-2025-027 | 2024-09-01 | 35 | 34 | 35 | 3 | TRUE
6798 | ST-2025-027 | 2024-10-01 | 39 | 37 | 38 | 3 | TRUE
6799 | ST-2025-027 | 2024-11-01 | 44 | 43 | 44 | 6 | TRUE
6800 | ST-2025-027 | 2024-12-01 | 48 | 47 | 48 | 4 | TRUE
6801 | ST-2025-027 | 2025-01-01 | 52 | 47 | 48 | 0 | TRUE
6802 | ST-2025-027 | 2025-02-01 | 56 | 51 | 53 | 4 | TRUE
6803 | ST-2025-027 | 2025-03-01 | 59 | 54 | 56 | 3 | TRUE
6804 | ST-2025-027 | 2025-04-01 | 63 | 63 | 65 | 9 | FALSE
6805 | ST-2025-027 | 2025-05-01 | 66 | 61 | 63 | 0 | TRUE
6806 | ST-2025-027 | 2025-06-01 | 69 | 64 | 66 | 3 | TRUE
6807 | ST-2025-027 | 2025-07-01 | 72 | 70 | 72 | 6 | TRUE
6808 | ST-2025-027 | 2025-08-01 | 74 | 72 | 74 | 2 | TRUE
6809 | ST-2025-027 | 2025-09-01 | 76 | 71 | 73 | 0 | TRUE
6810 | ST-2025-027 | 2025-10-01 | 78 | 77 | 80 | 6 | TRUE
6811 | ST-2025-027 | 2025-11-01 | 79 | 75 | 78 | 0 | TRUE
6812 | ST-2025-027 | 2025-12-01 | 81 | 78 | 81 | 3 | TRUE
6813 | ST-2025-027 | 2026-01-01 | 82 | 77 | 80 | 0 | TRUE
6814 | ST-2025-027 | 2026-02-01 | 83 | 81 | 84 | 4 | TRUE
6815 | ST-2025-027 | 2026-03-01 | 84 | 78 | 81 | 0 | TRUE
6816 | ST-2025-027 | 2026-04-01 | 84 | 80 | 83 | 2 | TRUE
6817 | ST-2025-027 | 2026-05-01 | 85 | 86 | 88 | 6 | FALSE
6818 | ST-2025-027 | 2026-06-01 | 85 |  | 87 |  | FALSE
6819 | ST-2025-027 | 2026-07-01 | 86 |  | 88 |  | FALSE
6820 | ST-2025-027 | 2026-08-01 | 86 |  | 88 |  | FALSE
6821 | ST-2025-027 | 2026-09-01 | 86 |  | 88 |  | FALSE
6822 | ST-2025-027 | 2026-10-01 | 86 |  | 88 |  | FALSE
6823 | ST-2025-027 | 2026-11-01 | 86 |  | 88 |  | FALSE
6824 | ST-2025-028 | 2025-10-01 | 1520 | 1384 | 1439 | 1384 | TRUE
6825 | ST-2025-028 | 2025-11-01 | 1888 | 1873 | 1947 | 489 | TRUE
6826 | ST-2025-028 | 2025-12-01 | 2342 | 2103 | 2187 | 230 | TRUE
6827 | ST-2025-028 | 2026-01-01 | 2900 | 2728 | 2837 | 625 | TRUE
6828 | ST-2025-028 | 2026-02-01 | 3583 | 3264 | 3394 | 536 | TRUE
6829 | ST-2025-028 | 2026-03-01 | 4417 | 4262 | 4432 | 998 | TRUE
6830 | ST-2025-028 | 2026-04-01 | 5429 | 4992 | 5191 | 730 | TRUE
6831 | ST-2025-028 | 2026-05-01 | 6648 | 6573 | 6835 | 1581 | TRUE
6832 | ST-2025-028 | 2026-06-01 | 8105 |  | 8210 |  | FALSE
6833 | ST-2025-028 | 2026-07-01 | 9831 |  | 9959 |  | FALSE
6834 | ST-2025-028 | 2026-08-01 | 11851 |  | 12005 |  | FALSE
6835 | ST-2025-028 | 2026-09-01 | 14185 |  | 14369 |  | FALSE
6836 | ST-2025-028 | 2026-10-01 | 16841 |  | 17060 |  | FALSE
6837 | ST-2025-028 | 2026-11-01 | 19811 |  | 20069 |  | FALSE
6838 | ST-2025-028 | 2026-12-01 | 23068 |  | 23368 |  | FALSE
6839 | ST-2025-028 | 2027-01-01 | 26566 |  | 26912 |  | FALSE
6840 | ST-2025-028 | 2027-02-01 | 30237 |  | 30631 |  | FALSE
6841 | ST-2025-028 | 2027-03-01 | 34000 |  | 34443 |  | FALSE
6842 | ST-2025-028 | 2027-04-01 | 37762 |  | 38254 |  | FALSE
6843 | ST-2025-028 | 2027-05-01 | 41433 |  | 41973 |  | FALSE
6844 | ST-2025-028 | 2027-06-01 | 44931 |  | 45516 |  | FALSE
6845 | ST-2025-028 | 2027-07-01 | 48188 |  | 48816 |  | FALSE
6846 | ST-2025-028 | 2027-08-01 | 51158 |  | 51825 |  | FALSE
6847 | ST-2025-028 | 2027-09-01 | 53814 |  | 54515 |  | FALSE
6848 | ST-2025-028 | 2027-10-01 | 56148 |  | 56880 |  | FALSE
6849 | ST-2025-028 | 2027-11-01 | 58168 |  | 58926 |  | FALSE
6850 | ST-2025-028 | 2027-12-01 | 59894 |  | 60675 |  | FALSE
6851 | ST-2025-028 | 2028-01-01 | 61351 |  | 62151 |  | FALSE
6852 | ST-2025-028 | 2028-02-01 | 62570 |  | 63385 |  | FALSE
6853 | ST-2025-028 | 2028-03-01 | 63582 |  | 64411 |  | FALSE
6854 | ST-2025-028 | 2028-04-01 | 64416 |  | 65256 |  | FALSE
6855 | ST-2025-028 | 2028-05-01 | 65099 |  | 65947 |  | FALSE
6856 | ST-2025-028 | 2028-06-01 | 65657 |  | 66513 |  | FALSE
6857 | ST-2025-028 | 2028-07-01 | 66111 |  | 66973 |  | FALSE
6858 | ST-2025-028 | 2028-08-01 | 66479 |  | 67345 |  | FALSE
6859 | ST-2025-028 | 2028-09-01 | 66776 |  | 67646 |  | FALSE
6860 | ST-2025-028 | 2028-10-01 | 66776 |  | 67646 |  | FALSE
6861 | ST-2025-028 | 2028-11-01 | 66776 |  | 67646 |  | FALSE
6862 | ST-2025-028 | 2028-12-01 | 66776 |  | 67646 |  | FALSE
6863 | ST-2025-029 | 2024-07-01 | 4 | 2 | 2 | 2 | TRUE
6864 | ST-2025-029 | 2024-08-01 | 6 | 3 | 3 | 1 | TRUE
6865 | ST-2025-029 | 2024-09-01 | 8 | 5 | 5 | 2 | TRUE
6866 | ST-2025-029 | 2024-10-01 | 11 | 6 | 6 | 1 | TRUE
6867 | ST-2025-029 | 2024-11-01 | 15 | 9 | 9 | 3 | TRUE
6868 | ST-2025-029 | 2024-12-01 | 20 | 12 | 12 | 3 | TRUE
6869 | ST-2025-029 | 2025-01-01 | 27 | 15 | 15 | 3 | TRUE
6870 | ST-2025-029 | 2025-02-01 | 35 | 20 | 20 | 5 | TRUE
6871 | ST-2025-029 | 2025-03-01 | 45 | 28 | 29 | 8 | TRUE
6872 | ST-2025-029 | 2025-04-01 | 56 | 34 | 35 | 6 | TRUE
6873 | ST-2025-029 | 2025-05-01 | 70 | 42 | 43 | 8 | TRUE
6874 | ST-2025-029 | 2025-06-01 | 84 | 52 | 54 | 10 | TRUE
6875 | ST-2025-029 | 2025-07-01 | 100 | 57 | 59 | 5 | TRUE
6876 | ST-2025-029 | 2025-08-01 | 115 | 68 | 70 | 11 | TRUE
6877 | ST-2025-029 | 2025-09-01 | 129 | 82 | 85 | 14 | TRUE
6878 | ST-2025-029 | 2025-10-01 | 143 | 82 | 85 | 0 | TRUE
6879 | ST-2025-029 | 2025-11-01 | 154 | 92 | 95 | 10 | TRUE
6880 | ST-2025-029 | 2025-12-01 | 164 | 97 | 100 | 5 | TRUE
6881 | ST-2025-029 | 2026-01-01 | 172 | 103 | 107 | 6 | TRUE
6882 | ST-2025-029 | 2026-02-01 | 179 | 105 | 109 | 2 | TRUE
6883 | ST-2025-029 | 2026-03-01 | 184 | 115 | 119 | 10 | TRUE
6884 | ST-2025-029 | 2026-04-01 | 188 | 117 | 121 | 2 | TRUE
6885 | ST-2025-029 | 2026-05-01 | 191 | 122 | 126 | 5 | TRUE
6886 | ST-2025-029 | 2026-06-01 | 193 |  | 173 |  | FALSE
6887 | ST-2025-029 | 2026-07-01 | 195 |  | 175 |  | FALSE
6888 | ST-2025-029 | 2026-08-01 | 196 |  | 176 |  | FALSE
6889 | ST-2025-029 | 2026-09-01 | 196 |  | 176 |  | FALSE
6890 | ST-2025-029 | 2026-10-01 | 196 |  | 176 |  | FALSE
6891 | ST-2025-029 | 2026-11-01 | 196 |  | 176 |  | FALSE
6892 | ST-2025-029 | 2026-12-01 | 196 |  | 176 |  | FALSE
6893 | ST-2025-030 | 2024-04-01 | 32 | 21 | 21 | 21 | TRUE
6894 | ST-2025-030 | 2024-05-01 | 43 | 31 | 32 | 10 | TRUE
6895 | ST-2025-030 | 2024-06-01 | 56 | 40 | 41 | 9 | TRUE
6896 | ST-2025-030 | 2024-07-01 | 73 | 49 | 50 | 9 | TRUE
6897 | ST-2025-030 | 2024-08-01 | 94 | 64 | 66 | 15 | TRUE
6898 | ST-2025-030 | 2024-09-01 | 122 | 85 | 88 | 21 | TRUE
6899 | ST-2025-030 | 2024-10-01 | 157 | 113 | 117 | 28 | TRUE
6900 | ST-2025-030 | 2024-11-01 | 199 | 144 | 149 | 31 | TRUE
6901 | ST-2025-030 | 2024-12-01 | 251 | 174 | 180 | 30 | TRUE
6902 | ST-2025-030 | 2025-01-01 | 313 | 213 | 221 | 39 | TRUE
6903 | ST-2025-030 | 2025-02-01 | 386 | 255 | 265 | 42 | TRUE
6904 | ST-2025-030 | 2025-03-01 | 467 | 334 | 347 | 79 | TRUE
6905 | ST-2025-030 | 2025-04-01 | 557 | 382 | 397 | 48 | TRUE
6906 | ST-2025-030 | 2025-05-01 | 651 | 434 | 451 | 52 | TRUE
6907 | ST-2025-030 | 2025-06-01 | 748 | 502 | 522 | 68 | TRUE
6908 | ST-2025-030 | 2025-07-01 | 842 | 563 | 585 | 61 | TRUE
6909 | ST-2025-030 | 2025-08-01 | 932 | 635 | 660 | 72 | TRUE
6910 | ST-2025-030 | 2025-09-01 | 1013 | 672 | 698 | 37 | TRUE
6911 | ST-2025-030 | 2025-10-01 | 1086 | 735 | 764 | 63 | TRUE
6912 | ST-2025-030 | 2025-11-01 | 1148 | 750 | 780 | 15 | TRUE
6913 | ST-2025-030 | 2025-12-01 | 1200 | 847 | 880 | 97 | TRUE
6914 | ST-2025-030 | 2026-01-01 | 1242 | 879 | 914 | 32 | TRUE
6915 | ST-2025-030 | 2026-02-01 | 1277 | 854 | 888 | 0 | TRUE
6916 | ST-2025-030 | 2026-03-01 | 1305 | 909 | 945 | 55 | TRUE
6917 | ST-2025-030 | 2026-04-01 | 1326 | 898 | 933 | 0 | TRUE
6918 | ST-2025-030 | 2026-05-01 | 1343 | 900 | 936 | 2 | TRUE
6919 | ST-2025-030 | 2026-06-01 | 1356 |  | 1220 |  | FALSE
6920 | ST-2025-030 | 2026-07-01 | 1367 |  | 1230 |  | FALSE
6921 | ST-2025-030 | 2026-08-01 | 1374 |  | 1236 |  | FALSE
6922 | ST-2025-030 | 2026-09-01 | 1374 |  | 1236 |  | FALSE
6923 | ST-2025-030 | 2026-10-01 | 1374 |  | 1236 |  | FALSE
6924 | ST-2025-030 | 2026-11-01 | 1374 |  | 1236 |  | FALSE
6925 | ST-2025-031 | 2027-01-01 | 1 |  | 1 |  | FALSE
6926 | ST-2025-031 | 2027-02-01 | 1 |  | 1 |  | FALSE
6927 | ST-2025-031 | 2027-03-01 | 2 |  | 2 |  | FALSE
6928 | ST-2025-031 | 2027-04-01 | 3 |  | 3 |  | FALSE
6929 | ST-2025-031 | 2027-05-01 | 3 |  | 3 |  | FALSE
6930 | ST-2025-031 | 2027-06-01 | 4 |  | 4 |  | FALSE
6931 | ST-2025-031 | 2027-07-01 | 5 |  | 5 |  | FALSE
6932 | ST-2025-031 | 2027-08-01 | 7 |  | 7 |  | FALSE
6933 | ST-2025-031 | 2027-09-01 | 8 |  | 8 |  | FALSE
6934 | ST-2025-031 | 2027-10-01 | 10 |  | 10 |  | FALSE
6935 | ST-2025-031 | 2027-11-01 | 13 |  | 13 |  | FALSE
6936 | ST-2025-031 | 2027-12-01 | 16 |  | 16 |  | FALSE
6937 | ST-2025-031 | 2028-01-01 | 19 |  | 19 |  | FALSE
6938 | ST-2025-031 | 2028-02-01 | 22 |  | 22 |  | FALSE
6939 | ST-2025-031 | 2028-03-01 | 26 |  | 26 |  | FALSE
6940 | ST-2025-031 | 2028-04-01 | 30 |  | 30 |  | FALSE
6941 | ST-2025-031 | 2028-05-01 | 34 |  | 34 |  | FALSE
6942 | ST-2025-031 | 2028-06-01 | 37 |  | 37 |  | FALSE
6943 | ST-2025-031 | 2028-07-01 | 41 |  | 41 |  | FALSE
6944 | ST-2025-031 | 2028-08-01 | 45 |  | 45 |  | FALSE
6945 | ST-2025-031 | 2028-09-01 | 48 |  | 48 |  | FALSE
6946 | ST-2025-031 | 2028-10-01 | 51 |  | 51 |  | FALSE
6947 | ST-2025-031 | 2028-11-01 | 54 |  | 54 |  | FALSE
6948 | ST-2025-031 | 2028-12-01 | 57 |  | 57 |  | FALSE
6949 | ST-2025-031 | 2029-01-01 | 59 |  | 59 |  | FALSE
6950 | ST-2025-031 | 2029-02-01 | 60 |  | 60 |  | FALSE
6951 | ST-2025-031 | 2029-03-01 | 62 |  | 62 |  | FALSE
6952 | ST-2025-031 | 2029-04-01 | 63 |  | 63 |  | FALSE
6953 | ST-2025-031 | 2029-05-01 | 64 |  | 64 |  | FALSE
6954 | ST-2025-031 | 2029-06-01 | 64 |  | 64 |  | FALSE
6955 | ST-2025-031 | 2029-07-01 | 65 |  | 65 |  | FALSE
6956 | ST-2025-031 | 2029-08-01 | 66 |  | 66 |  | FALSE
6957 | ST-2025-031 | 2029-09-01 | 66 |  | 66 |  | FALSE
6958 | ST-2025-031 | 2029-10-01 | 66 |  | 66 |  | FALSE
6959 | ST-2025-031 | 2029-11-01 | 66 |  | 66 |  | FALSE
6960 | ST-2025-031 | 2029-12-01 | 66 |  | 66 |  | FALSE
6961 | ST-2025-031 | 2030-01-01 | 66 |  | 66 |  | FALSE
6962 | ST-2025-031 | 2030-02-01 | 66 |  | 66 |  | FALSE
6963 | ST-2025-032 | 2025-05-01 | 6 | 5 | 5 | 5 | TRUE
6964 | ST-2025-032 | 2025-06-01 | 7 | 6 | 6 | 1 | TRUE
6965 | ST-2025-032 | 2025-07-01 | 8 | 7 | 7 | 1 | TRUE
6966 | ST-2025-032 | 2025-08-01 | 9 | 8 | 8 | 1 | TRUE
6967 | ST-2025-032 | 2025-09-01 | 10 | 9 | 9 | 1 | TRUE
6968 | ST-2025-032 | 2025-10-01 | 12 | 10 | 10 | 1 | TRUE
6969 | ST-2025-032 | 2025-11-01 | 14 | 13 | 13 | 3 | TRUE
6970 | ST-2025-032 | 2025-12-01 | 16 | 13 | 13 | 0 | TRUE
6971 | ST-2025-032 | 2026-01-01 | 18 | 16 | 16 | 3 | TRUE
6972 | ST-2025-032 | 2026-02-01 | 21 | 20 | 20 | 4 | TRUE
6973 | ST-2025-032 | 2026-03-01 | 24 | 22 | 22 | 2 | TRUE
6974 | ST-2025-032 | 2026-04-01 | 27 | 25 | 26 | 3 | TRUE
6975 | ST-2025-032 | 2026-05-01 | 31 | 28 | 29 | 3 | TRUE
6976 | ST-2025-032 | 2026-06-01 | 35 |  | 34 |  | FALSE
6977 | ST-2025-032 | 2026-07-01 | 40 |  | 39 |  | FALSE
6978 | ST-2025-032 | 2026-08-01 | 45 |  | 44 |  | FALSE
6979 | ST-2025-032 | 2026-09-01 | 51 |  | 50 |  | FALSE
6980 | ST-2025-032 | 2026-10-01 | 57 |  | 56 |  | FALSE
6981 | ST-2025-032 | 2026-11-01 | 64 |  | 62 |  | FALSE
6982 | ST-2025-032 | 2026-12-01 | 72 |  | 70 |  | FALSE
6983 | ST-2025-032 | 2027-01-01 | 80 |  | 78 |  | FALSE
6984 | ST-2025-032 | 2027-02-01 | 89 |  | 87 |  | FALSE
6985 | ST-2025-032 | 2027-03-01 | 98 |  | 96 |  | FALSE
6986 | ST-2025-032 | 2027-04-01 | 108 |  | 106 |  | FALSE
6987 | ST-2025-032 | 2027-05-01 | 118 |  | 116 |  | FALSE
6988 | ST-2025-032 | 2027-06-01 | 128 |  | 125 |  | FALSE
6989 | ST-2025-032 | 2027-07-01 | 139 |  | 136 |  | FALSE
6990 | ST-2025-032 | 2027-08-01 | 150 |  | 147 |  | FALSE
6991 | ST-2025-032 | 2027-09-01 | 160 |  | 157 |  | FALSE
6992 | ST-2025-032 | 2027-10-01 | 171 |  | 168 |  | FALSE
6993 | ST-2025-032 | 2027-11-01 | 181 |  | 178 |  | FALSE
6994 | ST-2025-032 | 2027-12-01 | 191 |  | 187 |  | FALSE
6995 | ST-2025-032 | 2028-01-01 | 201 |  | 197 |  | FALSE
6996 | ST-2025-032 | 2028-02-01 | 210 |  | 206 |  | FALSE
6997 | ST-2025-032 | 2028-03-01 | 219 |  | 215 |  | FALSE
6998 | ST-2025-032 | 2028-04-01 | 227 |  | 223 |  | FALSE
6999 | ST-2025-032 | 2028-05-01 | 235 |  | 231 |  | FALSE
7000 | ST-2025-032 | 2028-06-01 | 242 |  | 238 |  | FALSE
7001 | ST-2025-032 | 2028-07-01 | 248 |  | 244 |  | FALSE
7002 | ST-2025-032 | 2028-08-01 | 254 |  | 249 |  | FALSE
7003 | ST-2025-032 | 2028-09-01 | 259 |  | 254 |  | FALSE
7004 | ST-2025-032 | 2028-10-01 | 264 |  | 259 |  | FALSE
7005 | ST-2025-032 | 2028-11-01 | 268 |  | 263 |  | FALSE
7006 | ST-2025-032 | 2028-12-01 | 272 |  | 267 |  | FALSE
7007 | ST-2025-032 | 2029-01-01 | 275 |  | 270 |  | FALSE
7008 | ST-2025-032 | 2029-02-01 | 278 |  | 273 |  | FALSE
7009 | ST-2025-032 | 2029-03-01 | 281 |  | 276 |  | FALSE
7010 | ST-2025-032 | 2029-04-01 | 283 |  | 278 |  | FALSE
7011 | ST-2025-032 | 2029-05-01 | 285 |  | 280 |  | FALSE
7012 | ST-2025-032 | 2029-06-01 | 287 |  | 282 |  | FALSE
7013 | ST-2025-032 | 2029-07-01 | 289 |  | 284 |  | FALSE
7014 | ST-2025-032 | 2029-08-01 | 290 |  | 285 |  | FALSE
7015 | ST-2025-032 | 2029-09-01 | 291 |  | 286 |  | FALSE
7016 | ST-2025-032 | 2029-10-01 | 292 |  | 287 |  | FALSE
7017 | ST-2025-032 | 2029-11-01 | 293 |  | 288 |  | FALSE
7018 | ST-2025-032 | 2029-12-01 | 294 |  | 289 |  | FALSE
7019 | ST-2025-032 | 2030-01-01 | 294 |  | 289 |  | FALSE
7020 | ST-2025-032 | 2030-02-01 | 294 |  | 289 |  | FALSE
7021 | ST-2025-032 | 2030-03-01 | 294 |  | 289 |  | FALSE
7022 | ST-2025-033 | 2022-04-01 | 0 | 0 | 0 | 0 | FALSE
7023 | ST-2025-033 | 2022-05-01 | 0 | 0 | 0 | 0 | FALSE
7024 | ST-2025-033 | 2022-06-01 | 0 | 0 | 0 | 0 | FALSE
7025 | ST-2025-033 | 2022-07-01 | 0 | 0 | 0 | 0 | FALSE
7026 | ST-2025-033 | 2022-08-01 | 0 | 0 | 0 | 0 | FALSE
7027 | ST-2025-033 | 2022-09-01 | 0 | 0 | 0 | 0 | FALSE
7028 | ST-2025-033 | 2022-10-01 | 1 | 0 | 0 | 0 | TRUE
7029 | ST-2025-033 | 2022-11-01 | 1 | 0 | 0 | 0 | TRUE
7030 | ST-2025-033 | 2022-12-01 | 1 | 0 | 0 | 0 | TRUE
7031 | ST-2025-033 | 2023-01-01 | 1 | 0 | 0 | 0 | TRUE
7032 | ST-2025-033 | 2023-02-01 | 1 | 0 | 0 | 0 | TRUE
7033 | ST-2025-033 | 2023-03-01 | 2 | 1 | 1 | 1 | TRUE
7034 | ST-2025-033 | 2023-04-01 | 2 | 1 | 1 | 0 | TRUE
7035 | ST-2025-033 | 2023-05-01 | 3 | 2 | 2 | 1 | TRUE
7036 | ST-2025-033 | 2023-06-01 | 3 | 2 | 2 | 0 | TRUE
7037 | ST-2025-033 | 2023-07-01 | 4 | 3 | 3 | 1 | TRUE
7038 | ST-2025-033 | 2023-08-01 | 4 | 3 | 3 | 0 | TRUE
7039 | ST-2025-033 | 2023-09-01 | 5 | 4 | 4 | 1 | TRUE
7040 | ST-2025-033 | 2023-10-01 | 6 | 5 | 5 | 1 | TRUE
7041 | ST-2025-033 | 2023-11-01 | 6 | 5 | 5 | 0 | TRUE
7042 | ST-2025-033 | 2023-12-01 | 7 | 5 | 5 | 0 | TRUE
7043 | ST-2025-033 | 2024-01-01 | 8 | 7 | 7 | 2 | TRUE
7044 | ST-2025-033 | 2024-02-01 | 9 | 7 | 7 | 0 | TRUE
7045 | ST-2025-033 | 2024-03-01 | 9 | 7 | 7 | 0 | TRUE
7046 | ST-2025-033 | 2024-04-01 | 10 | 9 | 9 | 2 | TRUE
7047 | ST-2025-033 | 2024-05-01 | 11 | 9 | 9 | 0 | TRUE
7048 | ST-2025-033 | 2024-06-01 | 11 | 10 | 10 | 1 | TRUE
7049 | ST-2025-033 | 2024-07-01 | 12 | 10 | 10 | 0 | TRUE
7050 | ST-2025-033 | 2024-08-01 | 12 | 10 | 10 | 0 | TRUE
7051 | ST-2025-033 | 2024-09-01 | 13 | 11 | 11 | 1 | TRUE
7052 | ST-2025-033 | 2024-10-01 | 13 | 10 | 10 | 0 | TRUE
7053 | ST-2025-033 | 2024-11-01 | 14 | 12 | 12 | 2 | TRUE
7054 | ST-2025-033 | 2024-12-01 | 14 | 12 | 12 | 0 | TRUE
7055 | ST-2025-033 | 2025-01-01 | 14 | 11 | 11 | 0 | TRUE
7056 | ST-2025-033 | 2025-02-01 | 14 | 11 | 11 | 0 | TRUE
7057 | ST-2025-033 | 2025-03-01 | 14 | 12 | 12 | 1 | TRUE
7058 | ST-2025-033 | 2025-04-01 | 15 | 13 | 13 | 1 | TRUE
7059 | ST-2025-033 | 2025-05-01 | 15 | 13 | 13 | 0 | TRUE
7060 | ST-2025-033 | 2025-06-01 | 15 | 12 | 12 | 0 | TRUE
7061 | ST-2025-033 | 2025-07-01 | 15 | 12 | 12 | 0 | TRUE
7062 | ST-2025-033 | 2025-08-01 | 15 | 13 | 13 | 1 | TRUE
7063 | ST-2025-033 | 2025-09-01 | 15 | 13 | 13 | 0 | TRUE
7064 | ST-2025-033 | 2025-10-01 | 15 | 12 | 12 | 0 | TRUE
7065 | ST-2025-033 | 2025-11-01 | 15 | 12 | 12 | 0 | TRUE
7066 | ST-2025-033 | 2025-12-01 | 15 | 13 | 13 | 1 | TRUE
7067 | ST-2025-033 | 2026-01-01 | 15 | 13 | 13 | 0 | TRUE
7068 | ST-2025-034 | 2023-06-01 | 0 | 0 | 0 | 0 | FALSE
7069 | ST-2025-034 | 2023-07-01 | 0 | 0 | 0 | 0 | FALSE
7070 | ST-2025-034 | 2023-08-01 | 0 | 0 | 0 | 0 | FALSE
7071 | ST-2025-034 | 2023-09-01 | 0 | 0 | 0 | 0 | FALSE
7072 | ST-2025-034 | 2023-10-01 | 0 | 0 | 0 | 0 | FALSE
7073 | ST-2025-034 | 2023-11-01 | 1 | 0 | 0 | 0 | TRUE
7074 | ST-2025-034 | 2023-12-01 | 1 | 0 | 0 | 0 | TRUE
7075 | ST-2025-034 | 2024-01-01 | 1 | 0 | 0 | 0 | TRUE
7076 | ST-2025-034 | 2024-02-01 | 1 | 0 | 0 | 0 | TRUE
7077 | ST-2025-034 | 2024-03-01 | 2 | 1 | 1 | 1 | TRUE
7078 | ST-2025-034 | 2024-04-01 | 2 | 2 | 2 | 1 | FALSE
7079 | ST-2025-034 | 2024-05-01 | 3 | 2 | 2 | 0 | TRUE
7080 | ST-2025-034 | 2024-06-01 | 3 | 3 | 3 | 1 | FALSE
7081 | ST-2025-034 | 2024-07-01 | 4 | 3 | 3 | 0 | TRUE
7082 | ST-2025-034 | 2024-08-01 | 4 | 3 | 3 | 0 | TRUE
7083 | ST-2025-034 | 2024-09-01 | 5 | 5 | 5 | 2 | FALSE
7084 | ST-2025-034 | 2024-10-01 | 6 | 5 | 5 | 0 | TRUE
7085 | ST-2025-034 | 2024-11-01 | 7 | 6 | 6 | 1 | TRUE
7086 | ST-2025-034 | 2024-12-01 | 8 | 7 | 7 | 1 | TRUE
7087 | ST-2025-034 | 2025-01-01 | 9 | 9 | 9 | 2 | FALSE
7088 | ST-2025-034 | 2025-02-01 | 10 | 9 | 9 | 0 | TRUE
7089 | ST-2025-034 | 2025-03-01 | 10 | 9 | 9 | 0 | TRUE
7090 | ST-2025-034 | 2025-04-01 | 11 | 10 | 10 | 1 | TRUE
7091 | ST-2025-034 | 2025-05-01 | 12 | 11 | 11 | 1 | TRUE
7092 | ST-2025-034 | 2025-06-01 | 13 | 12 | 12 | 1 | TRUE
7093 | ST-2025-034 | 2025-07-01 | 14 | 14 | 14 | 2 | FALSE
7094 | ST-2025-034 | 2025-08-01 | 15 | 14 | 14 | 0 | TRUE
7095 | ST-2025-034 | 2025-09-01 | 15 | 15 | 15 | 1 | FALSE
7096 | ST-2025-034 | 2025-10-01 | 16 | 15 | 15 | 0 | TRUE
7097 | ST-2025-034 | 2025-11-01 | 16 | 15 | 15 | 0 | TRUE
7098 | ST-2025-034 | 2025-12-01 | 17 | 16 | 16 | 1 | TRUE
7099 | ST-2025-034 | 2026-01-01 | 17 | 16 | 16 | 0 | TRUE
7100 | ST-2025-034 | 2026-02-01 | 18 | 17 | 17 | 1 | TRUE
7101 | ST-2025-034 | 2026-03-01 | 18 | 18 | 18 | 1 | FALSE
7102 | ST-2025-034 | 2026-04-01 | 18 | 17 | 17 | 0 | TRUE
7103 | ST-2025-034 | 2026-05-01 | 18 | 17 | 17 | 0 | TRUE
7104 | ST-2025-034 | 2026-06-01 | 19 |  | 19 |  | FALSE
7105 | ST-2025-034 | 2026-07-01 | 19 |  | 19 |  | FALSE
7106 | ST-2025-034 | 2026-08-01 | 19 |  | 19 |  | FALSE
7107 | ST-2025-034 | 2026-09-01 | 19 |  | 19 |  | FALSE
7108 | ST-2025-034 | 2026-10-01 | 19 |  | 19 |  | FALSE
7109 | ST-2025-034 | 2026-11-01 | 19 |  | 19 |  | FALSE
7110 | ST-2025-034 | 2026-12-01 | 19 |  | 19 |  | FALSE
7111 | ST-2025-034 | 2027-01-01 | 19 |  | 19 |  | FALSE
7112 | ST-2025-034 | 2027-02-01 | 19 |  | 19 |  | FALSE
7113 | ST-2025-035 | 2025-06-01 | 0 | 0 | 0 | 0 | FALSE
7114 | ST-2025-035 | 2025-07-01 | 0 | 0 | 0 | 0 | FALSE
7115 | ST-2025-035 | 2025-08-01 | 0 | 0 | 0 | 0 | FALSE
7116 | ST-2025-035 | 2025-09-01 | 1 | 1 | 1 | 1 | FALSE
7117 | ST-2025-035 | 2025-10-01 | 1 | 1 | 1 | 0 | FALSE
7118 | ST-2025-035 | 2025-11-01 | 2 | 2 | 2 | 1 | FALSE
7119 | ST-2025-035 | 2025-12-01 | 3 | 3 | 3 | 1 | FALSE
7120 | ST-2025-035 | 2026-01-01 | 4 | 4 | 4 | 1 | FALSE
7121 | ST-2025-035 | 2026-02-01 | 5 | 5 | 5 | 1 | FALSE
7122 | ST-2025-035 | 2026-03-01 | 6 | 6 | 6 | 1 | FALSE
7123 | ST-2025-035 | 2026-04-01 | 8 | 8 | 8 | 2 | FALSE
7124 | ST-2025-035 | 2026-05-01 | 9 | 9 | 9 | 1 | FALSE
7125 | ST-2025-035 | 2026-06-01 | 10 |  | 10 |  | FALSE
7126 | ST-2025-035 | 2026-07-01 | 11 |  | 11 |  | FALSE
7127 | ST-2025-035 | 2026-08-01 | 12 |  | 12 |  | FALSE
7128 | ST-2025-035 | 2026-09-01 | 13 |  | 13 |  | FALSE
7129 | ST-2025-035 | 2026-10-01 | 13 |  | 13 |  | FALSE
7130 | ST-2025-035 | 2026-11-01 | 14 |  | 14 |  | FALSE
7131 | ST-2025-035 | 2026-12-01 | 14 |  | 14 |  | FALSE
7132 | ST-2025-035 | 2027-01-01 | 14 |  | 14 |  | FALSE
7133 | ST-2025-035 | 2027-02-01 | 14 |  | 14 |  | FALSE
7134 | ST-2025-035 | 2027-03-01 | 14 |  | 14 |  | FALSE
7135 | ST-2025-035 | 2027-04-01 | 14 |  | 14 |  | FALSE
7136 | ST-2025-035 | 2027-05-01 | 14 |  | 14 |  | FALSE
7137 | ST-2025-035 | 2027-06-01 | 14 |  | 14 |  | FALSE
7138 | ST-2025-036 | 2021-11-01 | 9 | 8 | 8 | 8 | TRUE
7139 | ST-2025-036 | 2021-12-01 | 11 | 10 | 10 | 2 | TRUE
7140 | ST-2025-036 | 2022-01-01 | 12 | 10 | 10 | 0 | TRUE
7141 | ST-2025-036 | 2022-02-01 | 13 | 11 | 11 | 1 | TRUE
7142 | ST-2025-036 | 2022-03-01 | 15 | 14 | 14 | 3 | TRUE
7143 | ST-2025-036 | 2022-04-01 | 16 | 14 | 14 | 0 | TRUE
7144 | ST-2025-036 | 2022-05-01 | 18 | 17 | 17 | 3 | TRUE
7145 | ST-2025-036 | 2022-06-01 | 20 | 18 | 18 | 1 | TRUE
7146 | ST-2025-036 | 2022-07-01 | 22 | 19 | 19 | 1 | TRUE
7147 | ST-2025-036 | 2022-08-01 | 25 | 22 | 22 | 3 | TRUE
7148 | ST-2025-036 | 2022-09-01 | 27 | 24 | 24 | 2 | TRUE
7149 | ST-2025-036 | 2022-10-01 | 30 | 27 | 28 | 3 | TRUE
7150 | ST-2025-036 | 2022-11-01 | 34 | 30 | 31 | 3 | TRUE
7151 | ST-2025-036 | 2022-12-01 | 37 | 33 | 34 | 3 | TRUE
7152 | ST-2025-036 | 2023-01-01 | 41 | 38 | 39 | 5 | TRUE
7153 | ST-2025-036 | 2023-02-01 | 45 | 43 | 44 | 5 | TRUE
7154 | ST-2025-036 | 2023-03-01 | 50 | 45 | 46 | 2 | TRUE
7155 | ST-2025-036 | 2023-04-01 | 55 | 51 | 53 | 6 | TRUE
7156 | ST-2025-036 | 2023-05-01 | 61 | 55 | 57 | 4 | TRUE
7157 | ST-2025-036 | 2023-06-01 | 66 | 58 | 60 | 3 | TRUE
7158 | ST-2025-036 | 2023-07-01 | 73 | 70 | 72 | 12 | TRUE
7159 | ST-2025-036 | 2023-08-01 | 80 | 71 | 73 | 1 | TRUE
7160 | ST-2025-036 | 2023-09-01 | 87 | 84 | 87 | 13 | TRUE
7161 | ST-2025-036 | 2023-10-01 | 95 | 91 | 94 | 7 | TRUE
7162 | ST-2025-036 | 2023-11-01 | 104 | 95 | 98 | 4 | TRUE
7163 | ST-2025-036 | 2023-12-01 | 113 | 110 | 114 | 15 | TRUE
7164 | ST-2025-036 | 2024-01-01 | 123 | 120 | 124 | 10 | TRUE
7165 | ST-2025-036 | 2024-02-01 | 133 | 124 | 128 | 4 | TRUE
7166 | ST-2025-036 | 2024-03-01 | 143 | 140 | 145 | 16 | TRUE
7167 | ST-2025-036 | 2024-04-01 | 155 | 140 | 145 | 0 | TRUE
7168 | ST-2025-036 | 2024-05-01 | 166 | 155 | 161 | 15 | TRUE
7169 | ST-2025-036 | 2024-06-01 | 178 | 166 | 172 | 11 | TRUE
7170 | ST-2025-036 | 2024-07-01 | 191 | 176 | 183 | 10 | TRUE
7171 | ST-2025-036 | 2024-08-01 | 203 | 194 | 201 | 18 | TRUE
7172 | ST-2025-036 | 2024-09-01 | 216 | 207 | 215 | 13 | TRUE
7173 | ST-2025-036 | 2024-10-01 | 230 | 210 | 218 | 3 | TRUE
7174 | ST-2025-036 | 2024-11-01 | 243 | 234 | 243 | 24 | TRUE
7175 | ST-2025-036 | 2024-12-01 | 256 | 227 | 236 | 0 | TRUE
7176 | ST-2025-036 | 2025-01-01 | 269 | 242 | 251 | 15 | TRUE
7177 | ST-2025-036 | 2025-02-01 | 283 | 263 | 273 | 21 | TRUE
7178 | ST-2025-036 | 2025-03-01 | 296 | 274 | 284 | 11 | TRUE
7179 | ST-2025-036 | 2025-04-01 | 308 | 288 | 299 | 14 | TRUE
7180 | ST-2025-036 | 2025-05-01 | 321 | 286 | 297 | 0 | TRUE
7181 | ST-2025-036 | 2025-06-01 | 333 | 313 | 325 | 27 | TRUE
7182 | ST-2025-036 | 2025-07-01 | 344 | 338 | 351 | 25 | TRUE
7183 | ST-2025-036 | 2025-08-01 | 356 | 334 | 347 | 0 | TRUE
7184 | ST-2025-036 | 2025-09-01 | 366 | 325 | 338 | 0 | TRUE
7185 | ST-2025-036 | 2025-10-01 | 376 | 350 | 364 | 25 | TRUE
7186 | ST-2025-036 | 2025-11-01 | 386 | 343 | 356 | 0 | TRUE
7187 | ST-2025-036 | 2025-12-01 | 395 | 371 | 385 | 28 | TRUE
7188 | ST-2025-036 | 2026-01-01 | 404 | 392 | 407 | 21 | TRUE
7189 | ST-2025-036 | 2026-02-01 | 412 | 399 | 414 | 7 | TRUE
7190 | ST-2025-036 | 2026-03-01 | 419 | 393 | 408 | 0 | TRUE
7191 | ST-2025-036 | 2026-04-01 | 426 | 403 | 419 | 10 | TRUE
7192 | ST-2025-036 | 2026-05-01 | 433 | 412 | 428 | 9 | TRUE
7193 | ST-2025-036 | 2026-06-01 | 438 |  | 439 |  | FALSE
7194 | ST-2025-036 | 2026-07-01 | 444 |  | 445 |  | FALSE
7195 | ST-2025-036 | 2026-08-01 | 449 |  | 450 |  | FALSE
7196 | ST-2025-036 | 2026-09-01 | 454 |  | 455 |  | FALSE
7197 | ST-2025-036 | 2026-10-01 | 458 |  | 459 |  | FALSE
7198 | ST-2025-036 | 2026-11-01 | 462 |  | 463 |  | FALSE
7199 | ST-2025-036 | 2026-12-01 | 465 |  | 466 |  | FALSE
7200 | ST-2025-036 | 2027-01-01 | 469 |  | 470 |  | FALSE
7201 | ST-2025-036 | 2027-02-01 | 472 |  | 473 |  | FALSE
7202 | ST-2025-036 | 2027-03-01 | 474 |  | 475 |  | FALSE
7203 | ST-2025-036 | 2027-04-01 | 477 |  | 478 |  | FALSE
7204 | ST-2025-036 | 2027-05-01 | 479 |  | 480 |  | FALSE
7205 | ST-2025-036 | 2027-06-01 | 481 |  | 482 |  | FALSE
7206 | ST-2025-036 | 2027-07-01 | 483 |  | 484 |  | FALSE
7207 | ST-2025-036 | 2027-08-01 | 484 |  | 485 |  | FALSE
7208 | ST-2025-036 | 2027-09-01 | 486 |  | 487 |  | FALSE
7209 | ST-2025-036 | 2027-10-01 | 487 |  | 488 |  | FALSE
7210 | ST-2025-036 | 2027-11-01 | 488 |  | 489 |  | FALSE
7211 | ST-2025-036 | 2027-12-01 | 490 |  | 491 |  | FALSE
7212 | ST-2025-036 | 2028-01-01 | 491 |  | 492 |  | FALSE
7213 | ST-2025-036 | 2028-02-01 | 491 |  | 492 |  | FALSE
7214 | ST-2025-036 | 2028-03-01 | 491 |  | 492 |  | FALSE
7215 | ST-2025-037 | 2026-08-01 | 277 |  | 249 |  | FALSE
7216 | ST-2025-037 | 2026-09-01 | 426 |  | 383 |  | FALSE
7217 | ST-2025-037 | 2026-10-01 | 649 |  | 584 |  | FALSE
7218 | ST-2025-037 | 2026-11-01 | 977 |  | 879 |  | FALSE
7219 | ST-2025-037 | 2026-12-01 | 1445 |  | 1300 |  | FALSE
7220 | ST-2025-037 | 2027-01-01 | 2086 |  | 1877 |  | FALSE
7221 | ST-2025-037 | 2027-02-01 | 2913 |  | 2621 |  | FALSE
7222 | ST-2025-037 | 2027-03-01 | 3906 |  | 3515 |  | FALSE
7223 | ST-2025-037 | 2027-04-01 | 5000 |  | 4500 |  | FALSE
7224 | ST-2025-037 | 2027-05-01 | 6093 |  | 5483 |  | FALSE
7225 | ST-2025-037 | 2027-06-01 | 7086 |  | 6377 |  | FALSE
7226 | ST-2025-037 | 2027-07-01 | 7913 |  | 7121 |  | FALSE
7227 | ST-2025-037 | 2027-08-01 | 8554 |  | 7698 |  | FALSE
7228 | ST-2025-037 | 2027-09-01 | 9022 |  | 8119 |  | FALSE
7229 | ST-2025-037 | 2027-10-01 | 9350 |  | 8415 |  | FALSE
7230 | ST-2025-037 | 2027-11-01 | 9573 |  | 8615 |  | FALSE
7231 | ST-2025-037 | 2027-12-01 | 9722 |  | 8749 |  | FALSE
7232 | ST-2025-037 | 2028-01-01 | 9820 |  | 8838 |  | FALSE
7233 | ST-2025-037 | 2028-02-01 | 9820 |  | 8838 |  | FALSE
7234 | ST-2025-037 | 2028-03-01 | 9820 |  | 8838 |  | FALSE
7235 | ST-2025-037 | 2028-04-01 | 9820 |  | 8838 |  | FALSE
7236 | ST-2025-037 | 2028-05-01 | 9820 |  | 8838 |  | FALSE

## Enrollment Rate
id | study_id | period_date | planned_rate | actual_rate | below_plan_flag
3437 | ST-2024-002 | 2024-09-01 | 3 | 2 | TRUE
3438 | ST-2024-002 | 2024-10-01 | 1 | 1 | TRUE
3439 | ST-2024-002 | 2024-11-01 | 1 | 1 | TRUE
3440 | ST-2024-002 | 2024-12-01 | 1 | 1 | TRUE
3441 | ST-2024-002 | 2025-01-01 | 1 | 0 | TRUE
3442 | ST-2024-002 | 2025-02-01 | 1 | 1 | TRUE
3443 | ST-2024-002 | 2025-03-01 | 2 | 2 | TRUE
3444 | ST-2024-002 | 2025-04-01 | 2 | 1 | TRUE
3445 | ST-2024-002 | 2025-05-01 | 2 | 2 | TRUE
3446 | ST-2024-002 | 2025-06-01 | 2 | 2 | TRUE
3447 | ST-2024-002 | 2025-07-01 | 3 | 3 | TRUE
3448 | ST-2024-002 | 2025-08-01 | 3 | 2 | TRUE
3449 | ST-2024-002 | 2025-09-01 | 4 | 2 | TRUE
3450 | ST-2024-002 | 2025-10-01 | 4 | 4 | TRUE
3451 | ST-2024-002 | 2025-11-01 | 5 | 3 | TRUE
3452 | ST-2024-002 | 2025-12-01 | 5 | 7 | TRUE
3453 | ST-2024-002 | 2026-01-01 | 6 | 5 | TRUE
3454 | ST-2024-002 | 2026-02-01 | 7 | 3 | TRUE
3455 | ST-2024-002 | 2026-03-01 | 6 | 7 | TRUE
3456 | ST-2024-002 | 2026-04-01 | 7 | 5 | TRUE
3457 | ST-2024-002 | 2026-05-01 | 8 | 4 | TRUE
3458 | ST-2024-003 | 2024-03-01 | 2 | 2 | FALSE
3459 | ST-2024-003 | 2024-04-01 | 1 | 1 | FALSE
3460 | ST-2024-003 | 2024-05-01 | 0 | 0 | FALSE
3461 | ST-2024-003 | 2024-06-01 | 1 | 1 | FALSE
3462 | ST-2024-003 | 2024-07-01 | 0 | 0 | FALSE
3463 | ST-2024-003 | 2024-08-01 | 1 | 0 | TRUE
3464 | ST-2024-003 | 2024-09-01 | 0 | 1 | FALSE
3465 | ST-2024-003 | 2024-10-01 | 1 | 1 | FALSE
3466 | ST-2024-003 | 2024-11-01 | 1 | 1 | FALSE
3467 | ST-2024-003 | 2024-12-01 | 1 | 1 | FALSE
3468 | ST-2024-003 | 2025-01-01 | 1 | 1 | FALSE
3469 | ST-2024-003 | 2025-02-01 | 1 | 0 | TRUE
3470 | ST-2024-003 | 2025-03-01 | 1 | 2 | FALSE
3471 | ST-2024-003 | 2025-04-01 | 2 | 2 | FALSE
3472 | ST-2024-003 | 2025-05-01 | 1 | 1 | FALSE
3473 | ST-2024-003 | 2025-06-01 | 2 | 2 | FALSE
3474 | ST-2024-003 | 2025-07-01 | 2 | 3 | FALSE
3475 | ST-2024-003 | 2025-08-01 | 2 | 0 | TRUE
3476 | ST-2024-003 | 2025-09-01 | 2 | 2 | TRUE
3477 | ST-2024-003 | 2025-10-01 | 2 | 3 | FALSE
3478 | ST-2024-003 | 2025-11-01 | 3 | 3 | FALSE
3479 | ST-2024-003 | 2025-12-01 | 2 | 3 | FALSE
3480 | ST-2024-003 | 2026-01-01 | 3 | 2 | FALSE
3481 | ST-2024-003 | 2026-02-01 | 4 | 6 | FALSE
3482 | ST-2024-003 | 2026-03-01 | 3 | 1 | FALSE
3483 | ST-2024-003 | 2026-04-01 | 3 | 5 | FALSE
3484 | ST-2024-003 | 2026-05-01 | 4 | 5 | FALSE
3485 | ST-2024-004 | 2025-01-01 | 3 | 2 | TRUE
3486 | ST-2024-004 | 2025-02-01 | 0 | 0 | TRUE
3487 | ST-2024-004 | 2025-03-01 | 1 | 1 | TRUE
3488 | ST-2024-004 | 2025-04-01 | 0 | 0 | TRUE
3489 | ST-2024-004 | 2025-05-01 | 1 | 1 | TRUE
3490 | ST-2024-004 | 2025-06-01 | 1 | 0 | TRUE
3491 | ST-2024-004 | 2025-07-01 | 2 | 2 | TRUE
3492 | ST-2024-004 | 2025-08-01 | 1 | 0 | TRUE
3493 | ST-2024-004 | 2025-09-01 | 1 | 1 | TRUE
3494 | ST-2024-004 | 2025-10-01 | 2 | 2 | TRUE
3495 | ST-2024-004 | 2025-11-01 | 2 | 2 | TRUE
3496 | ST-2024-004 | 2025-12-01 | 3 | 2 | TRUE
3497 | ST-2024-004 | 2026-01-01 | 2 | 2 | TRUE
3498 | ST-2024-004 | 2026-02-01 | 4 | 2 | TRUE
3499 | ST-2024-004 | 2026-03-01 | 3 | 2 | TRUE
3500 | ST-2024-004 | 2026-04-01 | 4 | 5 | TRUE
3501 | ST-2024-004 | 2026-05-01 | 4 | 2 | TRUE
3502 | ST-2024-005 | 2022-08-01 | 2 | 1 | TRUE
3503 | ST-2024-005 | 2022-09-01 | 0 | 0 | TRUE
3504 | ST-2024-005 | 2022-10-01 | 0 | 0 | TRUE
3505 | ST-2024-005 | 2022-11-01 | 1 | 1 | TRUE
3506 | ST-2024-005 | 2022-12-01 | 0 | 0 | TRUE
3507 | ST-2024-005 | 2023-01-01 | 1 | 1 | TRUE
3508 | ST-2024-005 | 2023-02-01 | 1 | 0 | TRUE
3509 | ST-2024-005 | 2023-03-01 | 0 | 0 | TRUE
3510 | ST-2024-005 | 2023-04-01 | 1 | 1 | TRUE
3511 | ST-2024-005 | 2023-05-01 | 1 | 0 | TRUE
3512 | ST-2024-005 | 2023-06-01 | 1 | 2 | TRUE
3513 | ST-2024-005 | 2023-07-01 | 2 | 1 | TRUE
3514 | ST-2024-005 | 2023-08-01 | 1 | 1 | TRUE
3515 | ST-2024-005 | 2023-09-01 | 2 | 1 | TRUE
3516 | ST-2024-005 | 2023-10-01 | 1 | 1 | TRUE
3517 | ST-2024-005 | 2023-11-01 | 3 | 2 | TRUE
3518 | ST-2024-005 | 2023-12-01 | 2 | 1 | TRUE
3519 | ST-2024-005 | 2024-01-01 | 2 | 1 | TRUE
3520 | ST-2024-005 | 2024-02-01 | 3 | 3 | TRUE
3521 | ST-2024-005 | 2024-03-01 | 3 | 3 | TRUE
3522 | ST-2024-005 | 2024-04-01 | 3 | 2 | TRUE
3523 | ST-2024-005 | 2024-05-01 | 3 | 3 | TRUE
3524 | ST-2024-005 | 2024-06-01 | 4 | 3 | TRUE
3525 | ST-2024-005 | 2024-07-01 | 3 | 0 | TRUE
3526 | ST-2024-005 | 2024-08-01 | 4 | 5 | TRUE
3527 | ST-2024-005 | 2024-09-01 | 4 | 1 | TRUE
3528 | ST-2024-005 | 2024-10-01 | 3 | 4 | TRUE
3529 | ST-2024-005 | 2024-11-01 | 4 | 2 | TRUE
3530 | ST-2024-005 | 2024-12-01 | 4 | 3 | TRUE
3531 | ST-2024-005 | 2025-01-01 | 3 | 2 | TRUE
3532 | ST-2024-005 | 2025-02-01 | 4 | 3 | TRUE
3533 | ST-2024-005 | 2025-03-01 | 3 | 2 | TRUE
3534 | ST-2024-005 | 2025-04-01 | 3 | 1 | TRUE
3535 | ST-2024-005 | 2025-05-01 | 3 | 4 | TRUE
3536 | ST-2024-005 | 2025-06-01 | 3 | 0 | TRUE
3537 | ST-2024-005 | 2025-07-01 | 2 | 4 | TRUE
3538 | ST-2024-005 | 2025-08-01 | 2 | 4 | TRUE
3539 | ST-2024-005 | 2025-09-01 | 3 | 0 | TRUE
3540 | ST-2024-005 | 2025-10-01 | 1 | 3 | TRUE
3541 | ST-2024-005 | 2025-11-01 | 2 | 2 | TRUE
3542 | ST-2024-005 | 2025-12-01 | 1 | 1 | TRUE
3543 | ST-2024-005 | 2026-01-01 | 2 | 0 | TRUE
3544 | ST-2024-005 | 2026-02-01 | 1 | 0 | TRUE
3545 | ST-2024-005 | 2026-03-01 | 1 | 1 | TRUE
3546 | ST-2024-005 | 2026-04-01 | 1 | 4 | TRUE
3547 | ST-2024-005 | 2026-05-01 | 0 | 1 | TRUE
3548 | ST-2024-006 | 2024-02-01 | 1 | 0 | TRUE
3549 | ST-2024-006 | 2024-03-01 | 1 | 1 | TRUE
3550 | ST-2024-006 | 2024-04-01 | 1 | 1 | TRUE
3551 | ST-2024-006 | 2024-05-01 | 2 | 2 | TRUE
3552 | ST-2024-006 | 2024-06-01 | 2 | 1 | TRUE
3553 | ST-2024-006 | 2024-07-01 | 3 | 2 | TRUE
3554 | ST-2024-006 | 2024-08-01 | 4 | 3 | TRUE
3555 | ST-2024-006 | 2024-09-01 | 5 | 4 | TRUE
3556 | ST-2024-006 | 2024-10-01 | 6 | 6 | TRUE
3557 | ST-2024-006 | 2024-11-01 | 6 | 5 | TRUE
3558 | ST-2024-006 | 2024-12-01 | 7 | 5 | TRUE
3559 | ST-2024-006 | 2025-01-01 | 6 | 5 | TRUE
3560 | ST-2024-006 | 2025-02-01 | 6 | 5 | TRUE
3561 | ST-2024-006 | 2025-03-01 | 5 | 1 | TRUE
3562 | ST-2024-006 | 2025-04-01 | 4 | 8 | TRUE
3563 | ST-2024-006 | 2025-05-01 | 3 | 0 | TRUE
3564 | ST-2024-006 | 2025-06-01 | 2 | 1 | TRUE
3565 | ST-2024-006 | 2025-07-01 | 2 | 3 | TRUE
3566 | ST-2024-006 | 2025-08-01 | 1 | 0 | TRUE
3567 | ST-2024-006 | 2025-09-01 | 1 | 4 | TRUE
3568 | ST-2024-006 | 2025-10-01 | 0 | 0 | TRUE
3569 | ST-2024-006 | 2025-11-01 | 0 | 0 | TRUE
3570 | ST-2024-006 | 2025-12-01 | 0 | 0 | TRUE
3571 | ST-2024-006 | 2026-01-01 | 0 | 5 | TRUE
3572 | ST-2024-006 | 2026-02-01 | 0 | 0 | TRUE
3573 | ST-2024-008 | 2021-09-01 | 1 | 0 | TRUE
3574 | ST-2024-008 | 2021-10-01 | 0 | 0 | TRUE
3575 | ST-2024-008 | 2021-11-01 | 0 | 0 | TRUE
3576 | ST-2024-008 | 2021-12-01 | 0 | 0 | TRUE
3577 | ST-2024-008 | 2022-01-01 | 0 | 0 | TRUE
3578 | ST-2024-008 | 2022-02-01 | 1 | 1 | TRUE
3579 | ST-2024-008 | 2022-03-01 | 0 | 0 | TRUE
3580 | ST-2024-008 | 2022-04-01 | 1 | 1 | TRUE
3581 | ST-2024-008 | 2022-05-01 | 0 | 0 | TRUE
3582 | ST-2024-008 | 2022-06-01 | 1 | 1 | TRUE
3583 | ST-2024-008 | 2022-07-01 | 0 | 0 | TRUE
3584 | ST-2024-008 | 2022-08-01 | 1 | 1 | TRUE
3585 | ST-2024-008 | 2022-09-01 | 1 | 0 | TRUE
3586 | ST-2024-008 | 2022-10-01 | 1 | 1 | TRUE
3587 | ST-2024-008 | 2022-11-01 | 1 | 2 | TRUE
3588 | ST-2024-008 | 2022-12-01 | 1 | 0 | TRUE
3589 | ST-2024-008 | 2023-01-01 | 2 | 2 | TRUE
3590 | ST-2024-008 | 2023-02-01 | 1 | 0 | TRUE
3591 | ST-2024-008 | 2023-03-01 | 2 | 2 | TRUE
3592 | ST-2024-008 | 2023-04-01 | 2 | 2 | TRUE
3593 | ST-2024-008 | 2023-05-01 | 2 | 1 | TRUE
3594 | ST-2024-008 | 2023-06-01 | 1 | 2 | TRUE
3595 | ST-2024-008 | 2023-07-01 | 2 | 1 | TRUE
3596 | ST-2024-008 | 2023-08-01 | 2 | 1 | TRUE
3597 | ST-2024-008 | 2023-09-01 | 3 | 3 | TRUE
3598 | ST-2024-008 | 2023-10-01 | 2 | 2 | TRUE
3599 | ST-2024-008 | 2023-11-01 | 2 | 1 | TRUE
3600 | ST-2024-008 | 2023-12-01 | 1 | 3 | TRUE
3601 | ST-2024-008 | 2024-01-01 | 2 | 0 | TRUE
3602 | ST-2024-008 | 2024-02-01 | 2 | 4 | TRUE
3603 | ST-2024-008 | 2024-03-01 | 2 | 0 | TRUE
3604 | ST-2024-008 | 2024-04-01 | 1 | 0 | TRUE
3605 | ST-2024-008 | 2024-05-01 | 2 | 3 | TRUE
3606 | ST-2024-008 | 2024-06-01 | 1 | 0 | TRUE
3607 | ST-2024-008 | 2024-07-01 | 1 | 1 | TRUE
3608 | ST-2024-008 | 2024-08-01 | 1 | 3 | TRUE
3609 | ST-2024-008 | 2024-09-01 | 1 | 0 | TRUE
3610 | ST-2024-008 | 2024-10-01 | 1 | 4 | TRUE
3611 | ST-2024-008 | 2024-11-01 | 0 | 0 | TRUE
3612 | ST-2024-008 | 2024-12-01 | 1 | 0 | TRUE
3613 | ST-2024-008 | 2025-01-01 | 0 | 2 | TRUE
3614 | ST-2024-008 | 2025-02-01 | 1 | 0 | TRUE
3615 | ST-2024-008 | 2025-03-01 | 0 | 2 | TRUE
3616 | ST-2024-008 | 2025-04-01 | 1 | 0 | TRUE
3617 | ST-2024-008 | 2025-05-01 | 0 | 4 | TRUE
3618 | ST-2024-008 | 2025-06-01 | 0 | 0 | TRUE
3619 | ST-2024-008 | 2025-07-01 | 0 | 0 | TRUE
3620 | ST-2024-008 | 2025-08-01 | 0 | 2 | TRUE
3621 | ST-2024-008 | 2025-09-01 | 1 | 1 | TRUE
3622 | ST-2024-008 | 2025-10-01 | 0 | 0 | TRUE
3623 | ST-2024-008 | 2025-11-01 | 0 | 1 | TRUE
3624 | ST-2024-008 | 2025-12-01 | 0 | 0 | TRUE
3625 | ST-2024-009 | 2025-11-01 | 6 | 4 | TRUE
3626 | ST-2024-009 | 2025-12-01 | 1 | 2 | TRUE
3627 | ST-2024-009 | 2026-01-01 | 2 | 1 | TRUE
3628 | ST-2024-009 | 2026-02-01 | 1 | 1 | TRUE
3629 | ST-2024-009 | 2026-03-01 | 3 | 2 | TRUE
3630 | ST-2024-009 | 2026-04-01 | 2 | 2 | TRUE
3631 | ST-2024-009 | 2026-05-01 | 3 | 2 | TRUE
3632 | ST-2024-010 | 2021-02-01 | 96 | 81 | TRUE
3633 | ST-2024-010 | 2021-03-01 | 6 | 11 | TRUE
3634 | ST-2024-010 | 2021-04-01 | 7 | 0 | TRUE
3635 | ST-2024-010 | 2021-05-01 | 7 | 15 | TRUE
3636 | ST-2024-010 | 2021-06-01 | 8 | 0 | TRUE
3637 | ST-2024-010 | 2021-07-01 | 8 | 16 | TRUE
3638 | ST-2024-010 | 2021-08-01 | 9 | 7 | TRUE
3639 | ST-2024-010 | 2021-09-01 | 10 | 8 | TRUE
3640 | ST-2024-010 | 2021-10-01 | 10 | 2 | TRUE
3641 | ST-2024-010 | 2021-11-01 | 11 | 10 | TRUE
3642 | ST-2024-010 | 2021-12-01 | 11 | 21 | TRUE
3643 | ST-2024-010 | 2022-01-01 | 12 | 0 | TRUE
3644 | ST-2024-010 | 2022-02-01 | 13 | 22 | TRUE
3645 | ST-2024-010 | 2022-03-01 | 14 | 7 | TRUE
3646 | ST-2024-010 | 2022-04-01 | 15 | 2 | TRUE
3647 | ST-2024-010 | 2022-05-01 | 15 | 26 | TRUE
3648 | ST-2024-010 | 2022-06-01 | 17 | 0 | TRUE
3649 | ST-2024-010 | 2022-07-01 | 17 | 19 | TRUE
3650 | ST-2024-010 | 2022-08-01 | 19 | 24 | TRUE
3651 | ST-2024-010 | 2022-09-01 | 19 | 2 | TRUE
3652 | ST-2024-010 | 2022-10-01 | 21 | 29 | TRUE
3653 | ST-2024-010 | 2022-11-01 | 22 | 36 | TRUE
3654 | ST-2024-010 | 2022-12-01 | 24 | 21 | TRUE
3655 | ST-2024-010 | 2023-01-01 | 24 | 18 | TRUE
3656 | ST-2024-010 | 2023-02-01 | 26 | 3 | TRUE
3657 | ST-2024-010 | 2023-03-01 | 28 | 14 | TRUE
3658 | ST-2024-010 | 2023-04-01 | 29 | 41 | TRUE
3659 | ST-2024-010 | 2023-05-01 | 31 | 22 | TRUE
3660 | ST-2024-010 | 2023-06-01 | 32 | 23 | TRUE
3661 | ST-2024-010 | 2023-07-01 | 35 | 58 | TRUE
3662 | ST-2024-010 | 2023-08-01 | 35 | 29 | TRUE
3663 | ST-2024-010 | 2023-09-01 | 38 | 1 | TRUE
3664 | ST-2024-010 | 2023-10-01 | 40 | 42 | TRUE
3665 | ST-2024-010 | 2023-11-01 | 41 | 79 | TRUE
3666 | ST-2024-010 | 2023-12-01 | 44 | 42 | TRUE
3667 | ST-2024-010 | 2024-01-01 | 45 | 23 | TRUE
3668 | ST-2024-010 | 2024-02-01 | 48 | 39 | TRUE
3669 | ST-2024-010 | 2024-03-01 | 50 | 27 | TRUE
3670 | ST-2024-010 | 2024-04-01 | 52 | 69 | TRUE
3671 | ST-2024-010 | 2024-05-01 | 54 | 0 | TRUE
3672 | ST-2024-010 | 2024-06-01 | 56 | 129 | TRUE
3673 | ST-2024-010 | 2024-07-01 | 58 | 0 | TRUE
3674 | ST-2024-010 | 2024-08-01 | 60 | 110 | TRUE
3675 | ST-2024-010 | 2024-09-01 | 63 | 66 | TRUE
3676 | ST-2024-010 | 2024-10-01 | 64 | 64 | TRUE
3677 | ST-2024-010 | 2024-11-01 | 67 | 0 | TRUE
3678 | ST-2024-010 | 2024-12-01 | 68 | 102 | TRUE
3679 | ST-2024-010 | 2025-01-01 | 71 | 123 | TRUE
3680 | ST-2024-010 | 2025-02-01 | 72 | 4 | TRUE
3681 | ST-2024-010 | 2025-03-01 | 74 | 122 | TRUE
3682 | ST-2024-010 | 2025-04-01 | 75 | 0 | TRUE
3683 | ST-2024-010 | 2025-05-01 | 77 | 47 | TRUE
3684 | ST-2024-010 | 2025-06-01 | 79 | 211 | TRUE
3685 | ST-2024-010 | 2025-07-01 | 79 | 0 | TRUE
3686 | ST-2024-010 | 2025-08-01 | 81 | 179 | TRUE
3687 | ST-2024-010 | 2025-09-01 | 81 | 76 | TRUE
3688 | ST-2024-010 | 2025-10-01 | 82 | 0 | TRUE
3689 | ST-2024-010 | 2025-11-01 | 83 | 100 | TRUE
3690 | ST-2024-010 | 2025-12-01 | 83 | 15 | TRUE
3691 | ST-2024-010 | 2026-01-01 | 84 | 114 | TRUE
3692 | ST-2024-010 | 2026-02-01 | 83 | 222 | TRUE
3693 | ST-2024-010 | 2026-03-01 | 83 | 0 | TRUE
3694 | ST-2024-010 | 2026-04-01 | 83 | 199 | TRUE
3695 | ST-2024-010 | 2026-05-01 | 82 | 0 | TRUE
3696 | ST-2024-011 | 2026-01-01 | 3 | 2 | TRUE
3697 | ST-2024-011 | 2026-02-01 | 0 | 0 | TRUE
3698 | ST-2024-011 | 2026-03-01 | 1 | 0 | TRUE
3699 | ST-2024-011 | 2026-04-01 | 1 | 1 | TRUE
3700 | ST-2024-011 | 2026-05-01 | 2 | 2 | TRUE
3701 | ST-2024-012 | 2025-06-01 | 0 | 0 | FALSE
3702 | ST-2024-012 | 2025-07-01 | 1 | 0 | TRUE
3703 | ST-2024-012 | 2025-08-01 | 0 | 0 | TRUE
3704 | ST-2024-012 | 2025-09-01 | 1 | 1 | TRUE
3705 | ST-2024-012 | 2025-10-01 | 2 | 1 | TRUE
3706 | ST-2024-012 | 2025-11-01 | 2 | 2 | TRUE
3707 | ST-2024-012 | 2025-12-01 | 2 | 1 | TRUE
3708 | ST-2024-012 | 2026-01-01 | 3 | 2 | TRUE
3709 | ST-2024-012 | 2026-02-01 | 4 | 3 | TRUE
3710 | ST-2024-012 | 2026-03-01 | 3 | 3 | TRUE
3711 | ST-2024-012 | 2026-04-01 | 3 | 1 | TRUE
3712 | ST-2024-012 | 2026-05-01 | 2 | 3 | TRUE
3713 | ST-2024-014 | 2025-03-01 | 0 | 0 | FALSE
3714 | ST-2024-014 | 2025-04-01 | 0 | 0 | FALSE
3715 | ST-2024-014 | 2025-05-01 | 1 | 0 | TRUE
3716 | ST-2024-014 | 2025-06-01 | 0 | 0 | TRUE
3717 | ST-2024-014 | 2025-07-01 | 0 | 0 | TRUE
3718 | ST-2024-014 | 2025-08-01 | 1 | 1 | TRUE
3719 | ST-2024-014 | 2025-09-01 | 0 | 1 | FALSE
3720 | ST-2024-014 | 2025-10-01 | 1 | 0 | TRUE
3721 | ST-2024-014 | 2025-11-01 | 0 | 0 | TRUE
3722 | ST-2024-014 | 2025-12-01 | 1 | 1 | TRUE
3723 | ST-2024-014 | 2026-01-01 | 1 | 1 | TRUE
3724 | ST-2024-014 | 2026-02-01 | 2 | 2 | TRUE
3725 | ST-2024-014 | 2026-03-01 | 1 | 1 | TRUE
3726 | ST-2024-014 | 2026-04-01 | 1 | 1 | TRUE
3727 | ST-2024-014 | 2026-05-01 | 2 | 2 | TRUE
3728 | ST-2024-015 | 2025-11-01 | 3 | 2 | TRUE
3729 | ST-2024-015 | 2025-12-01 | 1 | 1 | TRUE
3730 | ST-2024-015 | 2026-01-01 | 1 | 1 | TRUE
3731 | ST-2024-015 | 2026-02-01 | 2 | 2 | TRUE
3732 | ST-2024-015 | 2026-03-01 | 3 | 3 | TRUE
3733 | ST-2024-015 | 2026-04-01 | 3 | 3 | TRUE
3734 | ST-2024-015 | 2026-05-01 | 4 | 3 | TRUE
3735 | ST-2024-016 | 2025-03-01 | 2 | 1 | TRUE
3736 | ST-2024-016 | 2025-04-01 | 0 | 0 | TRUE
3737 | ST-2024-016 | 2025-05-01 | 1 | 1 | TRUE
3738 | ST-2024-016 | 2025-06-01 | 1 | 1 | TRUE
3739 | ST-2024-016 | 2025-07-01 | 2 | 2 | TRUE
3740 | ST-2024-016 | 2025-08-01 | 2 | 2 | TRUE
3741 | ST-2024-016 | 2025-09-01 | 2 | 1 | TRUE
3742 | ST-2024-016 | 2025-10-01 | 3 | 2 | TRUE
3743 | ST-2024-016 | 2025-11-01 | 4 | 4 | TRUE
3744 | ST-2024-016 | 2025-12-01 | 4 | 3 | TRUE
3745 | ST-2024-016 | 2026-01-01 | 5 | 5 | TRUE
3746 | ST-2024-016 | 2026-02-01 | 6 | 5 | TRUE
3747 | ST-2024-016 | 2026-03-01 | 6 | 7 | TRUE
3748 | ST-2024-016 | 2026-04-01 | 7 | 6 | TRUE
3749 | ST-2024-016 | 2026-05-01 | 6 | 5 | TRUE
3750 | ST-2024-017 | 2025-05-01 | 1 | 0 | TRUE
3751 | ST-2024-017 | 2025-06-01 | 0 | 0 | TRUE
3752 | ST-2024-017 | 2025-07-01 | 1 | 1 | TRUE
3753 | ST-2024-017 | 2025-08-01 | 0 | 0 | TRUE
3754 | ST-2024-017 | 2025-09-01 | 1 | 1 | TRUE
3755 | ST-2024-017 | 2025-10-01 | 0 | 0 | TRUE
3756 | ST-2024-017 | 2025-11-01 | 1 | 1 | TRUE
3757 | ST-2024-017 | 2025-12-01 | 1 | 1 | TRUE
3758 | ST-2024-017 | 2026-01-01 | 2 | 1 | TRUE
3759 | ST-2024-017 | 2026-02-01 | 1 | 1 | TRUE
3760 | ST-2024-017 | 2026-03-01 | 2 | 2 | TRUE
3761 | ST-2024-017 | 2026-04-01 | 2 | 1 | TRUE
3762 | ST-2024-017 | 2026-05-01 | 2 | 1 | TRUE
3763 | ST-2024-018 | 2022-06-01 | 0 | 0 | FALSE
3764 | ST-2024-018 | 2022-07-01 | 0 | 0 | FALSE
3765 | ST-2024-018 | 2022-08-01 | 0 | 0 | FALSE
3766 | ST-2024-018 | 2022-09-01 | 1 | 1 | FALSE
3767 | ST-2024-018 | 2022-10-01 | 0 | 0 | FALSE
3768 | ST-2024-018 | 2022-11-01 | 1 | 1 | FALSE
3769 | ST-2024-018 | 2022-12-01 | 0 | 0 | FALSE
3770 | ST-2024-018 | 2023-01-01 | 1 | 1 | FALSE
3771 | ST-2024-018 | 2023-02-01 | 1 | 1 | FALSE
3772 | ST-2024-018 | 2023-03-01 | 1 | 1 | FALSE
3773 | ST-2024-018 | 2023-04-01 | 1 | 1 | FALSE
3774 | ST-2024-018 | 2023-05-01 | 2 | 3 | FALSE
3775 | ST-2024-018 | 2023-06-01 | 1 | 0 | FALSE
3776 | ST-2024-018 | 2023-07-01 | 2 | 2 | FALSE
3777 | ST-2024-018 | 2023-08-01 | 1 | 1 | FALSE
3778 | ST-2024-018 | 2023-09-01 | 2 | 3 | FALSE
3779 | ST-2024-018 | 2023-10-01 | 1 | 1 | FALSE
3780 | ST-2024-018 | 2023-11-01 | 2 | 1 | FALSE
3781 | ST-2024-018 | 2023-12-01 | 1 | 3 | FALSE
3782 | ST-2024-018 | 2024-01-01 | 1 | 1 | FALSE
3783 | ST-2024-018 | 2024-02-01 | 1 | 0 | FALSE
3784 | ST-2024-018 | 2024-03-01 | 1 | 2 | FALSE
3785 | ST-2024-018 | 2024-04-01 | 0 | 1 | FALSE
3786 | ST-2024-018 | 2024-05-01 | 1 | 0 | FALSE
3787 | ST-2024-018 | 2024-06-01 | 0 | 0 | FALSE
3788 | ST-2024-018 | 2024-07-01 | 1 | 1 | FALSE
3789 | ST-2024-018 | 2024-08-01 | 0 | 1 | FALSE
3790 | ST-2024-018 | 2024-09-01 | 0 | 0 | FALSE
3791 | ST-2024-018 | 2024-10-01 | 0 | 0 | FALSE
3792 | ST-2024-018 | 2024-11-01 | 0 | 0 | FALSE
3793 | ST-2024-018 | 2024-12-01 | 0 | 0 | FALSE
3794 | ST-2024-018 | 2025-01-01 | 0 | 0 | FALSE
3795 | ST-2024-020 | 2024-01-01 | 0 | 0 | FALSE
3796 | ST-2024-020 | 2024-02-01 | 0 | 0 | FALSE
3797 | ST-2024-020 | 2024-03-01 | 0 | 0 | FALSE
3798 | ST-2024-020 | 2024-04-01 | 0 | 0 | FALSE
3799 | ST-2024-020 | 2024-05-01 | 0 | 0 | FALSE
3800 | ST-2024-020 | 2024-06-01 | 1 | 0 | TRUE
3801 | ST-2024-020 | 2024-07-01 | 0 | 0 | TRUE
3802 | ST-2024-020 | 2024-08-01 | 0 | 0 | TRUE
3803 | ST-2024-020 | 2024-09-01 | 1 | 1 | TRUE
3804 | ST-2024-020 | 2024-10-01 | 0 | 0 | TRUE
3805 | ST-2024-020 | 2024-11-01 | 1 | 1 | TRUE
3806 | ST-2024-020 | 2024-12-01 | 1 | 1 | TRUE
3807 | ST-2024-020 | 2025-01-01 | 0 | 0 | TRUE
3808 | ST-2024-020 | 2025-02-01 | 1 | 1 | TRUE
3809 | ST-2024-020 | 2025-03-01 | 1 | 1 | TRUE
3810 | ST-2024-020 | 2025-04-01 | 1 | 0 | TRUE
3811 | ST-2024-020 | 2025-05-01 | 1 | 2 | TRUE
3812 | ST-2024-020 | 2025-06-01 | 1 | 1 | TRUE
3813 | ST-2024-020 | 2025-07-01 | 1 | 0 | TRUE
3814 | ST-2024-020 | 2025-08-01 | 0 | 1 | TRUE
3815 | ST-2024-020 | 2025-09-01 | 1 | 0 | TRUE
3816 | ST-2024-020 | 2025-10-01 | 1 | 1 | TRUE
3817 | ST-2024-020 | 2025-11-01 | 0 | 0 | TRUE
3818 | ST-2024-020 | 2025-12-01 | 1 | 1 | TRUE
3819 | ST-2024-020 | 2026-01-01 | 0 | 0 | TRUE
3820 | ST-2024-020 | 2026-02-01 | 0 | 0 | TRUE
3821 | ST-2024-020 | 2026-03-01 | 1 | 1 | TRUE
3822 | ST-2024-020 | 2026-04-01 | 0 | 0 | TRUE
3823 | ST-2024-020 | 2026-05-01 | 0 | 1 | TRUE
3824 | ST-2025-021 | 2018-03-01 | 4 | 4 | FALSE
3825 | ST-2025-021 | 2018-04-01 | 1 | 1 | FALSE
3826 | ST-2025-021 | 2018-05-01 | 1 | 1 | FALSE
3827 | ST-2025-021 | 2018-06-01 | 2 | 1 | TRUE
3828 | ST-2025-021 | 2018-07-01 | 2 | 3 | FALSE
3829 | ST-2025-021 | 2018-08-01 | 2 | 2 | FALSE
3830 | ST-2025-021 | 2018-09-01 | 4 | 5 | FALSE
3831 | ST-2025-021 | 2018-10-01 | 3 | 1 | TRUE
3832 | ST-2025-021 | 2018-11-01 | 5 | 6 | FALSE
3833 | ST-2025-021 | 2018-12-01 | 5 | 6 | FALSE
3834 | ST-2025-021 | 2019-01-01 | 7 | 5 | TRUE
3835 | ST-2025-021 | 2019-02-01 | 7 | 8 | FALSE
3836 | ST-2025-021 | 2019-03-01 | 8 | 10 | FALSE
3837 | ST-2025-021 | 2019-04-01 | 10 | 12 | FALSE
3838 | ST-2025-021 | 2019-05-01 | 10 | 9 | FALSE
3839 | ST-2025-021 | 2019-06-01 | 10 | 6 | TRUE
3840 | ST-2025-021 | 2019-07-01 | 11 | 13 | FALSE
3841 | ST-2025-021 | 2019-08-01 | 11 | 11 | FALSE
3842 | ST-2025-021 | 2019-09-01 | 10 | 17 | FALSE
3843 | ST-2025-021 | 2019-10-01 | 10 | 10 | FALSE
3844 | ST-2025-021 | 2019-11-01 | 10 | 3 | FALSE
3845 | ST-2025-021 | 2019-12-01 | 8 | 15 | FALSE
3846 | ST-2025-021 | 2020-01-01 | 7 | 1 | FALSE
3847 | ST-2025-021 | 2020-02-01 | 7 | 11 | FALSE
3848 | ST-2025-021 | 2020-03-01 | 5 | 1 | FALSE
3849 | ST-2025-021 | 2020-04-01 | 5 | 2 | TRUE
3850 | ST-2025-021 | 2020-05-01 | 3 | 2 | TRUE
3851 | ST-2025-021 | 2020-06-01 | 4 | 7 | FALSE
3852 | ST-2025-021 | 2020-07-01 | 2 | 12 | FALSE
3853 | ST-2025-021 | 2020-08-01 | 2 | 0 | FALSE
3854 | ST-2025-021 | 2020-09-01 | 2 | 5 | FALSE
3855 | ST-2025-021 | 2020-10-01 | 1 | 0 | TRUE
3856 | ST-2025-021 | 2020-11-01 | 1 | 2 | FALSE
3857 | ST-2025-021 | 2020-12-01 | 1 | 5 | FALSE
3858 | ST-2025-021 | 2021-01-01 | 0 | 0 | FALSE
3859 | ST-2025-021 | 2021-02-01 | 0 | 0 | FALSE
3860 | ST-2025-021 | 2021-03-01 | 0 | 0 | FALSE
3861 | ST-2025-022 | 2022-08-01 | 1 | 0 | TRUE
3862 | ST-2025-022 | 2022-09-01 | 0 | 0 | TRUE
3863 | ST-2025-022 | 2022-10-01 | 0 | 1 | FALSE
3864 | ST-2025-022 | 2022-11-01 | 1 | 1 | FALSE
3865 | ST-2025-022 | 2022-12-01 | 0 | 0 | TRUE
3866 | ST-2025-022 | 2023-01-01 | 1 | 2 | FALSE
3867 | ST-2025-022 | 2023-02-01 | 1 | 0 | TRUE
3868 | ST-2025-022 | 2023-03-01 | 0 | 1 | FALSE
3869 | ST-2025-022 | 2023-04-01 | 1 | 1 | FALSE
3870 | ST-2025-022 | 2023-05-01 | 2 | 1 | TRUE
3871 | ST-2025-022 | 2023-06-01 | 1 | 2 | FALSE
3872 | ST-2025-022 | 2023-07-01 | 2 | 1 | TRUE
3873 | ST-2025-022 | 2023-08-01 | 1 | 2 | FALSE
3874 | ST-2025-022 | 2023-09-01 | 2 | 2 | FALSE
3875 | ST-2025-022 | 2023-10-01 | 3 | 3 | FALSE
3876 | ST-2025-022 | 2023-11-01 | 2 | 2 | FALSE
3877 | ST-2025-022 | 2023-12-01 | 3 | 4 | FALSE
3878 | ST-2025-022 | 2024-01-01 | 3 | 2 | FALSE
3879 | ST-2025-022 | 2024-02-01 | 3 | 2 | TRUE
3880 | ST-2025-022 | 2024-03-01 | 3 | 2 | TRUE
3881 | ST-2025-022 | 2024-04-01 | 2 | 6 | FALSE
3882 | ST-2025-022 | 2024-05-01 | 3 | 0 | TRUE
3883 | ST-2025-022 | 2024-06-01 | 3 | 3 | TRUE
3884 | ST-2025-022 | 2024-07-01 | 3 | 5 | FALSE
3885 | ST-2025-022 | 2024-08-01 | 2 | 0 | TRUE
3886 | ST-2025-022 | 2024-09-01 | 3 | 7 | FALSE
3887 | ST-2025-022 | 2024-10-01 | 2 | 0 | TRUE
3888 | ST-2025-022 | 2024-11-01 | 1 | 2 | TRUE
3889 | ST-2025-022 | 2024-12-01 | 2 | 1 | TRUE
3890 | ST-2025-022 | 2025-01-01 | 1 | 5 | FALSE
3891 | ST-2025-022 | 2025-02-01 | 2 | 0 | FALSE
3892 | ST-2025-022 | 2025-03-01 | 1 | 0 | TRUE
3893 | ST-2025-022 | 2025-04-01 | 0 | 4 | FALSE
3894 | ST-2025-022 | 2025-05-01 | 1 | 0 | FALSE
3895 | ST-2025-022 | 2025-06-01 | 1 | 0 | TRUE
3896 | ST-2025-022 | 2025-07-01 | 0 | 3 | FALSE
3897 | ST-2025-022 | 2025-08-01 | 1 | 0 | FALSE
3898 | ST-2025-022 | 2025-09-01 | 0 | 0 | FALSE
3899 | ST-2025-022 | 2025-10-01 | 0 | 0 | TRUE
3900 | ST-2025-022 | 2025-11-01 | 0 | 1 | TRUE
3901 | ST-2025-022 | 2025-12-01 | 0 | 2 | FALSE
3902 | ST-2025-022 | 2026-01-01 | 0 | 0 | FALSE
3903 | ST-2025-022 | 2026-02-01 | 0 | 2 | FALSE
3904 | ST-2025-022 | 2026-03-01 | 0 | 0 | TRUE
3905 | ST-2025-023 | 2022-04-01 | 30 | 27 | TRUE
3906 | ST-2025-023 | 2022-05-01 | 4 | 3 | TRUE
3907 | ST-2025-023 | 2022-06-01 | 5 | 3 | TRUE
3908 | ST-2025-023 | 2022-07-01 | 6 | 6 | TRUE
3909 | ST-2025-023 | 2022-08-01 | 6 | 5 | TRUE
3910 | ST-2025-023 | 2022-09-01 | 7 | 9 | TRUE
3911 | ST-2025-023 | 2022-10-01 | 7 | 4 | TRUE
3912 | ST-2025-023 | 2022-11-01 | 9 | 5 | TRUE
3913 | ST-2025-023 | 2022-12-01 | 10 | 11 | TRUE
3914 | ST-2025-023 | 2023-01-01 | 11 | 11 | TRUE
3915 | ST-2025-023 | 2023-02-01 | 12 | 11 | TRUE
3916 | ST-2025-023 | 2023-03-01 | 14 | 15 | TRUE
3917 | ST-2025-023 | 2023-04-01 | 16 | 19 | TRUE
3918 | ST-2025-023 | 2023-05-01 | 17 | 4 | TRUE
3919 | ST-2025-023 | 2023-06-01 | 19 | 19 | TRUE
3920 | ST-2025-023 | 2023-07-01 | 21 | 28 | TRUE
3921 | ST-2025-023 | 2023-08-01 | 24 | 21 | TRUE
3922 | ST-2025-023 | 2023-09-01 | 25 | 27 | TRUE
3923 | ST-2025-023 | 2023-10-01 | 28 | 26 | TRUE
3924 | ST-2025-023 | 2023-11-01 | 31 | 20 | TRUE
3925 | ST-2025-023 | 2023-12-01 | 33 | 22 | TRUE
3926 | ST-2025-023 | 2024-01-01 | 35 | 21 | TRUE
3927 | ST-2025-023 | 2024-02-01 | 38 | 44 | TRUE
3928 | ST-2025-023 | 2024-03-01 | 40 | 28 | TRUE
3929 | ST-2025-023 | 2024-04-01 | 42 | 48 | TRUE
3930 | ST-2025-023 | 2024-05-01 | 44 | 37 | TRUE
3931 | ST-2025-023 | 2024-06-01 | 46 | 34 | TRUE
3932 | ST-2025-023 | 2024-07-01 | 48 | 62 | TRUE
3933 | ST-2025-023 | 2024-08-01 | 48 | 9 | TRUE
3934 | ST-2025-023 | 2024-09-01 | 49 | 67 | TRUE
3935 | ST-2025-023 | 2024-10-01 | 49 | 39 | TRUE
3936 | ST-2025-023 | 2024-11-01 | 49 | 29 | TRUE
3937 | ST-2025-023 | 2024-12-01 | 48 | 80 | TRUE
3938 | ST-2025-023 | 2025-01-01 | 48 | 0 | TRUE
3939 | ST-2025-023 | 2025-02-01 | 46 | 80 | TRUE
3940 | ST-2025-023 | 2025-03-01 | 44 | 87 | TRUE
3941 | ST-2025-023 | 2025-04-01 | 42 | 8 | TRUE
3942 | ST-2025-023 | 2025-05-01 | 40 | 34 | TRUE
3943 | ST-2025-023 | 2025-06-01 | 38 | 42 | TRUE
3944 | ST-2025-023 | 2025-07-01 | 35 | 57 | TRUE
3945 | ST-2025-023 | 2025-08-01 | 33 | 0 | TRUE
3946 | ST-2025-023 | 2025-09-01 | 31 | 43 | TRUE
3947 | ST-2025-023 | 2025-10-01 | 28 | 0 | TRUE
3948 | ST-2025-023 | 2025-11-01 | 25 | 71 | TRUE
3949 | ST-2025-023 | 2025-12-01 | 24 | 0 | TRUE
3950 | ST-2025-023 | 2026-01-01 | 21 | 114 | TRUE
3951 | ST-2025-023 | 2026-02-01 | 19 | 0 | TRUE
3952 | ST-2025-023 | 2026-03-01 | 17 | 108 | TRUE
3953 | ST-2025-023 | 2026-04-01 | 16 | 0 | TRUE
3954 | ST-2025-023 | 2026-05-01 | 14 | 0 | TRUE
3955 | ST-2025-024 | 2025-01-01 | 5 | 3 | TRUE
3956 | ST-2025-024 | 2025-02-01 | 2 | 2 | TRUE
3957 | ST-2025-024 | 2025-03-01 | 3 | 1 | TRUE
3958 | ST-2025-024 | 2025-04-01 | 4 | 4 | TRUE
3959 | ST-2025-024 | 2025-05-01 | 5 | 3 | TRUE
3960 | ST-2025-024 | 2025-06-01 | 7 | 5 | TRUE
3961 | ST-2025-024 | 2025-07-01 | 8 | 5 | TRUE
3962 | ST-2025-024 | 2025-08-01 | 11 | 8 | TRUE
3963 | ST-2025-024 | 2025-09-01 | 14 | 9 | TRUE
3964 | ST-2025-024 | 2025-10-01 | 15 | 14 | TRUE
3965 | ST-2025-024 | 2025-11-01 | 17 | 14 | TRUE
3966 | ST-2025-024 | 2025-12-01 | 19 | 10 | TRUE
3967 | ST-2025-024 | 2026-01-01 | 18 | 16 | TRUE
3968 | ST-2025-024 | 2026-02-01 | 17 | 13 | TRUE
3969 | ST-2025-024 | 2026-03-01 | 15 | 4 | TRUE
3970 | ST-2025-024 | 2026-04-01 | 14 | 22 | TRUE
3971 | ST-2025-024 | 2026-05-01 | 11 | 2 | TRUE
3972 | ST-2025-026 | 2020-11-01 | 5 | 3 | TRUE
3973 | ST-2025-026 | 2020-12-01 | 0 | 0 | TRUE
3974 | ST-2025-026 | 2021-01-01 | 0 | 0 | TRUE
3975 | ST-2025-026 | 2021-02-01 | 1 | 0 | TRUE
3976 | ST-2025-026 | 2021-03-01 | 0 | 0 | TRUE
3977 | ST-2025-026 | 2021-04-01 | 1 | 1 | TRUE
3978 | ST-2025-026 | 2021-05-01 | 1 | 1 | TRUE
3979 | ST-2025-026 | 2021-06-01 | 0 | 0 | TRUE
3980 | ST-2025-026 | 2021-07-01 | 1 | 0 | TRUE
3981 | ST-2025-026 | 2021-08-01 | 1 | 1 | TRUE
3982 | ST-2025-026 | 2021-09-01 | 1 | 1 | TRUE
3983 | ST-2025-026 | 2021-10-01 | 1 | 0 | TRUE
3984 | ST-2025-026 | 2021-11-01 | 1 | 1 | TRUE
3985 | ST-2025-026 | 2021-12-01 | 1 | 1 | TRUE
3986 | ST-2025-026 | 2022-01-01 | 1 | 1 | TRUE
3987 | ST-2025-026 | 2022-02-01 | 1 | 0 | TRUE
3988 | ST-2025-026 | 2022-03-01 | 2 | 2 | TRUE
3989 | ST-2025-026 | 2022-04-01 | 1 | 1 | TRUE
3990 | ST-2025-026 | 2022-05-01 | 1 | 0 | TRUE
3991 | ST-2025-026 | 2022-06-01 | 2 | 3 | TRUE
3992 | ST-2025-026 | 2022-07-01 | 2 | 0 | TRUE
3993 | ST-2025-026 | 2022-08-01 | 2 | 3 | TRUE
3994 | ST-2025-026 | 2022-09-01 | 2 | 0 | TRUE
3995 | ST-2025-026 | 2022-10-01 | 2 | 1 | TRUE
3996 | ST-2025-026 | 2022-11-01 | 2 | 2 | TRUE
3997 | ST-2025-026 | 2022-12-01 | 3 | 1 | TRUE
3998 | ST-2025-026 | 2023-01-01 | 2 | 2 | TRUE
3999 | ST-2025-026 | 2023-02-01 | 3 | 2 | TRUE
4000 | ST-2025-026 | 2023-03-01 | 3 | 1 | TRUE
4001 | ST-2025-026 | 2023-04-01 | 3 | 4 | TRUE
4002 | ST-2025-026 | 2023-05-01 | 3 | 1 | TRUE
4003 | ST-2025-026 | 2023-06-01 | 4 | 4 | TRUE
4004 | ST-2025-026 | 2023-07-01 | 3 | 0 | TRUE
4005 | ST-2025-026 | 2023-08-01 | 4 | 1 | TRUE
4006 | ST-2025-026 | 2023-09-01 | 4 | 7 | TRUE
4007 | ST-2025-026 | 2023-10-01 | 4 | 0 | TRUE
4008 | ST-2025-026 | 2023-11-01 | 4 | 3 | TRUE
4009 | ST-2025-026 | 2023-12-01 | 4 | 3 | TRUE
4010 | ST-2025-026 | 2024-01-01 | 5 | 1 | TRUE
4011 | ST-2025-026 | 2024-02-01 | 5 | 5 | TRUE
4012 | ST-2025-026 | 2024-03-01 | 5 | 2 | TRUE
4013 | ST-2025-026 | 2024-04-01 | 4 | 3 | TRUE
4014 | ST-2025-026 | 2024-05-01 | 6 | 6 | TRUE
4015 | ST-2025-026 | 2024-06-01 | 5 | 3 | TRUE
4016 | ST-2025-026 | 2024-07-01 | 5 | 2 | TRUE
4017 | ST-2025-026 | 2024-08-01 | 5 | 6 | TRUE
4018 | ST-2025-026 | 2024-09-01 | 5 | 0 | TRUE
4019 | ST-2025-026 | 2024-10-01 | 6 | 10 | TRUE
4020 | ST-2025-026 | 2024-11-01 | 5 | 0 | TRUE
4021 | ST-2025-026 | 2024-12-01 | 6 | 13 | TRUE
4022 | ST-2025-026 | 2025-01-01 | 5 | 2 | TRUE
4023 | ST-2025-026 | 2025-02-01 | 5 | 0 | TRUE
4024 | ST-2025-026 | 2025-03-01 | 5 | 4 | TRUE
4025 | ST-2025-026 | 2025-04-01 | 5 | 3 | TRUE
4026 | ST-2025-026 | 2025-05-01 | 6 | 4 | TRUE
4027 | ST-2025-026 | 2025-06-01 | 4 | 7 | TRUE
4028 | ST-2025-026 | 2025-07-01 | 5 | 0 | TRUE
4029 | ST-2025-026 | 2025-08-01 | 5 | 2 | TRUE
4030 | ST-2025-026 | 2025-09-01 | 5 | 12 | TRUE
4031 | ST-2025-026 | 2025-10-01 | 4 | 0 | TRUE
4032 | ST-2025-026 | 2025-11-01 | 4 | 14 | TRUE
4033 | ST-2025-026 | 2025-12-01 | 4 | 5 | TRUE
4034 | ST-2025-026 | 2026-01-01 | 4 | 0 | TRUE
4035 | ST-2025-026 | 2026-02-01 | 4 | 14 | TRUE
4036 | ST-2025-026 | 2026-03-01 | 3 | 0 | TRUE
4037 | ST-2025-026 | 2026-04-01 | 4 | 12 | TRUE
4038 | ST-2025-026 | 2026-05-01 | 3 | 5 | TRUE
4039 | ST-2025-027 | 2023-03-01 | 1 | 0 | TRUE
4040 | ST-2025-027 | 2023-04-01 | 1 | 1 | TRUE
4041 | ST-2025-027 | 2023-05-01 | 0 | 0 | TRUE
4042 | ST-2025-027 | 2023-06-01 | 1 | 2 | FALSE
4043 | ST-2025-027 | 2023-07-01 | 0 | 0 | TRUE
4044 | ST-2025-027 | 2023-08-01 | 1 | 2 | FALSE
4045 | ST-2025-027 | 2023-09-01 | 1 | 0 | TRUE
4046 | ST-2025-027 | 2023-10-01 | 1 | 1 | TRUE
4047 | ST-2025-027 | 2023-11-01 | 2 | 2 | TRUE
4048 | ST-2025-027 | 2023-12-01 | 1 | 2 | FALSE
4049 | ST-2025-027 | 2024-01-01 | 2 | 2 | FALSE
4050 | ST-2025-027 | 2024-02-01 | 2 | 1 | TRUE
4051 | ST-2025-027 | 2024-03-01 | 2 | 2 | TRUE
4052 | ST-2025-027 | 2024-04-01 | 3 | 2 | TRUE
4053 | ST-2025-027 | 2024-05-01 | 3 | 4 | TRUE
4054 | ST-2025-027 | 2024-06-01 | 3 | 2 | TRUE
4055 | ST-2025-027 | 2024-07-01 | 4 | 6 | FALSE
4056 | ST-2025-027 | 2024-08-01 | 3 | 3 | FALSE
4057 | ST-2025-027 | 2024-09-01 | 4 | 3 | TRUE
4058 | ST-2025-027 | 2024-10-01 | 4 | 3 | TRUE
4059 | ST-2025-027 | 2024-11-01 | 5 | 6 | TRUE
4060 | ST-2025-027 | 2024-12-01 | 4 | 4 | TRUE
4061 | ST-2025-027 | 2025-01-01 | 4 | 0 | TRUE
4062 | ST-2025-027 | 2025-02-01 | 4 | 4 | TRUE
4063 | ST-2025-027 | 2025-03-01 | 3 | 3 | TRUE
4064 | ST-2025-027 | 2025-04-01 | 4 | 9 | FALSE
4065 | ST-2025-027 | 2025-05-01 | 3 | 0 | TRUE
4066 | ST-2025-027 | 2025-06-01 | 3 | 3 | TRUE
4067 | ST-2025-027 | 2025-07-01 | 3 | 6 | TRUE
4068 | ST-2025-027 | 2025-08-01 | 2 | 2 | TRUE
4069 | ST-2025-027 | 2025-09-01 | 2 | 0 | TRUE
4070 | ST-2025-027 | 2025-10-01 | 2 | 6 | TRUE
4071 | ST-2025-027 | 2025-11-01 | 1 | 0 | TRUE
4072 | ST-2025-027 | 2025-12-01 | 2 | 3 | TRUE
4073 | ST-2025-027 | 2026-01-01 | 1 | 0 | TRUE
4074 | ST-2025-027 | 2026-02-01 | 1 | 4 | TRUE
4075 | ST-2025-027 | 2026-03-01 | 1 | 0 | TRUE
4076 | ST-2025-027 | 2026-04-01 | 0 | 2 | TRUE
4077 | ST-2025-027 | 2026-05-01 | 1 | 6 | FALSE
4078 | ST-2025-028 | 2025-10-01 | 1520 | 1384 | TRUE
4079 | ST-2025-028 | 2025-11-01 | 368 | 489 | TRUE
4080 | ST-2025-028 | 2025-12-01 | 454 | 230 | TRUE
4081 | ST-2025-028 | 2026-01-01 | 558 | 625 | TRUE
4082 | ST-2025-028 | 2026-02-01 | 683 | 536 | TRUE
4083 | ST-2025-028 | 2026-03-01 | 834 | 998 | TRUE
4084 | ST-2025-028 | 2026-04-01 | 1012 | 730 | TRUE
4085 | ST-2025-028 | 2026-05-01 | 1219 | 1581 | TRUE
4086 | ST-2025-029 | 2024-07-01 | 4 | 2 | TRUE
4087 | ST-2025-029 | 2024-08-01 | 2 | 1 | TRUE
4088 | ST-2025-029 | 2024-09-01 | 2 | 2 | TRUE
4089 | ST-2025-029 | 2024-10-01 | 3 | 1 | TRUE
4090 | ST-2025-029 | 2024-11-01 | 4 | 3 | TRUE
4091 | ST-2025-029 | 2024-12-01 | 5 | 3 | TRUE
4092 | ST-2025-029 | 2025-01-01 | 7 | 3 | TRUE
4093 | ST-2025-029 | 2025-02-01 | 8 | 5 | TRUE
4094 | ST-2025-029 | 2025-03-01 | 10 | 8 | TRUE
4095 | ST-2025-029 | 2025-04-01 | 11 | 6 | TRUE
4096 | ST-2025-029 | 2025-05-01 | 14 | 8 | TRUE
4097 | ST-2025-029 | 2025-06-01 | 14 | 10 | TRUE
4098 | ST-2025-029 | 2025-07-01 | 16 | 5 | TRUE
4099 | ST-2025-029 | 2025-08-01 | 15 | 11 | TRUE
4100 | ST-2025-029 | 2025-09-01 | 14 | 14 | TRUE
4101 | ST-2025-029 | 2025-10-01 | 14 | 0 | TRUE
4102 | ST-2025-029 | 2025-11-01 | 11 | 10 | TRUE
4103 | ST-2025-029 | 2025-12-01 | 10 | 5 | TRUE
4104 | ST-2025-029 | 2026-01-01 | 8 | 6 | TRUE
4105 | ST-2025-029 | 2026-02-01 | 7 | 2 | TRUE
4106 | ST-2025-029 | 2026-03-01 | 5 | 10 | TRUE
4107 | ST-2025-029 | 2026-04-01 | 4 | 2 | TRUE
4108 | ST-2025-029 | 2026-05-01 | 3 | 5 | TRUE
4109 | ST-2025-030 | 2024-04-01 | 32 | 21 | TRUE
4110 | ST-2025-030 | 2024-05-01 | 11 | 10 | TRUE
4111 | ST-2025-030 | 2024-06-01 | 13 | 9 | TRUE
4112 | ST-2025-030 | 2024-07-01 | 17 | 9 | TRUE
4113 | ST-2025-030 | 2024-08-01 | 21 | 15 | TRUE
4114 | ST-2025-030 | 2024-09-01 | 28 | 21 | TRUE
4115 | ST-2025-030 | 2024-10-01 | 35 | 28 | TRUE
4116 | ST-2025-030 | 2024-11-01 | 42 | 31 | TRUE
4117 | ST-2025-030 | 2024-12-01 | 52 | 30 | TRUE
4118 | ST-2025-030 | 2025-01-01 | 62 | 39 | TRUE
4119 | ST-2025-030 | 2025-02-01 | 73 | 42 | TRUE
4120 | ST-2025-030 | 2025-03-01 | 81 | 79 | TRUE
4121 | ST-2025-030 | 2025-04-01 | 90 | 48 | TRUE
4122 | ST-2025-030 | 2025-05-01 | 94 | 52 | TRUE
4123 | ST-2025-030 | 2025-06-01 | 97 | 68 | TRUE
4124 | ST-2025-030 | 2025-07-01 | 94 | 61 | TRUE
4125 | ST-2025-030 | 2025-08-01 | 90 | 72 | TRUE
4126 | ST-2025-030 | 2025-09-01 | 81 | 37 | TRUE
4127 | ST-2025-030 | 2025-10-01 | 73 | 63 | TRUE
4128 | ST-2025-030 | 2025-11-01 | 62 | 15 | TRUE
4129 | ST-2025-030 | 2025-12-01 | 52 | 97 | TRUE
4130 | ST-2025-030 | 2026-01-01 | 42 | 32 | TRUE
4131 | ST-2025-030 | 2026-02-01 | 35 | 0 | TRUE
4132 | ST-2025-030 | 2026-03-01 | 28 | 55 | TRUE
4133 | ST-2025-030 | 2026-04-01 | 21 | 0 | TRUE
4134 | ST-2025-030 | 2026-05-01 | 17 | 2 | TRUE
4135 | ST-2025-032 | 2025-05-01 | 6 | 5 | TRUE
4136 | ST-2025-032 | 2025-06-01 | 1 | 1 | TRUE
4137 | ST-2025-032 | 2025-07-01 | 1 | 1 | TRUE
4138 | ST-2025-032 | 2025-08-01 | 1 | 1 | TRUE
4139 | ST-2025-032 | 2025-09-01 | 1 | 1 | TRUE
4140 | ST-2025-032 | 2025-10-01 | 2 | 1 | TRUE
4141 | ST-2025-032 | 2025-11-01 | 2 | 3 | TRUE
4142 | ST-2025-032 | 2025-12-01 | 2 | 0 | TRUE
4143 | ST-2025-032 | 2026-01-01 | 2 | 3 | TRUE
4144 | ST-2025-032 | 2026-02-01 | 3 | 4 | TRUE
4145 | ST-2025-032 | 2026-03-01 | 3 | 2 | TRUE
4146 | ST-2025-032 | 2026-04-01 | 3 | 3 | TRUE
4147 | ST-2025-032 | 2026-05-01 | 4 | 3 | TRUE
4148 | ST-2025-033 | 2022-04-01 | 0 | 0 | FALSE
4149 | ST-2025-033 | 2022-05-01 | 0 | 0 | FALSE
4150 | ST-2025-033 | 2022-06-01 | 0 | 0 | FALSE
4151 | ST-2025-033 | 2022-07-01 | 0 | 0 | FALSE
4152 | ST-2025-033 | 2022-08-01 | 0 | 0 | FALSE
4153 | ST-2025-033 | 2022-09-01 | 0 | 0 | FALSE
4154 | ST-2025-033 | 2022-10-01 | 1 | 0 | TRUE
4155 | ST-2025-033 | 2022-11-01 | 0 | 0 | TRUE
4156 | ST-2025-033 | 2022-12-01 | 0 | 0 | TRUE
4157 | ST-2025-033 | 2023-01-01 | 0 | 0 | TRUE
4158 | ST-2025-033 | 2023-02-01 | 0 | 0 | TRUE
4159 | ST-2025-033 | 2023-03-01 | 1 | 1 | TRUE
4160 | ST-2025-033 | 2023-04-01 | 0 | 0 | TRUE
4161 | ST-2025-033 | 2023-05-01 | 1 | 1 | TRUE
4162 | ST-2025-033 | 2023-06-01 | 0 | 0 | TRUE
4163 | ST-2025-033 | 2023-07-01 | 1 | 1 | TRUE
4164 | ST-2025-033 | 2023-08-01 | 0 | 0 | TRUE
4165 | ST-2025-033 | 2023-09-01 | 1 | 1 | TRUE
4166 | ST-2025-033 | 2023-10-01 | 1 | 1 | TRUE
4167 | ST-2025-033 | 2023-11-01 | 0 | 0 | TRUE
4168 | ST-2025-033 | 2023-12-01 | 1 | 0 | TRUE
4169 | ST-2025-033 | 2024-01-01 | 1 | 2 | TRUE
4170 | ST-2025-033 | 2024-02-01 | 1 | 0 | TRUE
4171 | ST-2025-033 | 2024-03-01 | 0 | 0 | TRUE
4172 | ST-2025-033 | 2024-04-01 | 1 | 2 | TRUE
4173 | ST-2025-033 | 2024-05-01 | 1 | 0 | TRUE
4174 | ST-2025-033 | 2024-06-01 | 0 | 1 | TRUE
4175 | ST-2025-033 | 2024-07-01 | 1 | 0 | TRUE
4176 | ST-2025-033 | 2024-08-01 | 0 | 0 | TRUE
4177 | ST-2025-033 | 2024-09-01 | 1 | 1 | TRUE
4178 | ST-2025-033 | 2024-10-01 | 0 | 0 | TRUE
4179 | ST-2025-033 | 2024-11-01 | 1 | 2 | TRUE
4180 | ST-2025-033 | 2024-12-01 | 0 | 0 | TRUE
4181 | ST-2025-033 | 2025-01-01 | 0 | 0 | TRUE
4182 | ST-2025-033 | 2025-02-01 | 0 | 0 | TRUE
4183 | ST-2025-033 | 2025-03-01 | 0 | 1 | TRUE
4184 | ST-2025-033 | 2025-04-01 | 1 | 1 | TRUE
4185 | ST-2025-033 | 2025-05-01 | 0 | 0 | TRUE
4186 | ST-2025-033 | 2025-06-01 | 0 | 0 | TRUE
4187 | ST-2025-033 | 2025-07-01 | 0 | 0 | TRUE
4188 | ST-2025-033 | 2025-08-01 | 0 | 1 | TRUE
4189 | ST-2025-033 | 2025-09-01 | 0 | 0 | TRUE
4190 | ST-2025-033 | 2025-10-01 | 0 | 0 | TRUE
4191 | ST-2025-033 | 2025-11-01 | 0 | 0 | TRUE
4192 | ST-2025-033 | 2025-12-01 | 0 | 1 | TRUE
4193 | ST-2025-033 | 2026-01-01 | 0 | 0 | TRUE
4194 | ST-2025-034 | 2023-06-01 | 0 | 0 | FALSE
4195 | ST-2025-034 | 2023-07-01 | 0 | 0 | FALSE
4196 | ST-2025-034 | 2023-08-01 | 0 | 0 | FALSE
4197 | ST-2025-034 | 2023-09-01 | 0 | 0 | FALSE
4198 | ST-2025-034 | 2023-10-01 | 0 | 0 | FALSE
4199 | ST-2025-034 | 2023-11-01 | 1 | 0 | TRUE
4200 | ST-2025-034 | 2023-12-01 | 0 | 0 | TRUE
4201 | ST-2025-034 | 2024-01-01 | 0 | 0 | TRUE
4202 | ST-2025-034 | 2024-02-01 | 0 | 0 | TRUE
4203 | ST-2025-034 | 2024-03-01 | 1 | 1 | TRUE
4204 | ST-2025-034 | 2024-04-01 | 0 | 1 | FALSE
4205 | ST-2025-034 | 2024-05-01 | 1 | 0 | TRUE
4206 | ST-2025-034 | 2024-06-01 | 0 | 1 | FALSE
4207 | ST-2025-034 | 2024-07-01 | 1 | 0 | TRUE
4208 | ST-2025-034 | 2024-08-01 | 0 | 0 | TRUE
4209 | ST-2025-034 | 2024-09-01 | 1 | 2 | FALSE
4210 | ST-2025-034 | 2024-10-01 | 1 | 0 | TRUE
4211 | ST-2025-034 | 2024-11-01 | 1 | 1 | TRUE
4212 | ST-2025-034 | 2024-12-01 | 1 | 1 | TRUE
4213 | ST-2025-034 | 2025-01-01 | 1 | 2 | FALSE
4214 | ST-2025-034 | 2025-02-01 | 1 | 0 | TRUE
4215 | ST-2025-034 | 2025-03-01 | 0 | 0 | TRUE
4216 | ST-2025-034 | 2025-04-01 | 1 | 1 | TRUE
4217 | ST-2025-034 | 2025-05-01 | 1 | 1 | TRUE
4218 | ST-2025-034 | 2025-06-01 | 1 | 1 | TRUE
4219 | ST-2025-034 | 2025-07-01 | 1 | 2 | FALSE
4220 | ST-2025-034 | 2025-08-01 | 1 | 0 | TRUE
4221 | ST-2025-034 | 2025-09-01 | 0 | 1 | FALSE
4222 | ST-2025-034 | 2025-10-01 | 1 | 0 | TRUE
4223 | ST-2025-034 | 2025-11-01 | 0 | 0 | TRUE
4224 | ST-2025-034 | 2025-12-01 | 1 | 1 | TRUE
4225 | ST-2025-034 | 2026-01-01 | 0 | 0 | TRUE
4226 | ST-2025-034 | 2026-02-01 | 1 | 1 | TRUE
4227 | ST-2025-034 | 2026-03-01 | 0 | 1 | FALSE
4228 | ST-2025-034 | 2026-04-01 | 0 | 0 | TRUE
4229 | ST-2025-034 | 2026-05-01 | 0 | 0 | TRUE
4230 | ST-2025-035 | 2025-06-01 | 0 | 0 | FALSE
4231 | ST-2025-035 | 2025-07-01 | 0 | 0 | FALSE
4232 | ST-2025-035 | 2025-08-01 | 0 | 0 | FALSE
4233 | ST-2025-035 | 2025-09-01 | 1 | 1 | FALSE
4234 | ST-2025-035 | 2025-10-01 | 0 | 0 | FALSE
4235 | ST-2025-035 | 2025-11-01 | 1 | 1 | FALSE
4236 | ST-2025-035 | 2025-12-01 | 1 | 1 | FALSE
4237 | ST-2025-035 | 2026-01-01 | 1 | 1 | FALSE
4238 | ST-2025-035 | 2026-02-01 | 1 | 1 | FALSE
4239 | ST-2025-035 | 2026-03-01 | 1 | 1 | FALSE
4240 | ST-2025-035 | 2026-04-01 | 2 | 2 | FALSE
4241 | ST-2025-035 | 2026-05-01 | 1 | 1 | FALSE
4242 | ST-2025-036 | 2021-11-01 | 9 | 8 | TRUE
4243 | ST-2025-036 | 2021-12-01 | 2 | 2 | TRUE
4244 | ST-2025-036 | 2022-01-01 | 1 | 0 | TRUE
4245 | ST-2025-036 | 2022-02-01 | 1 | 1 | TRUE
4246 | ST-2025-036 | 2022-03-01 | 2 | 3 | TRUE
4247 | ST-2025-036 | 2022-04-01 | 1 | 0 | TRUE
4248 | ST-2025-036 | 2022-05-01 | 2 | 3 | TRUE
4249 | ST-2025-036 | 2022-06-01 | 2 | 1 | TRUE
4250 | ST-2025-036 | 2022-07-01 | 2 | 1 | TRUE
4251 | ST-2025-036 | 2022-08-01 | 3 | 3 | TRUE
4252 | ST-2025-036 | 2022-09-01 | 2 | 2 | TRUE
4253 | ST-2025-036 | 2022-10-01 | 3 | 3 | TRUE
4254 | ST-2025-036 | 2022-11-01 | 4 | 3 | TRUE
4255 | ST-2025-036 | 2022-12-01 | 3 | 3 | TRUE
4256 | ST-2025-036 | 2023-01-01 | 4 | 5 | TRUE
4257 | ST-2025-036 | 2023-02-01 | 4 | 5 | TRUE
4258 | ST-2025-036 | 2023-03-01 | 5 | 2 | TRUE
4259 | ST-2025-036 | 2023-04-01 | 5 | 6 | TRUE
4260 | ST-2025-036 | 2023-05-01 | 6 | 4 | TRUE
4261 | ST-2025-036 | 2023-06-01 | 5 | 3 | TRUE
4262 | ST-2025-036 | 2023-07-01 | 7 | 12 | TRUE
4263 | ST-2025-036 | 2023-08-01 | 7 | 1 | TRUE
4264 | ST-2025-036 | 2023-09-01 | 7 | 13 | TRUE
4265 | ST-2025-036 | 2023-10-01 | 8 | 7 | TRUE
4266 | ST-2025-036 | 2023-11-01 | 9 | 4 | TRUE
4267 | ST-2025-036 | 2023-12-01 | 9 | 15 | TRUE
4268 | ST-2025-036 | 2024-01-01 | 10 | 10 | TRUE
4269 | ST-2025-036 | 2024-02-01 | 10 | 4 | TRUE
4270 | ST-2025-036 | 2024-03-01 | 10 | 16 | TRUE
4271 | ST-2025-036 | 2024-04-01 | 12 | 0 | TRUE
4272 | ST-2025-036 | 2024-05-01 | 11 | 15 | TRUE
4273 | ST-2025-036 | 2024-06-01 | 12 | 11 | TRUE
4274 | ST-2025-036 | 2024-07-01 | 13 | 10 | TRUE
4275 | ST-2025-036 | 2024-08-01 | 12 | 18 | TRUE
4276 | ST-2025-036 | 2024-09-01 | 13 | 13 | TRUE
4277 | ST-2025-036 | 2024-10-01 | 14 | 3 | TRUE
4278 | ST-2025-036 | 2024-11-01 | 13 | 24 | TRUE
4279 | ST-2025-036 | 2024-12-01 | 13 | 0 | TRUE
4280 | ST-2025-036 | 2025-01-01 | 13 | 15 | TRUE
4281 | ST-2025-036 | 2025-02-01 | 14 | 21 | TRUE
4282 | ST-2025-036 | 2025-03-01 | 13 | 11 | TRUE
4283 | ST-2025-036 | 2025-04-01 | 12 | 14 | TRUE
4284 | ST-2025-036 | 2025-05-01 | 13 | 0 | TRUE
4285 | ST-2025-036 | 2025-06-01 | 12 | 27 | TRUE
4286 | ST-2025-036 | 2025-07-01 | 11 | 25 | TRUE
4287 | ST-2025-036 | 2025-08-01 | 12 | 0 | TRUE
4288 | ST-2025-036 | 2025-09-01 | 10 | 0 | TRUE
4289 | ST-2025-036 | 2025-10-01 | 10 | 25 | TRUE
4290 | ST-2025-036 | 2025-11-01 | 10 | 0 | TRUE
4291 | ST-2025-036 | 2025-12-01 | 9 | 28 | TRUE
4292 | ST-2025-036 | 2026-01-01 | 9 | 21 | TRUE
4293 | ST-2025-036 | 2026-02-01 | 8 | 7 | TRUE
4294 | ST-2025-036 | 2026-03-01 | 7 | 0 | TRUE
4295 | ST-2025-036 | 2026-04-01 | 7 | 10 | TRUE
4296 | ST-2025-036 | 2026-05-01 | 7 | 9 | TRUE

## KPI Snapshot
id | study_id | enrollment_vs_plan_percent | current_rate_per_week | planned_rate_per_week | screen_failure_rate | dropout_rate | sites_activated | sites_planned | countries_activated | countries_planned | snapshot_date
527 | ST-2024-011 | 71.43 | 0.2 | 0.3 | 17.5 | 6.8 | 15 | 15 | 4 | 4 | 2026-05-18
528 | ST-2024-012 | 73.91 | 0.4 | 0.5 | 18 | 3.8 | 23 | 23 | 6 | 6 | 2026-05-18
529 | ST-2024-014 | 90.91 | 0.2 | 0.2 | 21.8 | 4.1 | 34 | 34 | 8 | 8 | 2026-05-18
530 | ST-2024-015 | 88.24 | 0.5 | 0.6 | 29.6 | 5.5 | 19 | 19 | 6 | 6 | 2026-05-18
531 | ST-2024-016 | 88.24 | 0.8 | 0.8 | 28.7 | 6.2 | 22 | 22 | 6 | 6 | 2026-05-18
532 | ST-2024-017 | 64.29 | 0.2 | 0.3 | 20.5 | 3.1 | 17 | 17 | 3 | 3 | 2026-05-18
533 | ST-2024-018 | 104.35 | 0.2 | 0.2 | 17.7 | 5.5 | 10 | 10 | 3 | 3 | 2026-05-18
534 | ST-2024-020 | 85.71 | 0.1 | 0.1 | 15.1 | 9.6 | 16 | 16 | 4 | 4 | 2026-05-18
535 | ST-2025-021 | 102.21 | 1.2 | 1.2 | 22.1 | 9 | 14 | 14 | 5 | 5 | 2026-05-18
536 | ST-2025-022 | 96.55 | 0.3 | 0.3 | 19.5 | 4.8 | 21 | 21 | 6 | 6 | 2026-05-18
537 | ST-2025-023 | 87.86 | 6.1 | 7 | 21.8 | 6.6 | 25 | 25 | 6 | 6 | 2026-05-18
538 | ST-2025-024 | 72.97 | 2 | 2.7 | 15 | 6.8 | 22 | 22 | 5 | 5 | 2026-05-18
539 | ST-2025-026 | 69.48 | 0.6 | 0.8 | 32.1 | 11.6 | 23 | 23 | 6 | 6 | 2026-05-18
540 | ST-2025-027 | 101.18 | 0.6 | 0.5 | 20 | 7.4 | 32 | 32 | 8 | 8 | 2026-05-18
541 | ST-2025-028 | 98.87 | 205.4 | 207.8 | 17.9 | 10.7 | 9 | 9 | 3 | 3 | 2026-05-18
542 | ST-2025-029 | 63.87 | 1.3 | 2.1 | 19.2 | 10 | 26 | 26 | 6 | 6 | 2026-05-18
543 | ST-2025-030 | 67.01 | 8.7 | 12.9 | 15.3 | 3.4 | 35 | 35 | 8 | 8 | 2026-05-18
544 | ST-2025-032 | 90.32 | 0.5 | 0.6 | 30.6 | 6 | 14 | 14 | 4 | 4 | 2026-05-18
545 | ST-2025-033 | 86.67 | 0.1 | 0.1 | 22.2 | 4.8 | 12 | 12 | 4 | 4 | 2026-05-18
546 | ST-2025-034 | 94.44 | 0.1 | 0.1 | 21.4 | 11.4 | 9 | 9 | 3 | 3 | 2026-05-18
548 | ST-2025-036 | 95.15 | 1.9 | 2 | 33.5 | 6 | 27 | 27 | 6 | 6 | 2026-05-18
547 | ST-2025-035 | 100 | 0.2 | 0.2 | 24.5 | 11.1 | 33 | 33 | 8 | 8 | 2026-05-18
519 | ST-2024-002 | 78.38 | 0.7 | 0.9 | 24.8 | 11.1 | 19 | 19 | 5 | 5 | 2026-05-18
520 | ST-2024-003 | 106.52 | 0.5 | 0.4 | 17.3 | 3.6 | 24 | 24 | 6 | 6 | 2026-05-18
521 | ST-2024-004 | 76.47 | 0.4 | 0.5 | 16 | 9.7 | 23 | 23 | 7 | 7 | 2026-05-18
522 | ST-2024-005 | 75.53 | 0.4 | 0.5 | 23.6 | 8.5 | 22 | 22 | 6 | 6 | 2026-05-18
523 | ST-2024-006 | 77.94 | 0.5 | 0.7 | 26.1 | 3.7 | 11 | 11 | 4 | 4 | 2026-05-18
524 | ST-2024-008 | 83.67 | 0.2 | 0.2 | 24.9 | 3.6 | 11 | 11 | 3 | 3 | 2026-05-18
525 | ST-2024-009 | 77.78 | 0.5 | 0.6 | 23.6 | 3.8 | 24 | 24 | 5 | 5 | 2026-05-18
526 | ST-2024-010 | 85.91 | 9.5 | 11.1 | 16.8 | 6.4 | 11 | 11 | 3 | 3 | 2026-05-18

## Country Breakdown
id | study_id | country | target_enrollment | actual_enrollment | enrollment_percent | sites_active | avg_enrollment_rate | performance_status | country_lead
722 | ST-2024-002 | United States | 18 | 13 | 72.2 | 5 | 1.9 | OFF_TRACK | Dr. Michelle Jones
723 | ST-2024-002 | Mexico | 44 | 41 | 93.2 | 3 | 2.6 | AT_RISK | Dr. Nicole Moore
724 | ST-2024-002 | Poland | 43 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Daniel White
725 | ST-2024-002 | Netherlands | 41 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. David Anderson
726 | ST-2024-002 | New Zealand | 25 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Amanda Harris
727 | ST-2024-003 | Canada | 31 | 27 | 87.1 | 2 | 3.4 | AT_RISK | Dr. Robert Davis
728 | ST-2024-003 | Mexico | 31 | 16 | 51.6 | 5 | 0.9 | OFF_TRACK | Dr. Robert Miller
729 | ST-2024-003 | France | 18 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Stephanie Taylor
730 | ST-2024-003 | Sweden | 29 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Stephanie Johnson
731 | ST-2024-003 | New Zealand | 22 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Charles Smith
732 | ST-2024-003 | South Korea | 17 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Nicole Smith
733 | ST-2024-004 | Canada | 33 | 23 | 69.7 | 4 | 2.1 | OFF_TRACK | Dr. Charles Williams
734 | ST-2024-004 | Mexico | 13 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Michelle Jackson
735 | ST-2024-004 | Norway | 30 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Nicole Moore
736 | ST-2024-004 | Belgium | 17 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Michael Davis
737 | ST-2024-004 | Denmark | 12 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Michael White
738 | ST-2024-004 | South Korea | 28 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Emily Harris
739 | ST-2024-004 | China | 12 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Jessica Smith
740 | ST-2024-005 | Mexico | 19 | 18 | 94.7 | 5 | 1.1 | AT_RISK | Dr. Jessica Wilson
741 | ST-2024-005 | United States | 17 | 17 | 100 | 6 | 2.8 | ON_TRACK | Dr. Amanda Thompson
742 | ST-2024-005 | France | 13 | 12 | 92.3 | 2 | 1.2 | AT_RISK | Dr. Christopher Harris
743 | ST-2024-005 | Denmark | 20 | 15 | 75 | 2 | 2.5 | OFF_TRACK | Dr. Amanda Anderson
744 | ST-2024-005 | New Zealand | 15 | 8 | 53.3 | 2 | 0.5 | OFF_TRACK | Dr. Michael Thompson
745 | ST-2024-005 | China | 16 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Michelle Johnson
746 | ST-2024-006 | United States | 17 | 17 | 100 | 2 | 1.7 | ON_TRACK | Dr. David Moore
747 | ST-2024-006 | United Kingdom | 12 | 10 | 83.3 | 4 | 1.2 | AT_RISK | Dr. Jessica Moore
748 | ST-2024-006 | Switzerland | 27 | 21 | 77.8 | 2 | 1.5 | OFF_TRACK | Dr. Jennifer Jones
749 | ST-2024-006 | South Korea | 14 | 7 | 50 | 3 | 0.4 | OFF_TRACK | Dr. Thomas Johnson
750 | ST-2024-007 | Canada | 8 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Robert Anderson
751 | ST-2024-007 | Mexico | 9 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Michael Thomas
752 | ST-2024-007 | Spain | 6 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. William Martin
753 | ST-2024-007 | Italy | 6 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Michelle Wilson
754 | ST-2024-007 | India | 11 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. William Jones
755 | ST-2024-007 | Singapore | 10 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Lisa Davis
756 | ST-2024-008 | United States | 19 | 17 | 89.5 | 3 | 1 | AT_RISK | Dr. Nicole Wilson
757 | ST-2024-008 | Sweden | 22 | 15 | 68.2 | 2 | 2.1 | OFF_TRACK | Dr. William Moore
758 | ST-2024-008 | Taiwan | 9 | 9 | 100 | 6 | 0.6 | ON_TRACK | Dr. Sarah Garcia
759 | ST-2024-009 | Canada | 48 | 12 | 25 | 3 | 0.9 | OFF_TRACK | Dr. Jennifer Taylor
760 | ST-2024-009 | United States | 75 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Christopher Davis
761 | ST-2024-009 | Sweden | 35 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Jennifer Garcia
762 | ST-2024-009 | Norway | 77 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. James Miller
763 | ST-2024-009 | Singapore | 65 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Stephanie Jackson
764 | ST-2024-010 | Mexico | 1254 | 1162 | 92.7 | 3 | 129.1 | AT_RISK | Dr. Jessica Wilson
765 | ST-2024-010 | United Kingdom | 2610 | 1318 | 50.5 | 4 | 73.2 | OFF_TRACK | Dr. Charles Taylor
766 | ST-2024-010 | Australia | 1136 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. William Davis
767 | ST-2024-011 | United States | 27 | 5 | 18.5 | 3 | 0.3 | OFF_TRACK | Dr. Michael Taylor
768 | ST-2024-011 | France | 38 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. William Miller
769 | ST-2024-011 | Singapore | 52 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Michael Thomas
770 | ST-2024-011 | Mexico | 23 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Emily Smith
771 | ST-2024-012 | Mexico | 3 | 2 | 66.7 | 6 | 0.2 | OFF_TRACK | Dr. Jessica Brown
772 | ST-2024-012 | Canada | 5 | 4 | 80 | 5 | 0.6 | AT_RISK | Dr. Thomas Wilson
773 | ST-2024-012 | Belgium | 6 | 6 | 100 | 4 | 0.6 | ON_TRACK | Dr. William Anderson
774 | ST-2024-012 | Norway | 6 | 3 | 50 | 3 | 0.4 | OFF_TRACK | Dr. Daniel Davis
775 | ST-2024-012 | Singapore | 5 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Charles Taylor
776 | ST-2024-012 | Chile | 5 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. James Martin
777 | ST-2024-013 | Mexico | -6 | -6 | 100 | 3 | -0.4 | ON_TRACK | Dr. Jennifer Jones
778 | ST-2024-013 | Poland | 5 | 5 | 100 | 2 | 0.4 | ON_TRACK | Dr. Thomas Thompson
779 | ST-2024-013 | South Korea | 5 | 1 | 20 | 5 | 0.1 | OFF_TRACK | Dr. Lisa Wilson
780 | ST-2024-013 | Chile | 5 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Jessica Harris
781 | ST-2024-014 | Mexico | -5 | -5 | 100 | 4 | -0.6 | ON_TRACK | Dr. Michelle Miller
782 | ST-2024-014 | Canada | 5 | 4 | 80 | 4 | 0.2 | AT_RISK | Dr. Michael Williams
783 | ST-2024-014 | United States | 5 | 4 | 80 | 2 | 0.3 | AT_RISK | Dr. James Jackson
784 | ST-2024-014 | Poland | 5 | 4 | 80 | 6 | 0.4 | AT_RISK | Dr. Sarah Moore
785 | ST-2024-014 | Norway | 5 | 1 | 20 | 4 | 0.1 | OFF_TRACK | Dr. Michelle Martin
786 | ST-2024-014 | Netherlands | 5 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Charles Davis
787 | ST-2024-014 | Denmark | 5 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Jessica Jones
788 | ST-2024-014 | Taiwan | 5 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Daniel Williams
789 | ST-2024-015 | Canada | 27 | 12 | 44.4 | 4 | 0.9 | OFF_TRACK | Dr. Michelle Davis
790 | ST-2024-015 | Mexico | 13 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Jessica Thomas
791 | ST-2024-015 | Sweden | 31 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Robert Anderson
792 | ST-2024-015 | Norway | 22 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Daniel Jones
793 | ST-2024-015 | Switzerland | 23 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Nicole Moore
794 | ST-2024-015 | India | 20 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Nicole Martin
795 | ST-2024-016 | United States | 18 | 13 | 72.2 | 5 | 2.2 | OFF_TRACK | Dr. Jessica Thompson
796 | ST-2024-016 | Canada | 17 | 17 | 100 | 2 | 1.5 | ON_TRACK | Dr. Michelle Jones
797 | ST-2024-016 | Germany | 10 | 9 | 90 | 4 | 0.6 | AT_RISK | Dr. Lisa Jones
798 | ST-2024-016 | Poland | 17 | 6 | 35.3 | 2 | 0.4 | OFF_TRACK | Dr. Charles Harris
799 | ST-2024-016 | Belgium | 11 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Daniel Williams
800 | ST-2024-016 | Australia | 17 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Jessica Jackson
801 | ST-2024-017 | Mexico | 23 | 8 | 34.8 | 5 | 0.5 | OFF_TRACK | Dr. Jessica White
802 | ST-2024-017 | Spain | 12 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. William Thompson
803 | ST-2024-017 | China | 25 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Amanda Jones
804 | ST-2024-018 | United States | 10 | 10 | 100 | 3 | 1 | ON_TRACK | Dr. Robert Jones
805 | ST-2024-018 | Denmark | 6 | 6 | 100 | 2 | 0.9 | ON_TRACK | Dr. James Jones
806 | ST-2024-018 | South Korea | 8 | 8 | 100 | 5 | 0.5 | ON_TRACK | Dr. Stephanie Jones
807 | ST-2024-019 | Mexico | 39 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Christopher Wilson
808 | ST-2024-019 | United States | 69 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Thomas Wilson
809 | ST-2024-019 | Poland | 55 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Michael Wilson
810 | ST-2024-019 | Denmark | 79 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Charles Taylor
811 | ST-2024-019 | United Kingdom | 72 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. William Garcia
812 | ST-2024-019 | Australia | 82 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Nicole Miller
813 | ST-2024-020 | Canada | 0 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Sarah Thompson
814 | ST-2024-020 | Norway | 5 | 5 | 100 | 4 | 0.8 | ON_TRACK | Dr. Emily Jackson
815 | ST-2024-020 | Netherlands | 5 | 3 | 60 | 4 | 0.2 | OFF_TRACK | Dr. Sarah Thomas
816 | ST-2024-020 | Japan | 5 | 4 | 80 | 4 | 0.5 | AT_RISK | Dr. Michelle Williams
817 | ST-2025-021 | Mexico | 48 | 48 | 100 | 4 | 6 | ON_TRACK | Dr. Jessica Smith
818 | ST-2025-021 | United States | 48 | 48 | 100 | 2 | 5.3 | ON_TRACK | Dr. Robert Jones
819 | ST-2025-021 | Belgium | 33 | 30 | 90.9 | 3 | 3 | AT_RISK | Dr. Robert Miller
820 | ST-2025-021 | Sweden | 27 | 27 | 100 | 3 | 3.9 | ON_TRACK | Dr. Stephanie Brown
821 | ST-2025-021 | Australia | 29 | 32 | 110.3 | 2 | 5.3 | ON_TRACK | Dr. Nicole White
822 | ST-2025-022 | United States | 9 | 8 | 88.9 | 4 | 0.7 | AT_RISK | Dr. Stephanie Taylor
823 | ST-2025-022 | Mexico | 9 | 6 | 66.7 | 2 | 0.4 | OFF_TRACK | Dr. David White
824 | ST-2025-022 | Poland | 10 | 7 | 70 | 4 | 0.7 | OFF_TRACK | Dr. Jennifer Wilson
825 | ST-2025-022 | Sweden | 10 | 8 | 80 | 6 | 0.9 | AT_RISK | Dr. Charles Davis
826 | ST-2025-022 | China | 11 | 8 | 72.7 | 2 | 1 | OFF_TRACK | Dr. David Smith
827 | ST-2025-022 | Chile | 11 | 23 | 209.1 | 3 | 1.3 | ON_TRACK | Dr. Jessica Harris
828 | ST-2025-023 | United States | 199 | 184 | 92.5 | 2 | 10.8 | AT_RISK | Dr. Christopher Garcia
829 | ST-2025-023 | Canada | 185 | 148 | 80 | 3 | 12.3 | AT_RISK | Dr. Sarah Williams
830 | ST-2025-023 | Italy | 206 | 165 | 80.1 | 5 | 9.7 | AT_RISK | Dr. Jessica Taylor
831 | ST-2025-023 | Poland | 314 | 230 | 73.2 | 6 | 13.5 | OFF_TRACK | Dr. Christopher Harris
832 | ST-2025-023 | Japan | 202 | 182 | 90.1 | 6 | 10.1 | AT_RISK | Dr. William Taylor
833 | ST-2025-023 | Mexico | 394 | 361 | 91.6 | 3 | 40.1 | AT_RISK | Dr. Jennifer Williams
834 | ST-2025-024 | United States | 51 | 51 | 100 | 6 | 3.4 | ON_TRACK | Dr. Thomas Jackson
835 | ST-2025-024 | Mexico | 44 | 44 | 100 | 6 | 7.3 | ON_TRACK | Dr. Nicole Smith
836 | ST-2025-024 | Sweden | 62 | 33 | 53.2 | 4 | 2.8 | OFF_TRACK | Dr. Jennifer White
837 | ST-2025-024 | Switzerland | 33 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Thomas Jackson
838 | ST-2025-024 | Japan | 30 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Emily Brown
839 | ST-2025-025 | Canada | -29 | -29 | 100 | 3 | -2.6 | ON_TRACK | Dr. Michelle Davis
840 | ST-2025-025 | United States | 5 | 5 | 100 | 3 | 0.6 | ON_TRACK | Dr. James Garcia
841 | ST-2025-025 | Spain | 5 | 3 | 60 | 4 | 0.4 | OFF_TRACK | Dr. James Jones
842 | ST-2025-025 | Sweden | 5 | 3 | 60 | 5 | 0.2 | OFF_TRACK | Dr. Emily Taylor
843 | ST-2025-025 | Netherlands | 5 | 3 | 60 | 3 | 0.3 | OFF_TRACK | Dr. Christopher Davis
844 | ST-2025-025 | Taiwan | 5 | 3 | 60 | 4 | 0.2 | OFF_TRACK | Dr. Amanda Garcia
845 | ST-2025-025 | Australia | 5 | 5 | 100 | 6 | 0.3 | ON_TRACK | Dr. Stephanie Williams
846 | ST-2025-025 | Chile | 5 | 7 | 140 | 2 | 0.9 | ON_TRACK | Dr. Robert Miller
847 | ST-2025-026 | Mexico | 28 | 23 | 82.1 | 6 | 1.8 | AT_RISK | Dr. Robert Wilson
848 | ST-2025-026 | Canada | 41 | 40 | 97.6 | 3 | 2.7 | ON_TRACK | Dr. Jennifer Smith
849 | ST-2025-026 | Switzerland | 43 | 30 | 69.8 | 2 | 1.7 | OFF_TRACK | Dr. Michael Jackson
850 | ST-2025-026 | Sweden | 35 | 33 | 94.3 | 5 | 1.9 | AT_RISK | Dr. Michael Thompson
851 | ST-2025-026 | Singapore | 46 | 17 | 37 | 3 | 1.4 | OFF_TRACK | Dr. Jennifer White
852 | ST-2025-026 | New Zealand | 67 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Jessica Thompson
853 | ST-2025-027 | Mexico | 17 | 17 | 100 | 6 | 1.4 | ON_TRACK | Dr. Michael Taylor
854 | ST-2025-027 | Canada | 7 | 6 | 85.7 | 2 | 0.5 | AT_RISK | Dr. Thomas Wilson
855 | ST-2025-027 | United States | 9 | 6 | 66.7 | 3 | 0.3 | OFF_TRACK | Dr. Lisa Wilson
856 | ST-2025-027 | Switzerland | 12 | 11 | 91.7 | 2 | 1.6 | AT_RISK | Dr. Charles Davis
857 | ST-2025-027 | Spain | 14 | 10 | 71.4 | 5 | 1.4 | OFF_TRACK | Dr. Emily Garcia
858 | ST-2025-027 | United Kingdom | 12 | 8 | 66.7 | 6 | 0.5 | OFF_TRACK | Dr. Jessica Martin
859 | ST-2025-027 | India | 10 | 7 | 70 | 2 | 0.5 | OFF_TRACK | Dr. Amanda Anderson
860 | ST-2025-027 | Singapore | 7 | 17 | 242.9 | 6 | 1.7 | ON_TRACK | Dr. Emily Johnson
861 | ST-2025-028 | Canada | 21031 | 5228 | 24.9 | 2 | 348.5 | OFF_TRACK | Dr. Thomas Brown
862 | ST-2025-028 | Denmark | 31608 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Sarah Jones
863 | ST-2025-028 | Australia | 15361 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Daniel Taylor
864 | ST-2025-029 | Mexico | 43 | 35 | 81.4 | 3 | 3.9 | AT_RISK | Dr. Robert Garcia
865 | ST-2025-029 | United States | 20 | 15 | 75 | 6 | 1.1 | OFF_TRACK | Dr. Daniel Taylor
866 | ST-2025-029 | Netherlands | 34 | 30 | 88.2 | 5 | 1.7 | AT_RISK | Dr. Robert Taylor
867 | ST-2025-029 | Belgium | 27 | 27 | 100 | 4 | 2.5 | ON_TRACK | Dr. Stephanie Johnson
868 | ST-2025-029 | Australia | 34 | 9 | 26.5 | 5 | 1 | OFF_TRACK | Dr. David Williams
869 | ST-2025-029 | India | 42 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Nicole Brown
870 | ST-2025-030 | United States | 158 | 138 | 87.3 | 2 | 19.7 | AT_RISK | Dr. Christopher Garcia
871 | ST-2025-030 | Canada | 177 | 177 | 100 | 6 | 16.1 | ON_TRACK | Dr. Charles Davis
872 | ST-2025-030 | Mexico | 210 | 163 | 77.6 | 6 | 27.2 | OFF_TRACK | Dr. Jessica Smith
873 | ST-2025-030 | Poland | 190 | 136 | 71.6 | 6 | 22.7 | OFF_TRACK | Dr. Christopher Anderson
874 | ST-2025-030 | Spain | 170 | 152 | 89.4 | 3 | 12.7 | AT_RISK | Dr. Sarah Moore
875 | ST-2025-030 | Switzerland | 156 | 112 | 71.8 | 6 | 18.7 | OFF_TRACK | Dr. Thomas Smith
876 | ST-2025-030 | China | 167 | 64 | 38.3 | 2 | 4.9 | OFF_TRACK | Dr. Emily White
877 | ST-2025-030 | Japan | 172 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Thomas Thomas
878 | ST-2025-031 | Canada | 10 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Jessica Davis
879 | ST-2025-031 | United States | 7 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Jennifer White
880 | ST-2025-031 | Mexico | 5 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. David Williams
881 | ST-2025-031 | United Kingdom | 12 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Emily Miller
882 | ST-2025-031 | France | 9 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Robert Smith
883 | ST-2025-031 | Belgium | 9 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Stephanie Moore
884 | ST-2025-031 | Taiwan | 11 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Jennifer Thompson
885 | ST-2025-031 | Japan | 5 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. David Martin
886 | ST-2025-032 | Canada | 118 | 25 | 21.2 | 2 | 1.5 | OFF_TRACK | Dr. Lisa Williams
887 | ST-2025-032 | Mexico | 82 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Daniel Taylor
888 | ST-2025-032 | United Kingdom | 48 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Daniel Williams
889 | ST-2025-032 | Norway | 52 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Stephanie Brown
890 | ST-2025-033 | Mexico | 1 | 1 | 100 | 5 | 0.2 | ON_TRACK | Dr. Thomas White
891 | ST-2025-033 | Canada | 5 | 5 | 100 | 3 | 0.6 | ON_TRACK | Dr. Nicole Williams
892 | ST-2025-033 | Switzerland | 5 | 3 | 60 | 2 | 0.3 | OFF_TRACK | Dr. David Miller
893 | ST-2025-033 | Poland | 5 | 4 | 80 | 2 | 0.3 | AT_RISK | Dr. Christopher Taylor
894 | ST-2025-034 | Canada | 8 | 7 | 87.5 | 2 | 0.4 | AT_RISK | Dr. Amanda Smith
895 | ST-2025-034 | France | 6 | 4 | 66.7 | 3 | 0.3 | OFF_TRACK | Dr. Nicole Taylor
896 | ST-2025-034 | New Zealand | 6 | 6 | 100 | 4 | 0.4 | ON_TRACK | Dr. Emily Garcia
897 | ST-2025-035 | Canada | -20 | -20 | 100 | 6 | -1.3 | ON_TRACK | Dr. Christopher Johnson
898 | ST-2025-035 | Mexico | 5 | 4 | 80 | 2 | 0.4 | AT_RISK | Dr. Amanda Johnson
899 | ST-2025-035 | United States | 5 | 5 | 100 | 3 | 0.3 | ON_TRACK | Dr. Emily Jackson
900 | ST-2025-035 | Sweden | 5 | 4 | 80 | 6 | 0.2 | AT_RISK | Dr. Michael Taylor
901 | ST-2025-035 | Netherlands | 5 | 3 | 60 | 4 | 0.2 | OFF_TRACK | Dr. Charles Smith
902 | ST-2025-035 | Italy | 5 | 5 | 100 | 3 | 0.3 | ON_TRACK | Dr. William Williams
903 | ST-2025-035 | Germany | 5 | 5 | 100 | 5 | 0.7 | ON_TRACK | Dr. David Wilson
904 | ST-2025-035 | Australia | 5 | 2 | 40 | 4 | 0.1 | OFF_TRACK | Dr. Daniel Moore
905 | ST-2025-036 | Mexico | 78 | 78 | 100 | 5 | 4.6 | ON_TRACK | Dr. Robert Taylor
906 | ST-2025-036 | United States | 95 | 95 | 100 | 2 | 11.9 | ON_TRACK | Dr. Thomas Harris
907 | ST-2025-036 | Poland | 99 | 99 | 100 | 6 | 5.5 | ON_TRACK | Dr. Stephanie Smith
908 | ST-2025-036 | United Kingdom | 43 | 37 | 86 | 5 | 2.5 | AT_RISK | Dr. Jessica Smith
909 | ST-2025-036 | Switzerland | 104 | 84 | 80.8 | 6 | 7 | AT_RISK | Dr. James Smith
910 | ST-2025-036 | Australia | 81 | 20 | 24.7 | 3 | 1.8 | OFF_TRACK | Dr. Stephanie Jones
911 | ST-2025-037 | Mexico | 1448 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Thomas Jackson
912 | ST-2025-037 | United States | 1362 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Jennifer Martin
913 | ST-2025-037 | Canada | 1496 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Amanda Moore
914 | ST-2025-037 | Denmark | 835 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Jessica Brown
915 | ST-2025-037 | Netherlands | 1461 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Charles Taylor
916 | ST-2025-037 | United Kingdom | 935 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Jennifer Jackson
917 | ST-2025-037 | Italy | 1633 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Nicole Thomas
918 | ST-2025-037 | Taiwan | 830 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Christopher Thomas

## Site Breakdown
id | study_id | country | site_id | site_name | target_enrollment | actual_enrollment | enrollment_percent | enrollment_rate | site_status | principal_investigator | site_coordinator
2847 | ST-2024-002 | United States | S0001 | UNIT-Medical Center | 5 | 4 | 80 | 0.4 | SCREENING | Dr. Sarah Taylor | Dr. Michael Thompson
2848 | ST-2024-002 | United States | S0002 | UNIT-University Hospital | 4 | 3 | 75 | 0.3 | CLOSED | Dr. Nicole Miller | Dr. Michelle Jones
2849 | ST-2024-002 | United States | S0003 | UNIT-General Hospital | 3 | 1 | 33.3 | 0.1 | CLOSED | Dr. Nicole Davis | Dr. Nicole White
2850 | ST-2024-002 | United States | S0004 | UNIT-University Hospital | 3 | 3 | 100 | 0.4 | SCREENING | Dr. Stephanie Thomas | Dr. Stephanie White
2851 | ST-2024-002 | United States | S0005 | UNIT-Clinical Center | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Emily Johnson | Dr. Charles Taylor
2852 | ST-2024-002 | Mexico | S0006 | MEXI-University Hospital | 23 | 21 | 91.3 | 2.1 | SCREENING | Dr. Lisa Williams | Dr. Christopher Moore
2853 | ST-2024-002 | Mexico | S0007 | MEXI-Medical Center | 10 | 6 | 60 | 1 | ON_HOLD | Dr. Michelle Smith | Dr. Michael Davis
2854 | ST-2024-002 | Mexico | S0008 | MEXI-University Hospital | 11 | 14 | 127.3 | 1.2 | SCREENING | Dr. Nicole Miller | Dr. Charles Johnson
2855 | ST-2024-002 | Poland | S0009 | POLA-Research Institute | 15 | 0 | 0 | 0 | CLOSED | Dr. Michelle Martin | Dr. Robert Miller
2856 | ST-2024-002 | Poland | S0010 | POLA-Research Institute | 10 | 0 | 0 | 0 | SCREENING | Dr. Michelle Johnson | Dr. Thomas Johnson
2857 | ST-2024-002 | Poland | S0011 | POLA-Medical Center | 18 | 0 | 0 | 0 | ON_HOLD | Dr. Daniel Thompson | Dr. Jennifer Johnson
2858 | ST-2024-002 | Netherlands | S0012 | NETH-University Hospital | 23 | 0 | 0 | 0 | SCREENING | Dr. Lisa Johnson | Dr. Michael White
2859 | ST-2024-002 | Netherlands | S0013 | NETH-General Hospital | 8 | 0 | 0 | 0 | CLOSED | Dr. Daniel Taylor | Dr. William Miller
2860 | ST-2024-002 | Netherlands | S0014 | NETH-General Hospital | 10 | 0 | 0 | 0 | ON_HOLD | Dr. Lisa Wilson | Dr. Charles Jones
2861 | ST-2024-002 | New Zealand | S0015 | NEW-University Hospital | 8 | 0 | 0 | 0 | ON_HOLD | Dr. Robert Thomas | Dr. Michael Davis
2862 | ST-2024-002 | New Zealand | S0016 | NEW-Research Institute | 4 | 0 | 0 | 0 | SCREENING | Dr. Christopher Moore | Dr. Jessica Thompson
2863 | ST-2024-002 | New Zealand | S0017 | NEW-Medical Center | 4 | 0 | 0 | 0 | CLOSED | Dr. Jessica Brown | Dr. Robert Wilson
2864 | ST-2024-002 | New Zealand | S0018 | NEW-Medical Center | 6 | 0 | 0 | 0 | CLOSED | Dr. Michelle Jones | Dr. William Anderson
2865 | ST-2024-002 | New Zealand | S0019 | NEW-Health System | 3 | 0 | 0 | 0 | CLOSED | Dr. Thomas Miller | Dr. William Thompson
2866 | ST-2024-003 | Canada | S0001 | CANA-Cancer Center | 20 | 16 | 80 | 1.3 | ON_HOLD | Dr. Michelle Davis | Dr. Nicole Davis
2867 | ST-2024-003 | Canada | S0002 | CANA-Research Institute | 11 | 11 | 100 | 0.9 | SCREENING | Dr. James Jackson | Dr. Thomas Jackson
2868 | ST-2024-003 | Mexico | S0003 | MEXI-Clinical Center | 8 | 8 | 100 | 1 | ON_HOLD | Dr. Jennifer Johnson | Dr. William Jackson
2869 | ST-2024-003 | Mexico | S0004 | MEXI-Research Institute | 6 | 5 | 83.3 | 0.6 | ON_HOLD | Dr. Thomas Taylor | Dr. Charles Wilson
2870 | ST-2024-003 | Mexico | S0005 | MEXI-Cancer Center | 6 | 3 | 50 | 0.2 | ON_HOLD | Dr. Michael Martin | Dr. James Moore
2871 | ST-2024-003 | Mexico | S0006 | MEXI-Medical Center | 7 | 0 | 0 | 0 | SCREENING | Dr. Michael Johnson | Dr. James Davis
2872 | ST-2024-003 | Mexico | S0007 | MEXI-University Hospital | 4 | 0 | 0 | 0 | CLOSED | Dr. Robert Davis | Dr. Robert Martin
2873 | ST-2024-003 | France | S0008 | FRAN-General Hospital | 10 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Brown | Dr. Jennifer Anderson
2874 | ST-2024-003 | France | S0009 | FRAN-Medical Center | 8 | 0 | 0 | 0 | SCREENING | Dr. Jessica Jackson | Dr. Charles Miller
2875 | ST-2024-003 | Sweden | S0010 | SWED-Clinical Center | 4 | 0 | 0 | 0 | ON_HOLD | Dr. Michael Thompson | Dr. Thomas Smith
2876 | ST-2024-003 | Sweden | S0011 | SWED-Cancer Center | 5 | 0 | 0 | 0 | ON_HOLD | Dr. Emily White | Dr. Amanda Harris
2877 | ST-2024-003 | Sweden | S0012 | SWED-General Hospital | 5 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Thompson | Dr. William Moore
2878 | ST-2024-003 | Sweden | S0013 | SWED-Cancer Center | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Wilson | Dr. Thomas Davis
2879 | ST-2024-003 | Sweden | S0014 | SWED-Cancer Center | 6 | 0 | 0 | 0 | ON_HOLD | Dr. Christopher Davis | Dr. Christopher Jackson
2880 | ST-2024-003 | Sweden | S0015 | SWED-Research Institute | 6 | 0 | 0 | 0 | ON_HOLD | Dr. Thomas Garcia | Dr. Nicole Miller
2881 | ST-2024-003 | New Zealand | S0016 | NEW-Health System | 9 | 0 | 0 | 0 | CLOSED | Dr. David Williams | Dr. Lisa White
2882 | ST-2024-003 | New Zealand | S0017 | NEW-Clinical Center | 6 | 0 | 0 | 0 | SCREENING | Dr. Nicole Martin | Dr. Christopher Smith
2883 | ST-2024-003 | New Zealand | S0018 | NEW-Medical Center | 7 | 0 | 0 | 0 | SCREENING | Dr. Charles Davis | Dr. Jessica Thomas
2884 | ST-2024-003 | South Korea | S0019 | SOUT-Health System | 2 | 0 | 0 | 0 | CLOSED | Dr. Jennifer Miller | Dr. David Martin
2885 | ST-2024-003 | South Korea | S0020 | SOUT-Research Institute | 3 | 0 | 0 | 0 | CLOSED | Dr. Daniel Anderson | Dr. Emily Miller
2886 | ST-2024-003 | South Korea | S0021 | SOUT-Research Institute | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Anderson | Dr. James Moore
2887 | ST-2024-003 | South Korea | S0022 | SOUT-University Hospital | 3 | 0 | 0 | 0 | SCREENING | Dr. Sarah Moore | Dr. Jessica Jones
2888 | ST-2024-003 | South Korea | S0023 | SOUT-General Hospital | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Emily Smith | Dr. Jessica Martin
2889 | ST-2024-003 | South Korea | S0024 | SOUT-Clinical Center | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Johnson | Dr. William Martin
2890 | ST-2024-004 | Canada | S0001 | CANA-Cancer Center | 6 | 4 | 66.7 | 0.5 | SCREENING | Dr. Jennifer Williams | Dr. Charles Davis
2891 | ST-2024-004 | Canada | S0002 | CANA-Clinical Center | 12 | 11 | 91.7 | 0.7 | SCREENING | Dr. Lisa Harris | Dr. William Harris
2892 | ST-2024-004 | Canada | S0003 | CANA-Research Institute | 7 | 6 | 85.7 | 0.4 | SCREENING | Dr. Christopher Anderson | Dr. Michelle Garcia
2893 | ST-2024-004 | Canada | S0004 | CANA-Medical Center | 8 | 2 | 25 | 0.2 | ON_HOLD | Dr. Jessica White | Dr. William Harris
2894 | ST-2024-004 | Mexico | S0005 | MEXI-General Hospital | 4 | 0 | 0 | 0 | SCREENING | Dr. Charles Wilson | Dr. James Johnson
2895 | ST-2024-004 | Mexico | S0006 | MEXI-Health System | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Jessica Davis | Dr. Amanda Davis
2896 | ST-2024-004 | Mexico | S0007 | MEXI-General Hospital | 3 | 0 | 0 | 0 | CLOSED | Dr. William Jones | Dr. Emily Johnson
2897 | ST-2024-004 | Mexico | S0008 | MEXI-Research Institute | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Sarah Thomas | Dr. Robert Williams
2898 | ST-2024-004 | Norway | S0009 | NORW-Health System | 12 | 0 | 0 | 0 | SCREENING | Dr. William Martin | Dr. Jessica Taylor
2899 | ST-2024-004 | Norway | S0010 | NORW-Cancer Center | 6 | 0 | 0 | 0 | ON_HOLD | Dr. Michael Jones | Dr. Lisa Jackson
2900 | ST-2024-004 | Norway | S0011 | NORW-Cancer Center | 7 | 0 | 0 | 0 | CLOSED | Dr. Amanda Williams | Dr. Charles Smith
2901 | ST-2024-004 | Norway | S0012 | NORW-Research Institute | 5 | 0 | 0 | 0 | SCREENING | Dr. Christopher Thomas | Dr. William Jackson
2902 | ST-2024-004 | Belgium | S0013 | BELG-University Hospital | 9 | 0 | 0 | 0 | SCREENING | Dr. Michelle Taylor | Dr. Lisa Williams
2903 | ST-2024-004 | Belgium | S0014 | BELG-General Hospital | 8 | 0 | 0 | 0 | CLOSED | Dr. Jessica White | Dr. Emily Jones
2904 | ST-2024-004 | Denmark | S0015 | DENM-Research Institute | 1 | 0 | 0 | 0 | CLOSED | Dr. Michelle White | Dr. Robert White
2905 | ST-2024-004 | Denmark | S0016 | DENM-General Hospital | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Wilson | Dr. Sarah Thomas
2906 | ST-2024-004 | Denmark | S0017 | DENM-University Hospital | 5 | 0 | 0 | 0 | ON_HOLD | Dr. Lisa Thomas | Dr. Emily Thomas
2907 | ST-2024-004 | Denmark | S0018 | DENM-Health System | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Sarah Jackson | Dr. William Miller
2908 | ST-2024-004 | South Korea | S0019 | SOUT-Medical Center | 15 | 0 | 0 | 0 | SCREENING | Dr. James Johnson | Dr. Thomas Davis
2909 | ST-2024-004 | South Korea | S0020 | SOUT-University Hospital | 13 | 0 | 0 | 0 | CLOSED | Dr. David Williams | Dr. Michelle Miller
2910 | ST-2024-004 | China | S0021 | CHIN-Health System | 4 | 0 | 0 | 0 | ON_HOLD | Dr. Robert Jones | Dr. Michelle Wilson
2911 | ST-2024-004 | China | S0022 | CHIN-Cancer Center | 5 | 0 | 0 | 0 | SCREENING | Dr. James Jones | Dr. James Thomas
2912 | ST-2024-004 | China | S0023 | CHIN-Cancer Center | 3 | 0 | 0 | 0 | SCREENING | Dr. Thomas Smith | Dr. Jennifer Wilson
2913 | ST-2024-005 | Mexico | S0001 | MEXI-Research Institute | 5 | 3 | 60 | 0.2 | ENROLLING | Dr. Daniel Garcia | Dr. Sarah Davis
2914 | ST-2024-005 | Mexico | S0002 | MEXI-General Hospital | 4 | 2 | 50 | 0.2 | SCREENING | Dr. Daniel Thompson | Dr. Jennifer Thomas
2915 | ST-2024-005 | Mexico | S0003 | MEXI-Research Institute | 4 | 2 | 50 | 0.2 | SCREENING | Dr. Stephanie Taylor | Dr. Sarah Taylor
2916 | ST-2024-005 | Mexico | S0004 | MEXI-Medical Center | 3 | 3 | 100 | 0.3 | ENROLLING | Dr. Michelle Jackson | Dr. Jessica Wilson
2917 | ST-2024-005 | Mexico | S0005 | MEXI-General Hospital | 3 | 8 | 266.7 | 0.5 | ON_HOLD | Dr. Robert Taylor | Dr. Michael Jones
2918 | ST-2024-005 | United States | S0006 | UNIT-General Hospital | 2 | 1 | 50 | 0.1 | SCREENING | Dr. Daniel Williams | Dr. Stephanie Thompson
2919 | ST-2024-005 | United States | S0007 | UNIT-Research Institute | 3 | 2 | 66.7 | 0.3 | ENROLLING | Dr. Jessica Garcia | Dr. David Taylor
2920 | ST-2024-005 | United States | S0008 | UNIT-Cancer Center | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Lisa Jones | Dr. Robert Williams
2921 | ST-2024-005 | United States | S0009 | UNIT-Research Institute | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Daniel Moore | Dr. Daniel Johnson
2922 | ST-2024-005 | United States | S0010 | UNIT-General Hospital | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Robert Jackson | Dr. Robert Garcia
2923 | ST-2024-005 | United States | S0011 | UNIT-University Hospital | 3 | 8 | 266.7 | 0.5 | SCREENING | Dr. Jennifer Harris | Dr. Sarah White
2924 | ST-2024-005 | France | S0012 | FRAN-Health System | 6 | 6 | 100 | 0.6 | ON_HOLD | Dr. Christopher Davis | Dr. Michelle Davis
2925 | ST-2024-005 | France | S0013 | FRAN-Research Institute | 7 | 6 | 85.7 | 0.3 | SCREENING | Dr. David Thomas | Dr. Christopher Harris
2926 | ST-2024-005 | Denmark | S0014 | DENM-Clinical Center | 10 | 9 | 90 | 1.1 | SCREENING | Dr. Robert Wilson | Dr. Sarah Martin
2927 | ST-2024-005 | Denmark | S0015 | DENM-Cancer Center | 10 | 6 | 60 | 0.5 | CLOSED | Dr. Emily Thompson | Dr. Emily Anderson
2928 | ST-2024-005 | New Zealand | S0016 | NEW-Health System | 8 | 6 | 75 | 0.8 | ON_HOLD | Dr. Michael Davis | Dr. Christopher Thomas
2929 | ST-2024-005 | New Zealand | S0017 | NEW-Medical Center | 7 | 2 | 28.6 | 0.2 | SCREENING | Dr. Charles Thompson | Dr. Amanda Davis
2930 | ST-2024-005 | China | S0018 | CHIN-Cancer Center | 4 | 0 | 0 | 0 | CLOSED | Dr. Robert Martin | Dr. Christopher Smith
2931 | ST-2024-005 | China | S0019 | CHIN-Medical Center | 3 | 0 | 0 | 0 | ON_HOLD | Dr. David Jones | Dr. Michelle Thompson
2932 | ST-2024-005 | China | S0020 | CHIN-Clinical Center | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Lisa Anderson | Dr. Emily Johnson
2933 | ST-2024-005 | China | S0021 | CHIN-University Hospital | 3 | 0 | 0 | 0 | CLOSED | Dr. Christopher Williams | Dr. Emily Martin
2934 | ST-2024-005 | China | S0022 | CHIN-Health System | 3 | 0 | 0 | 0 | SCREENING | Dr. Daniel Davis | Dr. Robert Anderson
2935 | ST-2024-006 | United States | S0001 | UNIT-General Hospital | 13 | 8 | 61.5 | 0.4 | SCREENING | Dr. William Miller | Dr. Stephanie Smith
2936 | ST-2024-006 | United States | S0002 | UNIT-Clinical Center | 4 | 9 | 225 | 0.6 | SCREENING | Dr. Jessica Anderson | Dr. Nicole Davis
2937 | ST-2024-006 | United Kingdom | S0003 | UNIT-University Hospital | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. Robert Taylor | Dr. Thomas Thomas
2938 | ST-2024-006 | United Kingdom | S0004 | UNIT-Clinical Center | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Daniel Moore | Dr. Emily Taylor
2939 | ST-2024-006 | United Kingdom | S0005 | UNIT-University Hospital | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. William Harris | Dr. Lisa Jones
2940 | ST-2024-006 | United Kingdom | S0006 | UNIT-Medical Center | 3 | 5 | 166.7 | 0.8 | SCREENING | Dr. Charles White | Dr. Lisa Garcia
2941 | ST-2024-006 | Switzerland | S0007 | SWIT-University Hospital | 13 | 13 | 100 | 0.7 | SCREENING | Dr. Nicole Thompson | Dr. Christopher Martin
2942 | ST-2024-006 | Switzerland | S0008 | SWIT-Research Institute | 14 | 8 | 57.1 | 0.6 | SCREENING | Dr. Michael Jackson | Dr. Daniel Harris
2943 | ST-2024-006 | South Korea | S0009 | SOUT-Cancer Center | 8 | 5 | 62.5 | 0.3 | CLOSED | Dr. Nicole Anderson | Dr. Michelle Smith
2944 | ST-2024-006 | South Korea | S0010 | SOUT-Cancer Center | 3 | 2 | 66.7 | 0.3 | ON_HOLD | Dr. Robert Wilson | Dr. Amanda Jackson
2945 | ST-2024-006 | South Korea | S0011 | SOUT-Research Institute | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Sarah Moore | Dr. David Thomas
2946 | ST-2024-007 | Canada | S0001 | CANA-General Hospital | -1 | -1 | 100 | -0.1 | SCREENING | Dr. James Moore | Dr. Jennifer White
2947 | ST-2024-007 | Canada | S0002 | CANA-General Hospital | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. David Anderson | Dr. Thomas Anderson
2948 | ST-2024-007 | Canada | S0003 | CANA-General Hospital | 3 | 0 | 0 | 0 | SCREENING | Dr. Lisa Moore | Dr. Sarah Garcia
2949 | ST-2024-007 | Canada | S0004 | CANA-Clinical Center | 3 | 0 | 0 | 0 | SCREENING | Dr. Charles Martin | Dr. Jennifer Anderson
2950 | ST-2024-007 | Mexico | S0005 | MEXI-Medical Center | 6 | 0 | 0 | 0 | ON_HOLD | Dr. Christopher Moore | Dr. Daniel Martin
2951 | ST-2024-007 | Mexico | S0006 | MEXI-University Hospital | 3 | 0 | 0 | 0 | ON_HOLD | Dr. William Miller | Dr. Emily Taylor
2952 | ST-2024-007 | Spain | S0007 | SPAI-Cancer Center | -6 | -6 | 100 | -0.4 | ON_HOLD | Dr. Stephanie Thompson | Dr. Thomas Williams
2953 | ST-2024-007 | Spain | S0008 | SPAI-Clinical Center | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Jennifer Jones | Dr. Nicole Taylor
2954 | ST-2024-007 | Spain | S0009 | SPAI-University Hospital | 3 | 3 | 100 | 0.5 | ON_HOLD | Dr. Charles Davis | Dr. Christopher Wilson
2955 | ST-2024-007 | Spain | S0010 | SPAI-Research Institute | 3 | 1 | 33.3 | 0.1 | CLOSED | Dr. James Wilson | Dr. Amanda Davis
2956 | ST-2024-007 | Spain | S0011 | SPAI-Medical Center | 3 | 0 | 0 | 0 | SCREENING | Dr. Christopher Anderson | Dr. Jennifer Jackson
2957 | ST-2024-007 | Italy | S0012 | ITAL-General Hospital | 0 | 0 | 0 | 0 | ON_HOLD | Dr. Lisa Davis | Dr. Robert Martin
2958 | ST-2024-007 | Italy | S0013 | ITAL-University Hospital | 3 | 0 | 0 | 0 | CLOSED | Dr. Amanda White | Dr. Michelle Martin
2959 | ST-2024-007 | Italy | S0014 | ITAL-Cancer Center | 3 | 0 | 0 | 0 | CLOSED | Dr. David Davis | Dr. Michael Thompson
2960 | ST-2024-007 | India | S0015 | INDI-Medical Center | -4 | -4 | 100 | -0.2 | SCREENING | Dr. Nicole Williams | Dr. Daniel Harris
2961 | ST-2024-007 | India | S0016 | INDI-Cancer Center | 3 | 2 | 66.7 | 0.3 | ON_HOLD | Dr. Robert Thompson | Dr. Stephanie Harris
2962 | ST-2024-007 | India | S0017 | INDI-Health System | 3 | 2 | 66.7 | 0.3 | CLOSED | Dr. Christopher Anderson | Dr. James Jackson
2963 | ST-2024-007 | India | S0018 | INDI-Research Institute | 3 | 0 | 0 | 0 | CLOSED | Dr. David Williams | Dr. Sarah White
2964 | ST-2024-007 | India | S0019 | INDI-Research Institute | 3 | 0 | 0 | 0 | SCREENING | Dr. Michelle Johnson | Dr. Michael Martin
2965 | ST-2024-007 | India | S0020 | INDI-Medical Center | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Jones | Dr. Stephanie Thomas
2966 | ST-2024-007 | Singapore | S0021 | SING-Clinical Center | 7 | 0 | 0 | 0 | SCREENING | Dr. Michelle Jones | Dr. Amanda Brown
2967 | ST-2024-007 | Singapore | S0022 | SING-University Hospital | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Daniel Jones | Dr. Lisa Smith
2968 | ST-2024-008 | United States | S0001 | UNIT-General Hospital | 8 | 7 | 87.5 | 0.6 | ENROLLING | Dr. Jessica Garcia | Dr. Lisa Jackson
2969 | ST-2024-008 | United States | S0002 | UNIT-General Hospital | 4 | 4 | 100 | 0.3 | SCREENING | Dr. Charles Jones | Dr. Michael Thompson
2970 | ST-2024-008 | United States | S0003 | UNIT-General Hospital | 7 | 6 | 85.7 | 0.5 | ENROLLING | Dr. Emily White | Dr. Lisa Williams
2971 | ST-2024-008 | Sweden | S0004 | SWED-Clinical Center | 9 | 9 | 100 | 0.5 | ON_HOLD | Dr. James Wilson | Dr. Christopher Martin
2972 | ST-2024-008 | Sweden | S0005 | SWED-University Hospital | 13 | 6 | 46.2 | 0.5 | CLOSED | Dr. Charles White | Dr. Jennifer Jackson
2973 | ST-2024-008 | Taiwan | S0006 | TAIW-Medical Center | -6 | -6 | 100 | -0.6 | ENROLLING | Dr. Amanda Wilson | Dr. Emily Jones
2974 | ST-2024-008 | Taiwan | S0007 | TAIW-Medical Center | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Christopher Moore | Dr. Michelle Thompson
2975 | ST-2024-008 | Taiwan | S0008 | TAIW-Clinical Center | 3 | 3 | 100 | 0.4 | ENROLLING | Dr. Michael Thomas | Dr. Michelle Williams
2976 | ST-2024-008 | Taiwan | S0009 | TAIW-Health System | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Charles Smith | Dr. Jessica White
2977 | ST-2024-008 | Taiwan | S0010 | TAIW-Clinical Center | 3 | 1 | 33.3 | 0.1 | ENROLLING | Dr. Michelle Davis | Dr. Daniel Garcia
2978 | ST-2024-008 | Taiwan | S0011 | TAIW-General Hospital | 3 | 7 | 233.3 | 0.6 | ENROLLING | Dr. Robert Wilson | Dr. Jessica Wilson
2979 | ST-2024-009 | Canada | S0001 | CANA-Health System | 13 | 12 | 92.3 | 1.7 | CLOSED | Dr. Jennifer Thomas | Dr. Thomas Miller
2980 | ST-2024-009 | Canada | S0002 | CANA-Clinical Center | 17 | 0 | 0 | 0 | ON_HOLD | Dr. Nicole Thompson | Dr. Thomas Jackson
2981 | ST-2024-009 | Canada | S0003 | CANA-Health System | 18 | 0 | 0 | 0 | CLOSED | Dr. Emily Thomas | Dr. Amanda Harris
2982 | ST-2024-009 | United States | S0004 | UNIT-Health System | 16 | 0 | 0 | 0 | ON_HOLD | Dr. Robert Jackson | Dr. Stephanie Garcia
2983 | ST-2024-009 | United States | S0005 | UNIT-Clinical Center | 16 | 0 | 0 | 0 | CLOSED | Dr. Jennifer Moore | Dr. Jennifer Martin
2984 | ST-2024-009 | United States | S0006 | UNIT-Research Institute | 14 | 0 | 0 | 0 | SCREENING | Dr. Thomas Harris | Dr. Sarah Thomas
2985 | ST-2024-009 | United States | S0007 | UNIT-Medical Center | 9 | 0 | 0 | 0 | SCREENING | Dr. David Jackson | Dr. Michelle Thompson
2986 | ST-2024-009 | United States | S0008 | UNIT-General Hospital | 13 | 0 | 0 | 0 | ON_HOLD | Dr. Nicole White | Dr. Christopher Martin
2987 | ST-2024-009 | United States | S0009 | UNIT-University Hospital | 7 | 0 | 0 | 0 | CLOSED | Dr. James Davis | Dr. Jessica Johnson
2988 | ST-2024-009 | Sweden | S0010 | SWED-Cancer Center | 8 | 0 | 0 | 0 | ON_HOLD | Dr. Michelle Johnson | Dr. Christopher Moore
2989 | ST-2024-009 | Sweden | S0011 | SWED-University Hospital | 7 | 0 | 0 | 0 | SCREENING | Dr. Lisa Anderson | Dr. Sarah Harris
2990 | ST-2024-009 | Sweden | S0012 | SWED-Research Institute | 4 | 0 | 0 | 0 | SCREENING | Dr. Christopher Brown | Dr. Lisa Miller
2991 | ST-2024-009 | Sweden | S0013 | SWED-Cancer Center | 7 | 0 | 0 | 0 | CLOSED | Dr. Amanda White | Dr. Jennifer Jones
2992 | ST-2024-009 | Sweden | S0014 | SWED-Cancer Center | 9 | 0 | 0 | 0 | SCREENING | Dr. Sarah Thomas | Dr. Michelle Wilson
2993 | ST-2024-009 | Norway | S0015 | NORW-University Hospital | 18 | 0 | 0 | 0 | ON_HOLD | Dr. Sarah Wilson | Dr. Robert Jones
2994 | ST-2024-009 | Norway | S0016 | NORW-University Hospital | 10 | 0 | 0 | 0 | CLOSED | Dr. Thomas Davis | Dr. Charles Martin
2995 | ST-2024-009 | Norway | S0017 | NORW-University Hospital | 22 | 0 | 0 | 0 | CLOSED | Dr. William White | Dr. Charles Harris
2996 | ST-2024-009 | Norway | S0018 | NORW-Medical Center | 11 | 0 | 0 | 0 | SCREENING | Dr. Charles Thompson | Dr. William Thomas
2997 | ST-2024-009 | Norway | S0019 | NORW-Clinical Center | 16 | 0 | 0 | 0 | ON_HOLD | Dr. James Williams | Dr. Christopher Thomas
2998 | ST-2024-009 | Singapore | S0020 | SING-University Hospital | 15 | 0 | 0 | 0 | ON_HOLD | Dr. Thomas Johnson | Dr. Sarah Brown
2999 | ST-2024-009 | Singapore | S0021 | SING-General Hospital | 13 | 0 | 0 | 0 | ON_HOLD | Dr. James Brown | Dr. Jennifer Harris
3000 | ST-2024-009 | Singapore | S0022 | SING-Clinical Center | 9 | 0 | 0 | 0 | ON_HOLD | Dr. David Jones | Dr. Jessica Garcia
3001 | ST-2024-009 | Singapore | S0023 | SING-Cancer Center | 15 | 0 | 0 | 0 | SCREENING | Dr. Amanda Wilson | Dr. Michael Thomas
3002 | ST-2024-009 | Singapore | S0024 | SING-General Hospital | 13 | 0 | 0 | 0 | SCREENING | Dr. Sarah Jackson | Dr. Jessica Davis
3003 | ST-2024-010 | Mexico | S0001 | MEXI-University Hospital | 283 | 269 | 95.1 | 20.7 | SCREENING | Dr. Thomas White | Dr. Emily Moore
3004 | ST-2024-010 | Mexico | S0002 | MEXI-Research Institute | 344 | 238 | 69.2 | 13.2 | ENROLLING | Dr. Christopher Anderson | Dr. Christopher Wilson
3005 | ST-2024-010 | Mexico | S0003 | MEXI-Cancer Center | 627 | 655 | 104.5 | 93.6 | ENROLLING | Dr. Jennifer Anderson | Dr. Sarah Miller
3006 | ST-2024-010 | United Kingdom | S0004 | UNIT-Research Institute | 997 | 811 | 81.3 | 101.4 | SCREENING | Dr. Charles Harris | Dr. Michelle Moore
3007 | ST-2024-010 | United Kingdom | S0005 | UNIT-University Hospital | 616 | 507 | 82.3 | 72.4 | ON_HOLD | Dr. Emily Jones | Dr. Emily Smith
3008 | ST-2024-010 | United Kingdom | S0006 | UNIT-Medical Center | 440 | 0 | 0 | 0 | SCREENING | Dr. Robert Miller | Dr. Charles Thomas
3009 | ST-2024-010 | United Kingdom | S0007 | UNIT-General Hospital | 557 | 0 | 0 | 0 | CLOSED | Dr. Michael Wilson | Dr. Michael Smith
3010 | ST-2024-010 | Australia | S0008 | AUST-Medical Center | 368 | 0 | 0 | 0 | ON_HOLD | Dr. Sarah Garcia | Dr. Stephanie Jackson
3011 | ST-2024-010 | Australia | S0009 | AUST-Clinical Center | 170 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Garcia | Dr. Amanda Miller
3012 | ST-2024-010 | Australia | S0010 | AUST-University Hospital | 279 | 0 | 0 | 0 | ON_HOLD | Dr. Christopher Jones | Dr. Sarah Davis
3013 | ST-2024-010 | Australia | S0011 | AUST-General Hospital | 319 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Moore | Dr. Nicole Johnson
3014 | ST-2024-011 | United States | S0001 | UNIT-Clinical Center | 7 | 4 | 57.1 | 0.4 | CLOSED | Dr. Charles Brown | Dr. Nicole Davis
3015 | ST-2024-011 | United States | S0002 | UNIT-University Hospital | 10 | 1 | 10 | 0.1 | SCREENING | Dr. Sarah Anderson | Dr. James Taylor
3016 | ST-2024-011 | United States | S0003 | UNIT-Research Institute | 10 | 0 | 0 | 0 | SCREENING | Dr. Thomas Garcia | Dr. Charles Garcia
3017 | ST-2024-011 | France | S0004 | FRAN-University Hospital | 11 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Johnson | Dr. Emily Taylor
3018 | ST-2024-011 | France | S0005 | FRAN-University Hospital | 7 | 0 | 0 | 0 | ON_HOLD | Dr. Michelle Moore | Dr. William Anderson
3019 | ST-2024-011 | France | S0006 | FRAN-Research Institute | 9 | 0 | 0 | 0 | SCREENING | Dr. Sarah Jackson | Dr. Michelle Martin
3020 | ST-2024-011 | France | S0007 | FRAN-University Hospital | 4 | 0 | 0 | 0 | ON_HOLD | Dr. James White | Dr. Michael Anderson
3021 | ST-2024-011 | France | S0008 | FRAN-Cancer Center | 7 | 0 | 0 | 0 | CLOSED | Dr. Nicole Miller | Dr. Emily Smith
3022 | ST-2024-011 | Singapore | S0009 | SING-Cancer Center | 12 | 0 | 0 | 0 | ON_HOLD | Dr. Nicole Wilson | Dr. Michael Moore
3023 | ST-2024-011 | Singapore | S0010 | SING-Clinical Center | 17 | 0 | 0 | 0 | ON_HOLD | Dr. Charles Thomas | Dr. Jennifer Harris
3024 | ST-2024-011 | Singapore | S0011 | SING-Medical Center | 23 | 0 | 0 | 0 | ON_HOLD | Dr. Christopher Wilson | Dr. Lisa Wilson
3025 | ST-2024-011 | Mexico | S0012 | MEXI-Cancer Center | 9 | 0 | 0 | 0 | SCREENING | Dr. Michelle Johnson | Dr. Charles Thompson
3026 | ST-2024-011 | Mexico | S0013 | MEXI-Clinical Center | 4 | 0 | 0 | 0 | CLOSED | Dr. Nicole Davis | Dr. Nicole Anderson
3027 | ST-2024-011 | Mexico | S0014 | MEXI-Medical Center | 7 | 0 | 0 | 0 | CLOSED | Dr. Sarah Thompson | Dr. Daniel Jones
3028 | ST-2024-011 | Mexico | S0015 | MEXI-Medical Center | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Garcia | Dr. David Miller
3029 | ST-2024-012 | Mexico | S0001 | MEXI-Cancer Center | -12 | -12 | 100 | -0.9 | CLOSED | Dr. Amanda Thompson | Dr. Jessica Garcia
3030 | ST-2024-012 | Mexico | S0002 | MEXI-Cancer Center | 3 | 2 | 66.7 | 0.1 | CLOSED | Dr. Jennifer Anderson | Dr. Emily Martin
3031 | ST-2024-012 | Mexico | S0003 | MEXI-University Hospital | 3 | 3 | 100 | 0.2 | ON_HOLD | Dr. Michelle Garcia | Dr. Thomas Williams
3032 | ST-2024-012 | Mexico | S0004 | MEXI-University Hospital | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Jessica White | Dr. Thomas Thomas
3033 | ST-2024-012 | Mexico | S0005 | MEXI-Research Institute | 3 | 2 | 66.7 | 0.1 | ON_HOLD | Dr. Christopher Brown | Dr. Nicole Johnson
3034 | ST-2024-012 | Mexico | S0006 | MEXI-Cancer Center | 3 | 5 | 166.7 | 0.3 | CLOSED | Dr. Michael Martin | Dr. David Thompson
3035 | ST-2024-012 | Canada | S0007 | CANA-Clinical Center | -7 | -7 | 100 | -0.9 | SCREENING | Dr. Jennifer Williams | Dr. Nicole Taylor
3036 | ST-2024-012 | Canada | S0008 | CANA-General Hospital | 3 | 3 | 100 | 0.4 | SCREENING | Dr. Sarah Smith | Dr. Christopher Wilson
3037 | ST-2024-012 | Canada | S0009 | CANA-University Hospital | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Jennifer Martin | Dr. Michael Jones
3038 | ST-2024-012 | Canada | S0010 | CANA-Health System | 3 | 3 | 100 | 0.2 | ON_HOLD | Dr. Stephanie Jackson | Dr. Stephanie Martin
3039 | ST-2024-012 | Canada | S0011 | CANA-Clinical Center | 3 | 3 | 100 | 0.5 | ENROLLING | Dr. Michelle Miller | Dr. Amanda Smith
3040 | ST-2024-012 | Belgium | S0012 | BELG-Research Institute | -3 | -3 | 100 | -0.3 | ENROLLING | Dr. Emily Jackson | Dr. Daniel Anderson
3041 | ST-2024-012 | Belgium | S0013 | BELG-University Hospital | 3 | 3 | 100 | 0.4 | ENROLLING | Dr. Jessica Anderson | Dr. Christopher Thompson
3042 | ST-2024-012 | Belgium | S0014 | BELG-Health System | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Stephanie Jones | Dr. Thomas Martin
3043 | ST-2024-012 | Belgium | S0015 | BELG-Research Institute | 3 | 4 | 133.3 | 0.2 | ENROLLING | Dr. Jennifer Jackson | Dr. James Davis
3044 | ST-2024-012 | Norway | S0016 | NORW-Medical Center | 0 | 0 | 0 | 0 | CLOSED | Dr. Sarah Jackson | Dr. William Moore
3045 | ST-2024-012 | Norway | S0017 | NORW-Health System | 3 | 2 | 66.7 | 0.3 | CLOSED | Dr. Sarah Brown | Dr. James Johnson
3046 | ST-2024-012 | Norway | S0018 | NORW-General Hospital | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. Christopher Jackson | Dr. Emily Moore
3047 | ST-2024-012 | Singapore | S0019 | SING-General Hospital | 2 | 0 | 0 | 0 | SCREENING | Dr. Jessica White | Dr. Emily Thompson
3048 | ST-2024-012 | Singapore | S0020 | SING-Research Institute | 3 | 0 | 0 | 0 | CLOSED | Dr. Robert White | Dr. Emily Thompson
3049 | ST-2024-012 | Chile | S0021 | CHIL-University Hospital | -1 | -1 | 100 | -0.1 | ON_HOLD | Dr. Daniel Miller | Dr. Amanda White
3050 | ST-2024-012 | Chile | S0022 | CHIL-Research Institute | 3 | 1 | 33.3 | 0.1 | SCREENING | Dr. Michelle Martin | Dr. David Martin
3051 | ST-2024-012 | Chile | S0023 | CHIL-Research Institute | 3 | 0 | 0 | 0 | SCREENING | Dr. James Williams | Dr. Emily Martin
3052 | ST-2024-013 | Mexico | S0001 | MEXI-Cancer Center | -12 | -12 | 100 | -0.7 | SCREENING | Dr. Thomas Moore | Dr. David Miller
3053 | ST-2024-013 | Mexico | S0002 | MEXI-University Hospital | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Jessica Thomas | Dr. Robert Garcia
3054 | ST-2024-013 | Mexico | S0003 | MEXI-Health System | 3 | 4 | 133.3 | 0.3 | SCREENING | Dr. Thomas Brown | Dr. Amanda Moore
3055 | ST-2024-013 | Poland | S0004 | POLA-Clinical Center | 2 | 2 | 100 | 0.1 | SCREENING | Dr. Michelle Anderson | Dr. Stephanie Smith
3056 | ST-2024-013 | Poland | S0005 | POLA-Health System | 3 | 3 | 100 | 0.4 | ENROLLING | Dr. Charles Jones | Dr. Sarah Johnson
3057 | ST-2024-013 | South Korea | S0006 | SOUT-Medical Center | -7 | -7 | 100 | -0.6 | ON_HOLD | Dr. Emily Moore | Dr. Lisa Moore
3058 | ST-2024-013 | South Korea | S0007 | SOUT-Clinical Center | 3 | 3 | 100 | 0.3 | CLOSED | Dr. Jessica Johnson | Dr. Charles Jackson
3059 | ST-2024-013 | South Korea | S0008 | SOUT-Clinical Center | 3 | 2 | 66.7 | 0.1 | CLOSED | Dr. Thomas Moore | Dr. Sarah Smith
3060 | ST-2024-013 | South Korea | S0009 | SOUT-General Hospital | 3 | 3 | 100 | 0.3 | SCREENING | Dr. Christopher Davis | Dr. Amanda Moore
3061 | ST-2024-013 | South Korea | S0010 | SOUT-General Hospital | 3 | 0 | 0 | 0 | SCREENING | Dr. David Anderson | Dr. Christopher Garcia
3062 | ST-2024-013 | Chile | S0011 | CHIL-Cancer Center | -7 | -7 | 100 | -0.7 | SCREENING | Dr. Thomas Harris | Dr. Robert Johnson
3063 | ST-2024-013 | Chile | S0012 | CHIL-University Hospital | 3 | 2 | 66.7 | 0.2 | CLOSED | Dr. Sarah Anderson | Dr. Nicole Moore
3064 | ST-2024-013 | Chile | S0013 | CHIL-Research Institute | 3 | 2 | 66.7 | 0.3 | CLOSED | Dr. Thomas Thompson | Dr. Lisa Garcia
3065 | ST-2024-013 | Chile | S0014 | CHIL-Health System | 3 | 2 | 66.7 | 0.3 | CLOSED | Dr. Jennifer White | Dr. Michelle Moore
3066 | ST-2024-013 | Chile | S0015 | CHIL-Clinical Center | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. Lisa Miller | Dr. Thomas Taylor
3067 | ST-2024-014 | Mexico | S0001 | MEXI-Health System | -14 | -14 | 100 | -1.8 | ENROLLING | Dr. Jennifer Garcia | Dr. Robert Martin
3068 | ST-2024-014 | Mexico | S0002 | MEXI-Research Institute | 3 | 2 | 66.7 | 0.3 | ENROLLING | Dr. Nicole Davis | Dr. Michael Wilson
3069 | ST-2024-014 | Mexico | S0003 | MEXI-Research Institute | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. David Thompson | Dr. Amanda Jackson
3070 | ST-2024-014 | Mexico | S0004 | MEXI-Clinical Center | 3 | 5 | 166.7 | 0.4 | ENROLLING | Dr. Sarah Taylor | Dr. Emily Thompson
3071 | ST-2024-014 | Canada | S0005 | CANA-Health System | -4 | -4 | 100 | -0.2 | ENROLLING | Dr. Daniel Wilson | Dr. Charles Davis
3072 | ST-2024-014 | Canada | S0006 | CANA-Health System | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Amanda Martin | Dr. Nicole Smith
3073 | ST-2024-014 | Canada | S0007 | CANA-Health System | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Jennifer Davis | Dr. Michael Thompson
3074 | ST-2024-014 | Canada | S0008 | CANA-General Hospital | 3 | 4 | 133.3 | 0.4 | ENROLLING | Dr. Robert Garcia | Dr. Jennifer Thomas
3075 | ST-2024-014 | United States | S0009 | UNIT-Clinical Center | 2 | 1 | 50 | 0.1 | SCREENING | Dr. Emily Martin | Dr. Nicole Martin
3076 | ST-2024-014 | United States | S0010 | UNIT-University Hospital | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. Stephanie Smith | Dr. Lisa Johnson
3077 | ST-2024-014 | Poland | S0011 | POLA-General Hospital | -10 | -10 | 100 | -1.7 | ON_HOLD | Dr. Jessica Williams | Dr. David Harris
3078 | ST-2024-014 | Poland | S0012 | POLA-Health System | 3 | 3 | 100 | 0.2 | SCREENING | Dr. Jennifer Davis | Dr. Stephanie Jones
3079 | ST-2024-014 | Poland | S0013 | POLA-Cancer Center | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Daniel Wilson | Dr. Jennifer Taylor
3080 | ST-2024-014 | Poland | S0014 | POLA-Clinical Center | 3 | 2 | 66.7 | 0.1 | ON_HOLD | Dr. Michael Davis | Dr. Charles Jackson
3081 | ST-2024-014 | Poland | S0015 | POLA-University Hospital | 3 | 3 | 100 | 0.4 | ENROLLING | Dr. David Thompson | Dr. Daniel White
3082 | ST-2024-014 | Poland | S0016 | POLA-Cancer Center | 3 | 4 | 133.3 | 0.5 | ON_HOLD | Dr. Emily Garcia | Dr. Nicole Johnson
3083 | ST-2024-014 | Norway | S0017 | NORW-Medical Center | -4 | -4 | 100 | -0.2 | CLOSED | Dr. Stephanie Thompson | Dr. Stephanie Thomas
3084 | ST-2024-014 | Norway | S0018 | NORW-Cancer Center | 3 | 3 | 100 | 0.5 | CLOSED | Dr. Daniel White | Dr. Lisa Martin
3085 | ST-2024-014 | Norway | S0019 | NORW-Cancer Center | 3 | 2 | 66.7 | 0.1 | ON_HOLD | Dr. Amanda Brown | Dr. Stephanie Jones
3086 | ST-2024-014 | Norway | S0020 | NORW-Research Institute | 3 | 0 | 0 | 0 | SCREENING | Dr. Michael Anderson | Dr. Michelle White
3087 | ST-2024-014 | Netherlands | S0021 | NETH-Health System | -1 | -1 | 100 | -0.2 | ON_HOLD | Dr. David Taylor | Dr. Stephanie Thomas
3088 | ST-2024-014 | Netherlands | S0022 | NETH-Medical Center | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. William Wilson | Dr. Michelle White
3089 | ST-2024-014 | Netherlands | S0023 | NETH-Health System | 3 | 0 | 0 | 0 | CLOSED | Dr. William Jackson | Dr. David White
3090 | ST-2024-014 | Denmark | S0024 | DENM-Medical Center | -10 | -10 | 100 | -0.6 | SCREENING | Dr. Christopher Garcia | Dr. Emily Miller
3091 | ST-2024-014 | Denmark | S0025 | DENM-Health System | 3 | 3 | 100 | 0.2 | ON_HOLD | Dr. Michelle Johnson | Dr. Jennifer Jackson
3092 | ST-2024-014 | Denmark | S0026 | DENM-General Hospital | 3 | 2 | 66.7 | 0.3 | SCREENING | Dr. Robert Martin | Dr. Stephanie Williams
3093 | ST-2024-014 | Denmark | S0027 | DENM-Medical Center | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Amanda Williams | Dr. Sarah Jackson
3094 | ST-2024-014 | Denmark | S0028 | DENM-Clinical Center | 3 | 3 | 100 | 0.2 | CLOSED | Dr. Daniel Anderson | Dr. Sarah Garcia
3095 | ST-2024-014 | Denmark | S0029 | DENM-General Hospital | 3 | 0 | 0 | 0 | ON_HOLD | Dr. James Miller | Dr. Daniel Anderson
3096 | ST-2024-014 | Taiwan | S0030 | TAIW-Medical Center | -7 | -7 | 100 | -0.7 | ON_HOLD | Dr. Amanda Jackson | Dr. Charles Miller
3097 | ST-2024-014 | Taiwan | S0031 | TAIW-Health System | 3 | 2 | 66.7 | 0.3 | CLOSED | Dr. Michael Williams | Dr. Michelle Anderson
3098 | ST-2024-014 | Taiwan | S0032 | TAIW-General Hospital | 3 | 2 | 66.7 | 0.1 | CLOSED | Dr. Amanda Thomas | Dr. William Davis
3099 | ST-2024-014 | Taiwan | S0033 | TAIW-Health System | 3 | 3 | 100 | 0.3 | ON_HOLD | Dr. Charles Smith | Dr. William Garcia
3100 | ST-2024-014 | Taiwan | S0034 | TAIW-Clinical Center | 3 | 0 | 0 | 0 | SCREENING | Dr. Michelle Williams | Dr. Daniel Anderson
3101 | ST-2024-015 | Canada | S0001 | CANA-Health System | 7 | 7 | 100 | 0.6 | ON_HOLD | Dr. Lisa Garcia | Dr. Charles Jackson
3102 | ST-2024-015 | Canada | S0002 | CANA-University Hospital | 7 | 5 | 71.4 | 0.5 | SCREENING | Dr. Stephanie Davis | Dr. Daniel Wilson
3103 | ST-2024-015 | Canada | S0003 | CANA-Research Institute | 7 | 0 | 0 | 0 | CLOSED | Dr. Michelle Wilson | Dr. Stephanie Miller
3104 | ST-2024-015 | Canada | S0004 | CANA-Cancer Center | 6 | 0 | 0 | 0 | SCREENING | Dr. Robert Anderson | Dr. Emily Harris
3105 | ST-2024-015 | Mexico | S0005 | MEXI-University Hospital | 8 | 0 | 0 | 0 | SCREENING | Dr. Robert Johnson | Dr. Michelle Smith
3106 | ST-2024-015 | Mexico | S0006 | MEXI-University Hospital | 5 | 0 | 0 | 0 | ON_HOLD | Dr. William Jones | Dr. Christopher Smith
3107 | ST-2024-015 | Sweden | S0007 | SWED-Research Institute | 7 | 0 | 0 | 0 | SCREENING | Dr. Sarah Wilson | Dr. Charles Williams
3108 | ST-2024-015 | Sweden | S0008 | SWED-Health System | 5 | 0 | 0 | 0 | SCREENING | Dr. David Wilson | Dr. Charles Smith
3109 | ST-2024-015 | Sweden | S0009 | SWED-Medical Center | 7 | 0 | 0 | 0 | CLOSED | Dr. Lisa Jackson | Dr. Christopher Davis
3110 | ST-2024-015 | Sweden | S0010 | SWED-General Hospital | 6 | 0 | 0 | 0 | SCREENING | Dr. Christopher Brown | Dr. Daniel Miller
3111 | ST-2024-015 | Sweden | S0011 | SWED-Clinical Center | 6 | 0 | 0 | 0 | CLOSED | Dr. Jessica Taylor | Dr. Jennifer Johnson
3112 | ST-2024-015 | Norway | S0012 | NORW-Clinical Center | 12 | 0 | 0 | 0 | ON_HOLD | Dr. David Thomas | Dr. Sarah Miller
3113 | ST-2024-015 | Norway | S0013 | NORW-Medical Center | 10 | 0 | 0 | 0 | CLOSED | Dr. Stephanie Taylor | Dr. James Garcia
3114 | ST-2024-015 | Switzerland | S0014 | SWIT-General Hospital | 8 | 0 | 0 | 0 | SCREENING | Dr. Amanda Williams | Dr. Lisa Garcia
3115 | ST-2024-015 | Switzerland | S0015 | SWIT-Clinical Center | 6 | 0 | 0 | 0 | CLOSED | Dr. Thomas Johnson | Dr. Sarah Thomas
3116 | ST-2024-015 | Switzerland | S0016 | SWIT-General Hospital | 5 | 0 | 0 | 0 | CLOSED | Dr. Michelle Brown | Dr. Robert Martin
3117 | ST-2024-015 | Switzerland | S0017 | SWIT-University Hospital | 4 | 0 | 0 | 0 | CLOSED | Dr. Amanda Harris | Dr. David Smith
3118 | ST-2024-015 | India | S0018 | INDI-Medical Center | 12 | 0 | 0 | 0 | CLOSED | Dr. Christopher Moore | Dr. Jessica Moore
3119 | ST-2024-015 | India | S0019 | INDI-General Hospital | 8 | 0 | 0 | 0 | SCREENING | Dr. Jennifer Moore | Dr. Amanda Taylor
3120 | ST-2024-016 | United States | S0001 | UNIT-Cancer Center | 5 | 3 | 60 | 0.4 | ON_HOLD | Dr. Michelle Miller | Dr. Nicole Jackson
3121 | ST-2024-016 | United States | S0002 | UNIT-General Hospital | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Michelle Thompson | Dr. Lisa Davis
3122 | ST-2024-016 | United States | S0003 | UNIT-Medical Center | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. Thomas Williams | Dr. Emily White
3123 | ST-2024-016 | United States | S0004 | UNIT-Clinical Center | 4 | 4 | 100 | 0.4 | ON_HOLD | Dr. David Taylor | Dr. Amanda Smith
3124 | ST-2024-016 | United States | S0005 | UNIT-Cancer Center | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Amanda Harris | Dr. Robert Harris
3125 | ST-2024-016 | Canada | S0006 | CANA-Research Institute | 5 | 3 | 60 | 0.4 | SCREENING | Dr. Michael Brown | Dr. Sarah Davis
3126 | ST-2024-016 | Canada | S0007 | CANA-Health System | 12 | 14 | 116.7 | 1.8 | ENROLLING | Dr. James Taylor | Dr. Emily Anderson
3127 | ST-2024-016 | Germany | S0008 | GERM-Clinical Center | 1 | 0 | 0 | 0 | ON_HOLD | Dr. Robert Smith | Dr. Charles Thompson
3128 | ST-2024-016 | Germany | S0009 | GERM-Medical Center | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Sarah Anderson | Dr. David Wilson
3129 | ST-2024-016 | Germany | S0010 | GERM-Medical Center | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. James Williams | Dr. Charles Wilson
3130 | ST-2024-016 | Germany | S0011 | GERM-General Hospital | 3 | 5 | 166.7 | 0.3 | SCREENING | Dr. Emily Smith | Dr. Jessica Jackson
3131 | ST-2024-016 | Poland | S0012 | POLA-Medical Center | 8 | 6 | 75 | 0.5 | ON_HOLD | Dr. Michelle Williams | Dr. Jennifer Miller
3132 | ST-2024-016 | Poland | S0013 | POLA-Health System | 9 | 0 | 0 | 0 | CLOSED | Dr. James Johnson | Dr. Lisa Thompson
3133 | ST-2024-016 | Belgium | S0014 | BELG-Research Institute | -4 | -4 | 100 | -0.3 | SCREENING | Dr. Michelle Wilson | Dr. Lisa Jones
3134 | ST-2024-016 | Belgium | S0015 | BELG-Research Institute | 3 | 3 | 100 | 0.2 | CLOSED | Dr. Robert Williams | Dr. Charles Thompson
3135 | ST-2024-016 | Belgium | S0016 | BELG-General Hospital | 3 | 1 | 33.3 | 0.1 | CLOSED | Dr. Lisa White | Dr. Lisa Jones
3136 | ST-2024-016 | Belgium | S0017 | BELG-Clinical Center | 3 | 0 | 0 | 0 | CLOSED | Dr. Thomas Harris | Dr. Michelle Jones
3137 | ST-2024-016 | Belgium | S0018 | BELG-University Hospital | 3 | 0 | 0 | 0 | SCREENING | Dr. Michelle Miller | Dr. Robert Anderson
3138 | ST-2024-016 | Belgium | S0019 | BELG-General Hospital | 3 | 0 | 0 | 0 | CLOSED | Dr. Robert White | Dr. Robert Garcia
3139 | ST-2024-016 | Australia | S0020 | AUST-University Hospital | 5 | 0 | 0 | 0 | SCREENING | Dr. Thomas White | Dr. Stephanie Anderson
3140 | ST-2024-016 | Australia | S0021 | AUST-Clinical Center | 5 | 0 | 0 | 0 | CLOSED | Dr. William Jones | Dr. David Brown
3141 | ST-2024-016 | Australia | S0022 | AUST-University Hospital | 7 | 0 | 0 | 0 | SCREENING | Dr. William Davis | Dr. Lisa Davis
3142 | ST-2024-017 | Mexico | S0001 | MEXI-Medical Center | 5 | 5 | 100 | 0.8 | ON_HOLD | Dr. Emily Miller | Dr. Stephanie White
3143 | ST-2024-017 | Mexico | S0002 | MEXI-Medical Center | 4 | 2 | 50 | 0.2 | ON_HOLD | Dr. Michelle Miller | Dr. James Miller
3144 | ST-2024-017 | Mexico | S0003 | MEXI-General Hospital | 5 | 1 | 20 | 0.1 | ON_HOLD | Dr. Michael Anderson | Dr. Jessica Thompson
3145 | ST-2024-017 | Mexico | S0004 | MEXI-Health System | 4 | 0 | 0 | 0 | SCREENING | Dr. Emily Taylor | Dr. Thomas Jackson
3146 | ST-2024-017 | Mexico | S0005 | MEXI-General Hospital | 5 | 0 | 0 | 0 | CLOSED | Dr. James Garcia | Dr. David Taylor
3147 | ST-2024-017 | Spain | S0006 | SPAI-Cancer Center | -3 | -3 | 100 | -0.2 | CLOSED | Dr. Sarah Thompson | Dr. Jessica Taylor
3148 | ST-2024-017 | Spain | S0007 | SPAI-Health System | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. David Taylor | Dr. Amanda Williams
3149 | ST-2024-017 | Spain | S0008 | SPAI-University Hospital | 3 | 1 | 33.3 | 0.1 | SCREENING | Dr. Thomas Jackson | Dr. Michelle Garcia
3150 | ST-2024-017 | Spain | S0009 | SPAI-Health System | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Brown | Dr. Jessica Taylor
3151 | ST-2024-017 | Spain | S0010 | SPAI-General Hospital | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Williams | Dr. Nicole Davis
3152 | ST-2024-017 | Spain | S0011 | SPAI-Research Institute | 3 | 0 | 0 | 0 | ON_HOLD | Dr. David Thompson | Dr. Jessica Garcia
3153 | ST-2024-017 | China | S0012 | CHIN-Health System | 4 | 0 | 0 | 0 | ON_HOLD | Dr. Robert Brown | Dr. Daniel Jones
3154 | ST-2024-017 | China | S0013 | CHIN-University Hospital | 5 | 0 | 0 | 0 | SCREENING | Dr. Christopher Jackson | Dr. Daniel Brown
3155 | ST-2024-017 | China | S0014 | CHIN-Medical Center | 5 | 0 | 0 | 0 | SCREENING | Dr. Michael Taylor | Dr. Christopher Johnson
3156 | ST-2024-017 | China | S0015 | CHIN-Medical Center | 5 | 0 | 0 | 0 | CLOSED | Dr. Jessica Smith | Dr. Jessica Miller
3157 | ST-2024-017 | China | S0016 | CHIN-Research Institute | 3 | 0 | 0 | 0 | SCREENING | Dr. Jessica Wilson | Dr. Michelle Taylor
3158 | ST-2024-017 | China | S0017 | CHIN-Cancer Center | 3 | 0 | 0 | 0 | CLOSED | Dr. Emily Wilson | Dr. Robert Garcia
3159 | ST-2024-018 | United States | S0001 | UNIT-Health System | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Jennifer Harris | Dr. Daniel White
3160 | ST-2024-018 | United States | S0002 | UNIT-Health System | 4 | 4 | 100 | 0.3 | ENROLLING | Dr. Amanda Davis | Dr. Jennifer White
3161 | ST-2024-018 | United States | S0003 | UNIT-Health System | 3 | 4 | 133.3 | 0.7 | SCREENING | Dr. Nicole Davis | Dr. Daniel Wilson
3162 | ST-2024-018 | Denmark | S0004 | DENM-Medical Center | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Amanda Brown | Dr. Nicole Williams
3163 | ST-2024-018 | Denmark | S0005 | DENM-University Hospital | 3 | 4 | 133.3 | 0.2 | SCREENING | Dr. Daniel Wilson | Dr. Christopher Thompson
3164 | ST-2024-018 | South Korea | S0006 | SOUT-Research Institute | -4 | -4 | 100 | -0.3 | ENROLLING | Dr. Thomas Moore | Dr. James Martin
3165 | ST-2024-018 | South Korea | S0007 | SOUT-Clinical Center | 3 | 1 | 33.3 | 0.1 | ENROLLING | Dr. Thomas White | Dr. Amanda Anderson
3166 | ST-2024-018 | South Korea | S0008 | SOUT-Research Institute | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Jessica Wilson | Dr. Sarah Martin
3167 | ST-2024-018 | South Korea | S0009 | SOUT-Health System | 3 | 3 | 100 | 0.4 | SCREENING | Dr. Sarah Anderson | Dr. James Anderson
3168 | ST-2024-018 | South Korea | S0010 | SOUT-Clinical Center | 3 | 6 | 200 | 0.9 | ENROLLING | Dr. Daniel Williams | Dr. William Wilson
3169 | ST-2024-019 | Mexico | S0001 | MEXI-University Hospital | 25 | 0 | 0 | 0 | ON_HOLD | Dr. David Brown | Dr. Christopher Wilson
3170 | ST-2024-019 | Mexico | S0002 | MEXI-Medical Center | 14 | 0 | 0 | 0 | SCREENING | Dr. Michael Wilson | Dr. Christopher Smith
3171 | ST-2024-019 | United States | S0003 | UNIT-Health System | 19 | 0 | 0 | 0 | ON_HOLD | Dr. Nicole White | Dr. Charles Williams
3172 | ST-2024-019 | United States | S0004 | UNIT-Health System | 7 | 0 | 0 | 0 | SCREENING | Dr. Charles Martin | Dr. Emily Moore
3173 | ST-2024-019 | United States | S0005 | UNIT-Research Institute | 13 | 0 | 0 | 0 | CLOSED | Dr. Jessica Jackson | Dr. Sarah Williams
3174 | ST-2024-019 | United States | S0006 | UNIT-Research Institute | 17 | 0 | 0 | 0 | ON_HOLD | Dr. Michael Harris | Dr. Jessica Miller
3175 | ST-2024-019 | United States | S0007 | UNIT-University Hospital | 13 | 0 | 0 | 0 | SCREENING | Dr. Charles Miller | Dr. Jessica Jackson
3176 | ST-2024-019 | Poland | S0008 | POLA-General Hospital | 24 | 0 | 0 | 0 | SCREENING | Dr. Sarah Miller | Dr. James Davis
3177 | ST-2024-019 | Poland | S0009 | POLA-Clinical Center | 18 | 0 | 0 | 0 | SCREENING | Dr. Michelle Anderson | Dr. Nicole Moore
3178 | ST-2024-019 | Poland | S0010 | POLA-Cancer Center | 13 | 0 | 0 | 0 | ON_HOLD | Dr. James Johnson | Dr. Thomas Johnson
3179 | ST-2024-019 | Denmark | S0011 | DENM-University Hospital | 33 | 0 | 0 | 0 | CLOSED | Dr. Daniel Harris | Dr. Michelle Jones
3180 | ST-2024-019 | Denmark | S0012 | DENM-General Hospital | 46 | 0 | 0 | 0 | SCREENING | Dr. Michael Johnson | Dr. Robert Martin
3181 | ST-2024-019 | United Kingdom | S0013 | UNIT-Medical Center | 40 | 0 | 0 | 0 | CLOSED | Dr. Robert Smith | Dr. Jennifer Johnson
3182 | ST-2024-019 | United Kingdom | S0014 | UNIT-Research Institute | 32 | 0 | 0 | 0 | SCREENING | Dr. Christopher Garcia | Dr. Michael Brown
3183 | ST-2024-019 | Australia | S0015 | AUST-Medical Center | 14 | 0 | 0 | 0 | CLOSED | Dr. Michelle Jones | Dr. Thomas Miller
3184 | ST-2024-019 | Australia | S0016 | AUST-Cancer Center | 21 | 0 | 0 | 0 | CLOSED | Dr. Jennifer Taylor | Dr. Michael Brown
3185 | ST-2024-019 | Australia | S0017 | AUST-Research Institute | 22 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Thomas | Dr. Michelle Garcia
3186 | ST-2024-019 | Australia | S0018 | AUST-Clinical Center | 11 | 0 | 0 | 0 | CLOSED | Dr. Sarah Jones | Dr. Emily Jackson
3187 | ST-2024-019 | Australia | S0019 | AUST-Cancer Center | 14 | 0 | 0 | 0 | SCREENING | Dr. Nicole Williams | Dr. James Smith
3188 | ST-2024-020 | Canada | S0001 | CANA-Cancer Center | -9 | -9 | 100 | -0.6 | CLOSED | Dr. David Davis | Dr. Thomas Thomas
3189 | ST-2024-020 | Canada | S0002 | CANA-Research Institute | 3 | 2 | 66.7 | 0.1 | CLOSED | Dr. Stephanie Wilson | Dr. Sarah Williams
3190 | ST-2024-020 | Canada | S0003 | CANA-Research Institute | 3 | 3 | 100 | 0.3 | ON_HOLD | Dr. Nicole Thompson | Dr. Daniel Brown
3191 | ST-2024-020 | Canada | S0004 | CANA-Clinical Center | 3 | 4 | 133.3 | 0.2 | CLOSED | Dr. Michelle Anderson | Dr. Christopher Thomas
3192 | ST-2024-020 | Norway | S0005 | NORW-Medical Center | -4 | -4 | 100 | -0.3 | ENROLLING | Dr. Jessica Williams | Dr. Emily Garcia
3193 | ST-2024-020 | Norway | S0006 | NORW-Research Institute | 3 | 3 | 100 | 0.4 | SCREENING | Dr. Robert Martin | Dr. Robert Miller
3194 | ST-2024-020 | Norway | S0007 | NORW-Health System | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Jessica White | Dr. Michelle Jones
3195 | ST-2024-020 | Norway | S0008 | NORW-Clinical Center | 3 | 4 | 133.3 | 0.4 | ENROLLING | Dr. Christopher Smith | Dr. Jessica Miller
3196 | ST-2024-020 | Netherlands | S0009 | NETH-General Hospital | -4 | -4 | 100 | -0.2 | ON_HOLD | Dr. Nicole Thompson | Dr. Michelle Harris
3197 | ST-2024-020 | Netherlands | S0010 | NETH-Clinical Center | 3 | 2 | 66.7 | 0.2 | CLOSED | Dr. Robert Anderson | Dr. Jennifer Wilson
3198 | ST-2024-020 | Netherlands | S0011 | NETH-University Hospital | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. Jessica Johnson | Dr. Robert Thomas
3199 | ST-2024-020 | Netherlands | S0012 | NETH-Research Institute | 3 | 3 | 100 | 0.2 | SCREENING | Dr. Jennifer Moore | Dr. Jessica Garcia
3200 | ST-2024-020 | Japan | S0013 | JAPA-Research Institute | -4 | -4 | 100 | -0.3 | ENROLLING | Dr. Christopher Wilson | Dr. Amanda Garcia
3201 | ST-2024-020 | Japan | S0014 | JAPA-University Hospital | 3 | 2 | 66.7 | 0.1 | ON_HOLD | Dr. Sarah Taylor | Dr. Amanda Jones
3202 | ST-2024-020 | Japan | S0015 | JAPA-Research Institute | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. Jennifer Moore | Dr. Jessica Brown
3203 | ST-2024-020 | Japan | S0016 | JAPA-Medical Center | 3 | 5 | 166.7 | 0.4 | SCREENING | Dr. Robert Harris | Dr. Thomas Jones
3204 | ST-2025-021 | Mexico | S0001 | MEXI-Medical Center | 9 | 5 | 55.6 | 0.5 | SCREENING | Dr. James Brown | Dr. Emily Miller
3205 | ST-2025-021 | Mexico | S0002 | MEXI-Health System | 8 | 5 | 62.5 | 0.6 | ENROLLING | Dr. Amanda Smith | Dr. Michael Jones
3206 | ST-2025-021 | Mexico | S0003 | MEXI-Cancer Center | 17 | 12 | 70.6 | 0.7 | ENROLLING | Dr. Amanda Thomas | Dr. Jennifer Thompson
3207 | ST-2025-021 | Mexico | S0004 | MEXI-Cancer Center | 14 | 26 | 185.7 | 1.5 | SCREENING | Dr. Lisa Thompson | Dr. Michael Brown
3208 | ST-2025-021 | United States | S0005 | UNIT-General Hospital | 25 | 22 | 88 | 2.4 | ENROLLING | Dr. Jennifer Moore | Dr. James Brown
3209 | ST-2025-021 | United States | S0006 | UNIT-University Hospital | 23 | 26 | 113 | 1.9 | SCREENING | Dr. Nicole Thomas | Dr. Jennifer Harris
3210 | ST-2025-021 | Belgium | S0007 | BELG-Health System | 13 | 13 | 100 | 1.4 | SCREENING | Dr. Emily Taylor | Dr. Emily Harris
3211 | ST-2025-021 | Belgium | S0008 | BELG-Medical Center | 6 | 5 | 83.3 | 0.4 | ENROLLING | Dr. Nicole Thomas | Dr. Jessica Moore
3212 | ST-2025-021 | Belgium | S0009 | BELG-General Hospital | 14 | 12 | 85.7 | 2 | ENROLLING | Dr. Thomas Martin | Dr. Emily Jackson
3213 | ST-2025-021 | Sweden | S0010 | SWED-Health System | 8 | 8 | 100 | 0.7 | ENROLLING | Dr. Stephanie Miller | Dr. Michael Martin
3214 | ST-2025-021 | Sweden | S0011 | SWED-General Hospital | 11 | 9 | 81.8 | 0.8 | ENROLLING | Dr. James Martin | Dr. Emily Jackson
3215 | ST-2025-021 | Sweden | S0012 | SWED-Clinical Center | 8 | 10 | 125 | 0.7 | SCREENING | Dr. Michael Brown | Dr. Robert Jackson
3216 | ST-2025-021 | Australia | S0013 | AUST-University Hospital | 14 | 9 | 64.3 | 1.3 | ENROLLING | Dr. David Taylor | Dr. David Jackson
3217 | ST-2025-021 | Australia | S0014 | AUST-Medical Center | 15 | 23 | 153.3 | 2.6 | ENROLLING | Dr. Nicole Wilson | Dr. William Jackson
3218 | ST-2025-022 | United States | S0001 | UNIT-Cancer Center | 0 | 0 | 0 | 0 | SCREENING | Dr. Michelle Garcia | Dr. Sarah Martin
3219 | ST-2025-022 | United States | S0002 | UNIT-Cancer Center | 3 | 2 | 66.7 | 0.3 | ENROLLING | Dr. Michael Taylor | Dr. Jessica Williams
3220 | ST-2025-022 | United States | S0003 | UNIT-Clinical Center | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. Michael Jackson | Dr. Robert Davis
3221 | ST-2025-022 | United States | S0004 | UNIT-Medical Center | 3 | 5 | 166.7 | 0.3 | ON_HOLD | Dr. Daniel Brown | Dr. Daniel Thompson
3222 | ST-2025-022 | Mexico | S0005 | MEXI-Medical Center | 4 | 2 | 50 | 0.1 | ON_HOLD | Dr. Thomas Jackson | Dr. Lisa White
3223 | ST-2025-022 | Mexico | S0006 | MEXI-University Hospital | 5 | 4 | 80 | 0.5 | SCREENING | Dr. Jennifer Miller | Dr. William Harris
3224 | ST-2025-022 | Poland | S0007 | POLA-Clinical Center | 1 | 1 | 100 | 0.1 | SCREENING | Dr. William Jones | Dr. Amanda Martin
3225 | ST-2025-022 | Poland | S0008 | POLA-General Hospital | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. James Johnson | Dr. Sarah Davis
3226 | ST-2025-022 | Poland | S0009 | POLA-Research Institute | 3 | 2 | 66.7 | 0.1 | ON_HOLD | Dr. Jessica Thomas | Dr. Emily Moore
3227 | ST-2025-022 | Poland | S0010 | POLA-Cancer Center | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. Charles Smith | Dr. Charles Wilson
3228 | ST-2025-022 | Sweden | S0011 | SWED-Research Institute | -5 | -5 | 100 | -0.7 | SCREENING | Dr. Nicole White | Dr. Thomas White
3229 | ST-2025-022 | Sweden | S0012 | SWED-Cancer Center | 3 | 2 | 66.7 | 0.3 | ENROLLING | Dr. William Thompson | Dr. Michael Thomas
3230 | ST-2025-022 | Sweden | S0013 | SWED-Clinical Center | 3 | 3 | 100 | 0.2 | ON_HOLD | Dr. Michelle Taylor | Dr. Christopher Smith
3231 | ST-2025-022 | Sweden | S0014 | SWED-Cancer Center | 3 | 2 | 66.7 | 0.3 | ON_HOLD | Dr. Jennifer Harris | Dr. Robert Smith
3232 | ST-2025-022 | Sweden | S0015 | SWED-Clinical Center | 3 | 3 | 100 | 0.3 | ON_HOLD | Dr. Jessica Taylor | Dr. Michael Brown
3233 | ST-2025-022 | Sweden | S0016 | SWED-University Hospital | 3 | 3 | 100 | 0.3 | ON_HOLD | Dr. Robert White | Dr. Thomas Harris
3234 | ST-2025-022 | China | S0017 | CHIN-General Hospital | 5 | 3 | 60 | 0.2 | ON_HOLD | Dr. Jessica Miller | Dr. Michael White
3235 | ST-2025-022 | China | S0018 | CHIN-Research Institute | 6 | 5 | 83.3 | 0.6 | ON_HOLD | Dr. Charles Davis | Dr. James Smith
3236 | ST-2025-022 | Chile | S0019 | CHIL-University Hospital | 5 | 5 | 100 | 0.5 | SCREENING | Dr. Jennifer Johnson | Dr. Charles White
3237 | ST-2025-022 | Chile | S0020 | CHIL-Health System | 3 | 3 | 100 | 0.3 | ENROLLING | Dr. Michael Thomas | Dr. Jennifer Brown
3238 | ST-2025-022 | Chile | S0021 | CHIL-Medical Center | 3 | 15 | 500 | 0.9 | SCREENING | Dr. Stephanie Harris | Dr. Nicole Brown
3239 | ST-2025-023 | United States | S0001 | UNIT-Medical Center | 106 | 106 | 100 | 8.8 | ON_HOLD | Dr. James Smith | Dr. Charles Brown
3240 | ST-2025-023 | United States | S0002 | UNIT-Medical Center | 93 | 78 | 83.9 | 9.8 | ON_HOLD | Dr. Nicole Harris | Dr. Charles Martin
3241 | ST-2025-023 | Canada | S0003 | CANA-General Hospital | 47 | 47 | 100 | 3.9 | SCREENING | Dr. Michael Jones | Dr. Robert Smith
3242 | ST-2025-023 | Canada | S0004 | CANA-University Hospital | 75 | 75 | 100 | 10.7 | ENROLLING | Dr. David Smith | Dr. David Martin
3243 | ST-2025-023 | Canada | S0005 | CANA-General Hospital | 63 | 26 | 41.3 | 3.2 | ON_HOLD | Dr. Lisa White | Dr. Michelle Miller
3244 | ST-2025-023 | Italy | S0006 | ITAL-Medical Center | 32 | 32 | 100 | 2.5 | ON_HOLD | Dr. Lisa Miller | Dr. Jessica Jackson
3245 | ST-2025-023 | Italy | S0007 | ITAL-Medical Center | 64 | 64 | 100 | 5.8 | ENROLLING | Dr. Emily White | Dr. Stephanie Martin
3246 | ST-2025-023 | Italy | S0008 | ITAL-General Hospital | 33 | 28 | 84.8 | 1.9 | ON_HOLD | Dr. Michelle Anderson | Dr. Sarah Martin
3247 | ST-2025-023 | Italy | S0009 | ITAL-Clinical Center | 46 | 40 | 87 | 3.1 | ON_HOLD | Dr. Nicole Davis | Dr. Sarah Thompson
3248 | ST-2025-023 | Italy | S0010 | ITAL-Medical Center | 31 | 1 | 3.2 | 0.1 | ON_HOLD | Dr. Thomas Moore | Dr. Michael Wilson
3249 | ST-2025-023 | Poland | S0011 | POLA-University Hospital | 70 | 70 | 100 | 5 | SCREENING | Dr. Thomas Harris | Dr. Robert Anderson
3250 | ST-2025-023 | Poland | S0012 | POLA-General Hospital | 43 | 26 | 60.5 | 1.5 | ON_HOLD | Dr. Stephanie Thomas | Dr. Nicole Garcia
3251 | ST-2025-023 | Poland | S0013 | POLA-Health System | 46 | 35 | 76.1 | 3.9 | ON_HOLD | Dr. Michael Martin | Dr. Robert Garcia
3252 | ST-2025-023 | Poland | S0014 | POLA-University Hospital | 47 | 33 | 70.2 | 4.1 | CLOSED | Dr. Nicole Brown | Dr. Stephanie Martin
3253 | ST-2025-023 | Poland | S0015 | POLA-Research Institute | 68 | 54 | 79.4 | 6 | SCREENING | Dr. Michelle Johnson | Dr. James Thomas
3254 | ST-2025-023 | Poland | S0016 | POLA-Research Institute | 40 | 12 | 30 | 1.1 | CLOSED | Dr. Jennifer Garcia | Dr. Daniel Johnson
3255 | ST-2025-023 | Japan | S0017 | JAPA-University Hospital | 50 | 50 | 100 | 2.9 | ON_HOLD | Dr. Emily Johnson | Dr. Christopher Harris
3256 | ST-2025-023 | Japan | S0018 | JAPA-Cancer Center | 30 | 30 | 100 | 1.7 | ENROLLING | Dr. Emily Brown | Dr. Michelle Johnson
3257 | ST-2025-023 | Japan | S0019 | JAPA-Health System | 22 | 22 | 100 | 3.1 | ENROLLING | Dr. Emily Miller | Dr. Amanda Garcia
3258 | ST-2025-023 | Japan | S0020 | JAPA-General Hospital | 26 | 26 | 100 | 2.6 | ON_HOLD | Dr. Christopher Thompson | Dr. Nicole Brown
3259 | ST-2025-023 | Japan | S0021 | JAPA-University Hospital | 38 | 35 | 92.1 | 2.2 | SCREENING | Dr. Thomas Jones | Dr. Emily Miller
3260 | ST-2025-023 | Japan | S0022 | JAPA-Clinical Center | 36 | 19 | 52.8 | 1.6 | ENROLLING | Dr. Lisa Martin | Dr. Thomas Anderson
3261 | ST-2025-023 | Mexico | S0023 | MEXI-General Hospital | 162 | 162 | 100 | 18 | ENROLLING | Dr. Daniel White | Dr. Lisa Jones
3262 | ST-2025-023 | Mexico | S0024 | MEXI-Cancer Center | 93 | 75 | 80.6 | 6.2 | SCREENING | Dr. Stephanie Harris | Dr. Daniel Thomas
3263 | ST-2025-023 | Mexico | S0025 | MEXI-Medical Center | 139 | 124 | 89.2 | 9.5 | ENROLLING | Dr. James Thompson | Dr. Michael Williams
3264 | ST-2025-024 | United States | S0001 | UNIT-Research Institute | 13 | 13 | 100 | 1.1 | ENROLLING | Dr. Thomas Jones | Dr. Stephanie Taylor
3265 | ST-2025-024 | United States | S0002 | UNIT-Research Institute | 6 | 3 | 50 | 0.2 | ENROLLING | Dr. Sarah Miller | Dr. Lisa Davis
3266 | ST-2025-024 | United States | S0003 | UNIT-Clinical Center | 5 | 5 | 100 | 0.4 | SCREENING | Dr. Charles Brown | Dr. William Johnson
3267 | ST-2025-024 | United States | S0004 | UNIT-Research Institute | 10 | 7 | 70 | 0.5 | SCREENING | Dr. Stephanie Williams | Dr. Nicole Smith
3268 | ST-2025-024 | United States | S0005 | UNIT-Clinical Center | 5 | 5 | 100 | 0.3 | ENROLLING | Dr. James Wilson | Dr. Michelle Brown
3269 | ST-2025-024 | United States | S0006 | UNIT-University Hospital | 12 | 18 | 150 | 1 | SCREENING | Dr. Robert Anderson | Dr. Stephanie Harris
3270 | ST-2025-024 | Mexico | S0007 | MEXI-Medical Center | 7 | 7 | 100 | 0.5 | SCREENING | Dr. Jessica Garcia | Dr. James Johnson
3271 | ST-2025-024 | Mexico | S0008 | MEXI-Clinical Center | 7 | 6 | 85.7 | 0.6 | SCREENING | Dr. William Jackson | Dr. Amanda Miller
3272 | ST-2025-024 | Mexico | S0009 | MEXI-Health System | 4 | 3 | 75 | 0.2 | ENROLLING | Dr. Sarah Garcia | Dr. Michelle Williams
3273 | ST-2025-024 | Mexico | S0010 | MEXI-Research Institute | 10 | 10 | 100 | 1.4 | ENROLLING | Dr. Emily Jones | Dr. Michelle Wilson
3274 | ST-2025-024 | Mexico | S0011 | MEXI-Clinical Center | 6 | 5 | 83.3 | 0.6 | SCREENING | Dr. Daniel Taylor | Dr. Thomas Wilson
3275 | ST-2025-024 | Mexico | S0012 | MEXI-Cancer Center | 10 | 13 | 130 | 0.8 | ENROLLING | Dr. William Davis | Dr. Thomas Taylor
3276 | ST-2025-024 | Sweden | S0013 | SWED-Medical Center | 12 | 8 | 66.7 | 1.3 | CLOSED | Dr. Jennifer White | Dr. Michelle Martin
3277 | ST-2025-024 | Sweden | S0014 | SWED-Cancer Center | 20 | 20 | 100 | 1.7 | CLOSED | Dr. Michael Williams | Dr. Michelle Smith
3278 | ST-2025-024 | Sweden | S0015 | SWED-Cancer Center | 11 | 5 | 45.5 | 0.3 | ON_HOLD | Dr. Emily Thomas | Dr. Charles Thomas
3279 | ST-2025-024 | Sweden | S0016 | SWED-Clinical Center | 19 | 0 | 0 | 0 | CLOSED | Dr. James Brown | Dr. Christopher Thomas
3280 | ST-2025-024 | Switzerland | S0017 | SWIT-Medical Center | 20 | 0 | 0 | 0 | ON_HOLD | Dr. Amanda Miller | Dr. Michael Anderson
3281 | ST-2025-024 | Switzerland | S0018 | SWIT-Cancer Center | 13 | 0 | 0 | 0 | SCREENING | Dr. Lisa Martin | Dr. Amanda Johnson
3282 | ST-2025-024 | Japan | S0019 | JAPA-Cancer Center | 7 | 0 | 0 | 0 | CLOSED | Dr. Daniel Martin | Dr. Jennifer Moore
3283 | ST-2025-024 | Japan | S0020 | JAPA-University Hospital | 10 | 0 | 0 | 0 | CLOSED | Dr. Jennifer Williams | Dr. Robert Williams
3284 | ST-2025-024 | Japan | S0021 | JAPA-University Hospital | 8 | 0 | 0 | 0 | CLOSED | Dr. Lisa Thompson | Dr. William Miller
3285 | ST-2025-024 | Japan | S0022 | JAPA-Cancer Center | 5 | 0 | 0 | 0 | SCREENING | Dr. Michelle Wilson | Dr. Michelle Harris
3286 | ST-2025-025 | Canada | S0001 | CANA-University Hospital | -35 | -35 | 100 | -5.8 | SCREENING | Dr. David Moore | Dr. Jessica Jones
3287 | ST-2025-025 | Canada | S0002 | CANA-Research Institute | 3 | 3 | 100 | 0.3 | ENROLLING | Dr. William Jones | Dr. Daniel Martin
3288 | ST-2025-025 | Canada | S0003 | CANA-University Hospital | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. Nicole Williams | Dr. Jennifer Thompson
3289 | ST-2025-025 | United States | S0004 | UNIT-University Hospital | -1 | -1 | 100 | -0.1 | SCREENING | Dr. Amanda Thompson | Dr. Nicole Martin
3290 | ST-2025-025 | United States | S0005 | UNIT-Clinical Center | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Charles Johnson | Dr. David Davis
3291 | ST-2025-025 | United States | S0006 | UNIT-University Hospital | 3 | 4 | 133.3 | 0.3 | ENROLLING | Dr. Charles Miller | Dr. Jessica White
3292 | ST-2025-025 | Spain | S0007 | SPAI-Clinical Center | -4 | -4 | 100 | -0.3 | ON_HOLD | Dr. Lisa Johnson | Dr. Christopher Thompson
3293 | ST-2025-025 | Spain | S0008 | SPAI-Health System | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. Christopher Harris | Dr. Stephanie White
3294 | ST-2025-025 | Spain | S0009 | SPAI-Research Institute | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. Thomas Wilson | Dr. Charles Smith
3295 | ST-2025-025 | Spain | S0010 | SPAI-University Hospital | 3 | 4 | 133.3 | 0.3 | SCREENING | Dr. William Williams | Dr. Amanda Williams
3296 | ST-2025-025 | Sweden | S0011 | SWED-Research Institute | -7 | -7 | 100 | -0.8 | CLOSED | Dr. Thomas Wilson | Dr. Jessica Wilson
3297 | ST-2025-025 | Sweden | S0012 | SWED-University Hospital | 3 | 2 | 66.7 | 0.1 | CLOSED | Dr. Robert Moore | Dr. William Smith
3298 | ST-2025-025 | Sweden | S0013 | SWED-Cancer Center | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. Amanda Jackson | Dr. Charles Smith
3299 | ST-2025-025 | Sweden | S0014 | SWED-Clinical Center | 3 | 2 | 66.7 | 0.1 | CLOSED | Dr. Robert Jackson | Dr. Lisa Davis
3300 | ST-2025-025 | Sweden | S0015 | SWED-General Hospital | 3 | 4 | 133.3 | 0.2 | SCREENING | Dr. Nicole Davis | Dr. Daniel Moore
3301 | ST-2025-025 | Netherlands | S0016 | NETH-University Hospital | -1 | -1 | 100 | -0.1 | CLOSED | Dr. Stephanie Miller | Dr. Christopher Harris
3302 | ST-2025-025 | Netherlands | S0017 | NETH-Cancer Center | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Amanda Jones | Dr. Robert Anderson
3303 | ST-2025-025 | Netherlands | S0018 | NETH-General Hospital | 3 | 2 | 66.7 | 0.3 | ON_HOLD | Dr. Amanda Taylor | Dr. Lisa White
3304 | ST-2025-025 | Taiwan | S0019 | TAIW-Medical Center | -4 | -4 | 100 | -0.5 | SCREENING | Dr. Thomas Jackson | Dr. Charles Miller
3305 | ST-2025-025 | Taiwan | S0020 | TAIW-Clinical Center | 3 | 2 | 66.7 | 0.3 | CLOSED | Dr. Charles Miller | Dr. Nicole Brown
3306 | ST-2025-025 | Taiwan | S0021 | TAIW-Research Institute | 3 | 2 | 66.7 | 0.1 | ON_HOLD | Dr. Jessica Williams | Dr. Jennifer Brown
3307 | ST-2025-025 | Taiwan | S0022 | TAIW-General Hospital | 3 | 3 | 100 | 0.2 | SCREENING | Dr. Sarah Martin | Dr. James Garcia
3308 | ST-2025-025 | Australia | S0023 | AUST-Clinical Center | -10 | -10 | 100 | -1.2 | ENROLLING | Dr. Robert Moore | Dr. Stephanie Martin
3309 | ST-2025-025 | Australia | S0024 | AUST-General Hospital | 3 | 2 | 66.7 | 0.3 | ENROLLING | Dr. David Jones | Dr. David Anderson
3310 | ST-2025-025 | Australia | S0025 | AUST-Clinical Center | 3 | 1 | 33.3 | 0.1 | SCREENING | Dr. Nicole Garcia | Dr. Jessica Miller
3311 | ST-2025-025 | Australia | S0026 | AUST-Health System | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Christopher Wilson | Dr. David Smith
3312 | ST-2025-025 | Australia | S0027 | AUST-University Hospital | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. Charles Davis | Dr. Daniel Taylor
3313 | ST-2025-025 | Australia | S0028 | AUST-Health System | 3 | 7 | 233.3 | 0.5 | ENROLLING | Dr. Christopher Johnson | Dr. Michael Anderson
3314 | ST-2025-025 | Chile | S0029 | CHIL-Cancer Center | 2 | 1 | 50 | 0.1 | ENROLLING | Dr. Charles Garcia | Dr. Stephanie Davis
3315 | ST-2025-025 | Chile | S0030 | CHIL-University Hospital | 3 | 6 | 200 | 0.4 | SCREENING | Dr. Stephanie Harris | Dr. Charles Garcia
3316 | ST-2025-026 | Mexico | S0001 | MEXI-University Hospital | 10 | 10 | 100 | 1 | ON_HOLD | Dr. David Jackson | Dr. Jessica Smith
3317 | ST-2025-026 | Mexico | S0002 | MEXI-University Hospital | 4 | 2 | 50 | 0.2 | ENROLLING | Dr. Emily Williams | Dr. Stephanie Thompson
3318 | ST-2025-026 | Mexico | S0003 | MEXI-Clinical Center | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Stephanie Garcia | Dr. Jennifer Thomas
3319 | ST-2025-026 | Mexico | S0004 | MEXI-University Hospital | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. David Martin | Dr. Jennifer Thompson
3320 | ST-2025-026 | Mexico | S0005 | MEXI-Medical Center | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. David Garcia | Dr. David Johnson
3321 | ST-2025-026 | Mexico | S0006 | MEXI-General Hospital | 5 | 4 | 80 | 0.5 | ENROLLING | Dr. William White | Dr. Christopher Brown
3322 | ST-2025-026 | Canada | S0007 | CANA-Research Institute | 21 | 17 | 81 | 2.8 | SCREENING | Dr. Lisa Martin | Dr. Nicole Brown
3323 | ST-2025-026 | Canada | S0008 | CANA-Medical Center | 9 | 6 | 66.7 | 1 | ENROLLING | Dr. James Johnson | Dr. Emily Miller
3324 | ST-2025-026 | Canada | S0009 | CANA-Health System | 11 | 17 | 154.5 | 0.9 | ENROLLING | Dr. Charles Thompson | Dr. William Martin
3325 | ST-2025-026 | Switzerland | S0010 | SWIT-Research Institute | 24 | 20 | 83.3 | 1.2 | ON_HOLD | Dr. Thomas Davis | Dr. Amanda Jackson
3326 | ST-2025-026 | Switzerland | S0011 | SWIT-Clinical Center | 19 | 10 | 52.6 | 0.7 | SCREENING | Dr. Amanda Taylor | Dr. Emily Smith
3327 | ST-2025-026 | Sweden | S0012 | SWED-Cancer Center | 9 | 8 | 88.9 | 0.9 | SCREENING | Dr. Christopher Martin | Dr. Daniel White
3328 | ST-2025-026 | Sweden | S0013 | SWED-General Hospital | 7 | 7 | 100 | 0.8 | ENROLLING | Dr. Thomas Smith | Dr. Amanda Johnson
3329 | ST-2025-026 | Sweden | S0014 | SWED-Cancer Center | 7 | 5 | 71.4 | 0.3 | SCREENING | Dr. Christopher Davis | Dr. Nicole Jackson
3330 | ST-2025-026 | Sweden | S0015 | SWED-General Hospital | 8 | 8 | 100 | 0.5 | ENROLLING | Dr. Amanda White | Dr. Nicole Brown
3331 | ST-2025-026 | Sweden | S0016 | SWED-General Hospital | 4 | 5 | 125 | 0.4 | SCREENING | Dr. David Jones | Dr. Daniel Thompson
3332 | ST-2025-026 | Singapore | S0017 | SING-Cancer Center | 13 | 13 | 100 | 1 | SCREENING | Dr. Christopher Brown | Dr. Nicole Moore
3333 | ST-2025-026 | Singapore | S0018 | SING-University Hospital | 21 | 4 | 19 | 0.4 | SCREENING | Dr. Jennifer Williams | Dr. Emily White
3334 | ST-2025-026 | Singapore | S0019 | SING-General Hospital | 12 | 0 | 0 | 0 | SCREENING | Dr. Thomas Jackson | Dr. William Davis
3335 | ST-2025-026 | New Zealand | S0020 | NEW-Clinical Center | 18 | 0 | 0 | 0 | CLOSED | Dr. Thomas Davis | Dr. Michael Taylor
3336 | ST-2025-026 | New Zealand | S0021 | NEW-Clinical Center | 15 | 0 | 0 | 0 | CLOSED | Dr. Charles Moore | Dr. Stephanie Davis
3337 | ST-2025-026 | New Zealand | S0022 | NEW-University Hospital | 19 | 0 | 0 | 0 | SCREENING | Dr. Jessica Williams | Dr. Emily Williams
3338 | ST-2025-026 | New Zealand | S0023 | NEW-Research Institute | 15 | 0 | 0 | 0 | CLOSED | Dr. David Brown | Dr. Amanda Jones
3339 | ST-2025-027 | Mexico | S0001 | MEXI-Medical Center | 2 | 1 | 50 | 0.1 | SCREENING | Dr. Robert Jones | Dr. Robert Jackson
3340 | ST-2025-027 | Mexico | S0002 | MEXI-Health System | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Sarah Thomas | Dr. Lisa White
3341 | ST-2025-027 | Mexico | S0003 | MEXI-General Hospital | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. Christopher Thomas | Dr. Christopher Thompson
3342 | ST-2025-027 | Mexico | S0004 | MEXI-Research Institute | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Daniel Davis | Dr. Jessica Williams
3343 | ST-2025-027 | Mexico | S0005 | MEXI-Research Institute | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Michael Williams | Dr. Michael Davis
3344 | ST-2025-027 | Mexico | S0006 | MEXI-Medical Center | 3 | 7 | 233.3 | 0.9 | SCREENING | Dr. Sarah Williams | Dr. Jessica Moore
3345 | ST-2025-027 | Canada | S0007 | CANA-Clinical Center | 4 | 2 | 50 | 0.1 | ON_HOLD | Dr. Robert Martin | Dr. Nicole Thompson
3346 | ST-2025-027 | Canada | S0008 | CANA-General Hospital | 3 | 4 | 133.3 | 0.2 | ON_HOLD | Dr. Emily Jackson | Dr. James Miller
3347 | ST-2025-027 | United States | S0009 | UNIT-University Hospital | 3 | 3 | 100 | 0.2 | CLOSED | Dr. Daniel Johnson | Dr. Christopher Garcia
3348 | ST-2025-027 | United States | S0010 | UNIT-General Hospital | 3 | 3 | 100 | 0.2 | CLOSED | Dr. Lisa Garcia | Dr. Michael Thomas
3349 | ST-2025-027 | United States | S0011 | UNIT-Cancer Center | 3 | 0 | 0 | 0 | CLOSED | Dr. Amanda Johnson | Dr. Stephanie Martin
3350 | ST-2025-027 | Switzerland | S0012 | SWIT-General Hospital | 7 | 4 | 57.1 | 0.4 | ON_HOLD | Dr. Emily Anderson | Dr. Jessica Martin
3351 | ST-2025-027 | Switzerland | S0013 | SWIT-Research Institute | 5 | 7 | 140 | 0.7 | ENROLLING | Dr. James Jackson | Dr. David Anderson
3352 | ST-2025-027 | Spain | S0014 | SPAI-Clinical Center | 2 | 2 | 100 | 0.2 | ON_HOLD | Dr. Amanda Brown | Dr. James Thomas
3353 | ST-2025-027 | Spain | S0015 | SPAI-General Hospital | 3 | 3 | 100 | 0.4 | ON_HOLD | Dr. Amanda Smith | Dr. Emily White
3354 | ST-2025-027 | Spain | S0016 | SPAI-Clinical Center | 3 | 1 | 33.3 | 0.1 | SCREENING | Dr. Daniel Thompson | Dr. Robert White
3355 | ST-2025-027 | Spain | S0017 | SPAI-Medical Center | 3 | 1 | 33.3 | 0.1 | SCREENING | Dr. Robert Wilson | Dr. Lisa Martin
3356 | ST-2025-027 | Spain | S0018 | SPAI-Clinical Center | 3 | 3 | 100 | 0.3 | ON_HOLD | Dr. Amanda White | Dr. Jennifer Moore
3357 | ST-2025-027 | United Kingdom | S0019 | UNIT-Medical Center | -3 | -3 | 100 | -0.4 | ON_HOLD | Dr. Stephanie Taylor | Dr. Sarah Garcia
3358 | ST-2025-027 | United Kingdom | S0020 | UNIT-General Hospital | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. William Brown | Dr. Stephanie Martin
3359 | ST-2025-027 | United Kingdom | S0021 | UNIT-Health System | 3 | 3 | 100 | 0.2 | CLOSED | Dr. Robert Taylor | Dr. Charles Thompson
3360 | ST-2025-027 | United Kingdom | S0022 | UNIT-General Hospital | 3 | 2 | 66.7 | 0.1 | ON_HOLD | Dr. Robert Brown | Dr. Emily Smith
3361 | ST-2025-027 | United Kingdom | S0023 | UNIT-University Hospital | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. Daniel Smith | Dr. Lisa Johnson
3362 | ST-2025-027 | United Kingdom | S0024 | UNIT-General Hospital | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. James White | Dr. Nicole Anderson
3363 | ST-2025-027 | India | S0025 | INDI-Health System | 6 | 5 | 83.3 | 0.6 | CLOSED | Dr. Daniel Garcia | Dr. Lisa Wilson
3364 | ST-2025-027 | India | S0026 | INDI-Cancer Center | 4 | 2 | 50 | 0.3 | ON_HOLD | Dr. Lisa White | Dr. David Martin
3365 | ST-2025-027 | Singapore | S0027 | SING-University Hospital | -8 | -8 | 100 | -1 | ENROLLING | Dr. James Miller | Dr. Michael Johnson
3366 | ST-2025-027 | Singapore | S0028 | SING-Clinical Center | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Jessica Davis | Dr. Lisa Taylor
3367 | ST-2025-027 | Singapore | S0029 | SING-Clinical Center | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Daniel White | Dr. Sarah Anderson
3368 | ST-2025-027 | Singapore | S0030 | SING-Medical Center | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. William Thomas | Dr. Stephanie Davis
3369 | ST-2025-027 | Singapore | S0031 | SING-Research Institute | 3 | 1 | 33.3 | 0.2 | ENROLLING | Dr. Sarah Smith | Dr. Sarah Taylor
3370 | ST-2025-027 | Singapore | S0032 | SING-University Hospital | 3 | 18 | 600 | 1.8 | ENROLLING | Dr. William Brown | Dr. Stephanie Garcia
3371 | ST-2025-028 | Canada | S0001 | CANA-General Hospital | 10148 | 5228 | 51.5 | 326.8 | ON_HOLD | Dr. Jessica Thomas | Dr. Emily Wilson
3372 | ST-2025-028 | Canada | S0002 | CANA-Clinical Center | 10883 | 0 | 0 | 0 | ON_HOLD | Dr. William Williams | Dr. James Jones
3373 | ST-2025-028 | Denmark | S0003 | DENM-Medical Center | 11480 | 0 | 0 | 0 | ON_HOLD | Dr. William Jones | Dr. Michael Taylor
3374 | ST-2025-028 | Denmark | S0004 | DENM-University Hospital | 5807 | 0 | 0 | 0 | ON_HOLD | Dr. Amanda Taylor | Dr. Nicole White
3375 | ST-2025-028 | Denmark | S0005 | DENM-Clinical Center | 5818 | 0 | 0 | 0 | ON_HOLD | Dr. Thomas Jones | Dr. Lisa Jackson
3376 | ST-2025-028 | Denmark | S0006 | DENM-Clinical Center | 8503 | 0 | 0 | 0 | ON_HOLD | Dr. Michelle Moore | Dr. Nicole Moore
3377 | ST-2025-028 | Australia | S0007 | AUST-Cancer Center | 6775 | 0 | 0 | 0 | CLOSED | Dr. Lisa Williams | Dr. Lisa Thomas
3378 | ST-2025-028 | Australia | S0008 | AUST-Medical Center | 4772 | 0 | 0 | 0 | SCREENING | Dr. Amanda Moore | Dr. Nicole Jones
3379 | ST-2025-028 | Australia | S0009 | AUST-Medical Center | 3814 | 0 | 0 | 0 | ON_HOLD | Dr. Amanda Jones | Dr. Jessica Harris
3380 | ST-2025-029 | Mexico | S0001 | MEXI-Cancer Center | 18 | 16 | 88.9 | 2.3 | SCREENING | Dr. Emily Harris | Dr. Thomas Garcia
3381 | ST-2025-029 | Mexico | S0002 | MEXI-Research Institute | 8 | 8 | 100 | 1 | ENROLLING | Dr. William Thomas | Dr. Amanda Williams
3382 | ST-2025-029 | Mexico | S0003 | MEXI-Medical Center | 17 | 11 | 64.7 | 1.4 | ON_HOLD | Dr. Christopher Wilson | Dr. Nicole Wilson
3383 | ST-2025-029 | United States | S0004 | UNIT-Clinical Center | 5 | 4 | 80 | 0.4 | CLOSED | Dr. Thomas Thomas | Dr. Michael White
3384 | ST-2025-029 | United States | S0005 | UNIT-Health System | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. Sarah Johnson | Dr. Lisa Moore
3385 | ST-2025-029 | United States | S0006 | UNIT-Medical Center | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Jessica Jackson | Dr. Jennifer Jackson
3386 | ST-2025-029 | United States | S0007 | UNIT-Cancer Center | 3 | 2 | 66.7 | 0.3 | SCREENING | Dr. Charles Harris | Dr. Michael Thomas
3387 | ST-2025-029 | United States | S0008 | UNIT-Clinical Center | 3 | 3 | 100 | 0.2 | CLOSED | Dr. Michelle Harris | Dr. Emily Williams
3388 | ST-2025-029 | United States | S0009 | UNIT-University Hospital | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Charles White | Dr. David Jackson
3389 | ST-2025-029 | Netherlands | S0010 | NETH-Clinical Center | 7 | 6 | 85.7 | 0.8 | ON_HOLD | Dr. David Taylor | Dr. Sarah Jackson
3390 | ST-2025-029 | Netherlands | S0011 | NETH-Medical Center | 5 | 3 | 60 | 0.2 | SCREENING | Dr. Stephanie Martin | Dr. David Johnson
3391 | ST-2025-029 | Netherlands | S0012 | NETH-University Hospital | 9 | 5 | 55.6 | 0.8 | ON_HOLD | Dr. Stephanie Wilson | Dr. William Garcia
3392 | ST-2025-029 | Netherlands | S0013 | NETH-Medical Center | 6 | 4 | 66.7 | 0.5 | ENROLLING | Dr. William Jackson | Dr. Michael Anderson
3393 | ST-2025-029 | Netherlands | S0014 | NETH-Cancer Center | 7 | 12 | 171.4 | 0.7 | SCREENING | Dr. Stephanie Thompson | Dr. David Wilson
3394 | ST-2025-029 | Belgium | S0015 | BELG-Clinical Center | 6 | 6 | 100 | 0.5 | ENROLLING | Dr. Michelle Garcia | Dr. Stephanie Thomas
3395 | ST-2025-029 | Belgium | S0016 | BELG-General Hospital | 4 | 3 | 75 | 0.2 | ENROLLING | Dr. James Moore | Dr. David Williams
3396 | ST-2025-029 | Belgium | S0017 | BELG-General Hospital | 10 | 7 | 70 | 0.4 | SCREENING | Dr. Robert Taylor | Dr. Thomas Smith
3397 | ST-2025-029 | Belgium | S0018 | BELG-University Hospital | 7 | 11 | 157.1 | 0.8 | ENROLLING | Dr. Nicole Taylor | Dr. Emily White
3398 | ST-2025-029 | Australia | S0019 | AUST-General Hospital | 6 | 5 | 83.3 | 0.6 | ON_HOLD | Dr. Michelle Garcia | Dr. Charles Miller
3399 | ST-2025-029 | Australia | S0020 | AUST-Research Institute | 6 | 4 | 66.7 | 0.4 | SCREENING | Dr. James Thomas | Dr. Amanda Smith
3400 | ST-2025-029 | Australia | S0021 | AUST-Research Institute | 8 | 0 | 0 | 0 | CLOSED | Dr. Emily Martin | Dr. Christopher White
3401 | ST-2025-029 | Australia | S0022 | AUST-Clinical Center | 7 | 0 | 0 | 0 | ON_HOLD | Dr. Michelle White | Dr. Daniel Taylor
3402 | ST-2025-029 | Australia | S0023 | AUST-Medical Center | 7 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Thomas | Dr. Jennifer Moore
3403 | ST-2025-029 | India | S0024 | INDI-Clinical Center | 16 | 0 | 0 | 0 | ON_HOLD | Dr. Emily Williams | Dr. Emily Williams
3404 | ST-2025-029 | India | S0025 | INDI-General Hospital | 14 | 0 | 0 | 0 | CLOSED | Dr. Stephanie Brown | Dr. Nicole Moore
3405 | ST-2025-029 | India | S0026 | INDI-Medical Center | 12 | 0 | 0 | 0 | ON_HOLD | Dr. Daniel Johnson | Dr. Jessica White
3406 | ST-2025-030 | United States | S0001 | UNIT-Health System | 73 | 57 | 78.1 | 9.5 | SCREENING | Dr. Jessica Harris | Dr. Nicole Brown
3407 | ST-2025-030 | United States | S0002 | UNIT-Cancer Center | 85 | 81 | 95.3 | 7.4 | ON_HOLD | Dr. Emily Smith | Dr. Lisa Johnson
3408 | ST-2025-030 | Canada | S0003 | CANA-Medical Center | 37 | 24 | 64.9 | 1.4 | ENROLLING | Dr. William Johnson | Dr. Emily Johnson
3409 | ST-2025-030 | Canada | S0004 | CANA-Research Institute | 16 | 16 | 100 | 2.3 | ENROLLING | Dr. Thomas Jackson | Dr. William Garcia
3410 | ST-2025-030 | Canada | S0005 | CANA-University Hospital | 39 | 39 | 100 | 2.6 | ENROLLING | Dr. Emily Jones | Dr. Thomas Jones
3411 | ST-2025-030 | Canada | S0006 | CANA-Cancer Center | 35 | 35 | 100 | 2.3 | ENROLLING | Dr. Christopher Brown | Dr. Daniel Thompson
3412 | ST-2025-030 | Canada | S0007 | CANA-University Hospital | 32 | 29 | 90.6 | 1.9 | ENROLLING | Dr. Nicole Wilson | Dr. Thomas Martin
3413 | ST-2025-030 | Canada | S0008 | CANA-University Hospital | 18 | 34 | 188.9 | 4.9 | ENROLLING | Dr. Jessica Williams | Dr. Amanda Moore
3414 | ST-2025-030 | Mexico | S0009 | MEXI-Clinical Center | 47 | 42 | 89.4 | 6 | ON_HOLD | Dr. David Thompson | Dr. Daniel Taylor
3415 | ST-2025-030 | Mexico | S0010 | MEXI-Cancer Center | 24 | 17 | 70.8 | 1.7 | CLOSED | Dr. Christopher Jones | Dr. Daniel Brown
3416 | ST-2025-030 | Mexico | S0011 | MEXI-University Hospital | 37 | 37 | 100 | 4.1 | ON_HOLD | Dr. Charles Harris | Dr. Daniel Miller
3417 | ST-2025-030 | Mexico | S0012 | MEXI-Cancer Center | 44 | 38 | 86.4 | 3.2 | SCREENING | Dr. Michael Wilson | Dr. Stephanie Garcia
3418 | ST-2025-030 | Mexico | S0013 | MEXI-General Hospital | 39 | 29 | 74.4 | 2.9 | CLOSED | Dr. Emily Jones | Dr. Christopher Brown
3419 | ST-2025-030 | Mexico | S0014 | MEXI-General Hospital | 19 | 0 | 0 | 0 | SCREENING | Dr. James Harris | Dr. Jennifer Wilson
3420 | ST-2025-030 | Poland | S0015 | POLA-Research Institute | 21 | 18 | 85.7 | 1.6 | SCREENING | Dr. Sarah Jackson | Dr. Stephanie Miller
3421 | ST-2025-030 | Poland | S0016 | POLA-Research Institute | 40 | 27 | 67.5 | 3 | ON_HOLD | Dr. Jennifer Wilson | Dr. Daniel Martin
3422 | ST-2025-030 | Poland | S0017 | POLA-Health System | 33 | 29 | 87.9 | 2.4 | SCREENING | Dr. Sarah Davis | Dr. Emily Davis
3423 | ST-2025-030 | Poland | S0018 | POLA-Medical Center | 26 | 23 | 88.5 | 3.8 | SCREENING | Dr. William Davis | Dr. Michael Moore
3424 | ST-2025-030 | Poland | S0019 | POLA-Medical Center | 50 | 31 | 62 | 3.1 | SCREENING | Dr. Charles Jackson | Dr. Charles Brown
3425 | ST-2025-030 | Poland | S0020 | POLA-University Hospital | 20 | 8 | 40 | 0.5 | CLOSED | Dr. William Martin | Dr. David Garcia
3426 | ST-2025-030 | Spain | S0021 | SPAI-Medical Center | 76 | 72 | 94.7 | 9 | ON_HOLD | Dr. Nicole Anderson | Dr. Lisa Garcia
3427 | ST-2025-030 | Spain | S0022 | SPAI-Research Institute | 49 | 49 | 100 | 3.1 | ENROLLING | Dr. Jennifer Garcia | Dr. Thomas Harris
3428 | ST-2025-030 | Spain | S0023 | SPAI-University Hospital | 45 | 31 | 68.9 | 5.2 | ON_HOLD | Dr. Nicole White | Dr. Thomas Smith
3429 | ST-2025-030 | Switzerland | S0024 | SWIT-Cancer Center | 21 | 21 | 100 | 3.5 | CLOSED | Dr. Jessica Davis | Dr. Daniel Thompson
3430 | ST-2025-030 | Switzerland | S0025 | SWIT-University Hospital | 21 | 19 | 90.5 | 1.1 | SCREENING | Dr. Emily Brown | Dr. Jessica Taylor
3431 | ST-2025-030 | Switzerland | S0026 | SWIT-Clinical Center | 15 | 13 | 86.7 | 1 | CLOSED | Dr. Amanda Moore | Dr. William Martin
3432 | ST-2025-030 | Switzerland | S0027 | SWIT-Research Institute | 32 | 23 | 71.9 | 2.1 | ON_HOLD | Dr. James Thomas | Dr. Jessica Taylor
3433 | ST-2025-030 | Switzerland | S0028 | SWIT-Health System | 37 | 24 | 64.9 | 1.3 | CLOSED | Dr. Nicole Brown | Dr. William Thompson
3434 | ST-2025-030 | Switzerland | S0029 | SWIT-General Hospital | 30 | 12 | 40 | 0.8 | SCREENING | Dr. Robert White | Dr. Lisa Jones
3435 | ST-2025-030 | China | S0030 | CHIN-General Hospital | 104 | 64 | 61.5 | 5.3 | ON_HOLD | Dr. David Williams | Dr. David Jackson
3436 | ST-2025-030 | China | S0031 | CHIN-General Hospital | 63 | 0 | 0 | 0 | ON_HOLD | Dr. Michelle Harris | Dr. Daniel Garcia
3437 | ST-2025-030 | Japan | S0032 | JAPA-Medical Center | 32 | 0 | 0 | 0 | CLOSED | Dr. Thomas Brown | Dr. Stephanie Harris
3438 | ST-2025-030 | Japan | S0033 | JAPA-Health System | 48 | 0 | 0 | 0 | ON_HOLD | Dr. Jessica Brown | Dr. James Martin
3439 | ST-2025-030 | Japan | S0034 | JAPA-General Hospital | 56 | 0 | 0 | 0 | ON_HOLD | Dr. Robert Thompson | Dr. Jessica Moore
3440 | ST-2025-030 | Japan | S0035 | JAPA-General Hospital | 36 | 0 | 0 | 0 | ON_HOLD | Dr. Nicole Anderson | Dr. Michael Anderson
3441 | ST-2025-031 | Canada | S0001 | CANA-University Hospital | -2 | -2 | 100 | -0.1 | CLOSED | Dr. Jessica Brown | Dr. Emily Martin
3442 | ST-2025-031 | Canada | S0002 | CANA-University Hospital | 3 | 2 | 66.7 | 0.3 | CLOSED | Dr. Michelle Taylor | Dr. James Davis
3443 | ST-2025-031 | Canada | S0003 | CANA-Cancer Center | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Charles Thomas | Dr. Michael Garcia
3444 | ST-2025-031 | Canada | S0004 | CANA-Research Institute | 3 | 0 | 0 | 0 | CLOSED | Dr. Lisa Thompson | Dr. Daniel Anderson
3445 | ST-2025-031 | Canada | S0005 | CANA-Clinical Center | 3 | 0 | 0 | 0 | SCREENING | Dr. Michelle Brown | Dr. Nicole Wilson
3446 | ST-2025-031 | United States | S0006 | UNIT-Medical Center | 1 | 0 | 0 | 0 | SCREENING | Dr. Michelle Taylor | Dr. Sarah Davis
3447 | ST-2025-031 | United States | S0007 | UNIT-Clinical Center | 3 | 0 | 0 | 0 | CLOSED | Dr. Sarah Thomas | Dr. Michael White
3448 | ST-2025-031 | United States | S0008 | UNIT-Health System | 3 | 0 | 0 | 0 | CLOSED | Dr. Michael Moore | Dr. Nicole Jones
3449 | ST-2025-031 | Mexico | S0009 | MEXI-Cancer Center | -10 | -10 | 100 | -0.6 | SCREENING | Dr. Michelle Jackson | Dr. James Moore
3450 | ST-2025-031 | Mexico | S0010 | MEXI-Clinical Center | 3 | 3 | 100 | 0.5 | ON_HOLD | Dr. Charles Jones | Dr. Stephanie White
3451 | ST-2025-031 | Mexico | S0011 | MEXI-Health System | 3 | 3 | 100 | 0.4 | SCREENING | Dr. Christopher Brown | Dr. Amanda Thomas
3452 | ST-2025-031 | Mexico | S0012 | MEXI-University Hospital | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. Sarah Davis | Dr. Lisa Williams
3453 | ST-2025-031 | Mexico | S0013 | MEXI-Health System | 3 | 1 | 33.3 | 0.2 | SCREENING | Dr. Stephanie Moore | Dr. Sarah Smith
3454 | ST-2025-031 | Mexico | S0014 | MEXI-Cancer Center | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Sarah Williams | Dr. Sarah Jones
3455 | ST-2025-031 | United Kingdom | S0015 | UNIT-Health System | -3 | -3 | 100 | -0.3 | ON_HOLD | Dr. Amanda Davis | Dr. Christopher Anderson
3456 | ST-2025-031 | United Kingdom | S0016 | UNIT-Research Institute | 3 | 2 | 66.7 | 0.1 | CLOSED | Dr. Jessica Davis | Dr. Daniel Wilson
3457 | ST-2025-031 | United Kingdom | S0017 | UNIT-Research Institute | 3 | 1 | 33.3 | 0.1 | CLOSED | Dr. Daniel Brown | Dr. Sarah Thomas
3458 | ST-2025-031 | United Kingdom | S0018 | UNIT-Clinical Center | 3 | 0 | 0 | 0 | CLOSED | Dr. Nicole Wilson | Dr. Michael Miller
3459 | ST-2025-031 | United Kingdom | S0019 | UNIT-University Hospital | 3 | 0 | 0 | 0 | SCREENING | Dr. Jessica Moore | Dr. David Brown
3460 | ST-2025-031 | United Kingdom | S0020 | UNIT-Research Institute | 3 | 0 | 0 | 0 | SCREENING | Dr. Sarah Davis | Dr. Christopher Harris
3461 | ST-2025-031 | France | S0021 | FRAN-Research Institute | 6 | 0 | 0 | 0 | CLOSED | Dr. Charles Anderson | Dr. Michael Johnson
3462 | ST-2025-031 | France | S0022 | FRAN-Research Institute | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Nicole Smith | Dr. Charles Jackson
3463 | ST-2025-031 | Belgium | S0023 | BELG-Cancer Center | 0 | 0 | 0 | 0 | SCREENING | Dr. Thomas Wilson | Dr. David Smith
3464 | ST-2025-031 | Belgium | S0024 | BELG-Research Institute | 3 | 0 | 0 | 0 | CLOSED | Dr. Stephanie White | Dr. Sarah Brown
3465 | ST-2025-031 | Belgium | S0025 | BELG-Health System | 3 | 0 | 0 | 0 | CLOSED | Dr. Jessica Moore | Dr. Christopher White
3466 | ST-2025-031 | Belgium | S0026 | BELG-Health System | 3 | 0 | 0 | 0 | CLOSED | Dr. Daniel Wilson | Dr. Jennifer Jackson
3467 | ST-2025-031 | Taiwan | S0027 | TAIW-Medical Center | 5 | 0 | 0 | 0 | CLOSED | Dr. William Williams | Dr. Lisa Moore
3468 | ST-2025-031 | Taiwan | S0028 | TAIW-Research Institute | 6 | 0 | 0 | 0 | CLOSED | Dr. Charles Johnson | Dr. William Thomas
3469 | ST-2025-031 | Japan | S0029 | JAPA-Clinical Center | -7 | -7 | 100 | -0.5 | SCREENING | Dr. Christopher Smith | Dr. Christopher Johnson
3470 | ST-2025-031 | Japan | S0030 | JAPA-Research Institute | 3 | 2 | 66.7 | 0.2 | CLOSED | Dr. Michelle Miller | Dr. Stephanie Johnson
3471 | ST-2025-031 | Japan | S0031 | JAPA-Health System | 3 | 3 | 100 | 0.4 | ON_HOLD | Dr. Michelle Taylor | Dr. Michael Harris
3472 | ST-2025-031 | Japan | S0032 | JAPA-University Hospital | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. William Martin | Dr. Robert Davis
3473 | ST-2025-031 | Japan | S0033 | JAPA-General Hospital | 3 | 0 | 0 | 0 | SCREENING | Dr. Sarah Davis | Dr. Emily Johnson
3474 | ST-2025-032 | Canada | S0001 | CANA-Cancer Center | 62 | 25 | 40.3 | 1.8 | CLOSED | Dr. Sarah Smith | Dr. Lisa Jones
3475 | ST-2025-032 | Canada | S0002 | CANA-Health System | 56 | 0 | 0 | 0 | SCREENING | Dr. David Wilson | Dr. Nicole Jones
3476 | ST-2025-032 | Mexico | S0003 | MEXI-General Hospital | 26 | 0 | 0 | 0 | SCREENING | Dr. James White | Dr. Michael Martin
3477 | ST-2025-032 | Mexico | S0004 | MEXI-Health System | 17 | 0 | 0 | 0 | SCREENING | Dr. Jennifer Johnson | Dr. Stephanie Wilson
3478 | ST-2025-032 | Mexico | S0005 | MEXI-Health System | 24 | 0 | 0 | 0 | CLOSED | Dr. Lisa Thomas | Dr. Nicole Thompson
3479 | ST-2025-032 | Mexico | S0006 | MEXI-General Hospital | 15 | 0 | 0 | 0 | ON_HOLD | Dr. Lisa Anderson | Dr. Nicole Martin
3480 | ST-2025-032 | United Kingdom | S0007 | UNIT-Cancer Center | 17 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Harris | Dr. Thomas Davis
3481 | ST-2025-032 | United Kingdom | S0008 | UNIT-General Hospital | 10 | 0 | 0 | 0 | SCREENING | Dr. Jennifer Harris | Dr. Thomas Brown
3482 | ST-2025-032 | United Kingdom | S0009 | UNIT-Research Institute | 10 | 0 | 0 | 0 | ON_HOLD | Dr. Robert Martin | Dr. Nicole White
3483 | ST-2025-032 | United Kingdom | S0010 | UNIT-General Hospital | 11 | 0 | 0 | 0 | SCREENING | Dr. Jessica Wilson | Dr. Daniel Miller
3484 | ST-2025-032 | Norway | S0011 | NORW-Clinical Center | 18 | 0 | 0 | 0 | ON_HOLD | Dr. William Johnson | Dr. William Martin
3485 | ST-2025-032 | Norway | S0012 | NORW-General Hospital | 14 | 0 | 0 | 0 | ON_HOLD | Dr. Sarah Anderson | Dr. Christopher White
3486 | ST-2025-032 | Norway | S0013 | NORW-University Hospital | 6 | 0 | 0 | 0 | SCREENING | Dr. Michelle Miller | Dr. Emily Taylor
3487 | ST-2025-032 | Norway | S0014 | NORW-University Hospital | 14 | 0 | 0 | 0 | CLOSED | Dr. James Smith | Dr. Charles Williams
3488 | ST-2025-033 | Mexico | S0001 | MEXI-Research Institute | -11 | -11 | 100 | -0.9 | SCREENING | Dr. Jessica Thomas | Dr. Charles Wilson
3489 | ST-2025-033 | Mexico | S0002 | MEXI-Health System | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. David Williams | Dr. Robert Brown
3490 | ST-2025-033 | Mexico | S0003 | MEXI-General Hospital | 3 | 1 | 33.3 | 0.1 | ENROLLING | Dr. Jennifer Wilson | Dr. Emily Jones
3491 | ST-2025-033 | Mexico | S0004 | MEXI-Cancer Center | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Charles Taylor | Dr. William Martin
3492 | ST-2025-033 | Mexico | S0005 | MEXI-University Hospital | 3 | 7 | 233.3 | 0.9 | ENROLLING | Dr. Lisa Miller | Dr. Michael Jones
3493 | ST-2025-033 | Canada | S0006 | CANA-University Hospital | -1 | -1 | 100 | -0.1 | ENROLLING | Dr. Stephanie Martin | Dr. Thomas Anderson
3494 | ST-2025-033 | Canada | S0007 | CANA-Health System | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. Lisa Moore | Dr. Charles Jackson
3495 | ST-2025-033 | Canada | S0008 | CANA-Cancer Center | 3 | 3 | 100 | 0.2 | SCREENING | Dr. Nicole Thomas | Dr. Jessica Thompson
3496 | ST-2025-033 | Switzerland | S0009 | SWIT-University Hospital | 2 | 1 | 50 | 0.1 | CLOSED | Dr. William Jones | Dr. Stephanie Moore
3497 | ST-2025-033 | Switzerland | S0010 | SWIT-Clinical Center | 3 | 2 | 66.7 | 0.2 | CLOSED | Dr. William Brown | Dr. Michelle White
3498 | ST-2025-033 | Poland | S0011 | POLA-Cancer Center | 2 | 2 | 100 | 0.2 | ON_HOLD | Dr. Amanda White | Dr. David Moore
3499 | ST-2025-033 | Poland | S0012 | POLA-University Hospital | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Jennifer Smith | Dr. David Harris
3500 | ST-2025-034 | Canada | S0001 | CANA-University Hospital | 5 | 4 | 80 | 0.2 | ENROLLING | Dr. Christopher Harris | Dr. Stephanie Jackson
3501 | ST-2025-034 | Canada | S0002 | CANA-Clinical Center | 3 | 3 | 100 | 0.3 | SCREENING | Dr. Amanda Taylor | Dr. Nicole Jackson
3502 | ST-2025-034 | France | S0003 | FRAN-Health System | 0 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Wilson | Dr. Charles Smith
3503 | ST-2025-034 | France | S0004 | FRAN-University Hospital | 3 | 3 | 100 | 0.2 | SCREENING | Dr. Jessica Thompson | Dr. David Jones
3504 | ST-2025-034 | France | S0005 | FRAN-University Hospital | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. Sarah Williams | Dr. Jessica Jones
3505 | ST-2025-034 | New Zealand | S0006 | NEW-Medical Center | -3 | -3 | 100 | -0.4 | ENROLLING | Dr. David White | Dr. Michael Davis
3506 | ST-2025-034 | New Zealand | S0007 | NEW-University Hospital | 3 | 3 | 100 | 0.2 | SCREENING | Dr. Amanda Smith | Dr. Nicole Garcia
3507 | ST-2025-034 | New Zealand | S0008 | NEW-Research Institute | 3 | 2 | 66.7 | 0.3 | ENROLLING | Dr. Michelle Jackson | Dr. David Martin
3508 | ST-2025-034 | New Zealand | S0009 | NEW-General Hospital | 3 | 4 | 133.3 | 0.3 | ENROLLING | Dr. Lisa Brown | Dr. Charles Jones
3509 | ST-2025-035 | Canada | S0001 | CANA-Health System | -35 | -35 | 100 | -2.9 | ENROLLING | Dr. Jessica Wilson | Dr. James White
3510 | ST-2025-035 | Canada | S0002 | CANA-University Hospital | 3 | 3 | 100 | 0.5 | ENROLLING | Dr. Robert Wilson | Dr. William Harris
3511 | ST-2025-035 | Canada | S0003 | CANA-Health System | 3 | 3 | 100 | 0.2 | SCREENING | Dr. Thomas Brown | Dr. Lisa Davis
3512 | ST-2025-035 | Canada | S0004 | CANA-Medical Center | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Lisa Williams | Dr. Jessica Harris
3513 | ST-2025-035 | Canada | S0005 | CANA-Health System | 3 | 3 | 100 | 0.2 | SCREENING | Dr. Thomas Moore | Dr. Charles Martin
3514 | ST-2025-035 | Canada | S0006 | CANA-Health System | 3 | 4 | 133.3 | 0.7 | ENROLLING | Dr. Thomas Taylor | Dr. Amanda Harris
3515 | ST-2025-035 | Mexico | S0007 | MEXI-Health System | 2 | 1 | 50 | 0.1 | ENROLLING | Dr. Charles Wilson | Dr. Charles Johnson
3516 | ST-2025-035 | Mexico | S0008 | MEXI-General Hospital | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. Nicole Moore | Dr. Amanda Williams
3517 | ST-2025-035 | United States | S0009 | UNIT-General Hospital | -1 | -1 | 100 | -0.1 | ENROLLING | Dr. Robert Garcia | Dr. Amanda White
3518 | ST-2025-035 | United States | S0010 | UNIT-Clinical Center | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Jessica Moore | Dr. Nicole Davis
3519 | ST-2025-035 | United States | S0011 | UNIT-Clinical Center | 3 | 4 | 133.3 | 0.3 | ENROLLING | Dr. Charles Brown | Dr. Emily Jackson
3520 | ST-2025-035 | Sweden | S0012 | SWED-Health System | -10 | -10 | 100 | -1 | SCREENING | Dr. Amanda Brown | Dr. Thomas Thompson
3521 | ST-2025-035 | Sweden | S0013 | SWED-Health System | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Lisa Jackson | Dr. Nicole Harris
3522 | ST-2025-035 | Sweden | S0014 | SWED-Research Institute | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Jennifer Jackson | Dr. Jessica Smith
3523 | ST-2025-035 | Sweden | S0015 | SWED-Health System | 3 | 3 | 100 | 0.3 | SCREENING | Dr. Jennifer Brown | Dr. Charles White
3524 | ST-2025-035 | Sweden | S0016 | SWED-Clinical Center | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. James Davis | Dr. Robert Thompson
3525 | ST-2025-035 | Sweden | S0017 | SWED-Medical Center | 3 | 5 | 166.7 | 0.3 | ON_HOLD | Dr. Stephanie Smith | Dr. Thomas Davis
3526 | ST-2025-035 | Netherlands | S0018 | NETH-Clinical Center | -4 | -4 | 100 | -0.3 | CLOSED | Dr. David Garcia | Dr. Christopher Thomas
3527 | ST-2025-035 | Netherlands | S0019 | NETH-General Hospital | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Nicole Miller | Dr. Thomas Jones
3528 | ST-2025-035 | Netherlands | S0020 | NETH-Research Institute | 3 | 3 | 100 | 0.4 | SCREENING | Dr. David Harris | Dr. Christopher Davis
3529 | ST-2025-035 | Netherlands | S0021 | NETH-General Hospital | 3 | 2 | 66.7 | 0.1 | ON_HOLD | Dr. Lisa Garcia | Dr. Christopher Thompson
3530 | ST-2025-035 | Italy | S0022 | ITAL-University Hospital | -1 | -1 | 100 | -0.1 | SCREENING | Dr. Michael Smith | Dr. Sarah White
3531 | ST-2025-035 | Italy | S0023 | ITAL-Cancer Center | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. Charles Williams | Dr. Stephanie Wilson
3532 | ST-2025-035 | Italy | S0024 | ITAL-General Hospital | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. Michelle Smith | Dr. Christopher Martin
3533 | ST-2025-035 | Germany | S0025 | GERM-Clinical Center | -7 | -7 | 100 | -0.6 | ENROLLING | Dr. Emily Jones | Dr. William Brown
3534 | ST-2025-035 | Germany | S0026 | GERM-General Hospital | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Stephanie Taylor | Dr. Robert Davis
3535 | ST-2025-035 | Germany | S0027 | GERM-Cancer Center | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. William Brown | Dr. Thomas Williams
3536 | ST-2025-035 | Germany | S0028 | GERM-Clinical Center | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Lisa Wilson | Dr. Thomas Anderson
3537 | ST-2025-035 | Germany | S0029 | GERM-General Hospital | 3 | 5 | 166.7 | 0.4 | ENROLLING | Dr. Christopher Wilson | Dr. William Johnson
3538 | ST-2025-035 | Australia | S0030 | AUST-General Hospital | -4 | -4 | 100 | -0.5 | CLOSED | Dr. Jessica Martin | Dr. Christopher Anderson
3539 | ST-2025-035 | Australia | S0031 | AUST-University Hospital | 3 | 2 | 66.7 | 0.1 | CLOSED | Dr. Robert Jones | Dr. Jessica Jackson
3540 | ST-2025-035 | Australia | S0032 | AUST-Research Institute | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. James Miller | Dr. Jessica Jones
3541 | ST-2025-035 | Australia | S0033 | AUST-Health System | 3 | 2 | 66.7 | 0.3 | ON_HOLD | Dr. Amanda Thompson | Dr. Daniel Jackson
3542 | ST-2025-036 | Mexico | S0001 | MEXI-General Hospital | 16 | 15 | 93.8 | 1 | ENROLLING | Dr. David Jones | Dr. David Anderson
3543 | ST-2025-036 | Mexico | S0002 | MEXI-University Hospital | 12 | 12 | 100 | 1.7 | ENROLLING | Dr. Michelle Johnson | Dr. Robert Moore
3544 | ST-2025-036 | Mexico | S0003 | MEXI-Research Institute | 20 | 18 | 90 | 2.6 | ENROLLING | Dr. Thomas Davis | Dr. David Miller
3545 | ST-2025-036 | Mexico | S0004 | MEXI-Research Institute | 14 | 11 | 78.6 | 1.4 | ENROLLING | Dr. William Davis | Dr. David Thomas
3546 | ST-2025-036 | Mexico | S0005 | MEXI-Medical Center | 16 | 22 | 137.5 | 2.8 | ENROLLING | Dr. Emily Jackson | Dr. James Harris
3547 | ST-2025-036 | United States | S0006 | UNIT-Medical Center | 48 | 34 | 70.8 | 2.6 | ENROLLING | Dr. Charles Miller | Dr. David Jackson
3548 | ST-2025-036 | United States | S0007 | UNIT-Health System | 47 | 61 | 129.8 | 8.7 | ENROLLING | Dr. Jennifer Thompson | Dr. Daniel Brown
3549 | ST-2025-036 | Poland | S0008 | POLA-Health System | 12 | 10 | 83.3 | 1.4 | ENROLLING | Dr. James Smith | Dr. Charles White
3550 | ST-2025-036 | Poland | S0009 | POLA-Clinical Center | 10 | 7 | 70 | 1 | ENROLLING | Dr. Amanda Anderson | Dr. Michael White
3551 | ST-2025-036 | Poland | S0010 | POLA-Cancer Center | 22 | 14 | 63.6 | 0.9 | ENROLLING | Dr. Lisa Williams | Dr. Charles Martin
3552 | ST-2025-036 | Poland | S0011 | POLA-Medical Center | 19 | 17 | 89.5 | 1.7 | SCREENING | Dr. Thomas Johnson | Dr. Robert Davis
3553 | ST-2025-036 | Poland | S0012 | POLA-University Hospital | 13 | 11 | 84.6 | 0.7 | ENROLLING | Dr. Robert Thompson | Dr. Robert Jones
3554 | ST-2025-036 | Poland | S0013 | POLA-General Hospital | 23 | 40 | 173.9 | 3.1 | ENROLLING | Dr. Sarah Miller | Dr. Jessica Thomas
3555 | ST-2025-036 | United Kingdom | S0014 | UNIT-Medical Center | 12 | 8 | 66.7 | 0.4 | ENROLLING | Dr. James Martin | Dr. David Anderson
3556 | ST-2025-036 | United Kingdom | S0015 | UNIT-Clinical Center | 11 | 11 | 100 | 0.7 | SCREENING | Dr. William Taylor | Dr. James Smith
3557 | ST-2025-036 | United Kingdom | S0016 | UNIT-Research Institute | 7 | 7 | 100 | 1.2 | SCREENING | Dr. Sarah Jones | Dr. Stephanie Johnson
3558 | ST-2025-036 | United Kingdom | S0017 | UNIT-Health System | 5 | 4 | 80 | 0.3 | ON_HOLD | Dr. Daniel Garcia | Dr. Jennifer Brown
3559 | ST-2025-036 | United Kingdom | S0018 | UNIT-Medical Center | 8 | 7 | 87.5 | 0.6 | ENROLLING | Dr. Michael White | Dr. Michael Brown
3560 | ST-2025-036 | Switzerland | S0019 | SWIT-Research Institute | 24 | 24 | 100 | 1.5 | ON_HOLD | Dr. Amanda Brown | Dr. Nicole Martin
3561 | ST-2025-036 | Switzerland | S0020 | SWIT-General Hospital | 14 | 8 | 57.1 | 0.5 | ENROLLING | Dr. Robert Davis | Dr. Daniel Jones
3562 | ST-2025-036 | Switzerland | S0021 | SWIT-Cancer Center | 13 | 11 | 84.6 | 1.4 | ENROLLING | Dr. Michael Brown | Dr. Charles Anderson
3563 | ST-2025-036 | Switzerland | S0022 | SWIT-Health System | 20 | 20 | 100 | 2.9 | ENROLLING | Dr. Lisa Wilson | Dr. Jennifer Anderson
3564 | ST-2025-036 | Switzerland | S0023 | SWIT-Research Institute | 13 | 9 | 69.2 | 0.5 | SCREENING | Dr. Daniel Thompson | Dr. William Jones
3565 | ST-2025-036 | Switzerland | S0024 | SWIT-Research Institute | 20 | 12 | 60 | 1 | SCREENING | Dr. Robert Johnson | Dr. Charles Johnson
3566 | ST-2025-036 | Australia | S0025 | AUST-University Hospital | 33 | 20 | 60.6 | 2.5 | ON_HOLD | Dr. Thomas Smith | Dr. Nicole Martin
3567 | ST-2025-036 | Australia | S0026 | AUST-Cancer Center | 36 | 0 | 0 | 0 | SCREENING | Dr. Charles Harris | Dr. David Harris
3568 | ST-2025-036 | Australia | S0027 | AUST-Health System | 12 | 0 | 0 | 0 | CLOSED | Dr. Christopher Brown | Dr. William Thompson
3569 | ST-2025-037 | Mexico | S0001 | MEXI-General Hospital | 276 | 0 | 0 | 0 | SCREENING | Dr. Michael Williams | Dr. Charles Wilson
3570 | ST-2025-037 | Mexico | S0002 | MEXI-University Hospital | 318 | 0 | 0 | 0 | ON_HOLD | Dr. Michelle Thomas | Dr. Charles Jones
3571 | ST-2025-037 | Mexico | S0003 | MEXI-Clinical Center | 179 | 0 | 0 | 0 | CLOSED | Dr. Jessica Williams | Dr. Thomas Davis
3572 | ST-2025-037 | Mexico | S0004 | MEXI-Clinical Center | 133 | 0 | 0 | 0 | SCREENING | Dr. Michelle Jones | Dr. William Smith
3573 | ST-2025-037 | Mexico | S0005 | MEXI-Clinical Center | 235 | 0 | 0 | 0 | CLOSED | Dr. Lisa Davis | Dr. Lisa Harris
3574 | ST-2025-037 | Mexico | S0006 | MEXI-General Hospital | 307 | 0 | 0 | 0 | SCREENING | Dr. Robert Smith | Dr. Jessica Davis
3575 | ST-2025-037 | United States | S0007 | UNIT-University Hospital | 422 | 0 | 0 | 0 | CLOSED | Dr. Charles Jackson | Dr. William Thomas
3576 | ST-2025-037 | United States | S0008 | UNIT-Cancer Center | 389 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Thomas | Dr. Amanda Davis
3577 | ST-2025-037 | United States | S0009 | UNIT-Research Institute | 282 | 0 | 0 | 0 | ON_HOLD | Dr. Michael Jones | Dr. Thomas Davis
3578 | ST-2025-037 | United States | S0010 | UNIT-Cancer Center | 269 | 0 | 0 | 0 | CLOSED | Dr. Robert Brown | Dr. Daniel Martin
3579 | ST-2025-037 | Canada | S0011 | CANA-University Hospital | 945 | 0 | 0 | 0 | ON_HOLD | Dr. Michelle Davis | Dr. Christopher Wilson
3580 | ST-2025-037 | Canada | S0012 | CANA-Health System | 551 | 0 | 0 | 0 | ON_HOLD | Dr. Christopher Martin | Dr. Stephanie Williams
3581 | ST-2025-037 | Denmark | S0013 | DENM-Research Institute | 382 | 0 | 0 | 0 | CLOSED | Dr. Robert Williams | Dr. Amanda Williams
3582 | ST-2025-037 | Denmark | S0014 | DENM-General Hospital | 176 | 0 | 0 | 0 | CLOSED | Dr. William Smith | Dr. Nicole White
3583 | ST-2025-037 | Denmark | S0015 | DENM-General Hospital | 277 | 0 | 0 | 0 | SCREENING | Dr. Charles Miller | Dr. Christopher Anderson
3584 | ST-2025-037 | Netherlands | S0016 | NETH-Health System | 686 | 0 | 0 | 0 | CLOSED | Dr. Stephanie Jones | Dr. Michelle Taylor
3585 | ST-2025-037 | Netherlands | S0017 | NETH-Cancer Center | 775 | 0 | 0 | 0 | CLOSED | Dr. Sarah Thomas | Dr. Emily Williams
3586 | ST-2025-037 | United Kingdom | S0018 | UNIT-Medical Center | 163 | 0 | 0 | 0 | SCREENING | Dr. Emily Jackson | Dr. Charles White
3587 | ST-2025-037 | United Kingdom | S0019 | UNIT-Clinical Center | 149 | 0 | 0 | 0 | ON_HOLD | Dr. Robert Taylor | Dr. Jennifer Brown
3588 | ST-2025-037 | United Kingdom | S0020 | UNIT-Research Institute | 178 | 0 | 0 | 0 | SCREENING | Dr. Stephanie Wilson | Dr. Nicole Williams
3589 | ST-2025-037 | United Kingdom | S0021 | UNIT-University Hospital | 178 | 0 | 0 | 0 | ON_HOLD | Dr. David Davis | Dr. Amanda Williams
3590 | ST-2025-037 | United Kingdom | S0022 | UNIT-Research Institute | 108 | 0 | 0 | 0 | SCREENING | Dr. Daniel Wilson | Dr. James Johnson
3591 | ST-2025-037 | United Kingdom | S0023 | UNIT-Health System | 159 | 0 | 0 | 0 | CLOSED | Dr. Amanda Brown | Dr. Jennifer Smith
3592 | ST-2025-037 | Italy | S0024 | ITAL-Health System | 799 | 0 | 0 | 0 | ON_HOLD | Dr. Michael Garcia | Dr. David Martin
3593 | ST-2025-037 | Italy | S0025 | ITAL-University Hospital | 560 | 0 | 0 | 0 | SCREENING | Dr. Amanda Brown | Dr. Robert Thomas
3594 | ST-2025-037 | Italy | S0026 | ITAL-Health System | 274 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Thompson | Dr. Robert Harris
3595 | ST-2025-037 | Taiwan | S0027 | TAIW-Research Institute | 125 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Thompson | Dr. Jennifer Brown
3596 | ST-2025-037 | Taiwan | S0028 | TAIW-Clinical Center | 125 | 0 | 0 | 0 | CLOSED | Dr. Robert Taylor | Dr. Christopher Moore
3597 | ST-2025-037 | Taiwan | S0029 | TAIW-Cancer Center | 241 | 0 | 0 | 0 | ON_HOLD | Dr. Emily Moore | Dr. Michael Taylor
3598 | ST-2025-037 | Taiwan | S0030 | TAIW-University Hospital | 339 | 0 | 0 | 0 | SCREENING | Dr. Lisa Martin | Dr. David Jackson

## Performance Drivers
id | study_id | driver_type | entity_type | entity_id | entity_name | gap_to_target | percent_above_target | rank
418 | ST-2024-002 | UNDERPERFORMING | COUNTRY | Poland | Poland | -43 | -100 | 1
419 | ST-2024-002 | UNDERPERFORMING | COUNTRY | Netherlands | Netherlands | -41 | -100 | 2
420 | ST-2024-002 | UNDERPERFORMING | COUNTRY | New Zealand | New Zealand | -25 | -100 | 3
421 | ST-2024-003 | UNDERPERFORMING | COUNTRY | France | France | -18 | -100 | 1
422 | ST-2024-003 | UNDERPERFORMING | COUNTRY | Sweden | Sweden | -29 | -100 | 2
423 | ST-2024-003 | UNDERPERFORMING | COUNTRY | New Zealand | New Zealand | -22 | -100 | 3
424 | ST-2024-004 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -13 | -100 | 1
425 | ST-2024-004 | UNDERPERFORMING | COUNTRY | Norway | Norway | -30 | -100 | 2
426 | ST-2024-004 | UNDERPERFORMING | COUNTRY | Belgium | Belgium | -17 | -100 | 3
427 | ST-2024-005 | UNDERPERFORMING | COUNTRY | China | China | -16 | -100 | 1
428 | ST-2024-005 | UNDERPERFORMING | COUNTRY | New Zealand | New Zealand | -7 | -46.7 | 2
429 | ST-2024-005 | UNDERPERFORMING | COUNTRY | Denmark | Denmark | -5 | -25 | 3
430 | ST-2024-006 | UNDERPERFORMING | COUNTRY | South Korea | South Korea | -7 | -50 | 1
431 | ST-2024-006 | UNDERPERFORMING | COUNTRY | Switzerland | Switzerland | -6 | -22.2 | 2
432 | ST-2024-006 | UNDERPERFORMING | COUNTRY | United Kingdom | United Kingdom | -2 | -16.7 | 3
433 | ST-2024-007 | UNDERPERFORMING | COUNTRY | Canada | Canada | -8 | -100 | 1
434 | ST-2024-007 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -9 | -100 | 2
435 | ST-2024-007 | UNDERPERFORMING | COUNTRY | Spain | Spain | -6 | -100 | 3
436 | ST-2024-008 | UNDERPERFORMING | COUNTRY | Sweden | Sweden | -7 | -31.8 | 1
437 | ST-2024-008 | UNDERPERFORMING | COUNTRY | United States | United States | -2 | -10.5 | 2
438 | ST-2024-009 | UNDERPERFORMING | COUNTRY | United States | United States | -75 | -100 | 1
439 | ST-2024-009 | UNDERPERFORMING | COUNTRY | Sweden | Sweden | -35 | -100 | 2
440 | ST-2024-009 | UNDERPERFORMING | COUNTRY | Norway | Norway | -77 | -100 | 3
441 | ST-2024-010 | UNDERPERFORMING | COUNTRY | Australia | Australia | -1136 | -100 | 1
442 | ST-2024-010 | UNDERPERFORMING | COUNTRY | United Kingdom | United Kingdom | -1292 | -49.5 | 2
443 | ST-2024-010 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -92 | -7.3 | 3
444 | ST-2024-011 | UNDERPERFORMING | COUNTRY | France | France | -38 | -100 | 1
445 | ST-2024-011 | UNDERPERFORMING | COUNTRY | Singapore | Singapore | -52 | -100 | 2
446 | ST-2024-011 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -23 | -100 | 3
447 | ST-2024-012 | UNDERPERFORMING | COUNTRY | Singapore | Singapore | -5 | -100 | 1
448 | ST-2024-012 | UNDERPERFORMING | COUNTRY | Chile | Chile | -5 | -100 | 2
449 | ST-2024-012 | UNDERPERFORMING | COUNTRY | Norway | Norway | -3 | -50 | 3
450 | ST-2024-013 | UNDERPERFORMING | COUNTRY | Chile | Chile | -5 | -100 | 1
451 | ST-2024-013 | UNDERPERFORMING | COUNTRY | South Korea | South Korea | -4 | -80 | 2
452 | ST-2024-014 | UNDERPERFORMING | COUNTRY | Netherlands | Netherlands | -5 | -100 | 1
453 | ST-2024-014 | UNDERPERFORMING | COUNTRY | Denmark | Denmark | -5 | -100 | 2
454 | ST-2024-014 | UNDERPERFORMING | COUNTRY | Taiwan | Taiwan | -5 | -100 | 3
455 | ST-2024-015 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -13 | -100 | 1
456 | ST-2024-015 | UNDERPERFORMING | COUNTRY | Sweden | Sweden | -31 | -100 | 2
457 | ST-2024-015 | UNDERPERFORMING | COUNTRY | Norway | Norway | -22 | -100 | 3
458 | ST-2024-016 | UNDERPERFORMING | COUNTRY | Belgium | Belgium | -11 | -100 | 1
459 | ST-2024-016 | UNDERPERFORMING | COUNTRY | Australia | Australia | -17 | -100 | 2
460 | ST-2024-016 | UNDERPERFORMING | COUNTRY | Poland | Poland | -11 | -64.7 | 3
461 | ST-2024-017 | UNDERPERFORMING | COUNTRY | Spain | Spain | -12 | -100 | 1
462 | ST-2024-017 | UNDERPERFORMING | COUNTRY | China | China | -25 | -100 | 2
463 | ST-2024-017 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -15 | -65.2 | 3
464 | ST-2024-019 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -39 | -100 | 1
465 | ST-2024-019 | UNDERPERFORMING | COUNTRY | United States | United States | -69 | -100 | 2
466 | ST-2024-019 | UNDERPERFORMING | COUNTRY | Poland | Poland | -55 | -100 | 3
467 | ST-2024-020 | UNDERPERFORMING | COUNTRY | Canada | Canada | 0 | -100 | 1
468 | ST-2024-020 | UNDERPERFORMING | COUNTRY | Netherlands | Netherlands | -2 | -40 | 2
469 | ST-2024-020 | UNDERPERFORMING | COUNTRY | Japan | Japan | -1 | -20 | 3
470 | ST-2025-021 | UNDERPERFORMING | COUNTRY | Belgium | Belgium | -3 | -9.1 | 1
471 | ST-2025-021 | OVERPERFORMING | COUNTRY | Australia | Australia | 3 | 10.3 | 1
472 | ST-2025-022 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -3 | -33.3 | 1
473 | ST-2025-022 | UNDERPERFORMING | COUNTRY | Poland | Poland | -3 | -30 | 2
474 | ST-2025-022 | UNDERPERFORMING | COUNTRY | China | China | -3 | -27.3 | 3
475 | ST-2025-022 | OVERPERFORMING | COUNTRY | Chile | Chile | 12 | 109.1 | 1
476 | ST-2025-023 | UNDERPERFORMING | COUNTRY | Poland | Poland | -84 | -26.8 | 1
477 | ST-2025-023 | UNDERPERFORMING | COUNTRY | Canada | Canada | -37 | -20 | 2
478 | ST-2025-023 | UNDERPERFORMING | COUNTRY | Italy | Italy | -41 | -19.9 | 3
479 | ST-2025-024 | UNDERPERFORMING | COUNTRY | Switzerland | Switzerland | -33 | -100 | 1
480 | ST-2025-024 | UNDERPERFORMING | COUNTRY | Japan | Japan | -30 | -100 | 2
481 | ST-2025-024 | UNDERPERFORMING | COUNTRY | Sweden | Sweden | -29 | -46.8 | 3
482 | ST-2025-025 | UNDERPERFORMING | COUNTRY | Spain | Spain | -2 | -40 | 1
483 | ST-2025-025 | UNDERPERFORMING | COUNTRY | Sweden | Sweden | -2 | -40 | 2
484 | ST-2025-025 | UNDERPERFORMING | COUNTRY | Netherlands | Netherlands | -2 | -40 | 3
485 | ST-2025-025 | OVERPERFORMING | COUNTRY | Chile | Chile | 2 | 40 | 1
486 | ST-2025-026 | UNDERPERFORMING | COUNTRY | New Zealand | New Zealand | -67 | -100 | 1
487 | ST-2025-026 | UNDERPERFORMING | COUNTRY | Singapore | Singapore | -29 | -63 | 2
488 | ST-2025-026 | UNDERPERFORMING | COUNTRY | Switzerland | Switzerland | -13 | -30.2 | 3
489 | ST-2025-027 | UNDERPERFORMING | COUNTRY | United States | United States | -3 | -33.3 | 1
490 | ST-2025-027 | UNDERPERFORMING | COUNTRY | United Kingdom | United Kingdom | -4 | -33.3 | 2
491 | ST-2025-027 | UNDERPERFORMING | COUNTRY | India | India | -3 | -30 | 3
492 | ST-2025-027 | OVERPERFORMING | COUNTRY | Singapore | Singapore | 10 | 142.9 | 1
493 | ST-2025-028 | UNDERPERFORMING | COUNTRY | Denmark | Denmark | -31608 | -100 | 1
494 | ST-2025-028 | UNDERPERFORMING | COUNTRY | Australia | Australia | -15361 | -100 | 2
495 | ST-2025-028 | UNDERPERFORMING | COUNTRY | Canada | Canada | -15803 | -75.1 | 3
496 | ST-2025-029 | UNDERPERFORMING | COUNTRY | India | India | -42 | -100 | 1
497 | ST-2025-029 | UNDERPERFORMING | COUNTRY | Australia | Australia | -25 | -73.5 | 2
498 | ST-2025-029 | UNDERPERFORMING | COUNTRY | United States | United States | -5 | -25 | 3
499 | ST-2025-030 | UNDERPERFORMING | COUNTRY | Japan | Japan | -172 | -100 | 1
500 | ST-2025-030 | UNDERPERFORMING | COUNTRY | China | China | -103 | -61.7 | 2
501 | ST-2025-030 | UNDERPERFORMING | COUNTRY | Poland | Poland | -54 | -28.4 | 3
502 | ST-2025-031 | UNDERPERFORMING | COUNTRY | Canada | Canada | -10 | -100 | 1
503 | ST-2025-031 | UNDERPERFORMING | COUNTRY | United States | United States | -7 | -100 | 2
504 | ST-2025-031 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -5 | -100 | 3
505 | ST-2025-032 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -82 | -100 | 1
506 | ST-2025-032 | UNDERPERFORMING | COUNTRY | United Kingdom | United Kingdom | -48 | -100 | 2
507 | ST-2025-032 | UNDERPERFORMING | COUNTRY | Norway | Norway | -52 | -100 | 3
508 | ST-2025-033 | UNDERPERFORMING | COUNTRY | Switzerland | Switzerland | -2 | -40 | 1
509 | ST-2025-033 | UNDERPERFORMING | COUNTRY | Poland | Poland | -1 | -20 | 2
510 | ST-2025-034 | UNDERPERFORMING | COUNTRY | France | France | -2 | -33.3 | 1
511 | ST-2025-034 | UNDERPERFORMING | COUNTRY | Canada | Canada | -1 | -12.5 | 2
512 | ST-2025-035 | UNDERPERFORMING | COUNTRY | Australia | Australia | -3 | -60 | 1
513 | ST-2025-035 | UNDERPERFORMING | COUNTRY | Netherlands | Netherlands | -2 | -40 | 2
514 | ST-2025-035 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -1 | -20 | 3
515 | ST-2025-036 | UNDERPERFORMING | COUNTRY | Australia | Australia | -61 | -75.3 | 1
516 | ST-2025-036 | UNDERPERFORMING | COUNTRY | Switzerland | Switzerland | -20 | -19.2 | 2
517 | ST-2025-036 | UNDERPERFORMING | COUNTRY | United Kingdom | United Kingdom | -6 | -14 | 3
518 | ST-2025-037 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -1448 | -100 | 1
519 | ST-2025-037 | UNDERPERFORMING | COUNTRY | United States | United States | -1362 | -100 | 2
520 | ST-2025-037 | UNDERPERFORMING | COUNTRY | Canada | Canada | -1496 | -100 | 3

## Site Detail
id | site_id | site_name | study_id | enrollment_history | site_status | target_enrollment | actual_enrollment | enrollment_percent | current_rate | principal_investigator | site_coordinator
2847 | S0001 | UNIT-Medical Center | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 5 | 4 | 80 | 0.4 | Dr. Sarah Taylor | Dr. Michael Thompson
2848 | S0002 | UNIT-University Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | CLOSED | 4 | 3 | 75 | 0.3 | Dr. Nicole Miller | Dr. Michelle Jones
2849 | S0003 | UNIT-General Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 3 | 1 | 33.3 | 0.1 | Dr. Nicole Davis | Dr. Nicole White
2850 | S0004 | UNIT-University Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | SCREENING | 3 | 3 | 100 | 0.4 | Dr. Stephanie Thomas | Dr. Stephanie White
2851 | S0005 | UNIT-Clinical Center | ST-2024-002 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Emily Johnson | Dr. Charles Taylor
2852 | S0006 | MEXI-University Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 2, 'cumulative': 5}, {'month': 3, 'enrolled': 2, 'cumulative': 7}, {'month': 4, 'enrolled': 1, 'cumulative': 8}, {'month': 5, 'enrolled': 3, 'cumulative': 11}, {'month': 6, 'enrolled': 5, 'cumulative': 16}] | SCREENING | 23 | 21 | 91.3 | 2.1 | Dr. Lisa Williams | Dr. Christopher Moore
2853 | S0007 | MEXI-Medical Center | ST-2024-002 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 3, 'cumulative': 5}, {'month': 3, 'enrolled': 0, 'cumulative': 5}, {'month': 4, 'enrolled': 0, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 10 | 6 | 60 | 1 | Dr. Michelle Smith | Dr. Michael Davis
2854 | S0008 | MEXI-University Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 0, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 3, 'cumulative': 9}, {'month': 6, 'enrolled': 1, 'cumulative': 10}] | SCREENING | 11 | 14 | 127.3 | 1.2 | Dr. Nicole Miller | Dr. Charles Johnson
2855 | S0009 | POLA-Research Institute | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | CLOSED | 15 | 0 | 0 | 0 | Dr. Michelle Martin | Dr. Robert Miller
2856 | S0010 | POLA-Research Institute | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 10 | 0 | 0 | 0 | Dr. Michelle Johnson | Dr. Thomas Johnson
2857 | S0011 | POLA-Medical Center | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 18 | 0 | 0 | 0 | Dr. Daniel Thompson | Dr. Jennifer Johnson
2858 | S0012 | NETH-University Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | SCREENING | 23 | 0 | 0 | 0 | Dr. Lisa Johnson | Dr. Michael White
2859 | S0013 | NETH-General Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 2, 'cumulative': 2}] | CLOSED | 8 | 0 | 0 | 0 | Dr. Daniel Taylor | Dr. William Miller
2860 | S0014 | NETH-General Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 10 | 0 | 0 | 0 | Dr. Lisa Wilson | Dr. Charles Jones
2861 | S0015 | NEW-University Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | ON_HOLD | 8 | 0 | 0 | 0 | Dr. Robert Thomas | Dr. Michael Davis
2862 | S0016 | NEW-Research Institute | ST-2024-002 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 4 | 0 | 0 | 0 | Dr. Christopher Moore | Dr. Jessica Thompson
2863 | S0017 | NEW-Medical Center | ST-2024-002 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 4 | 0 | 0 | 0 | Dr. Jessica Brown | Dr. Robert Wilson
2864 | S0018 | NEW-Medical Center | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 6 | 0 | 0 | 0 | Dr. Michelle Jones | Dr. William Anderson
2865 | S0019 | NEW-Health System | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Thomas Miller | Dr. William Thompson
2866 | S0001 | CANA-Cancer Center | ST-2024-003 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 0, 'cumulative': 3}, {'month': 3, 'enrolled': 4, 'cumulative': 7}, {'month': 4, 'enrolled': 0, 'cumulative': 7}, {'month': 5, 'enrolled': 1, 'cumulative': 8}, {'month': 6, 'enrolled': 1, 'cumulative': 9}] | ON_HOLD | 20 | 16 | 80 | 1.3 | Dr. Michelle Davis | Dr. Nicole Davis
2867 | S0002 | CANA-Research Institute | ST-2024-003 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 1, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 3, 'cumulative': 7}] | SCREENING | 11 | 11 | 100 | 0.9 | Dr. James Jackson | Dr. Thomas Jackson
2868 | S0003 | MEXI-Clinical Center | ST-2024-003 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 3, 'cumulative': 5}, {'month': 3, 'enrolled': 3, 'cumulative': 8}, {'month': 4, 'enrolled': 3, 'cumulative': 11}, {'month': 5, 'enrolled': 0, 'cumulative': 11}, {'month': 6, 'enrolled': 3, 'cumulative': 14}] | ON_HOLD | 8 | 8 | 100 | 1 | Dr. Jennifer Johnson | Dr. William Jackson
2869 | S0004 | MEXI-Research Institute | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | ON_HOLD | 6 | 5 | 83.3 | 0.6 | Dr. Thomas Taylor | Dr. Charles Wilson
2870 | S0005 | MEXI-Cancer Center | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ON_HOLD | 6 | 3 | 50 | 0.2 | Dr. Michael Martin | Dr. James Moore
2871 | S0006 | MEXI-Medical Center | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 7 | 0 | 0 | 0 | Dr. Michael Johnson | Dr. James Davis
2872 | S0007 | MEXI-University Hospital | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | CLOSED | 4 | 0 | 0 | 0 | Dr. Robert Davis | Dr. Robert Martin
2873 | S0008 | FRAN-General Hospital | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 10 | 0 | 0 | 0 | Dr. Jennifer Brown | Dr. Jennifer Anderson
2874 | S0009 | FRAN-Medical Center | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 8 | 0 | 0 | 0 | Dr. Jessica Jackson | Dr. Charles Miller
2875 | S0010 | SWED-Clinical Center | ST-2024-003 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 4 | 0 | 0 | 0 | Dr. Michael Thompson | Dr. Thomas Smith
2876 | S0011 | SWED-Cancer Center | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | 5 | 0 | 0 | 0 | Dr. Emily White | Dr. Amanda Harris
2877 | S0012 | SWED-General Hospital | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 5 | 0 | 0 | 0 | Dr. Jennifer Thompson | Dr. William Moore
2878 | S0013 | SWED-Cancer Center | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Stephanie Wilson | Dr. Thomas Davis
2879 | S0014 | SWED-Cancer Center | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ON_HOLD | 6 | 0 | 0 | 0 | Dr. Christopher Davis | Dr. Christopher Jackson
2880 | S0015 | SWED-Research Institute | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 6 | 0 | 0 | 0 | Dr. Thomas Garcia | Dr. Nicole Miller
2881 | S0016 | NEW-Health System | ST-2024-003 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | CLOSED | 9 | 0 | 0 | 0 | Dr. David Williams | Dr. Lisa White
2882 | S0017 | NEW-Clinical Center | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 6 | 0 | 0 | 0 | Dr. Nicole Martin | Dr. Christopher Smith
2883 | S0018 | NEW-Medical Center | ST-2024-003 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 7 | 0 | 0 | 0 | Dr. Charles Davis | Dr. Jessica Thomas
2884 | S0019 | SOUT-Health System | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 2 | 0 | 0 | 0 | Dr. Jennifer Miller | Dr. David Martin
2885 | S0020 | SOUT-Research Institute | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Daniel Anderson | Dr. Emily Miller
2886 | S0021 | SOUT-Research Institute | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Jennifer Anderson | Dr. James Moore
2887 | S0022 | SOUT-University Hospital | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Sarah Moore | Dr. Jessica Jones
2888 | S0023 | SOUT-General Hospital | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Emily Smith | Dr. Jessica Martin
2889 | S0024 | SOUT-Clinical Center | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Jennifer Johnson | Dr. William Martin
2890 | S0001 | CANA-Cancer Center | ST-2024-004 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 6 | 4 | 66.7 | 0.5 | Dr. Jennifer Williams | Dr. Charles Davis
2891 | S0002 | CANA-Clinical Center | ST-2024-004 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 3, 'cumulative': 6}, {'month': 3, 'enrolled': 0, 'cumulative': 6}, {'month': 4, 'enrolled': 2, 'cumulative': 8}, {'month': 5, 'enrolled': 3, 'cumulative': 11}, {'month': 6, 'enrolled': 0, 'cumulative': 11}] | SCREENING | 12 | 11 | 91.7 | 0.7 | Dr. Lisa Harris | Dr. William Harris
2892 | S0003 | CANA-Research Institute | ST-2024-004 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 0, 'cumulative': 3}, {'month': 3, 'enrolled': 3, 'cumulative': 6}, {'month': 4, 'enrolled': 1, 'cumulative': 7}, {'month': 5, 'enrolled': 2, 'cumulative': 9}, {'month': 6, 'enrolled': 0, 'cumulative': 9}] | SCREENING | 7 | 6 | 85.7 | 0.4 | Dr. Christopher Anderson | Dr. Michelle Garcia
2893 | S0004 | CANA-Medical Center | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 8 | 2 | 25 | 0.2 | Dr. Jessica White | Dr. William Harris
2894 | S0005 | MEXI-General Hospital | ST-2024-004 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 4 | 0 | 0 | 0 | Dr. Charles Wilson | Dr. James Johnson
2895 | S0006 | MEXI-Health System | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Jessica Davis | Dr. Amanda Davis
2896 | S0007 | MEXI-General Hospital | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | CLOSED | 3 | 0 | 0 | 0 | Dr. William Jones | Dr. Emily Johnson
2897 | S0008 | MEXI-Research Institute | ST-2024-004 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 1, 'cumulative': 5}, {'month': 4, 'enrolled': 0, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 2, 'cumulative': 7}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Sarah Thomas | Dr. Robert Williams
2898 | S0009 | NORW-Health System | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 12 | 0 | 0 | 0 | Dr. William Martin | Dr. Jessica Taylor
2899 | S0010 | NORW-Cancer Center | ST-2024-004 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 6 | 0 | 0 | 0 | Dr. Michael Jones | Dr. Lisa Jackson
2900 | S0011 | NORW-Cancer Center | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 7 | 0 | 0 | 0 | Dr. Amanda Williams | Dr. Charles Smith
2901 | S0012 | NORW-Research Institute | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 5 | 0 | 0 | 0 | Dr. Christopher Thomas | Dr. William Jackson
2902 | S0013 | BELG-University Hospital | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | SCREENING | 9 | 0 | 0 | 0 | Dr. Michelle Taylor | Dr. Lisa Williams
2903 | S0014 | BELG-General Hospital | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 8 | 0 | 0 | 0 | Dr. Jessica White | Dr. Emily Jones
2904 | S0015 | DENM-Research Institute | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 1 | 0 | 0 | 0 | Dr. Michelle White | Dr. Robert White
2905 | S0016 | DENM-General Hospital | ST-2024-004 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Stephanie Wilson | Dr. Sarah Thomas
2906 | S0017 | DENM-University Hospital | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 5 | 0 | 0 | 0 | Dr. Lisa Thomas | Dr. Emily Thomas
2907 | S0018 | DENM-Health System | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 2, 'cumulative': 7}, {'month': 6, 'enrolled': 2, 'cumulative': 9}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Sarah Jackson | Dr. William Miller
2908 | S0019 | SOUT-Medical Center | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 15 | 0 | 0 | 0 | Dr. James Johnson | Dr. Thomas Davis
2909 | S0020 | SOUT-University Hospital | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | 13 | 0 | 0 | 0 | Dr. David Williams | Dr. Michelle Miller
2910 | S0021 | CHIN-Health System | ST-2024-004 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 4 | 0 | 0 | 0 | Dr. Robert Jones | Dr. Michelle Wilson
2911 | S0022 | CHIN-Cancer Center | ST-2024-004 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 5 | 0 | 0 | 0 | Dr. James Jones | Dr. James Thomas
2912 | S0023 | CHIN-Cancer Center | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Thomas Smith | Dr. Jennifer Wilson
2913 | S0001 | MEXI-Research Institute | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ENROLLING | 5 | 3 | 60 | 0.2 | Dr. Daniel Garcia | Dr. Sarah Davis
2914 | S0002 | MEXI-General Hospital | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | SCREENING | 4 | 2 | 50 | 0.2 | Dr. Daniel Thompson | Dr. Jennifer Thomas
2915 | S0003 | MEXI-Research Institute | ST-2024-005 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | SCREENING | 4 | 2 | 50 | 0.2 | Dr. Stephanie Taylor | Dr. Sarah Taylor
2916 | S0004 | MEXI-Medical Center | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | 3 | 3 | 100 | 0.3 | Dr. Michelle Jackson | Dr. Jessica Wilson
2917 | S0005 | MEXI-General Hospital | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 3, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 3 | 8 | 266.7 | 0.5 | Dr. Robert Taylor | Dr. Michael Jones
2918 | S0006 | UNIT-General Hospital | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 2 | 1 | 50 | 0.1 | Dr. Daniel Williams | Dr. Stephanie Thompson
2919 | S0007 | UNIT-Research Institute | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ENROLLING | 3 | 2 | 66.7 | 0.3 | Dr. Jessica Garcia | Dr. David Taylor
2920 | S0008 | UNIT-Cancer Center | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Lisa Jones | Dr. Robert Williams
2921 | S0009 | UNIT-Research Institute | ST-2024-005 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 2, 'cumulative': 5}, {'month': 4, 'enrolled': 1, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Daniel Moore | Dr. Daniel Johnson
2922 | S0010 | UNIT-General Hospital | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Robert Jackson | Dr. Robert Garcia
2923 | S0011 | UNIT-University Hospital | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 2, 'cumulative': 7}, {'month': 6, 'enrolled': 2, 'cumulative': 9}] | SCREENING | 3 | 8 | 266.7 | 0.5 | Dr. Jennifer Harris | Dr. Sarah White
2924 | S0012 | FRAN-Health System | ST-2024-005 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 3, 'cumulative': 9}] | ON_HOLD | 6 | 6 | 100 | 0.6 | Dr. Christopher Davis | Dr. Michelle Davis
2925 | S0013 | FRAN-Research Institute | ST-2024-005 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 3, 'cumulative': 8}] | SCREENING | 7 | 6 | 85.7 | 0.3 | Dr. David Thomas | Dr. Christopher Harris
2926 | S0014 | DENM-Clinical Center | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 3, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 10 | 9 | 90 | 1.1 | Dr. Robert Wilson | Dr. Sarah Martin
2927 | S0015 | DENM-Cancer Center | ST-2024-005 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 3, 'cumulative': 8}, {'month': 6, 'enrolled': 2, 'cumulative': 10}] | CLOSED | 10 | 6 | 60 | 0.5 | Dr. Emily Thompson | Dr. Emily Anderson
2928 | S0016 | NEW-Health System | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | ON_HOLD | 8 | 6 | 75 | 0.8 | Dr. Michael Davis | Dr. Christopher Thomas
2929 | S0017 | NEW-Medical Center | ST-2024-005 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 7 | 2 | 28.6 | 0.2 | Dr. Charles Thompson | Dr. Amanda Davis
2930 | S0018 | CHIN-Cancer Center | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 4 | 0 | 0 | 0 | Dr. Robert Martin | Dr. Christopher Smith
2931 | S0019 | CHIN-Medical Center | ST-2024-005 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. David Jones | Dr. Michelle Thompson
2932 | S0020 | CHIN-Clinical Center | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Lisa Anderson | Dr. Emily Johnson
2933 | S0021 | CHIN-University Hospital | ST-2024-005 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Christopher Williams | Dr. Emily Martin
2934 | S0022 | CHIN-Health System | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Daniel Davis | Dr. Robert Anderson
2935 | S0001 | UNIT-General Hospital | ST-2024-006 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 2, 'cumulative': 5}, {'month': 3, 'enrolled': 3, 'cumulative': 8}, {'month': 4, 'enrolled': 1, 'cumulative': 9}, {'month': 5, 'enrolled': 3, 'cumulative': 12}, {'month': 6, 'enrolled': 3, 'cumulative': 15}] | SCREENING | 13 | 8 | 61.5 | 0.4 | Dr. William Miller | Dr. Stephanie Smith
2936 | S0002 | UNIT-Clinical Center | ST-2024-006 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 4 | 9 | 225 | 0.6 | Dr. Jessica Anderson | Dr. Nicole Davis
2937 | S0003 | UNIT-University Hospital | ST-2024-006 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. Robert Taylor | Dr. Thomas Thomas
2938 | S0004 | UNIT-Clinical Center | ST-2024-006 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Daniel Moore | Dr. Emily Taylor
2939 | S0005 | UNIT-University Hospital | ST-2024-006 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. William Harris | Dr. Lisa Jones
2940 | S0006 | UNIT-Medical Center | ST-2024-006 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 3 | 5 | 166.7 | 0.8 | Dr. Charles White | Dr. Lisa Garcia
2941 | S0007 | SWIT-University Hospital | ST-2024-006 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 4, 'cumulative': 7}, {'month': 3, 'enrolled': 2, 'cumulative': 9}, {'month': 4, 'enrolled': 4, 'cumulative': 13}, {'month': 5, 'enrolled': 2, 'cumulative': 15}, {'month': 6, 'enrolled': 4, 'cumulative': 19}] | SCREENING | 13 | 13 | 100 | 0.7 | Dr. Nicole Thompson | Dr. Christopher Martin
2942 | S0008 | SWIT-Research Institute | ST-2024-006 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 3, 'cumulative': 6}, {'month': 3, 'enrolled': 2, 'cumulative': 8}, {'month': 4, 'enrolled': 3, 'cumulative': 11}, {'month': 5, 'enrolled': 1, 'cumulative': 12}, {'month': 6, 'enrolled': 2, 'cumulative': 14}] | SCREENING | 14 | 8 | 57.1 | 0.6 | Dr. Michael Jackson | Dr. Daniel Harris
2943 | S0009 | SOUT-Cancer Center | ST-2024-006 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | CLOSED | 8 | 5 | 62.5 | 0.3 | Dr. Nicole Anderson | Dr. Michelle Smith
2944 | S0010 | SOUT-Cancer Center | ST-2024-006 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.3 | Dr. Robert Wilson | Dr. Amanda Jackson
2945 | S0011 | SOUT-Research Institute | ST-2024-006 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Sarah Moore | Dr. David Thomas
2946 | S0001 | CANA-General Hospital | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | SCREENING | -1 | -1 | 100 | -0.1 | Dr. James Moore | Dr. Jennifer White
2947 | S0002 | CANA-General Hospital | ST-2024-007 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. David Anderson | Dr. Thomas Anderson
2948 | S0003 | CANA-General Hospital | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Lisa Moore | Dr. Sarah Garcia
2949 | S0004 | CANA-Clinical Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 2, 'cumulative': 2}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Charles Martin | Dr. Jennifer Anderson
2950 | S0005 | MEXI-Medical Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 6 | 0 | 0 | 0 | Dr. Christopher Moore | Dr. Daniel Martin
2951 | S0006 | MEXI-University Hospital | ST-2024-007 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. William Miller | Dr. Emily Taylor
2952 | S0007 | SPAI-Cancer Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | -6 | -6 | 100 | -0.4 | Dr. Stephanie Thompson | Dr. Thomas Williams
2953 | S0008 | SPAI-Clinical Center | ST-2024-007 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Jennifer Jones | Dr. Nicole Taylor
2954 | S0009 | SPAI-University Hospital | ST-2024-007 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 3 | 100 | 0.5 | Dr. Charles Davis | Dr. Christopher Wilson
2955 | S0010 | SPAI-Research Institute | ST-2024-007 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 2, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | CLOSED | 3 | 1 | 33.3 | 0.1 | Dr. James Wilson | Dr. Amanda Davis
2956 | S0011 | SPAI-Medical Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Christopher Anderson | Dr. Jennifer Jackson
2957 | S0012 | ITAL-General Hospital | ST-2024-007 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 0 | 0 | 0 | 0 | Dr. Lisa Davis | Dr. Robert Martin
2958 | S0013 | ITAL-University Hospital | ST-2024-007 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Amanda White | Dr. Michelle Martin
2959 | S0014 | ITAL-Cancer Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | CLOSED | 3 | 0 | 0 | 0 | Dr. David Davis | Dr. Michael Thompson
2960 | S0015 | INDI-Medical Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -4 | -4 | 100 | -0.2 | Dr. Nicole Williams | Dr. Daniel Harris
2961 | S0016 | INDI-Cancer Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 2 | 66.7 | 0.3 | Dr. Robert Thompson | Dr. Stephanie Harris
2962 | S0017 | INDI-Health System | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 3 | 2 | 66.7 | 0.3 | Dr. Christopher Anderson | Dr. James Jackson
2963 | S0018 | INDI-Research Institute | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | CLOSED | 3 | 0 | 0 | 0 | Dr. David Williams | Dr. Sarah White
2964 | S0019 | INDI-Research Institute | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Michelle Johnson | Dr. Michael Martin
2965 | S0020 | INDI-Medical Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Jennifer Jones | Dr. Stephanie Thomas
2966 | S0021 | SING-Clinical Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 7 | 0 | 0 | 0 | Dr. Michelle Jones | Dr. Amanda Brown
2967 | S0022 | SING-University Hospital | ST-2024-007 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Daniel Jones | Dr. Lisa Smith
2968 | S0001 | UNIT-General Hospital | ST-2024-008 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 2, 'cumulative': 5}, {'month': 4, 'enrolled': 1, 'cumulative': 6}, {'month': 5, 'enrolled': 2, 'cumulative': 8}, {'month': 6, 'enrolled': 0, 'cumulative': 8}] | ENROLLING | 8 | 7 | 87.5 | 0.6 | Dr. Jessica Garcia | Dr. Lisa Jackson
2969 | S0002 | UNIT-General Hospital | ST-2024-008 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | SCREENING | 4 | 4 | 100 | 0.3 | Dr. Charles Jones | Dr. Michael Thompson
2970 | S0003 | UNIT-General Hospital | ST-2024-008 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | 7 | 6 | 85.7 | 0.5 | Dr. Emily White | Dr. Lisa Williams
2971 | S0004 | SWED-Clinical Center | ST-2024-008 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 3, 'cumulative': 6}, {'month': 4, 'enrolled': 2, 'cumulative': 8}, {'month': 5, 'enrolled': 1, 'cumulative': 9}, {'month': 6, 'enrolled': 2, 'cumulative': 11}] | ON_HOLD | 9 | 9 | 100 | 0.5 | Dr. James Wilson | Dr. Christopher Martin
2972 | S0005 | SWED-University Hospital | ST-2024-008 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 3, 'cumulative': 6}, {'month': 4, 'enrolled': 0, 'cumulative': 6}, {'month': 5, 'enrolled': 1, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | CLOSED | 13 | 6 | 46.2 | 0.5 | Dr. Charles White | Dr. Jennifer Jackson
2973 | S0006 | TAIW-Medical Center | ST-2024-008 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ENROLLING | -6 | -6 | 100 | -0.6 | Dr. Amanda Wilson | Dr. Emily Jones
2974 | S0007 | TAIW-Medical Center | ST-2024-008 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Christopher Moore | Dr. Michelle Thompson
2975 | S0008 | TAIW-Clinical Center | ST-2024-008 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ENROLLING | 3 | 3 | 100 | 0.4 | Dr. Michael Thomas | Dr. Michelle Williams
2976 | S0009 | TAIW-Health System | ST-2024-008 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Charles Smith | Dr. Jessica White
2977 | S0010 | TAIW-Clinical Center | ST-2024-008 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ENROLLING | 3 | 1 | 33.3 | 0.1 | Dr. Michelle Davis | Dr. Daniel Garcia
2978 | S0011 | TAIW-General Hospital | ST-2024-008 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 7 | 233.3 | 0.6 | Dr. Robert Wilson | Dr. Jessica Wilson
2979 | S0001 | CANA-Health System | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 3, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | CLOSED | 13 | 12 | 92.3 | 1.7 | Dr. Jennifer Thomas | Dr. Thomas Miller
2980 | S0002 | CANA-Clinical Center | ST-2024-009 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 17 | 0 | 0 | 0 | Dr. Nicole Thompson | Dr. Thomas Jackson
2981 | S0003 | CANA-Health System | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 18 | 0 | 0 | 0 | Dr. Emily Thomas | Dr. Amanda Harris
2982 | S0004 | UNIT-Health System | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 16 | 0 | 0 | 0 | Dr. Robert Jackson | Dr. Stephanie Garcia
2983 | S0005 | UNIT-Clinical Center | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 16 | 0 | 0 | 0 | Dr. Jennifer Moore | Dr. Jennifer Martin
2984 | S0006 | UNIT-Research Institute | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | SCREENING | 14 | 0 | 0 | 0 | Dr. Thomas Harris | Dr. Sarah Thomas
2985 | S0007 | UNIT-Medical Center | ST-2024-009 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 9 | 0 | 0 | 0 | Dr. David Jackson | Dr. Michelle Thompson
2986 | S0008 | UNIT-General Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 13 | 0 | 0 | 0 | Dr. Nicole White | Dr. Christopher Martin
2987 | S0009 | UNIT-University Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 7 | 0 | 0 | 0 | Dr. James Davis | Dr. Jessica Johnson
2988 | S0010 | SWED-Cancer Center | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 8 | 0 | 0 | 0 | Dr. Michelle Johnson | Dr. Christopher Moore
2989 | S0011 | SWED-University Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 7 | 0 | 0 | 0 | Dr. Lisa Anderson | Dr. Sarah Harris
2990 | S0012 | SWED-Research Institute | ST-2024-009 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 2, 'cumulative': 6}, {'month': 4, 'enrolled': 0, 'cumulative': 6}, {'month': 5, 'enrolled': 1, 'cumulative': 7}, {'month': 6, 'enrolled': 0, 'cumulative': 7}] | SCREENING | 4 | 0 | 0 | 0 | Dr. Christopher Brown | Dr. Lisa Miller
2991 | S0013 | SWED-Cancer Center | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 7 | 0 | 0 | 0 | Dr. Amanda White | Dr. Jennifer Jones
2992 | S0014 | SWED-Cancer Center | ST-2024-009 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 9 | 0 | 0 | 0 | Dr. Sarah Thomas | Dr. Michelle Wilson
2993 | S0015 | NORW-University Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 18 | 0 | 0 | 0 | Dr. Sarah Wilson | Dr. Robert Jones
2994 | S0016 | NORW-University Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | CLOSED | 10 | 0 | 0 | 0 | Dr. Thomas Davis | Dr. Charles Martin
2995 | S0017 | NORW-University Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | 22 | 0 | 0 | 0 | Dr. William White | Dr. Charles Harris
2996 | S0018 | NORW-Medical Center | ST-2024-009 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | SCREENING | 11 | 0 | 0 | 0 | Dr. Charles Thompson | Dr. William Thomas
2997 | S0019 | NORW-Clinical Center | ST-2024-009 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 2, 'cumulative': 7}, {'month': 6, 'enrolled': 0, 'cumulative': 7}] | ON_HOLD | 16 | 0 | 0 | 0 | Dr. James Williams | Dr. Christopher Thomas
2998 | S0020 | SING-University Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 15 | 0 | 0 | 0 | Dr. Thomas Johnson | Dr. Sarah Brown
2999 | S0021 | SING-General Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 13 | 0 | 0 | 0 | Dr. James Brown | Dr. Jennifer Harris
3000 | S0022 | SING-Clinical Center | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 9 | 0 | 0 | 0 | Dr. David Jones | Dr. Jessica Garcia
3001 | S0023 | SING-Cancer Center | ST-2024-009 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | SCREENING | 15 | 0 | 0 | 0 | Dr. Amanda Wilson | Dr. Michael Thomas
3002 | S0024 | SING-General Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 13 | 0 | 0 | 0 | Dr. Sarah Jackson | Dr. Jessica Davis
3003 | S0001 | MEXI-University Hospital | ST-2024-010 | [{'month': 1, 'enrolled': 45, 'cumulative': 45}, {'month': 2, 'enrolled': 43, 'cumulative': 88}, {'month': 3, 'enrolled': 46, 'cumulative': 134}, {'month': 4, 'enrolled': 43, 'cumulative': 177}, {'month': 5, 'enrolled': 46, 'cumulative': 223}, {'month': 6, 'enrolled': 42, 'cumulative': 265}] | SCREENING | 283 | 269 | 95.1 | 20.7 | Dr. Thomas White | Dr. Emily Moore
3004 | S0002 | MEXI-Research Institute | ST-2024-010 | [{'month': 1, 'enrolled': 40, 'cumulative': 40}, {'month': 2, 'enrolled': 39, 'cumulative': 79}, {'month': 3, 'enrolled': 40, 'cumulative': 119}, {'month': 4, 'enrolled': 41, 'cumulative': 160}, {'month': 5, 'enrolled': 40, 'cumulative': 200}, {'month': 6, 'enrolled': 39, 'cumulative': 239}] | ENROLLING | 344 | 238 | 69.2 | 13.2 | Dr. Christopher Anderson | Dr. Christopher Wilson
3005 | S0003 | MEXI-Cancer Center | ST-2024-010 | [{'month': 1, 'enrolled': 111, 'cumulative': 111}, {'month': 2, 'enrolled': 111, 'cumulative': 222}, {'month': 3, 'enrolled': 109, 'cumulative': 331}, {'month': 4, 'enrolled': 110, 'cumulative': 441}, {'month': 5, 'enrolled': 109, 'cumulative': 550}, {'month': 6, 'enrolled': 108, 'cumulative': 658}] | ENROLLING | 627 | 655 | 104.5 | 93.6 | Dr. Jennifer Anderson | Dr. Sarah Miller
3006 | S0004 | UNIT-Research Institute | ST-2024-010 | [{'month': 1, 'enrolled': 133, 'cumulative': 133}, {'month': 2, 'enrolled': 135, 'cumulative': 268}, {'month': 3, 'enrolled': 137, 'cumulative': 405}, {'month': 4, 'enrolled': 134, 'cumulative': 539}, {'month': 5, 'enrolled': 133, 'cumulative': 672}, {'month': 6, 'enrolled': 135, 'cumulative': 807}] | SCREENING | 997 | 811 | 81.3 | 101.4 | Dr. Charles Harris | Dr. Michelle Moore
3007 | S0005 | UNIT-University Hospital | ST-2024-010 | [{'month': 1, 'enrolled': 82, 'cumulative': 82}, {'month': 2, 'enrolled': 85, 'cumulative': 167}, {'month': 3, 'enrolled': 86, 'cumulative': 253}, {'month': 4, 'enrolled': 84, 'cumulative': 337}, {'month': 5, 'enrolled': 86, 'cumulative': 423}, {'month': 6, 'enrolled': 83, 'cumulative': 506}] | ON_HOLD | 616 | 507 | 82.3 | 72.4 | Dr. Emily Jones | Dr. Emily Smith
3008 | S0006 | UNIT-Medical Center | ST-2024-010 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 2, 'cumulative': 2}] | SCREENING | 440 | 0 | 0 | 0 | Dr. Robert Miller | Dr. Charles Thomas
3009 | S0007 | UNIT-General Hospital | ST-2024-010 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 557 | 0 | 0 | 0 | Dr. Michael Wilson | Dr. Michael Smith
3010 | S0008 | AUST-Medical Center | ST-2024-010 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 368 | 0 | 0 | 0 | Dr. Sarah Garcia | Dr. Stephanie Jackson
3011 | S0009 | AUST-Clinical Center | ST-2024-010 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | ON_HOLD | 170 | 0 | 0 | 0 | Dr. Stephanie Garcia | Dr. Amanda Miller
3012 | S0010 | AUST-University Hospital | ST-2024-010 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 279 | 0 | 0 | 0 | Dr. Christopher Jones | Dr. Sarah Davis
3013 | S0011 | AUST-General Hospital | ST-2024-010 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 319 | 0 | 0 | 0 | Dr. Stephanie Moore | Dr. Nicole Johnson
3014 | S0001 | UNIT-Clinical Center | ST-2024-011 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 7 | 4 | 57.1 | 0.4 | Dr. Charles Brown | Dr. Nicole Davis
3015 | S0002 | UNIT-University Hospital | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | SCREENING | 10 | 1 | 10 | 0.1 | Dr. Sarah Anderson | Dr. James Taylor
3016 | S0003 | UNIT-Research Institute | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | SCREENING | 10 | 0 | 0 | 0 | Dr. Thomas Garcia | Dr. Charles Garcia
3017 | S0004 | FRAN-University Hospital | ST-2024-011 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 1, 'cumulative': 5}, {'month': 4, 'enrolled': 0, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ON_HOLD | 11 | 0 | 0 | 0 | Dr. Jennifer Johnson | Dr. Emily Taylor
3018 | S0005 | FRAN-University Hospital | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ON_HOLD | 7 | 0 | 0 | 0 | Dr. Michelle Moore | Dr. William Anderson
3019 | S0006 | FRAN-Research Institute | ST-2024-011 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | SCREENING | 9 | 0 | 0 | 0 | Dr. Sarah Jackson | Dr. Michelle Martin
3020 | S0007 | FRAN-University Hospital | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | ON_HOLD | 4 | 0 | 0 | 0 | Dr. James White | Dr. Michael Anderson
3021 | S0008 | FRAN-Cancer Center | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | CLOSED | 7 | 0 | 0 | 0 | Dr. Nicole Miller | Dr. Emily Smith
3022 | S0009 | SING-Cancer Center | ST-2024-011 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 12 | 0 | 0 | 0 | Dr. Nicole Wilson | Dr. Michael Moore
3023 | S0010 | SING-Clinical Center | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 17 | 0 | 0 | 0 | Dr. Charles Thomas | Dr. Jennifer Harris
3024 | S0011 | SING-Medical Center | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 23 | 0 | 0 | 0 | Dr. Christopher Wilson | Dr. Lisa Wilson
3025 | S0012 | MEXI-Cancer Center | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | SCREENING | 9 | 0 | 0 | 0 | Dr. Michelle Johnson | Dr. Charles Thompson
3026 | S0013 | MEXI-Clinical Center | ST-2024-011 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | CLOSED | 4 | 0 | 0 | 0 | Dr. Nicole Davis | Dr. Nicole Anderson
3027 | S0014 | MEXI-Medical Center | ST-2024-011 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 7 | 0 | 0 | 0 | Dr. Sarah Thompson | Dr. Daniel Jones
3028 | S0015 | MEXI-Medical Center | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Jennifer Garcia | Dr. David Miller
3029 | S0001 | MEXI-Cancer Center | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | -12 | -12 | 100 | -0.9 | Dr. Amanda Thompson | Dr. Jessica Garcia
3030 | S0002 | MEXI-Cancer Center | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 3 | 2 | 66.7 | 0.1 | Dr. Jennifer Anderson | Dr. Emily Martin
3031 | S0003 | MEXI-University Hospital | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 3 | 3 | 100 | 0.2 | Dr. Michelle Garcia | Dr. Thomas Williams
3032 | S0004 | MEXI-University Hospital | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Jessica White | Dr. Thomas Thomas
3033 | S0005 | MEXI-Research Institute | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 2 | 66.7 | 0.1 | Dr. Christopher Brown | Dr. Nicole Johnson
3034 | S0006 | MEXI-Cancer Center | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | CLOSED | 3 | 5 | 166.7 | 0.3 | Dr. Michael Martin | Dr. David Thompson
3035 | S0007 | CANA-Clinical Center | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -7 | -7 | 100 | -0.9 | Dr. Jennifer Williams | Dr. Nicole Taylor
3036 | S0008 | CANA-General Hospital | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | SCREENING | 3 | 3 | 100 | 0.4 | Dr. Sarah Smith | Dr. Christopher Wilson
3037 | S0009 | CANA-University Hospital | ST-2024-012 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Jennifer Martin | Dr. Michael Jones
3038 | S0010 | CANA-Health System | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 3 | 3 | 100 | 0.2 | Dr. Stephanie Jackson | Dr. Stephanie Martin
3039 | S0011 | CANA-Clinical Center | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 3 | 3 | 100 | 0.5 | Dr. Michelle Miller | Dr. Amanda Smith
3040 | S0012 | BELG-Research Institute | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | -3 | -3 | 100 | -0.3 | Dr. Emily Jackson | Dr. Daniel Anderson
3041 | S0013 | BELG-University Hospital | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | ENROLLING | 3 | 3 | 100 | 0.4 | Dr. Jessica Anderson | Dr. Christopher Thompson
3042 | S0014 | BELG-Health System | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Stephanie Jones | Dr. Thomas Martin
3043 | S0015 | BELG-Research Institute | ST-2024-012 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ENROLLING | 3 | 4 | 133.3 | 0.2 | Dr. Jennifer Jackson | Dr. James Davis
3044 | S0016 | NORW-Medical Center | ST-2024-012 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 0 | 0 | 0 | 0 | Dr. Sarah Jackson | Dr. William Moore
3045 | S0017 | NORW-Health System | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.3 | Dr. Sarah Brown | Dr. James Johnson
3046 | S0018 | NORW-General Hospital | ST-2024-012 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. Christopher Jackson | Dr. Emily Moore
3047 | S0019 | SING-General Hospital | ST-2024-012 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 2 | 0 | 0 | 0 | Dr. Jessica White | Dr. Emily Thompson
3048 | S0020 | SING-Research Institute | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Robert White | Dr. Emily Thompson
3049 | S0021 | CHIL-University Hospital | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ON_HOLD | -1 | -1 | 100 | -0.1 | Dr. Daniel Miller | Dr. Amanda White
3050 | S0022 | CHIL-Research Institute | ST-2024-012 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | SCREENING | 3 | 1 | 33.3 | 0.1 | Dr. Michelle Martin | Dr. David Martin
3051 | S0023 | CHIL-Research Institute | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 3 | 0 | 0 | 0 | Dr. James Williams | Dr. Emily Martin
3052 | S0001 | MEXI-Cancer Center | ST-2024-013 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -12 | -12 | 100 | -0.7 | Dr. Thomas Moore | Dr. David Miller
3053 | S0002 | MEXI-University Hospital | ST-2024-013 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Jessica Thomas | Dr. Robert Garcia
3054 | S0003 | MEXI-Health System | ST-2024-013 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | SCREENING | 3 | 4 | 133.3 | 0.3 | Dr. Thomas Brown | Dr. Amanda Moore
3055 | S0004 | POLA-Clinical Center | ST-2024-013 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 2 | 2 | 100 | 0.1 | Dr. Michelle Anderson | Dr. Stephanie Smith
3056 | S0005 | POLA-Health System | ST-2024-013 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 1, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | ENROLLING | 3 | 3 | 100 | 0.4 | Dr. Charles Jones | Dr. Sarah Johnson
3057 | S0006 | SOUT-Medical Center | ST-2024-013 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | -7 | -7 | 100 | -0.6 | Dr. Emily Moore | Dr. Lisa Moore
3058 | S0007 | SOUT-Clinical Center | ST-2024-013 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 3 | 100 | 0.3 | Dr. Jessica Johnson | Dr. Charles Jackson
3059 | S0008 | SOUT-Clinical Center | ST-2024-013 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | CLOSED | 3 | 2 | 66.7 | 0.1 | Dr. Thomas Moore | Dr. Sarah Smith
3060 | S0009 | SOUT-General Hospital | ST-2024-013 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 3 | 3 | 100 | 0.3 | Dr. Christopher Davis | Dr. Amanda Moore
3061 | S0010 | SOUT-General Hospital | ST-2024-013 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 3 | 0 | 0 | 0 | Dr. David Anderson | Dr. Christopher Garcia
3062 | S0011 | CHIL-Cancer Center | ST-2024-013 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -7 | -7 | 100 | -0.7 | Dr. Thomas Harris | Dr. Robert Johnson
3063 | S0012 | CHIL-University Hospital | ST-2024-013 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.2 | Dr. Sarah Anderson | Dr. Nicole Moore
3064 | S0013 | CHIL-Research Institute | ST-2024-013 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 3 | 2 | 66.7 | 0.3 | Dr. Thomas Thompson | Dr. Lisa Garcia
3065 | S0014 | CHIL-Health System | ST-2024-013 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.3 | Dr. Jennifer White | Dr. Michelle Moore
3066 | S0015 | CHIL-Clinical Center | ST-2024-013 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. Lisa Miller | Dr. Thomas Taylor
3067 | S0001 | MEXI-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | -14 | -14 | 100 | -1.8 | Dr. Jennifer Garcia | Dr. Robert Martin
3068 | S0002 | MEXI-Research Institute | ST-2024-014 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ENROLLING | 3 | 2 | 66.7 | 0.3 | Dr. Nicole Davis | Dr. Michael Wilson
3069 | S0003 | MEXI-Research Institute | ST-2024-014 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. David Thompson | Dr. Amanda Jackson
3070 | S0004 | MEXI-Clinical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | ENROLLING | 3 | 5 | 166.7 | 0.4 | Dr. Sarah Taylor | Dr. Emily Thompson
3071 | S0005 | CANA-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | -4 | -4 | 100 | -0.2 | Dr. Daniel Wilson | Dr. Charles Davis
3072 | S0006 | CANA-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Amanda Martin | Dr. Nicole Smith
3073 | S0007 | CANA-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Jennifer Davis | Dr. Michael Thompson
3074 | S0008 | CANA-General Hospital | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ENROLLING | 3 | 4 | 133.3 | 0.4 | Dr. Robert Garcia | Dr. Jennifer Thomas
3075 | S0009 | UNIT-Clinical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 2 | 1 | 50 | 0.1 | Dr. Emily Martin | Dr. Nicole Martin
3076 | S0010 | UNIT-University Hospital | ST-2024-014 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. Stephanie Smith | Dr. Lisa Johnson
3077 | S0011 | POLA-General Hospital | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | -10 | -10 | 100 | -1.7 | Dr. Jessica Williams | Dr. David Harris
3078 | S0012 | POLA-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 3 | 3 | 100 | 0.2 | Dr. Jennifer Davis | Dr. Stephanie Jones
3079 | S0013 | POLA-Cancer Center | ST-2024-014 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Daniel Wilson | Dr. Jennifer Taylor
3080 | S0014 | POLA-Clinical Center | ST-2024-014 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | ON_HOLD | 3 | 2 | 66.7 | 0.1 | Dr. Michael Davis | Dr. Charles Jackson
3081 | S0015 | POLA-University Hospital | ST-2024-014 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ENROLLING | 3 | 3 | 100 | 0.4 | Dr. David Thompson | Dr. Daniel White
3082 | S0016 | POLA-Cancer Center | ST-2024-014 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 3 | 4 | 133.3 | 0.5 | Dr. Emily Garcia | Dr. Nicole Johnson
3083 | S0017 | NORW-Medical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | -4 | -4 | 100 | -0.2 | Dr. Stephanie Thompson | Dr. Stephanie Thomas
3084 | S0018 | NORW-Cancer Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 3 | 100 | 0.5 | Dr. Daniel White | Dr. Lisa Martin
3085 | S0019 | NORW-Cancer Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 2 | 66.7 | 0.1 | Dr. Amanda Brown | Dr. Stephanie Jones
3086 | S0020 | NORW-Research Institute | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Michael Anderson | Dr. Michelle White
3087 | S0021 | NETH-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | ON_HOLD | -1 | -1 | 100 | -0.2 | Dr. David Taylor | Dr. Stephanie Thomas
3088 | S0022 | NETH-Medical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. William Wilson | Dr. Michelle White
3089 | S0023 | NETH-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 0 | 0 | 0 | Dr. William Jackson | Dr. David White
3090 | S0024 | DENM-Medical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -10 | -10 | 100 | -0.6 | Dr. Christopher Garcia | Dr. Emily Miller
3091 | S0025 | DENM-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 3 | 100 | 0.2 | Dr. Michelle Johnson | Dr. Jennifer Jackson
3092 | S0026 | DENM-General Hospital | ST-2024-014 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 3 | 2 | 66.7 | 0.3 | Dr. Robert Martin | Dr. Stephanie Williams
3093 | S0027 | DENM-Medical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Amanda Williams | Dr. Sarah Jackson
3094 | S0028 | DENM-Clinical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 3 | 3 | 100 | 0.2 | Dr. Daniel Anderson | Dr. Sarah Garcia
3095 | S0029 | DENM-General Hospital | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. James Miller | Dr. Daniel Anderson
3096 | S0030 | TAIW-Medical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | -7 | -7 | 100 | -0.7 | Dr. Amanda Jackson | Dr. Charles Miller
3097 | S0031 | TAIW-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.3 | Dr. Michael Williams | Dr. Michelle Anderson
3098 | S0032 | TAIW-General Hospital | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.1 | Dr. Amanda Thomas | Dr. William Davis
3099 | S0033 | TAIW-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | ON_HOLD | 3 | 3 | 100 | 0.3 | Dr. Charles Smith | Dr. William Garcia
3100 | S0034 | TAIW-Clinical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Michelle Williams | Dr. Daniel Anderson
3101 | S0001 | CANA-Health System | ST-2024-015 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 3, 'cumulative': 6}, {'month': 3, 'enrolled': 0, 'cumulative': 6}, {'month': 4, 'enrolled': 0, 'cumulative': 6}, {'month': 5, 'enrolled': 3, 'cumulative': 9}, {'month': 6, 'enrolled': 0, 'cumulative': 9}] | ON_HOLD | 7 | 7 | 100 | 0.6 | Dr. Lisa Garcia | Dr. Charles Jackson
3102 | S0002 | CANA-University Hospital | ST-2024-015 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 7 | 5 | 71.4 | 0.5 | Dr. Stephanie Davis | Dr. Daniel Wilson
3103 | S0003 | CANA-Research Institute | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | CLOSED | 7 | 0 | 0 | 0 | Dr. Michelle Wilson | Dr. Stephanie Miller
3104 | S0004 | CANA-Cancer Center | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 6 | 0 | 0 | 0 | Dr. Robert Anderson | Dr. Emily Harris
3105 | S0005 | MEXI-University Hospital | ST-2024-015 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | SCREENING | 8 | 0 | 0 | 0 | Dr. Robert Johnson | Dr. Michelle Smith
3106 | S0006 | MEXI-University Hospital | ST-2024-015 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 5 | 0 | 0 | 0 | Dr. William Jones | Dr. Christopher Smith
3107 | S0007 | SWED-Research Institute | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 7 | 0 | 0 | 0 | Dr. Sarah Wilson | Dr. Charles Williams
3108 | S0008 | SWED-Health System | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 5 | 0 | 0 | 0 | Dr. David Wilson | Dr. Charles Smith
3109 | S0009 | SWED-Medical Center | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | CLOSED | 7 | 0 | 0 | 0 | Dr. Lisa Jackson | Dr. Christopher Davis
3110 | S0010 | SWED-General Hospital | ST-2024-015 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 6 | 0 | 0 | 0 | Dr. Christopher Brown | Dr. Daniel Miller
3111 | S0011 | SWED-Clinical Center | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | CLOSED | 6 | 0 | 0 | 0 | Dr. Jessica Taylor | Dr. Jennifer Johnson
3112 | S0012 | NORW-Clinical Center | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 12 | 0 | 0 | 0 | Dr. David Thomas | Dr. Sarah Miller
3113 | S0013 | NORW-Medical Center | ST-2024-015 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 10 | 0 | 0 | 0 | Dr. Stephanie Taylor | Dr. James Garcia
3114 | S0014 | SWIT-General Hospital | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 8 | 0 | 0 | 0 | Dr. Amanda Williams | Dr. Lisa Garcia
3115 | S0015 | SWIT-Clinical Center | ST-2024-015 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 6 | 0 | 0 | 0 | Dr. Thomas Johnson | Dr. Sarah Thomas
3116 | S0016 | SWIT-General Hospital | ST-2024-015 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 1, 'cumulative': 7}, {'month': 6, 'enrolled': 0, 'cumulative': 7}] | CLOSED | 5 | 0 | 0 | 0 | Dr. Michelle Brown | Dr. Robert Martin
3117 | S0017 | SWIT-University Hospital | ST-2024-015 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 4 | 0 | 0 | 0 | Dr. Amanda Harris | Dr. David Smith
3118 | S0018 | INDI-Medical Center | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 12 | 0 | 0 | 0 | Dr. Christopher Moore | Dr. Jessica Moore
3119 | S0019 | INDI-General Hospital | ST-2024-015 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 1, 'cumulative': 5}, {'month': 4, 'enrolled': 0, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 2, 'cumulative': 7}] | SCREENING | 8 | 0 | 0 | 0 | Dr. Jennifer Moore | Dr. Amanda Taylor
3120 | S0001 | UNIT-Cancer Center | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ON_HOLD | 5 | 3 | 60 | 0.4 | Dr. Michelle Miller | Dr. Nicole Jackson
3121 | S0002 | UNIT-General Hospital | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Michelle Thompson | Dr. Lisa Davis
3122 | S0003 | UNIT-Medical Center | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. Thomas Williams | Dr. Emily White
3123 | S0004 | UNIT-Clinical Center | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 4 | 4 | 100 | 0.4 | Dr. David Taylor | Dr. Amanda Smith
3124 | S0005 | UNIT-Cancer Center | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Amanda Harris | Dr. Robert Harris
3125 | S0006 | CANA-Research Institute | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 5 | 3 | 60 | 0.4 | Dr. Michael Brown | Dr. Sarah Davis
3126 | S0007 | CANA-Health System | ST-2024-016 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 4, 'cumulative': 7}, {'month': 3, 'enrolled': 4, 'cumulative': 11}, {'month': 4, 'enrolled': 4, 'cumulative': 15}, {'month': 5, 'enrolled': 4, 'cumulative': 19}, {'month': 6, 'enrolled': 4, 'cumulative': 23}] | ENROLLING | 12 | 14 | 116.7 | 1.8 | Dr. James Taylor | Dr. Emily Anderson
3127 | S0008 | GERM-Clinical Center | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 1 | 0 | 0 | 0 | Dr. Robert Smith | Dr. Charles Thompson
3128 | S0009 | GERM-Medical Center | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 2, 'cumulative': 7}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Sarah Anderson | Dr. David Wilson
3129 | S0010 | GERM-Medical Center | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. James Williams | Dr. Charles Wilson
3130 | S0011 | GERM-General Hospital | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | SCREENING | 3 | 5 | 166.7 | 0.3 | Dr. Emily Smith | Dr. Jessica Jackson
3131 | S0012 | POLA-Medical Center | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 3, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 3, 'cumulative': 7}, {'month': 5, 'enrolled': 0, 'cumulative': 7}, {'month': 6, 'enrolled': 2, 'cumulative': 9}] | ON_HOLD | 8 | 6 | 75 | 0.5 | Dr. Michelle Williams | Dr. Jennifer Miller
3132 | S0013 | POLA-Health System | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | CLOSED | 9 | 0 | 0 | 0 | Dr. James Johnson | Dr. Lisa Thompson
3133 | S0014 | BELG-Research Institute | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | -4 | -4 | 100 | -0.3 | Dr. Michelle Wilson | Dr. Lisa Jones
3134 | S0015 | BELG-Research Institute | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | CLOSED | 3 | 3 | 100 | 0.2 | Dr. Robert Williams | Dr. Charles Thompson
3135 | S0016 | BELG-General Hospital | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | 3 | 1 | 33.3 | 0.1 | Dr. Lisa White | Dr. Lisa Jones
3136 | S0017 | BELG-Clinical Center | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Thomas Harris | Dr. Michelle Jones
3137 | S0018 | BELG-University Hospital | ST-2024-016 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 2, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Michelle Miller | Dr. Robert Anderson
3138 | S0019 | BELG-General Hospital | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Robert White | Dr. Robert Garcia
3139 | S0020 | AUST-University Hospital | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 5 | 0 | 0 | 0 | Dr. Thomas White | Dr. Stephanie Anderson
3140 | S0021 | AUST-Clinical Center | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 5 | 0 | 0 | 0 | Dr. William Jones | Dr. David Brown
3141 | S0022 | AUST-University Hospital | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 7 | 0 | 0 | 0 | Dr. William Davis | Dr. Lisa Davis
3142 | S0001 | MEXI-Medical Center | ST-2024-017 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 2, 'cumulative': 6}, {'month': 4, 'enrolled': 0, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | ON_HOLD | 5 | 5 | 100 | 0.8 | Dr. Emily Miller | Dr. Stephanie White
3143 | S0002 | MEXI-Medical Center | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 4 | 2 | 50 | 0.2 | Dr. Michelle Miller | Dr. James Miller
3144 | S0003 | MEXI-General Hospital | ST-2024-017 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 5 | 1 | 20 | 0.1 | Dr. Michael Anderson | Dr. Jessica Thompson
3145 | S0004 | MEXI-Health System | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 4 | 0 | 0 | 0 | Dr. Emily Taylor | Dr. Thomas Jackson
3146 | S0005 | MEXI-General Hospital | ST-2024-017 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 5 | 0 | 0 | 0 | Dr. James Garcia | Dr. David Taylor
3147 | S0006 | SPAI-Cancer Center | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | -3 | -3 | 100 | -0.2 | Dr. Sarah Thompson | Dr. Jessica Taylor
3148 | S0007 | SPAI-Health System | ST-2024-017 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. David Taylor | Dr. Amanda Williams
3149 | S0008 | SPAI-University Hospital | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 3 | 1 | 33.3 | 0.1 | Dr. Thomas Jackson | Dr. Michelle Garcia
3150 | S0009 | SPAI-Health System | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Jennifer Brown | Dr. Jessica Taylor
3151 | S0010 | SPAI-General Hospital | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Stephanie Williams | Dr. Nicole Davis
3152 | S0011 | SPAI-Research Institute | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. David Thompson | Dr. Jessica Garcia
3153 | S0012 | CHIN-Health System | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ON_HOLD | 4 | 0 | 0 | 0 | Dr. Robert Brown | Dr. Daniel Jones
3154 | S0013 | CHIN-University Hospital | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 5 | 0 | 0 | 0 | Dr. Christopher Jackson | Dr. Daniel Brown
3155 | S0014 | CHIN-Medical Center | ST-2024-017 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | SCREENING | 5 | 0 | 0 | 0 | Dr. Michael Taylor | Dr. Christopher Johnson
3156 | S0015 | CHIN-Medical Center | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | CLOSED | 5 | 0 | 0 | 0 | Dr. Jessica Smith | Dr. Jessica Miller
3157 | S0016 | CHIN-Research Institute | ST-2024-017 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Jessica Wilson | Dr. Michelle Taylor
3158 | S0017 | CHIN-Cancer Center | ST-2024-017 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Emily Wilson | Dr. Robert Garcia
3159 | S0001 | UNIT-Health System | ST-2024-018 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Jennifer Harris | Dr. Daniel White
3160 | S0002 | UNIT-Health System | ST-2024-018 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ENROLLING | 4 | 4 | 100 | 0.3 | Dr. Amanda Davis | Dr. Jennifer White
3161 | S0003 | UNIT-Health System | ST-2024-018 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 4 | 133.3 | 0.7 | Dr. Nicole Davis | Dr. Daniel Wilson
3162 | S0004 | DENM-Medical Center | ST-2024-018 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Amanda Brown | Dr. Nicole Williams
3163 | S0005 | DENM-University Hospital | ST-2024-018 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 4 | 133.3 | 0.2 | Dr. Daniel Wilson | Dr. Christopher Thompson
3164 | S0006 | SOUT-Research Institute | ST-2024-018 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | -4 | -4 | 100 | -0.3 | Dr. Thomas Moore | Dr. James Martin
3165 | S0007 | SOUT-Clinical Center | ST-2024-018 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ENROLLING | 3 | 1 | 33.3 | 0.1 | Dr. Thomas White | Dr. Amanda Anderson
3166 | S0008 | SOUT-Research Institute | ST-2024-018 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Jessica Wilson | Dr. Sarah Martin
3167 | S0009 | SOUT-Health System | ST-2024-018 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 3 | 100 | 0.4 | Dr. Sarah Anderson | Dr. James Anderson
3168 | S0010 | SOUT-Clinical Center | ST-2024-018 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 0, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 3, 'cumulative': 6}, {'month': 5, 'enrolled': 1, 'cumulative': 7}, {'month': 6, 'enrolled': 2, 'cumulative': 9}] | ENROLLING | 3 | 6 | 200 | 0.9 | Dr. Daniel Williams | Dr. William Wilson
3169 | S0001 | MEXI-University Hospital | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 25 | 0 | 0 | 0 | Dr. David Brown | Dr. Christopher Wilson
3170 | S0002 | MEXI-Medical Center | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | SCREENING | 14 | 0 | 0 | 0 | Dr. Michael Wilson | Dr. Christopher Smith
3171 | S0003 | UNIT-Health System | ST-2024-019 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 19 | 0 | 0 | 0 | Dr. Nicole White | Dr. Charles Williams
3172 | S0004 | UNIT-Health System | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 7 | 0 | 0 | 0 | Dr. Charles Martin | Dr. Emily Moore
3173 | S0005 | UNIT-Research Institute | ST-2024-019 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 13 | 0 | 0 | 0 | Dr. Jessica Jackson | Dr. Sarah Williams
3174 | S0006 | UNIT-Research Institute | ST-2024-019 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | ON_HOLD | 17 | 0 | 0 | 0 | Dr. Michael Harris | Dr. Jessica Miller
3175 | S0007 | UNIT-University Hospital | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 13 | 0 | 0 | 0 | Dr. Charles Miller | Dr. Jessica Jackson
3176 | S0008 | POLA-General Hospital | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 24 | 0 | 0 | 0 | Dr. Sarah Miller | Dr. James Davis
3177 | S0009 | POLA-Clinical Center | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | SCREENING | 18 | 0 | 0 | 0 | Dr. Michelle Anderson | Dr. Nicole Moore
3178 | S0010 | POLA-Cancer Center | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 13 | 0 | 0 | 0 | Dr. James Johnson | Dr. Thomas Johnson
3179 | S0011 | DENM-University Hospital | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | CLOSED | 33 | 0 | 0 | 0 | Dr. Daniel Harris | Dr. Michelle Jones
3180 | S0012 | DENM-General Hospital | ST-2024-019 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | SCREENING | 46 | 0 | 0 | 0 | Dr. Michael Johnson | Dr. Robert Martin
3181 | S0013 | UNIT-Medical Center | ST-2024-019 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 40 | 0 | 0 | 0 | Dr. Robert Smith | Dr. Jennifer Johnson
3182 | S0014 | UNIT-Research Institute | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | SCREENING | 32 | 0 | 0 | 0 | Dr. Christopher Garcia | Dr. Michael Brown
3183 | S0015 | AUST-Medical Center | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 14 | 0 | 0 | 0 | Dr. Michelle Jones | Dr. Thomas Miller
3184 | S0016 | AUST-Cancer Center | ST-2024-019 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 21 | 0 | 0 | 0 | Dr. Jennifer Taylor | Dr. Michael Brown
3185 | S0017 | AUST-Research Institute | ST-2024-019 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ON_HOLD | 22 | 0 | 0 | 0 | Dr. Jennifer Thomas | Dr. Michelle Garcia
3186 | S0018 | AUST-Clinical Center | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | 11 | 0 | 0 | 0 | Dr. Sarah Jones | Dr. Emily Jackson
3187 | S0019 | AUST-Cancer Center | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 14 | 0 | 0 | 0 | Dr. Nicole Williams | Dr. James Smith
3188 | S0001 | CANA-Cancer Center | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | -9 | -9 | 100 | -0.6 | Dr. David Davis | Dr. Thomas Thomas
3189 | S0002 | CANA-Research Institute | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.1 | Dr. Stephanie Wilson | Dr. Sarah Williams
3190 | S0003 | CANA-Research Institute | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 3 | 3 | 100 | 0.3 | Dr. Nicole Thompson | Dr. Daniel Brown
3191 | S0004 | CANA-Clinical Center | ST-2024-020 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 4 | 133.3 | 0.2 | Dr. Michelle Anderson | Dr. Christopher Thomas
3192 | S0005 | NORW-Medical Center | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ENROLLING | -4 | -4 | 100 | -0.3 | Dr. Jessica Williams | Dr. Emily Garcia
3193 | S0006 | NORW-Research Institute | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 2, 'cumulative': 2}] | SCREENING | 3 | 3 | 100 | 0.4 | Dr. Robert Martin | Dr. Robert Miller
3194 | S0007 | NORW-Health System | ST-2024-020 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Jessica White | Dr. Michelle Jones
3195 | S0008 | NORW-Clinical Center | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ENROLLING | 3 | 4 | 133.3 | 0.4 | Dr. Christopher Smith | Dr. Jessica Miller
3196 | S0009 | NETH-General Hospital | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | -4 | -4 | 100 | -0.2 | Dr. Nicole Thompson | Dr. Michelle Harris
3197 | S0010 | NETH-Clinical Center | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | CLOSED | 3 | 2 | 66.7 | 0.2 | Dr. Robert Anderson | Dr. Jennifer Wilson
3198 | S0011 | NETH-University Hospital | ST-2024-020 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. Jessica Johnson | Dr. Robert Thomas
3199 | S0012 | NETH-Research Institute | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 3 | 3 | 100 | 0.2 | Dr. Jennifer Moore | Dr. Jessica Garcia
3200 | S0013 | JAPA-Research Institute | ST-2024-020 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ENROLLING | -4 | -4 | 100 | -0.3 | Dr. Christopher Wilson | Dr. Amanda Garcia
3201 | S0014 | JAPA-University Hospital | ST-2024-020 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.1 | Dr. Sarah Taylor | Dr. Amanda Jones
3202 | S0015 | JAPA-Research Institute | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. Jennifer Moore | Dr. Jessica Brown
3203 | S0016 | JAPA-Medical Center | ST-2024-020 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 3 | 5 | 166.7 | 0.4 | Dr. Robert Harris | Dr. Thomas Jones
3204 | S0001 | MEXI-Medical Center | ST-2025-021 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | SCREENING | 9 | 5 | 55.6 | 0.5 | Dr. James Brown | Dr. Emily Miller
3205 | S0002 | MEXI-Health System | ST-2025-021 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 8 | 5 | 62.5 | 0.6 | Dr. Amanda Smith | Dr. Michael Jones
3206 | S0003 | MEXI-Cancer Center | ST-2025-021 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 3, 'cumulative': 4}] | ENROLLING | 17 | 12 | 70.6 | 0.7 | Dr. Amanda Thomas | Dr. Jennifer Thompson
3207 | S0004 | MEXI-Cancer Center | ST-2025-021 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 3, 'cumulative': 5}, {'month': 3, 'enrolled': 5, 'cumulative': 10}, {'month': 4, 'enrolled': 6, 'cumulative': 16}, {'month': 5, 'enrolled': 4, 'cumulative': 20}, {'month': 6, 'enrolled': 3, 'cumulative': 23}] | SCREENING | 14 | 26 | 185.7 | 1.5 | Dr. Lisa Thompson | Dr. Michael Brown
3208 | S0005 | UNIT-General Hospital | ST-2025-021 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 5, 'cumulative': 8}, {'month': 3, 'enrolled': 5, 'cumulative': 13}, {'month': 4, 'enrolled': 1, 'cumulative': 14}, {'month': 5, 'enrolled': 1, 'cumulative': 15}, {'month': 6, 'enrolled': 5, 'cumulative': 20}] | ENROLLING | 25 | 22 | 88 | 2.4 | Dr. Jennifer Moore | Dr. James Brown
3209 | S0006 | UNIT-University Hospital | ST-2025-021 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 5, 'cumulative': 10}, {'month': 3, 'enrolled': 3, 'cumulative': 13}, {'month': 4, 'enrolled': 4, 'cumulative': 17}, {'month': 5, 'enrolled': 5, 'cumulative': 22}, {'month': 6, 'enrolled': 5, 'cumulative': 27}] | SCREENING | 23 | 26 | 113 | 1.9 | Dr. Nicole Thomas | Dr. Jennifer Harris
3210 | S0007 | BELG-Health System | ST-2025-021 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 2, 'cumulative': 6}, {'month': 3, 'enrolled': 4, 'cumulative': 10}, {'month': 4, 'enrolled': 2, 'cumulative': 12}, {'month': 5, 'enrolled': 4, 'cumulative': 16}, {'month': 6, 'enrolled': 4, 'cumulative': 20}] | SCREENING | 13 | 13 | 100 | 1.4 | Dr. Emily Taylor | Dr. Emily Harris
3211 | S0008 | BELG-Medical Center | ST-2025-021 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ENROLLING | 6 | 5 | 83.3 | 0.4 | Dr. Nicole Thomas | Dr. Jessica Moore
3212 | S0009 | BELG-General Hospital | ST-2025-021 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 3, 'cumulative': 5}, {'month': 3, 'enrolled': 3, 'cumulative': 8}, {'month': 4, 'enrolled': 3, 'cumulative': 11}, {'month': 5, 'enrolled': 0, 'cumulative': 11}, {'month': 6, 'enrolled': 0, 'cumulative': 11}] | ENROLLING | 14 | 12 | 85.7 | 2 | Dr. Thomas Martin | Dr. Emily Jackson
3213 | S0010 | SWED-Health System | ST-2025-021 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 3, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | ENROLLING | 8 | 8 | 100 | 0.7 | Dr. Stephanie Miller | Dr. Michael Martin
3214 | S0011 | SWED-General Hospital | ST-2025-021 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 3, 'cumulative': 8}] | ENROLLING | 11 | 9 | 81.8 | 0.8 | Dr. James Martin | Dr. Emily Jackson
3215 | S0012 | SWED-Clinical Center | ST-2025-021 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 3, 'cumulative': 5}, {'month': 3, 'enrolled': 3, 'cumulative': 8}, {'month': 4, 'enrolled': 3, 'cumulative': 11}, {'month': 5, 'enrolled': 2, 'cumulative': 13}, {'month': 6, 'enrolled': 2, 'cumulative': 15}] | SCREENING | 8 | 10 | 125 | 0.7 | Dr. Michael Brown | Dr. Robert Jackson
3216 | S0013 | AUST-University Hospital | ST-2025-021 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 0, 'cumulative': 3}, {'month': 3, 'enrolled': 3, 'cumulative': 6}, {'month': 4, 'enrolled': 0, 'cumulative': 6}, {'month': 5, 'enrolled': 2, 'cumulative': 8}, {'month': 6, 'enrolled': 1, 'cumulative': 9}] | ENROLLING | 14 | 9 | 64.3 | 1.3 | Dr. David Taylor | Dr. David Jackson
3217 | S0014 | AUST-Medical Center | ST-2025-021 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 5, 'cumulative': 9}, {'month': 3, 'enrolled': 4, 'cumulative': 13}, {'month': 4, 'enrolled': 5, 'cumulative': 18}, {'month': 5, 'enrolled': 3, 'cumulative': 21}, {'month': 6, 'enrolled': 3, 'cumulative': 24}] | ENROLLING | 15 | 23 | 153.3 | 2.6 | Dr. Nicole Wilson | Dr. William Jackson
3218 | S0001 | UNIT-Cancer Center | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | SCREENING | 0 | 0 | 0 | 0 | Dr. Michelle Garcia | Dr. Sarah Martin
3219 | S0002 | UNIT-Cancer Center | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ENROLLING | 3 | 2 | 66.7 | 0.3 | Dr. Michael Taylor | Dr. Jessica Williams
3220 | S0003 | UNIT-Clinical Center | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. Michael Jackson | Dr. Robert Davis
3221 | S0004 | UNIT-Medical Center | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 3 | 5 | 166.7 | 0.3 | Dr. Daniel Brown | Dr. Daniel Thompson
3222 | S0005 | MEXI-Medical Center | ST-2025-022 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 4 | 2 | 50 | 0.1 | Dr. Thomas Jackson | Dr. Lisa White
3223 | S0006 | MEXI-University Hospital | ST-2025-022 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 5 | 4 | 80 | 0.5 | Dr. Jennifer Miller | Dr. William Harris
3224 | S0007 | POLA-Clinical Center | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 1 | 1 | 100 | 0.1 | Dr. William Jones | Dr. Amanda Martin
3225 | S0008 | POLA-General Hospital | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. James Johnson | Dr. Sarah Davis
3226 | S0009 | POLA-Research Institute | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.1 | Dr. Jessica Thomas | Dr. Emily Moore
3227 | S0010 | POLA-Cancer Center | ST-2025-022 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. Charles Smith | Dr. Charles Wilson
3228 | S0011 | SWED-Research Institute | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | -5 | -5 | 100 | -0.7 | Dr. Nicole White | Dr. Thomas White
3229 | S0012 | SWED-Cancer Center | ST-2025-022 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ENROLLING | 3 | 2 | 66.7 | 0.3 | Dr. William Thompson | Dr. Michael Thomas
3230 | S0013 | SWED-Clinical Center | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | 3 | 3 | 100 | 0.2 | Dr. Michelle Taylor | Dr. Christopher Smith
3231 | S0014 | SWED-Cancer Center | ST-2025-022 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 3 | 2 | 66.7 | 0.3 | Dr. Jennifer Harris | Dr. Robert Smith
3232 | S0015 | SWED-Clinical Center | ST-2025-022 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 3 | 100 | 0.3 | Dr. Jessica Taylor | Dr. Michael Brown
3233 | S0016 | SWED-University Hospital | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 3 | 3 | 100 | 0.3 | Dr. Robert White | Dr. Thomas Harris
3234 | S0017 | CHIN-General Hospital | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | 5 | 3 | 60 | 0.2 | Dr. Jessica Miller | Dr. Michael White
3235 | S0018 | CHIN-Research Institute | ST-2025-022 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 6 | 5 | 83.3 | 0.6 | Dr. Charles Davis | Dr. James Smith
3236 | S0019 | CHIL-University Hospital | ST-2025-022 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | SCREENING | 5 | 5 | 100 | 0.5 | Dr. Jennifer Johnson | Dr. Charles White
3237 | S0020 | CHIL-Health System | ST-2025-022 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 3 | 3 | 100 | 0.3 | Dr. Michael Thomas | Dr. Jennifer Brown
3238 | S0021 | CHIL-Medical Center | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 4, 'cumulative': 9}] | SCREENING | 3 | 15 | 500 | 0.9 | Dr. Stephanie Harris | Dr. Nicole Brown
3239 | S0001 | UNIT-Medical Center | ST-2025-023 | [{'month': 1, 'enrolled': 16, 'cumulative': 16}, {'month': 2, 'enrolled': 18, 'cumulative': 34}, {'month': 3, 'enrolled': 15, 'cumulative': 49}, {'month': 4, 'enrolled': 18, 'cumulative': 67}, {'month': 5, 'enrolled': 15, 'cumulative': 82}, {'month': 6, 'enrolled': 16, 'cumulative': 98}] | ON_HOLD | 106 | 106 | 100 | 8.8 | Dr. James Smith | Dr. Charles Brown
3240 | S0002 | UNIT-Medical Center | ST-2025-023 | [{'month': 1, 'enrolled': 15, 'cumulative': 15}, {'month': 2, 'enrolled': 11, 'cumulative': 26}, {'month': 3, 'enrolled': 15, 'cumulative': 41}, {'month': 4, 'enrolled': 13, 'cumulative': 54}, {'month': 5, 'enrolled': 14, 'cumulative': 68}, {'month': 6, 'enrolled': 14, 'cumulative': 82}] | ON_HOLD | 93 | 78 | 83.9 | 9.8 | Dr. Nicole Harris | Dr. Charles Martin
3241 | S0003 | CANA-General Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 9, 'cumulative': 9}, {'month': 2, 'enrolled': 7, 'cumulative': 16}, {'month': 3, 'enrolled': 7, 'cumulative': 23}, {'month': 4, 'enrolled': 7, 'cumulative': 30}, {'month': 5, 'enrolled': 5, 'cumulative': 35}, {'month': 6, 'enrolled': 7, 'cumulative': 42}] | SCREENING | 47 | 47 | 100 | 3.9 | Dr. Michael Jones | Dr. Robert Smith
3242 | S0004 | CANA-University Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 14, 'cumulative': 14}, {'month': 2, 'enrolled': 14, 'cumulative': 28}, {'month': 3, 'enrolled': 11, 'cumulative': 39}, {'month': 4, 'enrolled': 13, 'cumulative': 52}, {'month': 5, 'enrolled': 13, 'cumulative': 65}, {'month': 6, 'enrolled': 11, 'cumulative': 76}] | ENROLLING | 75 | 75 | 100 | 10.7 | Dr. David Smith | Dr. David Martin
3243 | S0005 | CANA-General Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 6, 'cumulative': 6}, {'month': 2, 'enrolled': 6, 'cumulative': 12}, {'month': 3, 'enrolled': 6, 'cumulative': 18}, {'month': 4, 'enrolled': 5, 'cumulative': 23}, {'month': 5, 'enrolled': 4, 'cumulative': 27}, {'month': 6, 'enrolled': 5, 'cumulative': 32}] | ON_HOLD | 63 | 26 | 41.3 | 3.2 | Dr. Lisa White | Dr. Michelle Miller
3244 | S0006 | ITAL-Medical Center | ST-2025-023 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 5, 'cumulative': 9}, {'month': 3, 'enrolled': 3, 'cumulative': 12}, {'month': 4, 'enrolled': 3, 'cumulative': 15}, {'month': 5, 'enrolled': 7, 'cumulative': 22}, {'month': 6, 'enrolled': 5, 'cumulative': 27}] | ON_HOLD | 32 | 32 | 100 | 2.5 | Dr. Lisa Miller | Dr. Jessica Jackson
3245 | S0007 | ITAL-Medical Center | ST-2025-023 | [{'month': 1, 'enrolled': 11, 'cumulative': 11}, {'month': 2, 'enrolled': 9, 'cumulative': 20}, {'month': 3, 'enrolled': 12, 'cumulative': 32}, {'month': 4, 'enrolled': 12, 'cumulative': 44}, {'month': 5, 'enrolled': 10, 'cumulative': 54}, {'month': 6, 'enrolled': 9, 'cumulative': 63}] | ENROLLING | 64 | 64 | 100 | 5.8 | Dr. Emily White | Dr. Stephanie Martin
3246 | S0008 | ITAL-General Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 6, 'cumulative': 8}, {'month': 3, 'enrolled': 6, 'cumulative': 14}, {'month': 4, 'enrolled': 4, 'cumulative': 18}, {'month': 5, 'enrolled': 6, 'cumulative': 24}, {'month': 6, 'enrolled': 4, 'cumulative': 28}] | ON_HOLD | 33 | 28 | 84.8 | 1.9 | Dr. Michelle Anderson | Dr. Sarah Martin
3247 | S0009 | ITAL-Clinical Center | ST-2025-023 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 4, 'cumulative': 9}, {'month': 3, 'enrolled': 4, 'cumulative': 13}, {'month': 4, 'enrolled': 8, 'cumulative': 21}, {'month': 5, 'enrolled': 8, 'cumulative': 29}, {'month': 6, 'enrolled': 6, 'cumulative': 35}] | ON_HOLD | 46 | 40 | 87 | 3.1 | Dr. Nicole Davis | Dr. Sarah Thompson
3248 | S0010 | ITAL-Medical Center | ST-2025-023 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 31 | 1 | 3.2 | 0.1 | Dr. Thomas Moore | Dr. Michael Wilson
3249 | S0011 | POLA-University Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 11, 'cumulative': 11}, {'month': 2, 'enrolled': 11, 'cumulative': 22}, {'month': 3, 'enrolled': 13, 'cumulative': 35}, {'month': 4, 'enrolled': 11, 'cumulative': 46}, {'month': 5, 'enrolled': 9, 'cumulative': 55}, {'month': 6, 'enrolled': 9, 'cumulative': 64}] | SCREENING | 70 | 70 | 100 | 5 | Dr. Thomas Harris | Dr. Robert Anderson
3250 | S0012 | POLA-General Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 5, 'cumulative': 7}, {'month': 3, 'enrolled': 4, 'cumulative': 11}, {'month': 4, 'enrolled': 6, 'cumulative': 17}, {'month': 5, 'enrolled': 2, 'cumulative': 19}, {'month': 6, 'enrolled': 5, 'cumulative': 24}] | ON_HOLD | 43 | 26 | 60.5 | 1.5 | Dr. Stephanie Thomas | Dr. Nicole Garcia
3251 | S0013 | POLA-Health System | ST-2025-023 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 4, 'cumulative': 9}, {'month': 3, 'enrolled': 7, 'cumulative': 16}, {'month': 4, 'enrolled': 7, 'cumulative': 23}, {'month': 5, 'enrolled': 7, 'cumulative': 30}, {'month': 6, 'enrolled': 7, 'cumulative': 37}] | ON_HOLD | 46 | 35 | 76.1 | 3.9 | Dr. Michael Martin | Dr. Robert Garcia
3252 | S0014 | POLA-University Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 5, 'cumulative': 9}, {'month': 3, 'enrolled': 5, 'cumulative': 14}, {'month': 4, 'enrolled': 5, 'cumulative': 19}, {'month': 5, 'enrolled': 7, 'cumulative': 26}, {'month': 6, 'enrolled': 4, 'cumulative': 30}] | CLOSED | 47 | 33 | 70.2 | 4.1 | Dr. Nicole Brown | Dr. Stephanie Martin
3253 | S0015 | POLA-Research Institute | ST-2025-023 | [{'month': 1, 'enrolled': 10, 'cumulative': 10}, {'month': 2, 'enrolled': 11, 'cumulative': 21}, {'month': 3, 'enrolled': 8, 'cumulative': 29}, {'month': 4, 'enrolled': 7, 'cumulative': 36}, {'month': 5, 'enrolled': 9, 'cumulative': 45}, {'month': 6, 'enrolled': 11, 'cumulative': 56}] | SCREENING | 68 | 54 | 79.4 | 6 | Dr. Michelle Johnson | Dr. James Thomas
3254 | S0016 | POLA-Research Institute | ST-2025-023 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 1, 'cumulative': 5}, {'month': 3, 'enrolled': 2, 'cumulative': 7}, {'month': 4, 'enrolled': 3, 'cumulative': 10}, {'month': 5, 'enrolled': 0, 'cumulative': 10}, {'month': 6, 'enrolled': 1, 'cumulative': 11}] | CLOSED | 40 | 12 | 30 | 1.1 | Dr. Jennifer Garcia | Dr. Daniel Johnson
3255 | S0017 | JAPA-University Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 9, 'cumulative': 9}, {'month': 2, 'enrolled': 9, 'cumulative': 18}, {'month': 3, 'enrolled': 6, 'cumulative': 24}, {'month': 4, 'enrolled': 6, 'cumulative': 30}, {'month': 5, 'enrolled': 6, 'cumulative': 36}, {'month': 6, 'enrolled': 9, 'cumulative': 45}] | ON_HOLD | 50 | 50 | 100 | 2.9 | Dr. Emily Johnson | Dr. Christopher Harris
3256 | S0018 | JAPA-Cancer Center | ST-2025-023 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 6, 'cumulative': 10}, {'month': 3, 'enrolled': 4, 'cumulative': 14}, {'month': 4, 'enrolled': 6, 'cumulative': 20}, {'month': 5, 'enrolled': 3, 'cumulative': 23}, {'month': 6, 'enrolled': 5, 'cumulative': 28}] | ENROLLING | 30 | 30 | 100 | 1.7 | Dr. Emily Brown | Dr. Michelle Johnson
3257 | S0019 | JAPA-Health System | ST-2025-023 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 4, 'cumulative': 9}, {'month': 3, 'enrolled': 5, 'cumulative': 14}, {'month': 4, 'enrolled': 5, 'cumulative': 19}, {'month': 5, 'enrolled': 5, 'cumulative': 24}, {'month': 6, 'enrolled': 4, 'cumulative': 28}] | ENROLLING | 22 | 22 | 100 | 3.1 | Dr. Emily Miller | Dr. Amanda Garcia
3258 | S0020 | JAPA-General Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 6, 'cumulative': 10}, {'month': 3, 'enrolled': 5, 'cumulative': 15}, {'month': 4, 'enrolled': 5, 'cumulative': 20}, {'month': 5, 'enrolled': 5, 'cumulative': 25}, {'month': 6, 'enrolled': 5, 'cumulative': 30}] | ON_HOLD | 26 | 26 | 100 | 2.6 | Dr. Christopher Thompson | Dr. Nicole Brown
3259 | S0021 | JAPA-University Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 6, 'cumulative': 6}, {'month': 2, 'enrolled': 4, 'cumulative': 10}, {'month': 3, 'enrolled': 4, 'cumulative': 14}, {'month': 4, 'enrolled': 7, 'cumulative': 21}, {'month': 5, 'enrolled': 4, 'cumulative': 25}, {'month': 6, 'enrolled': 6, 'cumulative': 31}] | SCREENING | 38 | 35 | 92.1 | 2.2 | Dr. Thomas Jones | Dr. Emily Miller
3260 | S0022 | JAPA-Clinical Center | ST-2025-023 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 2, 'cumulative': 6}, {'month': 3, 'enrolled': 5, 'cumulative': 11}, {'month': 4, 'enrolled': 5, 'cumulative': 16}, {'month': 5, 'enrolled': 1, 'cumulative': 17}, {'month': 6, 'enrolled': 2, 'cumulative': 19}] | ENROLLING | 36 | 19 | 52.8 | 1.6 | Dr. Lisa Martin | Dr. Thomas Anderson
3261 | S0023 | MEXI-General Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 28, 'cumulative': 28}, {'month': 2, 'enrolled': 28, 'cumulative': 56}, {'month': 3, 'enrolled': 25, 'cumulative': 81}, {'month': 4, 'enrolled': 26, 'cumulative': 107}, {'month': 5, 'enrolled': 29, 'cumulative': 136}, {'month': 6, 'enrolled': 27, 'cumulative': 163}] | ENROLLING | 162 | 162 | 100 | 18 | Dr. Daniel White | Dr. Lisa Jones
3262 | S0024 | MEXI-Cancer Center | ST-2025-023 | [{'month': 1, 'enrolled': 10, 'cumulative': 10}, {'month': 2, 'enrolled': 14, 'cumulative': 24}, {'month': 3, 'enrolled': 13, 'cumulative': 37}, {'month': 4, 'enrolled': 10, 'cumulative': 47}, {'month': 5, 'enrolled': 10, 'cumulative': 57}, {'month': 6, 'enrolled': 12, 'cumulative': 69}] | SCREENING | 93 | 75 | 80.6 | 6.2 | Dr. Stephanie Harris | Dr. Daniel Thomas
3263 | S0025 | MEXI-Medical Center | ST-2025-023 | [{'month': 1, 'enrolled': 22, 'cumulative': 22}, {'month': 2, 'enrolled': 20, 'cumulative': 42}, {'month': 3, 'enrolled': 18, 'cumulative': 60}, {'month': 4, 'enrolled': 22, 'cumulative': 82}, {'month': 5, 'enrolled': 19, 'cumulative': 101}, {'month': 6, 'enrolled': 18, 'cumulative': 119}] | ENROLLING | 139 | 124 | 89.2 | 9.5 | Dr. James Thompson | Dr. Michael Williams
3264 | S0001 | UNIT-Research Institute | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 3, 'cumulative': 5}, {'month': 4, 'enrolled': 3, 'cumulative': 8}, {'month': 5, 'enrolled': 2, 'cumulative': 10}, {'month': 6, 'enrolled': 0, 'cumulative': 10}] | ENROLLING | 13 | 13 | 100 | 1.1 | Dr. Thomas Jones | Dr. Stephanie Taylor
3265 | S0002 | UNIT-Research Institute | ST-2025-024 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ENROLLING | 6 | 3 | 50 | 0.2 | Dr. Sarah Miller | Dr. Lisa Davis
3266 | S0003 | UNIT-Clinical Center | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 5 | 5 | 100 | 0.4 | Dr. Charles Brown | Dr. William Johnson
3267 | S0004 | UNIT-Research Institute | ST-2025-024 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 10 | 7 | 70 | 0.5 | Dr. Stephanie Williams | Dr. Nicole Smith
3268 | S0005 | UNIT-Clinical Center | ST-2025-024 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | 5 | 5 | 100 | 0.3 | Dr. James Wilson | Dr. Michelle Brown
3269 | S0006 | UNIT-University Hospital | ST-2025-024 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 3, 'cumulative': 7}, {'month': 4, 'enrolled': 3, 'cumulative': 10}, {'month': 5, 'enrolled': 1, 'cumulative': 11}, {'month': 6, 'enrolled': 1, 'cumulative': 12}] | SCREENING | 12 | 18 | 150 | 1 | Dr. Robert Anderson | Dr. Stephanie Harris
3270 | S0007 | MEXI-Medical Center | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 3, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | SCREENING | 7 | 7 | 100 | 0.5 | Dr. Jessica Garcia | Dr. James Johnson
3271 | S0008 | MEXI-Clinical Center | ST-2025-024 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 7 | 6 | 85.7 | 0.6 | Dr. William Jackson | Dr. Amanda Miller
3272 | S0009 | MEXI-Health System | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ENROLLING | 4 | 3 | 75 | 0.2 | Dr. Sarah Garcia | Dr. Michelle Williams
3273 | S0010 | MEXI-Research Institute | ST-2025-024 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 2, 'cumulative': 5}, {'month': 3, 'enrolled': 0, 'cumulative': 5}, {'month': 4, 'enrolled': 2, 'cumulative': 7}, {'month': 5, 'enrolled': 3, 'cumulative': 10}, {'month': 6, 'enrolled': 0, 'cumulative': 10}] | ENROLLING | 10 | 10 | 100 | 1.4 | Dr. Emily Jones | Dr. Michelle Wilson
3274 | S0011 | MEXI-Clinical Center | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 6 | 5 | 83.3 | 0.6 | Dr. Daniel Taylor | Dr. Thomas Wilson
3275 | S0012 | MEXI-Cancer Center | ST-2025-024 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 3, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 4, 'cumulative': 10}] | ENROLLING | 10 | 13 | 130 | 0.8 | Dr. William Davis | Dr. Thomas Taylor
3276 | S0013 | SWED-Medical Center | ST-2025-024 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 3, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 12 | 8 | 66.7 | 1.3 | Dr. Jennifer White | Dr. Michelle Martin
3277 | S0014 | SWED-Cancer Center | ST-2025-024 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 4, 'cumulative': 7}, {'month': 3, 'enrolled': 4, 'cumulative': 11}, {'month': 4, 'enrolled': 1, 'cumulative': 12}, {'month': 5, 'enrolled': 5, 'cumulative': 17}, {'month': 6, 'enrolled': 4, 'cumulative': 21}] | CLOSED | 20 | 20 | 100 | 1.7 | Dr. Michael Williams | Dr. Michelle Smith
3278 | S0015 | SWED-Cancer Center | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | ON_HOLD | 11 | 5 | 45.5 | 0.3 | Dr. Emily Thomas | Dr. Charles Thomas
3279 | S0016 | SWED-Clinical Center | ST-2025-024 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | CLOSED | 19 | 0 | 0 | 0 | Dr. James Brown | Dr. Christopher Thomas
3280 | S0017 | SWIT-Medical Center | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 20 | 0 | 0 | 0 | Dr. Amanda Miller | Dr. Michael Anderson
3281 | S0018 | SWIT-Cancer Center | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 13 | 0 | 0 | 0 | Dr. Lisa Martin | Dr. Amanda Johnson
3282 | S0019 | JAPA-Cancer Center | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 7 | 0 | 0 | 0 | Dr. Daniel Martin | Dr. Jennifer Moore
3283 | S0020 | JAPA-University Hospital | ST-2025-024 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 10 | 0 | 0 | 0 | Dr. Jennifer Williams | Dr. Robert Williams
3284 | S0021 | JAPA-University Hospital | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 2, 'cumulative': 2}] | CLOSED | 8 | 0 | 0 | 0 | Dr. Lisa Thompson | Dr. William Miller
3285 | S0022 | JAPA-Cancer Center | ST-2025-024 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 2, 'cumulative': 7}] | SCREENING | 5 | 0 | 0 | 0 | Dr. Michelle Wilson | Dr. Michelle Harris
3286 | S0001 | CANA-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -35 | -35 | 100 | -5.8 | Dr. David Moore | Dr. Jessica Jones
3287 | S0002 | CANA-Research Institute | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ENROLLING | 3 | 3 | 100 | 0.3 | Dr. William Jones | Dr. Daniel Martin
3288 | S0003 | CANA-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. Nicole Williams | Dr. Jennifer Thompson
3289 | S0004 | UNIT-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | -1 | -1 | 100 | -0.1 | Dr. Amanda Thompson | Dr. Nicole Martin
3290 | S0005 | UNIT-Clinical Center | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Charles Johnson | Dr. David Davis
3291 | S0006 | UNIT-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ENROLLING | 3 | 4 | 133.3 | 0.3 | Dr. Charles Miller | Dr. Jessica White
3292 | S0007 | SPAI-Clinical Center | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | -4 | -4 | 100 | -0.3 | Dr. Lisa Johnson | Dr. Christopher Thompson
3293 | S0008 | SPAI-Health System | ST-2025-025 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. Christopher Harris | Dr. Stephanie White
3294 | S0009 | SPAI-Research Institute | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. Thomas Wilson | Dr. Charles Smith
3295 | S0010 | SPAI-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 3 | 4 | 133.3 | 0.3 | Dr. William Williams | Dr. Amanda Williams
3296 | S0011 | SWED-Research Institute | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | -7 | -7 | 100 | -0.8 | Dr. Thomas Wilson | Dr. Jessica Wilson
3297 | S0012 | SWED-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 3 | 2 | 66.7 | 0.1 | Dr. Robert Moore | Dr. William Smith
3298 | S0013 | SWED-Cancer Center | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. Amanda Jackson | Dr. Charles Smith
3299 | S0014 | SWED-Clinical Center | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.1 | Dr. Robert Jackson | Dr. Lisa Davis
3300 | S0015 | SWED-General Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 3 | 4 | 133.3 | 0.2 | Dr. Nicole Davis | Dr. Daniel Moore
3301 | S0016 | NETH-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | -1 | -1 | 100 | -0.1 | Dr. Stephanie Miller | Dr. Christopher Harris
3302 | S0017 | NETH-Cancer Center | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Amanda Jones | Dr. Robert Anderson
3303 | S0018 | NETH-General Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 2 | 66.7 | 0.3 | Dr. Amanda Taylor | Dr. Lisa White
3304 | S0019 | TAIW-Medical Center | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | -4 | -4 | 100 | -0.5 | Dr. Thomas Jackson | Dr. Charles Miller
3305 | S0020 | TAIW-Clinical Center | ST-2025-025 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.3 | Dr. Charles Miller | Dr. Nicole Brown
3306 | S0021 | TAIW-Research Institute | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | ON_HOLD | 3 | 2 | 66.7 | 0.1 | Dr. Jessica Williams | Dr. Jennifer Brown
3307 | S0022 | TAIW-General Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 3 | 3 | 100 | 0.2 | Dr. Sarah Martin | Dr. James Garcia
3308 | S0023 | AUST-Clinical Center | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | -10 | -10 | 100 | -1.2 | Dr. Robert Moore | Dr. Stephanie Martin
3309 | S0024 | AUST-General Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 2 | 66.7 | 0.3 | Dr. David Jones | Dr. David Anderson
3310 | S0025 | AUST-Clinical Center | ST-2025-025 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | SCREENING | 3 | 1 | 33.3 | 0.1 | Dr. Nicole Garcia | Dr. Jessica Miller
3311 | S0026 | AUST-Health System | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Christopher Wilson | Dr. David Smith
3312 | S0027 | AUST-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. Charles Davis | Dr. Daniel Taylor
3313 | S0028 | AUST-Health System | ST-2025-025 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 3, 'cumulative': 7}, {'month': 4, 'enrolled': 0, 'cumulative': 7}, {'month': 5, 'enrolled': 3, 'cumulative': 10}, {'month': 6, 'enrolled': 3, 'cumulative': 13}] | ENROLLING | 3 | 7 | 233.3 | 0.5 | Dr. Christopher Johnson | Dr. Michael Anderson
3314 | S0029 | CHIL-Cancer Center | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 2 | 1 | 50 | 0.1 | Dr. Charles Garcia | Dr. Stephanie Davis
3315 | S0030 | CHIL-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 3, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 3 | 6 | 200 | 0.4 | Dr. Stephanie Harris | Dr. Charles Garcia
3316 | S0001 | MEXI-University Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 0, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 3, 'cumulative': 7}, {'month': 6, 'enrolled': 3, 'cumulative': 10}] | ON_HOLD | 10 | 10 | 100 | 1 | Dr. David Jackson | Dr. Jessica Smith
3317 | S0002 | MEXI-University Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 4 | 2 | 50 | 0.2 | Dr. Emily Williams | Dr. Stephanie Thompson
3318 | S0003 | MEXI-Clinical Center | ST-2025-026 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 2, 'cumulative': 6}, {'month': 4, 'enrolled': 0, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Stephanie Garcia | Dr. Jennifer Thomas
3319 | S0004 | MEXI-University Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. David Martin | Dr. Jennifer Thompson
3320 | S0005 | MEXI-Medical Center | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. David Garcia | Dr. David Johnson
3321 | S0006 | MEXI-General Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ENROLLING | 5 | 4 | 80 | 0.5 | Dr. William White | Dr. Christopher Brown
3322 | S0007 | CANA-Research Institute | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 4, 'cumulative': 6}, {'month': 4, 'enrolled': 3, 'cumulative': 9}, {'month': 5, 'enrolled': 1, 'cumulative': 10}, {'month': 6, 'enrolled': 3, 'cumulative': 13}] | SCREENING | 21 | 17 | 81 | 2.8 | Dr. Lisa Martin | Dr. Nicole Brown
3323 | S0008 | CANA-Medical Center | ST-2025-026 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 9 | 6 | 66.7 | 1 | Dr. James Johnson | Dr. Emily Miller
3324 | S0009 | CANA-Health System | ST-2025-026 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 3, 'cumulative': 5}, {'month': 5, 'enrolled': 3, 'cumulative': 8}, {'month': 6, 'enrolled': 2, 'cumulative': 10}] | ENROLLING | 11 | 17 | 154.5 | 0.9 | Dr. Charles Thompson | Dr. William Martin
3325 | S0010 | SWIT-Research Institute | ST-2025-026 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 5, 'cumulative': 8}, {'month': 4, 'enrolled': 4, 'cumulative': 12}, {'month': 5, 'enrolled': 3, 'cumulative': 15}, {'month': 6, 'enrolled': 4, 'cumulative': 19}] | ON_HOLD | 24 | 20 | 83.3 | 1.2 | Dr. Thomas Davis | Dr. Amanda Jackson
3326 | S0011 | SWIT-Clinical Center | ST-2025-026 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 2, 'cumulative': 5}, {'month': 4, 'enrolled': 2, 'cumulative': 7}, {'month': 5, 'enrolled': 0, 'cumulative': 7}, {'month': 6, 'enrolled': 3, 'cumulative': 10}] | SCREENING | 19 | 10 | 52.6 | 0.7 | Dr. Amanda Taylor | Dr. Emily Smith
3327 | S0012 | SWED-Cancer Center | ST-2025-026 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 3, 'cumulative': 5}, {'month': 5, 'enrolled': 2, 'cumulative': 7}, {'month': 6, 'enrolled': 0, 'cumulative': 7}] | SCREENING | 9 | 8 | 88.9 | 0.9 | Dr. Christopher Martin | Dr. Daniel White
3328 | S0013 | SWED-General Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 3, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 2, 'cumulative': 7}] | ENROLLING | 7 | 7 | 100 | 0.8 | Dr. Thomas Smith | Dr. Amanda Johnson
3329 | S0014 | SWED-Cancer Center | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 7 | 5 | 71.4 | 0.3 | Dr. Christopher Davis | Dr. Nicole Jackson
3330 | S0015 | SWED-General Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | ENROLLING | 8 | 8 | 100 | 0.5 | Dr. Amanda White | Dr. Nicole Brown
3331 | S0016 | SWED-General Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 4 | 5 | 125 | 0.4 | Dr. David Jones | Dr. Daniel Thompson
3332 | S0017 | SING-Cancer Center | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 3, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | SCREENING | 13 | 13 | 100 | 1 | Dr. Christopher Brown | Dr. Nicole Moore
3333 | S0018 | SING-University Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 21 | 4 | 19 | 0.4 | Dr. Jennifer Williams | Dr. Emily White
3334 | S0019 | SING-General Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | SCREENING | 12 | 0 | 0 | 0 | Dr. Thomas Jackson | Dr. William Davis
3335 | S0020 | NEW-Clinical Center | ST-2025-026 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 18 | 0 | 0 | 0 | Dr. Thomas Davis | Dr. Michael Taylor
3336 | S0021 | NEW-Clinical Center | ST-2025-026 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 15 | 0 | 0 | 0 | Dr. Charles Moore | Dr. Stephanie Davis
3337 | S0022 | NEW-University Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | SCREENING | 19 | 0 | 0 | 0 | Dr. Jessica Williams | Dr. Emily Williams
3338 | S0023 | NEW-Research Institute | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | CLOSED | 15 | 0 | 0 | 0 | Dr. David Brown | Dr. Amanda Jones
3339 | S0001 | MEXI-Medical Center | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 2, 'cumulative': 2}] | SCREENING | 2 | 1 | 50 | 0.1 | Dr. Robert Jones | Dr. Robert Jackson
3340 | S0002 | MEXI-Health System | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Sarah Thomas | Dr. Lisa White
3341 | S0003 | MEXI-General Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. Christopher Thomas | Dr. Christopher Thompson
3342 | S0004 | MEXI-Research Institute | ST-2025-027 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Daniel Davis | Dr. Jessica Williams
3343 | S0005 | MEXI-Research Institute | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Michael Williams | Dr. Michael Davis
3344 | S0006 | MEXI-Medical Center | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 3, 'cumulative': 3}, {'month': 3, 'enrolled': 3, 'cumulative': 6}, {'month': 4, 'enrolled': 1, 'cumulative': 7}, {'month': 5, 'enrolled': 1, 'cumulative': 8}, {'month': 6, 'enrolled': 2, 'cumulative': 10}] | SCREENING | 3 | 7 | 233.3 | 0.9 | Dr. Sarah Williams | Dr. Jessica Moore
3345 | S0007 | CANA-Clinical Center | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 4 | 2 | 50 | 0.1 | Dr. Robert Martin | Dr. Nicole Thompson
3346 | S0008 | CANA-General Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 4 | 133.3 | 0.2 | Dr. Emily Jackson | Dr. James Miller
3347 | S0009 | UNIT-University Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | CLOSED | 3 | 3 | 100 | 0.2 | Dr. Daniel Johnson | Dr. Christopher Garcia
3348 | S0010 | UNIT-General Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | CLOSED | 3 | 3 | 100 | 0.2 | Dr. Lisa Garcia | Dr. Michael Thomas
3349 | S0011 | UNIT-Cancer Center | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Amanda Johnson | Dr. Stephanie Martin
3350 | S0012 | SWIT-General Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ON_HOLD | 7 | 4 | 57.1 | 0.4 | Dr. Emily Anderson | Dr. Jessica Martin
3351 | S0013 | SWIT-Research Institute | ST-2025-027 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 3, 'cumulative': 5}, {'month': 3, 'enrolled': 2, 'cumulative': 7}, {'month': 4, 'enrolled': 3, 'cumulative': 10}, {'month': 5, 'enrolled': 2, 'cumulative': 12}, {'month': 6, 'enrolled': 2, 'cumulative': 14}] | ENROLLING | 5 | 7 | 140 | 0.7 | Dr. James Jackson | Dr. David Anderson
3352 | S0014 | SPAI-Clinical Center | ST-2025-027 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 2 | 2 | 100 | 0.2 | Dr. Amanda Brown | Dr. James Thomas
3353 | S0015 | SPAI-General Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | ON_HOLD | 3 | 3 | 100 | 0.4 | Dr. Amanda Smith | Dr. Emily White
3354 | S0016 | SPAI-Clinical Center | ST-2025-027 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 3 | 1 | 33.3 | 0.1 | Dr. Daniel Thompson | Dr. Robert White
3355 | S0017 | SPAI-Medical Center | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 3 | 1 | 33.3 | 0.1 | Dr. Robert Wilson | Dr. Lisa Martin
3356 | S0018 | SPAI-Clinical Center | ST-2025-027 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 3 | 3 | 100 | 0.3 | Dr. Amanda White | Dr. Jennifer Moore
3357 | S0019 | UNIT-Medical Center | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | ON_HOLD | -3 | -3 | 100 | -0.4 | Dr. Stephanie Taylor | Dr. Sarah Garcia
3358 | S0020 | UNIT-General Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. William Brown | Dr. Stephanie Martin
3359 | S0021 | UNIT-Health System | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | CLOSED | 3 | 3 | 100 | 0.2 | Dr. Robert Taylor | Dr. Charles Thompson
3360 | S0022 | UNIT-General Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | 3 | 2 | 66.7 | 0.1 | Dr. Robert Brown | Dr. Emily Smith
3361 | S0023 | UNIT-University Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. Daniel Smith | Dr. Lisa Johnson
3362 | S0024 | UNIT-General Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. James White | Dr. Nicole Anderson
3363 | S0025 | INDI-Health System | ST-2025-027 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | CLOSED | 6 | 5 | 83.3 | 0.6 | Dr. Daniel Garcia | Dr. Lisa Wilson
3364 | S0026 | INDI-Cancer Center | ST-2025-027 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 4 | 2 | 50 | 0.3 | Dr. Lisa White | Dr. David Martin
3365 | S0027 | SING-University Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | -8 | -8 | 100 | -1 | Dr. James Miller | Dr. Michael Johnson
3366 | S0028 | SING-Clinical Center | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Jessica Davis | Dr. Lisa Taylor
3367 | S0029 | SING-Clinical Center | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Daniel White | Dr. Sarah Anderson
3368 | S0030 | SING-Medical Center | ST-2025-027 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. William Thomas | Dr. Stephanie Davis
3369 | S0031 | SING-Research Institute | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 1 | 33.3 | 0.2 | Dr. Sarah Smith | Dr. Sarah Taylor
3370 | S0032 | SING-University Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 5, 'cumulative': 6}, {'month': 3, 'enrolled': 1, 'cumulative': 7}, {'month': 4, 'enrolled': 4, 'cumulative': 11}, {'month': 5, 'enrolled': 4, 'cumulative': 15}, {'month': 6, 'enrolled': 1, 'cumulative': 16}] | ENROLLING | 3 | 18 | 600 | 1.8 | Dr. William Brown | Dr. Stephanie Garcia
3371 | S0001 | CANA-General Hospital | ST-2025-028 | [{'month': 1, 'enrolled': 872, 'cumulative': 872}, {'month': 2, 'enrolled': 870, 'cumulative': 1742}, {'month': 3, 'enrolled': 870, 'cumulative': 2612}, {'month': 4, 'enrolled': 870, 'cumulative': 3482}, {'month': 5, 'enrolled': 869, 'cumulative': 4351}, {'month': 6, 'enrolled': 870, 'cumulative': 5221}] | ON_HOLD | 10148 | 5228 | 51.5 | 326.8 | Dr. Jessica Thomas | Dr. Emily Wilson
3372 | S0002 | CANA-Clinical Center | ST-2025-028 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 10883 | 0 | 0 | 0 | Dr. William Williams | Dr. James Jones
3373 | S0003 | DENM-Medical Center | ST-2025-028 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 11480 | 0 | 0 | 0 | Dr. William Jones | Dr. Michael Taylor
3374 | S0004 | DENM-University Hospital | ST-2025-028 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | 5807 | 0 | 0 | 0 | Dr. Amanda Taylor | Dr. Nicole White
3375 | S0005 | DENM-Clinical Center | ST-2025-028 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 5818 | 0 | 0 | 0 | Dr. Thomas Jones | Dr. Lisa Jackson
3376 | S0006 | DENM-Clinical Center | ST-2025-028 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 8503 | 0 | 0 | 0 | Dr. Michelle Moore | Dr. Nicole Moore
3377 | S0007 | AUST-Cancer Center | ST-2025-028 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 6775 | 0 | 0 | 0 | Dr. Lisa Williams | Dr. Lisa Thomas
3378 | S0008 | AUST-Medical Center | ST-2025-028 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 4772 | 0 | 0 | 0 | Dr. Amanda Moore | Dr. Nicole Jones
3379 | S0009 | AUST-Medical Center | ST-2025-028 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 3814 | 0 | 0 | 0 | Dr. Amanda Jones | Dr. Jessica Harris
3380 | S0001 | MEXI-Cancer Center | ST-2025-029 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 3, 'cumulative': 7}, {'month': 3, 'enrolled': 0, 'cumulative': 7}, {'month': 4, 'enrolled': 1, 'cumulative': 8}, {'month': 5, 'enrolled': 3, 'cumulative': 11}, {'month': 6, 'enrolled': 0, 'cumulative': 11}] | SCREENING | 18 | 16 | 88.9 | 2.3 | Dr. Emily Harris | Dr. Thomas Garcia
3381 | S0002 | MEXI-Research Institute | ST-2025-029 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 2, 'cumulative': 5}, {'month': 4, 'enrolled': 2, 'cumulative': 7}, {'month': 5, 'enrolled': 0, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | ENROLLING | 8 | 8 | 100 | 1 | Dr. William Thomas | Dr. Amanda Williams
3382 | S0003 | MEXI-Medical Center | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 3, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | ON_HOLD | 17 | 11 | 64.7 | 1.4 | Dr. Christopher Wilson | Dr. Nicole Wilson
3383 | S0004 | UNIT-Clinical Center | ST-2025-029 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 5 | 4 | 80 | 0.4 | Dr. Thomas Thomas | Dr. Michael White
3384 | S0005 | UNIT-Health System | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. Sarah Johnson | Dr. Lisa Moore
3385 | S0006 | UNIT-Medical Center | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Jessica Jackson | Dr. Jennifer Jackson
3386 | S0007 | UNIT-Cancer Center | ST-2025-029 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | SCREENING | 3 | 2 | 66.7 | 0.3 | Dr. Charles Harris | Dr. Michael Thomas
3387 | S0008 | UNIT-Clinical Center | ST-2025-029 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 3 | 3 | 100 | 0.2 | Dr. Michelle Harris | Dr. Emily Williams
3388 | S0009 | UNIT-University Hospital | ST-2025-029 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Charles White | Dr. David Jackson
3389 | S0010 | NETH-Clinical Center | ST-2025-029 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 0, 'cumulative': 3}, {'month': 3, 'enrolled': 3, 'cumulative': 6}, {'month': 4, 'enrolled': 2, 'cumulative': 8}, {'month': 5, 'enrolled': 1, 'cumulative': 9}, {'month': 6, 'enrolled': 3, 'cumulative': 12}] | ON_HOLD | 7 | 6 | 85.7 | 0.8 | Dr. David Taylor | Dr. Sarah Jackson
3390 | S0011 | NETH-Medical Center | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 5 | 3 | 60 | 0.2 | Dr. Stephanie Martin | Dr. David Johnson
3391 | S0012 | NETH-University Hospital | ST-2025-029 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 9 | 5 | 55.6 | 0.8 | Dr. Stephanie Wilson | Dr. William Garcia
3392 | S0013 | NETH-Medical Center | ST-2025-029 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ENROLLING | 6 | 4 | 66.7 | 0.5 | Dr. William Jackson | Dr. Michael Anderson
3393 | S0014 | NETH-Cancer Center | ST-2025-029 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 2, 'cumulative': 5}, {'month': 3, 'enrolled': 1, 'cumulative': 6}, {'month': 4, 'enrolled': 1, 'cumulative': 7}, {'month': 5, 'enrolled': 1, 'cumulative': 8}, {'month': 6, 'enrolled': 2, 'cumulative': 10}] | SCREENING | 7 | 12 | 171.4 | 0.7 | Dr. Stephanie Thompson | Dr. David Wilson
3394 | S0015 | BELG-Clinical Center | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 3, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ENROLLING | 6 | 6 | 100 | 0.5 | Dr. Michelle Garcia | Dr. Stephanie Thomas
3395 | S0016 | BELG-General Hospital | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 4 | 3 | 75 | 0.2 | Dr. James Moore | Dr. David Williams
3396 | S0017 | BELG-General Hospital | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 3, 'cumulative': 5}, {'month': 4, 'enrolled': 0, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 10 | 7 | 70 | 0.4 | Dr. Robert Taylor | Dr. Thomas Smith
3397 | S0018 | BELG-University Hospital | ST-2025-029 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ENROLLING | 7 | 11 | 157.1 | 0.8 | Dr. Nicole Taylor | Dr. Emily White
3398 | S0019 | AUST-General Hospital | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 6 | 5 | 83.3 | 0.6 | Dr. Michelle Garcia | Dr. Charles Miller
3399 | S0020 | AUST-Research Institute | ST-2025-029 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | SCREENING | 6 | 4 | 66.7 | 0.4 | Dr. James Thomas | Dr. Amanda Smith
3400 | S0021 | AUST-Research Institute | ST-2025-029 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 8 | 0 | 0 | 0 | Dr. Emily Martin | Dr. Christopher White
3401 | S0022 | AUST-Clinical Center | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 7 | 0 | 0 | 0 | Dr. Michelle White | Dr. Daniel Taylor
3402 | S0023 | AUST-Medical Center | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 2, 'cumulative': 7}] | ON_HOLD | 7 | 0 | 0 | 0 | Dr. Stephanie Thomas | Dr. Jennifer Moore
3403 | S0024 | INDI-Clinical Center | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 16 | 0 | 0 | 0 | Dr. Emily Williams | Dr. Emily Williams
3404 | S0025 | INDI-General Hospital | ST-2025-029 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | CLOSED | 14 | 0 | 0 | 0 | Dr. Stephanie Brown | Dr. Nicole Moore
3405 | S0026 | INDI-Medical Center | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | 12 | 0 | 0 | 0 | Dr. Daniel Johnson | Dr. Jessica White
3406 | S0001 | UNIT-Health System | ST-2025-030 | [{'month': 1, 'enrolled': 9, 'cumulative': 9}, {'month': 2, 'enrolled': 11, 'cumulative': 20}, {'month': 3, 'enrolled': 7, 'cumulative': 27}, {'month': 4, 'enrolled': 7, 'cumulative': 34}, {'month': 5, 'enrolled': 10, 'cumulative': 44}, {'month': 6, 'enrolled': 9, 'cumulative': 53}] | SCREENING | 73 | 57 | 78.1 | 9.5 | Dr. Jessica Harris | Dr. Nicole Brown
3407 | S0002 | UNIT-Cancer Center | ST-2025-030 | [{'month': 1, 'enrolled': 11, 'cumulative': 11}, {'month': 2, 'enrolled': 14, 'cumulative': 25}, {'month': 3, 'enrolled': 13, 'cumulative': 38}, {'month': 4, 'enrolled': 11, 'cumulative': 49}, {'month': 5, 'enrolled': 11, 'cumulative': 60}, {'month': 6, 'enrolled': 13, 'cumulative': 73}] | ON_HOLD | 85 | 81 | 95.3 | 7.4 | Dr. Emily Smith | Dr. Lisa Johnson
3408 | S0003 | CANA-Medical Center | ST-2025-030 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 4, 'cumulative': 7}, {'month': 3, 'enrolled': 4, 'cumulative': 11}, {'month': 4, 'enrolled': 6, 'cumulative': 17}, {'month': 5, 'enrolled': 6, 'cumulative': 23}, {'month': 6, 'enrolled': 3, 'cumulative': 26}] | ENROLLING | 37 | 24 | 64.9 | 1.4 | Dr. William Johnson | Dr. Emily Johnson
3409 | S0004 | CANA-Research Institute | ST-2025-030 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 3, 'cumulative': 7}, {'month': 6, 'enrolled': 4, 'cumulative': 11}] | ENROLLING | 16 | 16 | 100 | 2.3 | Dr. Thomas Jackson | Dr. William Garcia
3410 | S0005 | CANA-University Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 6, 'cumulative': 10}, {'month': 3, 'enrolled': 5, 'cumulative': 15}, {'month': 4, 'enrolled': 4, 'cumulative': 19}, {'month': 5, 'enrolled': 7, 'cumulative': 26}, {'month': 6, 'enrolled': 6, 'cumulative': 32}] | ENROLLING | 39 | 39 | 100 | 2.6 | Dr. Emily Jones | Dr. Thomas Jones
3411 | S0006 | CANA-Cancer Center | ST-2025-030 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 6, 'cumulative': 10}, {'month': 3, 'enrolled': 6, 'cumulative': 16}, {'month': 4, 'enrolled': 6, 'cumulative': 22}, {'month': 5, 'enrolled': 3, 'cumulative': 25}, {'month': 6, 'enrolled': 5, 'cumulative': 30}] | ENROLLING | 35 | 35 | 100 | 2.3 | Dr. Christopher Brown | Dr. Daniel Thompson
3412 | S0007 | CANA-University Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 6, 'cumulative': 10}, {'month': 3, 'enrolled': 4, 'cumulative': 14}, {'month': 4, 'enrolled': 3, 'cumulative': 17}, {'month': 5, 'enrolled': 6, 'cumulative': 23}, {'month': 6, 'enrolled': 5, 'cumulative': 28}] | ENROLLING | 32 | 29 | 90.6 | 1.9 | Dr. Nicole Wilson | Dr. Thomas Martin
3413 | S0008 | CANA-University Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 7, 'cumulative': 12}, {'month': 3, 'enrolled': 4, 'cumulative': 16}, {'month': 4, 'enrolled': 4, 'cumulative': 20}, {'month': 5, 'enrolled': 5, 'cumulative': 25}, {'month': 6, 'enrolled': 4, 'cumulative': 29}] | ENROLLING | 18 | 34 | 188.9 | 4.9 | Dr. Jessica Williams | Dr. Amanda Moore
3414 | S0009 | MEXI-Clinical Center | ST-2025-030 | [{'month': 1, 'enrolled': 8, 'cumulative': 8}, {'month': 2, 'enrolled': 9, 'cumulative': 17}, {'month': 3, 'enrolled': 6, 'cumulative': 23}, {'month': 4, 'enrolled': 7, 'cumulative': 30}, {'month': 5, 'enrolled': 7, 'cumulative': 37}, {'month': 6, 'enrolled': 5, 'cumulative': 42}] | ON_HOLD | 47 | 42 | 89.4 | 6 | Dr. David Thompson | Dr. Daniel Taylor
3415 | S0010 | MEXI-Cancer Center | ST-2025-030 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 4, 'cumulative': 6}, {'month': 3, 'enrolled': 3, 'cumulative': 9}, {'month': 4, 'enrolled': 4, 'cumulative': 13}, {'month': 5, 'enrolled': 1, 'cumulative': 14}, {'month': 6, 'enrolled': 3, 'cumulative': 17}] | CLOSED | 24 | 17 | 70.8 | 1.7 | Dr. Christopher Jones | Dr. Daniel Brown
3416 | S0011 | MEXI-University Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 7, 'cumulative': 7}, {'month': 2, 'enrolled': 4, 'cumulative': 11}, {'month': 3, 'enrolled': 5, 'cumulative': 16}, {'month': 4, 'enrolled': 8, 'cumulative': 24}, {'month': 5, 'enrolled': 7, 'cumulative': 31}, {'month': 6, 'enrolled': 6, 'cumulative': 37}] | ON_HOLD | 37 | 37 | 100 | 4.1 | Dr. Charles Harris | Dr. Daniel Miller
3417 | S0012 | MEXI-Cancer Center | ST-2025-030 | [{'month': 1, 'enrolled': 8, 'cumulative': 8}, {'month': 2, 'enrolled': 6, 'cumulative': 14}, {'month': 3, 'enrolled': 7, 'cumulative': 21}, {'month': 4, 'enrolled': 6, 'cumulative': 27}, {'month': 5, 'enrolled': 7, 'cumulative': 34}, {'month': 6, 'enrolled': 7, 'cumulative': 41}] | SCREENING | 44 | 38 | 86.4 | 3.2 | Dr. Michael Wilson | Dr. Stephanie Garcia
3418 | S0013 | MEXI-General Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 5, 'cumulative': 10}, {'month': 3, 'enrolled': 5, 'cumulative': 15}, {'month': 4, 'enrolled': 2, 'cumulative': 17}, {'month': 5, 'enrolled': 6, 'cumulative': 23}, {'month': 6, 'enrolled': 2, 'cumulative': 25}] | CLOSED | 39 | 29 | 74.4 | 2.9 | Dr. Emily Jones | Dr. Christopher Brown
3419 | S0014 | MEXI-General Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 19 | 0 | 0 | 0 | Dr. James Harris | Dr. Jennifer Wilson
3420 | S0015 | POLA-Research Institute | ST-2025-030 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 5, 'cumulative': 10}, {'month': 3, 'enrolled': 3, 'cumulative': 13}, {'month': 4, 'enrolled': 2, 'cumulative': 15}, {'month': 5, 'enrolled': 5, 'cumulative': 20}, {'month': 6, 'enrolled': 5, 'cumulative': 25}] | SCREENING | 21 | 18 | 85.7 | 1.6 | Dr. Sarah Jackson | Dr. Stephanie Miller
3421 | S0016 | POLA-Research Institute | ST-2025-030 | [{'month': 1, 'enrolled': 6, 'cumulative': 6}, {'month': 2, 'enrolled': 4, 'cumulative': 10}, {'month': 3, 'enrolled': 2, 'cumulative': 12}, {'month': 4, 'enrolled': 5, 'cumulative': 17}, {'month': 5, 'enrolled': 3, 'cumulative': 20}, {'month': 6, 'enrolled': 5, 'cumulative': 25}] | ON_HOLD | 40 | 27 | 67.5 | 3 | Dr. Jennifer Wilson | Dr. Daniel Martin
3422 | S0017 | POLA-Health System | ST-2025-030 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 5, 'cumulative': 7}, {'month': 3, 'enrolled': 6, 'cumulative': 13}, {'month': 4, 'enrolled': 5, 'cumulative': 18}, {'month': 5, 'enrolled': 2, 'cumulative': 20}, {'month': 6, 'enrolled': 2, 'cumulative': 22}] | SCREENING | 33 | 29 | 87.9 | 2.4 | Dr. Sarah Davis | Dr. Emily Davis
3423 | S0018 | POLA-Medical Center | ST-2025-030 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 3, 'cumulative': 4}, {'month': 3, 'enrolled': 1, 'cumulative': 5}, {'month': 4, 'enrolled': 3, 'cumulative': 8}, {'month': 5, 'enrolled': 5, 'cumulative': 13}, {'month': 6, 'enrolled': 1, 'cumulative': 14}] | SCREENING | 26 | 23 | 88.5 | 3.8 | Dr. William Davis | Dr. Michael Moore
3424 | S0019 | POLA-Medical Center | ST-2025-030 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 7, 'cumulative': 12}, {'month': 3, 'enrolled': 6, 'cumulative': 18}, {'month': 4, 'enrolled': 5, 'cumulative': 23}, {'month': 5, 'enrolled': 3, 'cumulative': 26}, {'month': 6, 'enrolled': 3, 'cumulative': 29}] | SCREENING | 50 | 31 | 62 | 3.1 | Dr. Charles Jackson | Dr. Charles Brown
3425 | S0020 | POLA-University Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 3, 'cumulative': 6}, {'month': 3, 'enrolled': 0, 'cumulative': 6}, {'month': 4, 'enrolled': 0, 'cumulative': 6}, {'month': 5, 'enrolled': 3, 'cumulative': 9}, {'month': 6, 'enrolled': 0, 'cumulative': 9}] | CLOSED | 20 | 8 | 40 | 0.5 | Dr. William Martin | Dr. David Garcia
3426 | S0021 | SPAI-Medical Center | ST-2025-030 | [{'month': 1, 'enrolled': 14, 'cumulative': 14}, {'month': 2, 'enrolled': 13, 'cumulative': 27}, {'month': 3, 'enrolled': 11, 'cumulative': 38}, {'month': 4, 'enrolled': 11, 'cumulative': 49}, {'month': 5, 'enrolled': 11, 'cumulative': 60}, {'month': 6, 'enrolled': 12, 'cumulative': 72}] | ON_HOLD | 76 | 72 | 94.7 | 9 | Dr. Nicole Anderson | Dr. Lisa Garcia
3427 | S0022 | SPAI-Research Institute | ST-2025-030 | [{'month': 1, 'enrolled': 8, 'cumulative': 8}, {'month': 2, 'enrolled': 6, 'cumulative': 14}, {'month': 3, 'enrolled': 9, 'cumulative': 23}, {'month': 4, 'enrolled': 10, 'cumulative': 33}, {'month': 5, 'enrolled': 7, 'cumulative': 40}, {'month': 6, 'enrolled': 6, 'cumulative': 46}] | ENROLLING | 49 | 49 | 100 | 3.1 | Dr. Jennifer Garcia | Dr. Thomas Harris
3428 | S0023 | SPAI-University Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 3, 'cumulative': 6}, {'month': 3, 'enrolled': 4, 'cumulative': 10}, {'month': 4, 'enrolled': 7, 'cumulative': 17}, {'month': 5, 'enrolled': 3, 'cumulative': 20}, {'month': 6, 'enrolled': 7, 'cumulative': 27}] | ON_HOLD | 45 | 31 | 68.9 | 5.2 | Dr. Nicole White | Dr. Thomas Smith
3429 | S0024 | SWIT-Cancer Center | ST-2025-030 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 2, 'cumulative': 5}, {'month': 4, 'enrolled': 1, 'cumulative': 6}, {'month': 5, 'enrolled': 4, 'cumulative': 10}, {'month': 6, 'enrolled': 1, 'cumulative': 11}] | CLOSED | 21 | 21 | 100 | 3.5 | Dr. Jessica Davis | Dr. Daniel Thompson
3430 | S0025 | SWIT-University Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 4, 'cumulative': 9}, {'month': 3, 'enrolled': 4, 'cumulative': 13}, {'month': 4, 'enrolled': 1, 'cumulative': 14}, {'month': 5, 'enrolled': 1, 'cumulative': 15}, {'month': 6, 'enrolled': 3, 'cumulative': 18}] | SCREENING | 21 | 19 | 90.5 | 1.1 | Dr. Emily Brown | Dr. Jessica Taylor
3431 | S0026 | SWIT-Clinical Center | ST-2025-030 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 3, 'cumulative': 6}, {'month': 3, 'enrolled': 1, 'cumulative': 7}, {'month': 4, 'enrolled': 1, 'cumulative': 8}, {'month': 5, 'enrolled': 4, 'cumulative': 12}, {'month': 6, 'enrolled': 2, 'cumulative': 14}] | CLOSED | 15 | 13 | 86.7 | 1 | Dr. Amanda Moore | Dr. William Martin
3432 | S0027 | SWIT-Research Institute | ST-2025-030 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 4, 'cumulative': 9}, {'month': 3, 'enrolled': 5, 'cumulative': 14}, {'month': 4, 'enrolled': 1, 'cumulative': 15}, {'month': 5, 'enrolled': 4, 'cumulative': 19}, {'month': 6, 'enrolled': 2, 'cumulative': 21}] | ON_HOLD | 32 | 23 | 71.9 | 2.1 | Dr. James Thomas | Dr. Jessica Taylor
3433 | S0028 | SWIT-Health System | ST-2025-030 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 3, 'cumulative': 5}, {'month': 3, 'enrolled': 3, 'cumulative': 8}, {'month': 4, 'enrolled': 3, 'cumulative': 11}, {'month': 5, 'enrolled': 3, 'cumulative': 14}, {'month': 6, 'enrolled': 6, 'cumulative': 20}] | CLOSED | 37 | 24 | 64.9 | 1.3 | Dr. Nicole Brown | Dr. William Thompson
3434 | S0029 | SWIT-General Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 1, 'cumulative': 5}, {'month': 3, 'enrolled': 3, 'cumulative': 8}, {'month': 4, 'enrolled': 3, 'cumulative': 11}, {'month': 5, 'enrolled': 2, 'cumulative': 13}, {'month': 6, 'enrolled': 2, 'cumulative': 15}] | SCREENING | 30 | 12 | 40 | 0.8 | Dr. Robert White | Dr. Lisa Jones
3435 | S0030 | CHIN-General Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 8, 'cumulative': 8}, {'month': 2, 'enrolled': 12, 'cumulative': 20}, {'month': 3, 'enrolled': 11, 'cumulative': 31}, {'month': 4, 'enrolled': 10, 'cumulative': 41}, {'month': 5, 'enrolled': 10, 'cumulative': 51}, {'month': 6, 'enrolled': 11, 'cumulative': 62}] | ON_HOLD | 104 | 64 | 61.5 | 5.3 | Dr. David Williams | Dr. David Jackson
3436 | S0031 | CHIN-General Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 63 | 0 | 0 | 0 | Dr. Michelle Harris | Dr. Daniel Garcia
3437 | S0032 | JAPA-Medical Center | ST-2025-030 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | CLOSED | 32 | 0 | 0 | 0 | Dr. Thomas Brown | Dr. Stephanie Harris
3438 | S0033 | JAPA-Health System | ST-2025-030 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ON_HOLD | 48 | 0 | 0 | 0 | Dr. Jessica Brown | Dr. James Martin
3439 | S0034 | JAPA-General Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 56 | 0 | 0 | 0 | Dr. Robert Thompson | Dr. Jessica Moore
3440 | S0035 | JAPA-General Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 36 | 0 | 0 | 0 | Dr. Nicole Anderson | Dr. Michael Anderson
3441 | S0001 | CANA-University Hospital | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | -2 | -2 | 100 | -0.1 | Dr. Jessica Brown | Dr. Emily Martin
3442 | S0002 | CANA-University Hospital | ST-2025-031 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 3 | 2 | 66.7 | 0.3 | Dr. Michelle Taylor | Dr. James Davis
3443 | S0003 | CANA-Cancer Center | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Charles Thomas | Dr. Michael Garcia
3444 | S0004 | CANA-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Lisa Thompson | Dr. Daniel Anderson
3445 | S0005 | CANA-Clinical Center | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Michelle Brown | Dr. Nicole Wilson
3446 | S0006 | UNIT-Medical Center | ST-2025-031 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 1 | 0 | 0 | 0 | Dr. Michelle Taylor | Dr. Sarah Davis
3447 | S0007 | UNIT-Clinical Center | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Sarah Thomas | Dr. Michael White
3448 | S0008 | UNIT-Health System | ST-2025-031 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Michael Moore | Dr. Nicole Jones
3449 | S0009 | MEXI-Cancer Center | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -10 | -10 | 100 | -0.6 | Dr. Michelle Jackson | Dr. James Moore
3450 | S0010 | MEXI-Clinical Center | ST-2025-031 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | ON_HOLD | 3 | 3 | 100 | 0.5 | Dr. Charles Jones | Dr. Stephanie White
3451 | S0011 | MEXI-Health System | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 3 | 100 | 0.4 | Dr. Christopher Brown | Dr. Amanda Thomas
3452 | S0012 | MEXI-University Hospital | ST-2025-031 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. Sarah Davis | Dr. Lisa Williams
3453 | S0013 | MEXI-Health System | ST-2025-031 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 1, 'cumulative': 5}, {'month': 4, 'enrolled': 2, 'cumulative': 7}, {'month': 5, 'enrolled': 0, 'cumulative': 7}, {'month': 6, 'enrolled': 2, 'cumulative': 9}] | SCREENING | 3 | 1 | 33.3 | 0.2 | Dr. Stephanie Moore | Dr. Sarah Smith
3454 | S0014 | MEXI-Cancer Center | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 2, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Sarah Williams | Dr. Sarah Jones
3455 | S0015 | UNIT-Health System | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | -3 | -3 | 100 | -0.3 | Dr. Amanda Davis | Dr. Christopher Anderson
3456 | S0016 | UNIT-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 3 | 2 | 66.7 | 0.1 | Dr. Jessica Davis | Dr. Daniel Wilson
3457 | S0017 | UNIT-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 3 | 1 | 33.3 | 0.1 | Dr. Daniel Brown | Dr. Sarah Thomas
3458 | S0018 | UNIT-Clinical Center | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Nicole Wilson | Dr. Michael Miller
3459 | S0019 | UNIT-University Hospital | ST-2025-031 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Jessica Moore | Dr. David Brown
3460 | S0020 | UNIT-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Sarah Davis | Dr. Christopher Harris
3461 | S0021 | FRAN-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 6 | 0 | 0 | 0 | Dr. Charles Anderson | Dr. Michael Johnson
3462 | S0022 | FRAN-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Nicole Smith | Dr. Charles Jackson
3463 | S0023 | BELG-Cancer Center | ST-2025-031 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 0 | 0 | 0 | 0 | Dr. Thomas Wilson | Dr. David Smith
3464 | S0024 | BELG-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Stephanie White | Dr. Sarah Brown
3465 | S0025 | BELG-Health System | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Jessica Moore | Dr. Christopher White
3466 | S0026 | BELG-Health System | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Daniel Wilson | Dr. Jennifer Jackson
3467 | S0027 | TAIW-Medical Center | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 5 | 0 | 0 | 0 | Dr. William Williams | Dr. Lisa Moore
3468 | S0028 | TAIW-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | CLOSED | 6 | 0 | 0 | 0 | Dr. Charles Johnson | Dr. William Thomas
3469 | S0029 | JAPA-Clinical Center | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -7 | -7 | 100 | -0.5 | Dr. Christopher Smith | Dr. Christopher Johnson
3470 | S0030 | JAPA-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.2 | Dr. Michelle Miller | Dr. Stephanie Johnson
3471 | S0031 | JAPA-Health System | ST-2025-031 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | ON_HOLD | 3 | 3 | 100 | 0.4 | Dr. Michelle Taylor | Dr. Michael Harris
3472 | S0032 | JAPA-University Hospital | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. William Martin | Dr. Robert Davis
3473 | S0033 | JAPA-General Hospital | ST-2025-031 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Sarah Davis | Dr. Emily Johnson
3474 | S0001 | CANA-Cancer Center | ST-2025-032 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 6, 'cumulative': 10}, {'month': 3, 'enrolled': 2, 'cumulative': 12}, {'month': 4, 'enrolled': 2, 'cumulative': 14}, {'month': 5, 'enrolled': 6, 'cumulative': 20}, {'month': 6, 'enrolled': 3, 'cumulative': 23}] | CLOSED | 62 | 25 | 40.3 | 1.8 | Dr. Sarah Smith | Dr. Lisa Jones
3475 | S0002 | CANA-Health System | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | SCREENING | 56 | 0 | 0 | 0 | Dr. David Wilson | Dr. Nicole Jones
3476 | S0003 | MEXI-General Hospital | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | SCREENING | 26 | 0 | 0 | 0 | Dr. James White | Dr. Michael Martin
3477 | S0004 | MEXI-Health System | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 17 | 0 | 0 | 0 | Dr. Jennifer Johnson | Dr. Stephanie Wilson
3478 | S0005 | MEXI-Health System | ST-2025-032 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | CLOSED | 24 | 0 | 0 | 0 | Dr. Lisa Thomas | Dr. Nicole Thompson
3479 | S0006 | MEXI-General Hospital | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | 15 | 0 | 0 | 0 | Dr. Lisa Anderson | Dr. Nicole Martin
3480 | S0007 | UNIT-Cancer Center | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 17 | 0 | 0 | 0 | Dr. Stephanie Harris | Dr. Thomas Davis
3481 | S0008 | UNIT-General Hospital | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | SCREENING | 10 | 0 | 0 | 0 | Dr. Jennifer Harris | Dr. Thomas Brown
3482 | S0009 | UNIT-Research Institute | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 10 | 0 | 0 | 0 | Dr. Robert Martin | Dr. Nicole White
3483 | S0010 | UNIT-General Hospital | ST-2025-032 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 11 | 0 | 0 | 0 | Dr. Jessica Wilson | Dr. Daniel Miller
3484 | S0011 | NORW-Clinical Center | ST-2025-032 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 18 | 0 | 0 | 0 | Dr. William Johnson | Dr. William Martin
3485 | S0012 | NORW-General Hospital | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 14 | 0 | 0 | 0 | Dr. Sarah Anderson | Dr. Christopher White
3486 | S0013 | NORW-University Hospital | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 6 | 0 | 0 | 0 | Dr. Michelle Miller | Dr. Emily Taylor
3487 | S0014 | NORW-University Hospital | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 14 | 0 | 0 | 0 | Dr. James Smith | Dr. Charles Williams
3488 | S0001 | MEXI-Research Institute | ST-2025-033 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -11 | -11 | 100 | -0.9 | Dr. Jessica Thomas | Dr. Charles Wilson
3489 | S0002 | MEXI-Health System | ST-2025-033 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. David Williams | Dr. Robert Brown
3490 | S0003 | MEXI-General Hospital | ST-2025-033 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 3 | 1 | 33.3 | 0.1 | Dr. Jennifer Wilson | Dr. Emily Jones
3491 | S0004 | MEXI-Cancer Center | ST-2025-033 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Charles Taylor | Dr. William Martin
3492 | S0005 | MEXI-University Hospital | ST-2025-033 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 3, 'cumulative': 5}, {'month': 4, 'enrolled': 0, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | ENROLLING | 3 | 7 | 233.3 | 0.9 | Dr. Lisa Miller | Dr. Michael Jones
3493 | S0006 | CANA-University Hospital | ST-2025-033 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ENROLLING | -1 | -1 | 100 | -0.1 | Dr. Stephanie Martin | Dr. Thomas Anderson
3494 | S0007 | CANA-Health System | ST-2025-033 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. Lisa Moore | Dr. Charles Jackson
3495 | S0008 | CANA-Cancer Center | ST-2025-033 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 3 | 3 | 100 | 0.2 | Dr. Nicole Thomas | Dr. Jessica Thompson
3496 | S0009 | SWIT-University Hospital | ST-2025-033 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 2 | 1 | 50 | 0.1 | Dr. William Jones | Dr. Stephanie Moore
3497 | S0010 | SWIT-Clinical Center | ST-2025-033 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 3 | 2 | 66.7 | 0.2 | Dr. William Brown | Dr. Michelle White
3498 | S0011 | POLA-Cancer Center | ST-2025-033 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ON_HOLD | 2 | 2 | 100 | 0.2 | Dr. Amanda White | Dr. David Moore
3499 | S0012 | POLA-University Hospital | ST-2025-033 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Jennifer Smith | Dr. David Harris
3500 | S0001 | CANA-University Hospital | ST-2025-034 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ENROLLING | 5 | 4 | 80 | 0.2 | Dr. Christopher Harris | Dr. Stephanie Jackson
3501 | S0002 | CANA-Clinical Center | ST-2025-034 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 3 | 3 | 100 | 0.3 | Dr. Amanda Taylor | Dr. Nicole Jackson
3502 | S0003 | FRAN-Health System | ST-2025-034 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 0 | 0 | 0 | 0 | Dr. Stephanie Wilson | Dr. Charles Smith
3503 | S0004 | FRAN-University Hospital | ST-2025-034 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | SCREENING | 3 | 3 | 100 | 0.2 | Dr. Jessica Thompson | Dr. David Jones
3504 | S0005 | FRAN-University Hospital | ST-2025-034 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. Sarah Williams | Dr. Jessica Jones
3505 | S0006 | NEW-Medical Center | ST-2025-034 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | -3 | -3 | 100 | -0.4 | Dr. David White | Dr. Michael Davis
3506 | S0007 | NEW-University Hospital | ST-2025-034 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | SCREENING | 3 | 3 | 100 | 0.2 | Dr. Amanda Smith | Dr. Nicole Garcia
3507 | S0008 | NEW-Research Institute | ST-2025-034 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 3 | 2 | 66.7 | 0.3 | Dr. Michelle Jackson | Dr. David Martin
3508 | S0009 | NEW-General Hospital | ST-2025-034 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 4 | 133.3 | 0.3 | Dr. Lisa Brown | Dr. Charles Jones
3509 | S0001 | CANA-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | -35 | -35 | 100 | -2.9 | Dr. Jessica Wilson | Dr. James White
3510 | S0002 | CANA-University Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ENROLLING | 3 | 3 | 100 | 0.5 | Dr. Robert Wilson | Dr. William Harris
3511 | S0003 | CANA-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 3 | 3 | 100 | 0.2 | Dr. Thomas Brown | Dr. Lisa Davis
3512 | S0004 | CANA-Medical Center | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Lisa Williams | Dr. Jessica Harris
3513 | S0005 | CANA-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 3 | 3 | 100 | 0.2 | Dr. Thomas Moore | Dr. Charles Martin
3514 | S0006 | CANA-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 4 | 133.3 | 0.7 | Dr. Thomas Taylor | Dr. Amanda Harris
3515 | S0007 | MEXI-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | 2 | 1 | 50 | 0.1 | Dr. Charles Wilson | Dr. Charles Johnson
3516 | S0008 | MEXI-General Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. Nicole Moore | Dr. Amanda Williams
3517 | S0009 | UNIT-General Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | -1 | -1 | 100 | -0.1 | Dr. Robert Garcia | Dr. Amanda White
3518 | S0010 | UNIT-Clinical Center | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Jessica Moore | Dr. Nicole Davis
3519 | S0011 | UNIT-Clinical Center | ST-2025-035 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 4 | 133.3 | 0.3 | Dr. Charles Brown | Dr. Emily Jackson
3520 | S0012 | SWED-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -10 | -10 | 100 | -1 | Dr. Amanda Brown | Dr. Thomas Thompson
3521 | S0013 | SWED-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Lisa Jackson | Dr. Nicole Harris
3522 | S0014 | SWED-Research Institute | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Jennifer Jackson | Dr. Jessica Smith
3523 | S0015 | SWED-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 3 | 100 | 0.3 | Dr. Jennifer Brown | Dr. Charles White
3524 | S0016 | SWED-Clinical Center | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. James Davis | Dr. Robert Thompson
3525 | S0017 | SWED-Medical Center | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 5 | 166.7 | 0.3 | Dr. Stephanie Smith | Dr. Thomas Davis
3526 | S0018 | NETH-Clinical Center | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | -4 | -4 | 100 | -0.3 | Dr. David Garcia | Dr. Christopher Thomas
3527 | S0019 | NETH-General Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Nicole Miller | Dr. Thomas Jones
3528 | S0020 | NETH-Research Institute | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 3 | 3 | 100 | 0.4 | Dr. David Harris | Dr. Christopher Davis
3529 | S0021 | NETH-General Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 3 | 2 | 66.7 | 0.1 | Dr. Lisa Garcia | Dr. Christopher Thompson
3530 | S0022 | ITAL-University Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | -1 | -1 | 100 | -0.1 | Dr. Michael Smith | Dr. Sarah White
3531 | S0023 | ITAL-Cancer Center | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. Charles Williams | Dr. Stephanie Wilson
3532 | S0024 | ITAL-General Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. Michelle Smith | Dr. Christopher Martin
3533 | S0025 | GERM-Clinical Center | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | -7 | -7 | 100 | -0.6 | Dr. Emily Jones | Dr. William Brown
3534 | S0026 | GERM-General Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Stephanie Taylor | Dr. Robert Davis
3535 | S0027 | GERM-Cancer Center | ST-2025-035 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. William Brown | Dr. Thomas Williams
3536 | S0028 | GERM-Clinical Center | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Lisa Wilson | Dr. Thomas Anderson
3537 | S0029 | GERM-General Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ENROLLING | 3 | 5 | 166.7 | 0.4 | Dr. Christopher Wilson | Dr. William Johnson
3538 | S0030 | AUST-General Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | -4 | -4 | 100 | -0.5 | Dr. Jessica Martin | Dr. Christopher Anderson
3539 | S0031 | AUST-University Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | 3 | 2 | 66.7 | 0.1 | Dr. Robert Jones | Dr. Jessica Jackson
3540 | S0032 | AUST-Research Institute | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. James Miller | Dr. Jessica Jones
3541 | S0033 | AUST-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 2 | 66.7 | 0.3 | Dr. Amanda Thompson | Dr. Daniel Jackson
3542 | S0001 | MEXI-General Hospital | ST-2025-036 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 2, 'cumulative': 5}, {'month': 4, 'enrolled': 3, 'cumulative': 8}, {'month': 5, 'enrolled': 4, 'cumulative': 12}, {'month': 6, 'enrolled': 3, 'cumulative': 15}] | ENROLLING | 16 | 15 | 93.8 | 1 | Dr. David Jones | Dr. David Anderson
3543 | S0002 | MEXI-University Hospital | ST-2025-036 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 4, 'cumulative': 6}, {'month': 4, 'enrolled': 2, 'cumulative': 8}, {'month': 5, 'enrolled': 0, 'cumulative': 8}, {'month': 6, 'enrolled': 2, 'cumulative': 10}] | ENROLLING | 12 | 12 | 100 | 1.7 | Dr. Michelle Johnson | Dr. Robert Moore
3544 | S0003 | MEXI-Research Institute | ST-2025-036 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 1, 'cumulative': 5}, {'month': 3, 'enrolled': 5, 'cumulative': 10}, {'month': 4, 'enrolled': 2, 'cumulative': 12}, {'month': 5, 'enrolled': 1, 'cumulative': 13}, {'month': 6, 'enrolled': 2, 'cumulative': 15}] | ENROLLING | 20 | 18 | 90 | 2.6 | Dr. Thomas Davis | Dr. David Miller
3545 | S0004 | MEXI-Research Institute | ST-2025-036 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 3, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ENROLLING | 14 | 11 | 78.6 | 1.4 | Dr. William Davis | Dr. David Thomas
3546 | S0005 | MEXI-Medical Center | ST-2025-036 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 3, 'cumulative': 6}, {'month': 3, 'enrolled': 4, 'cumulative': 10}, {'month': 4, 'enrolled': 4, 'cumulative': 14}, {'month': 5, 'enrolled': 5, 'cumulative': 19}, {'month': 6, 'enrolled': 1, 'cumulative': 20}] | ENROLLING | 16 | 22 | 137.5 | 2.8 | Dr. Emily Jackson | Dr. James Harris
3547 | S0006 | UNIT-Medical Center | ST-2025-036 | [{'month': 1, 'enrolled': 7, 'cumulative': 7}, {'month': 2, 'enrolled': 4, 'cumulative': 11}, {'month': 3, 'enrolled': 6, 'cumulative': 17}, {'month': 4, 'enrolled': 7, 'cumulative': 24}, {'month': 5, 'enrolled': 4, 'cumulative': 28}, {'month': 6, 'enrolled': 4, 'cumulative': 32}] | ENROLLING | 48 | 34 | 70.8 | 2.6 | Dr. Charles Miller | Dr. David Jackson
3548 | S0007 | UNIT-Health System | ST-2025-036 | [{'month': 1, 'enrolled': 9, 'cumulative': 9}, {'month': 2, 'enrolled': 8, 'cumulative': 17}, {'month': 3, 'enrolled': 9, 'cumulative': 26}, {'month': 4, 'enrolled': 10, 'cumulative': 36}, {'month': 5, 'enrolled': 12, 'cumulative': 48}, {'month': 6, 'enrolled': 12, 'cumulative': 60}] | ENROLLING | 47 | 61 | 129.8 | 8.7 | Dr. Jennifer Thompson | Dr. Daniel Brown
3549 | S0008 | POLA-Health System | ST-2025-036 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 3, 'cumulative': 3}, {'month': 3, 'enrolled': 3, 'cumulative': 6}, {'month': 4, 'enrolled': 3, 'cumulative': 9}, {'month': 5, 'enrolled': 0, 'cumulative': 9}, {'month': 6, 'enrolled': 3, 'cumulative': 12}] | ENROLLING | 12 | 10 | 83.3 | 1.4 | Dr. James Smith | Dr. Charles White
3550 | S0009 | POLA-Clinical Center | ST-2025-036 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 3, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 3, 'cumulative': 7}, {'month': 5, 'enrolled': 0, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | ENROLLING | 10 | 7 | 70 | 1 | Dr. Amanda Anderson | Dr. Michael White
3551 | S0010 | POLA-Cancer Center | ST-2025-036 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 4, 'cumulative': 6}, {'month': 5, 'enrolled': 1, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | ENROLLING | 22 | 14 | 63.6 | 0.9 | Dr. Lisa Williams | Dr. Charles Martin
3552 | S0011 | POLA-Medical Center | ST-2025-036 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 4, 'cumulative': 8}, {'month': 3, 'enrolled': 3, 'cumulative': 11}, {'month': 4, 'enrolled': 1, 'cumulative': 12}, {'month': 5, 'enrolled': 2, 'cumulative': 14}, {'month': 6, 'enrolled': 0, 'cumulative': 14}] | SCREENING | 19 | 17 | 89.5 | 1.7 | Dr. Thomas Johnson | Dr. Robert Davis
3553 | S0012 | POLA-University Hospital | ST-2025-036 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 2, 'cumulative': 5}, {'month': 4, 'enrolled': 3, 'cumulative': 8}, {'month': 5, 'enrolled': 2, 'cumulative': 10}, {'month': 6, 'enrolled': 2, 'cumulative': 12}] | ENROLLING | 13 | 11 | 84.6 | 0.7 | Dr. Robert Thompson | Dr. Robert Jones
3554 | S0013 | POLA-General Hospital | ST-2025-036 | [{'month': 1, 'enrolled': 7, 'cumulative': 7}, {'month': 2, 'enrolled': 6, 'cumulative': 13}, {'month': 3, 'enrolled': 5, 'cumulative': 18}, {'month': 4, 'enrolled': 6, 'cumulative': 24}, {'month': 5, 'enrolled': 4, 'cumulative': 28}, {'month': 6, 'enrolled': 4, 'cumulative': 32}] | ENROLLING | 23 | 40 | 173.9 | 3.1 | Dr. Sarah Miller | Dr. Jessica Thomas
3555 | S0014 | UNIT-Medical Center | ST-2025-036 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 3, 'cumulative': 4}, {'month': 3, 'enrolled': 1, 'cumulative': 5}, {'month': 4, 'enrolled': 0, 'cumulative': 5}, {'month': 5, 'enrolled': 3, 'cumulative': 8}, {'month': 6, 'enrolled': 3, 'cumulative': 11}] | ENROLLING | 12 | 8 | 66.7 | 0.4 | Dr. James Martin | Dr. David Anderson
3556 | S0015 | UNIT-Clinical Center | ST-2025-036 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 11 | 11 | 100 | 0.7 | Dr. William Taylor | Dr. James Smith
3557 | S0016 | UNIT-Research Institute | ST-2025-036 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | SCREENING | 7 | 7 | 100 | 1.2 | Dr. Sarah Jones | Dr. Stephanie Johnson
3558 | S0017 | UNIT-Health System | ST-2025-036 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 5 | 4 | 80 | 0.3 | Dr. Daniel Garcia | Dr. Jennifer Brown
3559 | S0018 | UNIT-Medical Center | ST-2025-036 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 3, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ENROLLING | 8 | 7 | 87.5 | 0.6 | Dr. Michael White | Dr. Michael Brown
3560 | S0019 | SWIT-Research Institute | ST-2025-036 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 5, 'cumulative': 8}, {'month': 3, 'enrolled': 3, 'cumulative': 11}, {'month': 4, 'enrolled': 4, 'cumulative': 15}, {'month': 5, 'enrolled': 4, 'cumulative': 19}, {'month': 6, 'enrolled': 2, 'cumulative': 21}] | ON_HOLD | 24 | 24 | 100 | 1.5 | Dr. Amanda Brown | Dr. Nicole Martin
3561 | S0020 | SWIT-General Hospital | ST-2025-036 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 3, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 3, 'cumulative': 7}, {'month': 5, 'enrolled': 0, 'cumulative': 7}, {'month': 6, 'enrolled': 3, 'cumulative': 10}] | ENROLLING | 14 | 8 | 57.1 | 0.5 | Dr. Robert Davis | Dr. Daniel Jones
3562 | S0021 | SWIT-Cancer Center | ST-2025-036 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 3, 'cumulative': 8}] | ENROLLING | 13 | 11 | 84.6 | 1.4 | Dr. Michael Brown | Dr. Charles Anderson
3563 | S0022 | SWIT-Health System | ST-2025-036 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 4, 'cumulative': 9}, {'month': 3, 'enrolled': 2, 'cumulative': 11}, {'month': 4, 'enrolled': 1, 'cumulative': 12}, {'month': 5, 'enrolled': 3, 'cumulative': 15}, {'month': 6, 'enrolled': 3, 'cumulative': 18}] | ENROLLING | 20 | 20 | 100 | 2.9 | Dr. Lisa Wilson | Dr. Jennifer Anderson
3564 | S0023 | SWIT-Research Institute | ST-2025-036 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 2, 'cumulative': 7}] | SCREENING | 13 | 9 | 69.2 | 0.5 | Dr. Daniel Thompson | Dr. William Jones
3565 | S0024 | SWIT-Research Institute | ST-2025-036 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 1, 'cumulative': 5}, {'month': 3, 'enrolled': 3, 'cumulative': 8}, {'month': 4, 'enrolled': 2, 'cumulative': 10}, {'month': 5, 'enrolled': 1, 'cumulative': 11}, {'month': 6, 'enrolled': 4, 'cumulative': 15}] | SCREENING | 20 | 12 | 60 | 1 | Dr. Robert Johnson | Dr. Charles Johnson
3566 | S0025 | AUST-University Hospital | ST-2025-036 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 5, 'cumulative': 7}, {'month': 4, 'enrolled': 5, 'cumulative': 12}, {'month': 5, 'enrolled': 3, 'cumulative': 15}, {'month': 6, 'enrolled': 2, 'cumulative': 17}] | ON_HOLD | 33 | 20 | 60.6 | 2.5 | Dr. Thomas Smith | Dr. Nicole Martin
3567 | S0026 | AUST-Cancer Center | ST-2025-036 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 36 | 0 | 0 | 0 | Dr. Charles Harris | Dr. David Harris
3568 | S0027 | AUST-Health System | ST-2025-036 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 12 | 0 | 0 | 0 | Dr. Christopher Brown | Dr. William Thompson
3569 | S0001 | MEXI-General Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 276 | 0 | 0 | 0 | Dr. Michael Williams | Dr. Charles Wilson
3570 | S0002 | MEXI-University Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | ON_HOLD | 318 | 0 | 0 | 0 | Dr. Michelle Thomas | Dr. Charles Jones
3571 | S0003 | MEXI-Clinical Center | ST-2025-037 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 1, 'cumulative': 5}, {'month': 4, 'enrolled': 2, 'cumulative': 7}, {'month': 5, 'enrolled': 0, 'cumulative': 7}, {'month': 6, 'enrolled': 0, 'cumulative': 7}] | CLOSED | 179 | 0 | 0 | 0 | Dr. Jessica Williams | Dr. Thomas Davis
3572 | S0004 | MEXI-Clinical Center | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | SCREENING | 133 | 0 | 0 | 0 | Dr. Michelle Jones | Dr. William Smith
3573 | S0005 | MEXI-Clinical Center | ST-2025-037 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 235 | 0 | 0 | 0 | Dr. Lisa Davis | Dr. Lisa Harris
3574 | S0006 | MEXI-General Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | SCREENING | 307 | 0 | 0 | 0 | Dr. Robert Smith | Dr. Jessica Davis
3575 | S0007 | UNIT-University Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 422 | 0 | 0 | 0 | Dr. Charles Jackson | Dr. William Thomas
3576 | S0008 | UNIT-Cancer Center | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 389 | 0 | 0 | 0 | Dr. Stephanie Thomas | Dr. Amanda Davis
3577 | S0009 | UNIT-Research Institute | ST-2025-037 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 282 | 0 | 0 | 0 | Dr. Michael Jones | Dr. Thomas Davis
3578 | S0010 | UNIT-Cancer Center | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | CLOSED | 269 | 0 | 0 | 0 | Dr. Robert Brown | Dr. Daniel Martin
3579 | S0011 | CANA-University Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 2, 'cumulative': 7}] | ON_HOLD | 945 | 0 | 0 | 0 | Dr. Michelle Davis | Dr. Christopher Wilson
3580 | S0012 | CANA-Health System | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 551 | 0 | 0 | 0 | Dr. Christopher Martin | Dr. Stephanie Williams
3581 | S0013 | DENM-Research Institute | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 382 | 0 | 0 | 0 | Dr. Robert Williams | Dr. Amanda Williams
3582 | S0014 | DENM-General Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 176 | 0 | 0 | 0 | Dr. William Smith | Dr. Nicole White
3583 | S0015 | DENM-General Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 277 | 0 | 0 | 0 | Dr. Charles Miller | Dr. Christopher Anderson
3584 | S0016 | NETH-Health System | ST-2025-037 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 686 | 0 | 0 | 0 | Dr. Stephanie Jones | Dr. Michelle Taylor
3585 | S0017 | NETH-Cancer Center | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | CLOSED | 775 | 0 | 0 | 0 | Dr. Sarah Thomas | Dr. Emily Williams
3586 | S0018 | UNIT-Medical Center | ST-2025-037 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 163 | 0 | 0 | 0 | Dr. Emily Jackson | Dr. Charles White
3587 | S0019 | UNIT-Clinical Center | ST-2025-037 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 149 | 0 | 0 | 0 | Dr. Robert Taylor | Dr. Jennifer Brown
3588 | S0020 | UNIT-Research Institute | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 178 | 0 | 0 | 0 | Dr. Stephanie Wilson | Dr. Nicole Williams
3589 | S0021 | UNIT-University Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | 178 | 0 | 0 | 0 | Dr. David Davis | Dr. Amanda Williams
3590 | S0022 | UNIT-Research Institute | ST-2025-037 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 108 | 0 | 0 | 0 | Dr. Daniel Wilson | Dr. James Johnson
3591 | S0023 | UNIT-Health System | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 159 | 0 | 0 | 0 | Dr. Amanda Brown | Dr. Jennifer Smith
3592 | S0024 | ITAL-Health System | ST-2025-037 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 799 | 0 | 0 | 0 | Dr. Michael Garcia | Dr. David Martin
3593 | S0025 | ITAL-University Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | SCREENING | 560 | 0 | 0 | 0 | Dr. Amanda Brown | Dr. Robert Thomas
3594 | S0026 | ITAL-Health System | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 274 | 0 | 0 | 0 | Dr. Jennifer Thompson | Dr. Robert Harris
3595 | S0027 | TAIW-Research Institute | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 125 | 0 | 0 | 0 | Dr. Jennifer Thompson | Dr. Jennifer Brown
3596 | S0028 | TAIW-Clinical Center | ST-2025-037 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | CLOSED | 125 | 0 | 0 | 0 | Dr. Robert Taylor | Dr. Christopher Moore
3597 | S0029 | TAIW-Cancer Center | ST-2025-037 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 241 | 0 | 0 | 0 | Dr. Emily Moore | Dr. Michael Taylor
3598 | S0030 | TAIW-University Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 339 | 0 | 0 | 0 | Dr. Lisa Martin | Dr. David Jackson

## Protocols
protocol_id | title | phase | therapeutic_area | indication | full_summary | inclusion_criteria | exclusion_criteria | target_enrollment | actual_enrollment | planned_start_date | actual_end_date | planned_duration_months | actual_duration_months | lessons_learned
NCT06567015 | Phase I/II First-In-Human Open-label Trial to Assess Safety and Efficacy of STX-241 in Participants With Locally Advanced or Metastatic Non-small Cell Lung Cancer (NSCLC) Resistant to EGFR Tyrosine Kinase Inhibitors (TKIs). | PHASE_I | Oncology | Non-small Cell Lung Cancer (NSCLC) | The goal of this First-In-Human (FIH) Phase I/II trial is to establish the safety profile, determine the Recommended Phase II Dose (RP2D), explore the pharmacokinetic (PK) exposure and pharmacodynamic (PD) properties as well as assess the efficacy of STX-241/PFL-241, a mutant selective Central Nervous System (CNS)-penetrant fourth generation EGFR TKI, in participants with locally advanced or metastatic NSCLC that progressed during or following third generation EGFR TKI such as osimertinib due to C797X double acquired (secondary) mutations. | 1. Signed and dated informed consent for participation in the trial obtained according to International Council for Harmonisation of Technical Requirements of Pharmaceuticals for Human Use (ICH) Good Clinical Practice (GCP), and national/local regulations. 2. Male or female ≥ 18 years of age at the time of signing informed consent. 3. Histological confirmation of locally advanced or metastatic, EGFR-mutant (ex19del or L858R mutations) non-small cell lung cancer (NSCLC) Stage IIIB/C or IV (AJCC 8th edition) not eligible for curative intent surgery or chemoradiation. 4. Part 1\&2 Disease progression on a 3rd generation EGFR TKI-based therapy (monotherapy or in combination) received at any prior line of treatment. 5. Tumor mutation profile: • Part 1 (backfilling component) and Part 2: Presence of C797X and absence of T790M mutations documented locally (as part of clinical practice) on a sample (blood or tissue) collected after progression on treatment with 3rd generation EGFR TKI. 6. Part 1 (Backfilling component), Part 2: At least one measurable target lesion according to RECIST v1.1. 7. Eastern cooperative oncology group (ECOG) performance status 0-1. 8. Adequate organ function as defined below: * Absolute neutrophil count (ANC) ≥ 1.5 x 10\^9/L * Platelets ≥ 75 x 10\^9/L * Hemoglobin ≥ 90 g/L. * Serum total bilirubin ≤ 1.5 x ULN or ≤ 3.0 × ULN for participants with documented Gilbert's syndrome. * Alanine aminotransferase (ALT) and aspartate aminotransferase (AST) ≤ 3.0 x ULN. If the participant has liver metastases, AST and ALT ≤5 × ULN. * Estimated glomerular filtration rate (GFR) ≥ 50 mL/min by CKD-EPI equation 9. Adequate cardiac function as defined below: * Mean QT interval corrected for heart rate according to Fridericia's formula (QTcF) value ≤ 470 msec for women and ≤ 450 msec for men and no history of long QT syndrome or risk factors for torsade de pointe. * Left ventricular ejection fraction (LVEF) ≥ 50% . * Systolic blood pressure \< 150 mmHg and diastolic blood pressure \< 100 mmHg 10. Female participants of childbearing potential: * Negative highly sensitive serum β-HCG test performed within 7 days prior to first dose of STX-241 (C1D1) and a negative urine pregnancy test performed prior to C1D1. * Agreement to use one highly effective contraceptive method (as defined in protocol and according to local regulations), starting at screening period, throughout the trial and until at least 182 days (i.e. more than 5 estimated STX- 241 half-lives (2 days) plus 6 months (180 days)) after the last dose of STX-241. If the highly effective method of contraception is a hormonal contraceptive method, it must be supplemented by one additional effective (barrier) method of contraception. * Agreement to not donate eggs (ova, oocytes) for the purpose of assisted reproduction during the trial and for a period of 182 days after the last dose of STX-241. Note: a female participant of childbearing potential is a woman who is not permanently sterilized or not postmenopausal (postmenopausal is defined as 12 months with no menses without an alternative medical cause). 11. Male participants/partners with female spouse/partners of childbearing potential must agree to take appropriate precautions to avoid fathering a child, i.e.: * Consistently use a barrier method \[e.g., condom with spermicidal foam / gel / film /cream/suppository\], and his female partner use a highly effective method of contraception as defined in protocol and according to local regulations), starting at screening and continuing throughout the trial period and for 92 days (ie. more than 5 estimated STX-241 half-lives (2 days) plus 3 months (90 days)) after the last dose of STX-241. * Not donate sperm from Day 1 (first administration of STX-241) until at least 92 days after the last dose of STX-241. NOTE: Other protocol defined inclusion criteria may apply. | 1. Participant candidate for targeted therapies available to them (such as but not limited to therapies targeting ALK, BRAF, MET, NTRK, ROS1) as identified by local testing performed after progression to the last line of systemic therapy. 2. Participant with rapid progressive disease eligible to receive a platinum-based chemotherapy. 3. Participant unable ingest or digest tablets. This can be caused by any impaired gastrointestinal function or disease, such as for example: ulcerative diseases, malabsorption syndrome, small bowel resection, ileus, etc. or any condition causing uncontrolled nausea, vomiting or diarrhea. 4. History of a primary malignancy other than NSCLC with the exception of: * Participants with a previous malignancy that completed all anticancer treatment at least 2 years before signing informed consent and with no evidence of residual disease from the prior malignancy at screening. * Malignancies with a negligible risk of metastasis or death (i.e. 5-year overall survival rate \> 90%) that are adequately treated - Examples include, but are not limited to, completely resected basal cell carcinoma and squamous cell carcinoma of skin, melanoma in situ, curatively treated prostate cancer, breast cancer and early gastric cancer cured by endoscopic mucosal resection or endoscopic submucosal dissection. 5. Spinal cord compression or CNS metastases that are associated with progressive neurological symptoms or require increasing doses of corticosteroids to control the CNS disease. If a participant requires corticosteroids for management of CNS disease, the dose must have been stable for 2 weeks prior to enrollment in the trial. 6. History of hypersensitivity to active or inactive ingredients of STX-241, or drugs with a similar chemical structure or from the same class. 7. Active, bacterial, fungal, or viral infection, including, but not limited to: Hepatitis B Virus (HBV), Hepatitis C Virus (HCV), and known Human Immunodeficiency Virus (HIV) or Acquired Immunodeficiency Syndrome (AIDS)-related illness, tuberculosis or an infection requiring systemic therapeutic treatment within 2 weeks prior to Day 1 (first administration of STX-241). Note: Participants with known HIV infection are permitted if they have controlled infection (undetectable viral load \[HIV ribonucleic acid polymerase chain reaction (PCR)\] and CD4 count \>350 either spontaneously or on a stable antiviral regimen). For participants with controlled HIV infection, monitoring will be performed per local standards. 8. Positive SARs-CoV-2 or variants of SARs-CoV2 RT-PCR test or suspected to be infected with SARs-CoV2 or variants of SARsCoV2 with confirmation pending within 2 weeks of first dose of STX-241. 9. Impaired cardiovascular function or clinically significant cardiovascular disease (either active or within 6 months prior to signing informed consent), including any of the following: * Myocardial infarction, acute coronary syndromes including unstable angina, coronary/peripheral artery bypass graft, coronary angioplasty or stenting. * Symptomatic congestive heart failure (New York Heart Association Classification Class ≥ II). * Cerebrovascular accident or transient ischemic attack. * Symptomatic bradycardia, requirement for anti-arrhythmic medication. * Ongoing cardiac dysrhythmias of NCI-CTCAE Grade ≥2. 10. Uncontrolled intercurrent illness including, but not limited to ongoing or active infection or psychiatric illness/social situation that would limit compliance with trial requirements. 11. Past medical history of Interstitial Lung Disease (ILD), drug-induced ILD, radiation pneumonitis that required steroid treatment, or any evidence of clinically active ILD. 12. Past medical history of Stevens-Jonhson Syndrome (SJS) or Toxic epidermal necrolysis (TEN) or any evidence of clinically active SJS/TEN. 13. Women who are breast feeding. 14. Prior anticancer therapy: * EGFR-targeted TKI within 7 days prior to the first dose of STX-241. * Any other systemic anticancer therapy within 28 days or 5 half-lives prior to the first dose of STX-241, whichever is the shortest, but with a minimum of 14 days in all circumstances. * Radiotherapy to a large field or including a vital organ (including whole brain radiotherapy or stereotactic radiosurgery to brain) within 14 days before the first dose of STX-241. 15. Live attenuated vaccine received within 30 days prior to the first dose of STX-241. 16. Any toxicities from prior therapy with a NCI-CTCAE Grade ≥1 at the time of the first dose of STX-241 (C1D1). Exceptions include alopecia (any grade), fatigue with a Grade ≤2, and peripheral neuropathy with a Grade ≤2. 17. Major surgical procedure within 14 days of the first dose of STX-241 (procedures such as central venous catheter placement, tumor needle biopsy, and feeding tube placement are not considered major surgical procedures). Sequelae of surgical procedures must have resolved, including adequate wound healing, prior to the first dose of STX-241. 18. Treatment with a prohibited medication or herbal remedy known to be strong CYP1A2 or CYP3A4 inducers, strong CYP1A2 or CYP3A4 inhibitors, sensitive CYP1A2, CYP2B6 and CYP3A4 substrates, sensitive MATE1 and OATP1B1 substrates and proton pump inhibitors (PPI) and H2 antagonists unless discontinued prior to the first administration of STX-241 within the following timeframe: * At least 5 half-lives plus 14 days for strong CYP inducers. * At least 5 half-lives for CYP inhibitors, CYP/transporter substrates, proton pump inhibitor (PPI) and H2 antagonists. 19. Participation in a clinical trial with administration of an investigational drug within 5 half-lives plus 14 days of the investigational drug, before the first dose of STX-241. 20. Any condition for which, in the opinion of the investigator, participation would not be in the best interest of the participant (e. g, could compromise the participant's well-being) or would prevent, limit, or confound the protocol-specified assessments. 21. Employee or family member of the investigator or site staff. NOTE: Other protocol defined exclusion criteria may apply. | 171 | 54 | 2024-09-17 | 2028-05-17 | 45 | 45 | Protocol eligibility criteria restricted enrollment to 32%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT05655078 | Hemithoracic Irradiation With Proton Therapy in Malignant Pleural Mesothelioma |  | Oncology | Malignant Pleural Mesothelioma | Study design: Randomised phase III clinical trial for patients with unilateral MPM. Primary endpoint: Progression free survival (PFS) and overall survival (OS), defined as the time from randomisation to the date of progression and death from any cause. Secondary Endpoints: Safety and Tolerability, Health related Quality of Life (QOL): EuroQoL EQ-5D-3L, Locoregional Control. Randomisation and stratification: 1:1 randomisation. Patients with be stratified for histology (epithelioid versus non-epithelioid), potential PBT centre (UCLH or The Christie) , laterality (left or right sided) and time since diagnosis (\<1 year or \> 1 year) Treatment: Experimental Arm: Patients in the experimental arm will receive PBT to the hemithorax to a dose of 50Gy in 25 fractions with a boost to 60Gy for the visible tumour (gross tumour volume-GTV). Treatment is given daily Monday-Friday over 5 weeks. Following completion of treatment in the experimental arm patients will have 2 years of follow-up from time of randomisation at the local recruiting/referring centre. Control Arm: The patients in the control arm would be under standard of care surveillance i.e. "watch and wait", with no treatment or other intervention. Patients will have 2 years of follow-up from time of randomisation at the local recruiting/referring centre. If the disease progresses, the patient will receive SOC treatment i.e. immunotherapy with nivolumab and ipilimumab, or chemotherapy at the clinician's discretion. Statistical analysis plan: The sample size is 148 patients (74 patients per arm). This is to detect a OS hazard ratio of 0.58, equivalent to an improvement in 2-year OS from 30% to 50%, with 85% power and 5% two-sided alpha. Recruitment to complete in 3 years across 20 UK centres with 2 years of additional follow-up and up to 5% dropout. Interim analyses for OS efficacy will be performed when 50, 75 and 110 patients have been randomised at around 1.5, 2.0 and 2.5 years respectively. Using a fixed-se | * Patients ≥18 years of age, with biopsy confirmed MPM and histological subtyping (epithelioid or non-epithelioid) * N0 or N1 and M0 disease * Written informed consent * Patient and local/regional MDT opt for active surveillance and deferral of SACT until clinical or radiological progression * WHO Performance Status 0-1 * Disease confined to one hemithorax based on CT assessment * Adequate pulmonary function * ≥ 40% predicted post-FEV1; * ≥ 40% predicted DLCO/TLCO * Agreement to travel to either proton beam therapy centres (i.e. UCLH or The Christie) if randomised to arm 2 * Agreement to be followed up at a local HIT-Meso trial site * Patient likely able to complete PBT planning based on local assessment | * Presence of metastatic or contralateral disease * Cytological diagnosis and/or undetermined histological subtype * Prior thoracic radiotherapy, chemotherapy, immunotherapy for MPM * Prior radical surgery for MPM (extrapleural pneumonectomy or extended pleurectomy decortication or pleurectomy decortication) * Initial systemic therapy or surgery is required and the patient and local/regional MDT do not opt for active surveillance * Involvement of contralateral or supraclavicular lymph nodes * T4 disease with invasion of the myocardium * N2 and/or M1 disease * Presence of new effusion that is not amenable to drainage * WHO Performance Status ≥ 2 * Women who are pregnant or breast feeding * Current or previous malignant disease which may impact on the patient's life expectancy * Patient fitted with a pacemaker or implantable cardioverter-defibrillator (ICD)\\ * Diagnosis of clinically significant interstitial lung disease (ILD), excluding mild fibrosis or incidental findings * Chronic non-malignant disease with an estimated three-year survival rate of less than 20% * Patient with prior thoracic / abdominal radiotherapy for malignancy who was not discussed with sponsor before recruitment | 148 | 43 | 2024-03-28 | 2029-09-30 | 67 | 67 | Protocol eligibility criteria restricted enrollment to 29%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06793189 | A Prospective Study to Evaluate the Efficacy and Safety of MZL-IPI Risk-adapted Targeted Therapy in Patients With Untreated Marginal Zone B-cell Lymphoma | PHASE_II | Oncology | Marginal Zone Lymphoma(MZL) | Marginal zone lymphoma (MZL) is a common type of indolent lymphoma that originates from the marginal zone of lymphoid follicles. This study aims to evaluate targeted therapy based on the prognostic risk stratification of MZL-IPI in newly diagnosed MZL cases requiring systemic treatment, and provides a basis for precision treatment of MZL. | * 1\. Histopathologically confirmed CD20-positive marginal zone lymphoma (according to the 2016 WHO classification). 2\. Age ≥ 18 years old, regardless of gender. 3. MZL patients requiring systemic treatment, including but not limited to: 1. Helicobacter pylori (HP)-positive or HP - negative gastric mucosa extranodal marginal zone lymphoma (MALT) patients with progression/relapse after local treatment (including surgery, radiotherapy, and anti - Helicobacter pylori treatment). 2. Non - gastric MALT patients with Ann Arbor stage I - II who have progression/relapse after local treatment (including surgery, radiotherapy, etc.), or untreated patients with Ann Arbor stage III - IV who meet the GELF criteria recommended by the NCCN guidelines. 3. Splenic marginal zone lymphoma (SMZL) patients with progression/relapse after local treatment (including splenectomy, antiviral treatment for HCV - positive patients, etc.), or untreated patients meeting the criteria of progressive or painful splenomegaly, symptomatic or progressive cytopenia such as HB \< 100g/L, PLT \< 80×10⁹/L, absolute neutrophil count (ANC) \< 1.0×10⁹/L. 4. Nodal marginal zone lymphoma (NMZL) patients with Ann Arbor stage I - II who have progression/relapse after local treatment (including surgery, radiotherapy, etc.), or untreated patients with Ann Arbor stage III - IV who meet the GELF criteria recommended by the NCCN guidelines. 4\. Eastern Cooperative Oncology Group (ECOG) performance status score of 0-2. 5. Life expectancy of at least 3 months. 6. The patient has adequate bone marrow (except those caused by MZL), liver and kidney functions. 7\. Able to comply with the research procedures and cooperate in the implementation of the entire research process; 8. Written informed consent; 9. Women with fertility agree to take appropriate measures to avoid pregnancy during the treatment period until at least one year after the end of treatment; Men agree to maintain abstinence or use barrier contraception. | * 1\. Histologically transformed into high-grade lymphoma. 2. Known central nervous system involvement of MZL. 3. Previous systemic treatment including immunotherapy, chemotherapy or targeted drugs. 4\. Previous autologous stem-cell transplantation or allogeneic tissue/solid organ transplantation. 5\. History of other invasive cancers within the past 3 years that have not received curative treatment or are still receiving anti-cancer treatment (including hormonal therapy for breast or prostate cancer). 6\. Complicated with uncontrolled cardiovascular and cerebrovascular diseases (such as New York Heart Association-defined grade 3 or 4 heart failure, arrhythmia, myocardial infarction, stroke, or intracranial hemorrhage), coagulation - disorder diseases, connective tissue diseases, severe infectious diseases (including active pulmonary tuberculosis), etc. 7\. Known human immunodeficiency virus (HIV) infection, or active hepatitis B or C virus infection (positive result shown by polymerase chain reaction \[PCR\]). Serological antibody - positive is allowed if HBV DNA \< 10³ IU/ml; HCV RNA test must be negative. 8\. Vaccinated with live attenuated vaccines within 4 weeks before starting investigational treatment. During the study, patients are prohibited from receiving live attenuated vaccine inoculations, including influenza vaccines. 9\. Requiring continuous treatment with potent and moderate-effect CYP3A inhibitors or CYP3A inducers. 10\. Unable to swallow capsules or having diseases that significantly affect gastrointestinal function, such as malabsorption syndrome, bariatric surgery, inflammatory bowel disease, or partial or complete intestinal obstruction. 11\. Psychiatric patients or other patients known or suspected to be unable to fully comply with the study protocol. 12\. Pregnant or lactating women. 13. Other concurrent and uncontrolled medical conditions that, in the investigator's opinion, will affect the patient's participation in the study. | 145 | 23 | 2025-01-23 | 2028-12-31 | 48 | 48 | Protocol eligibility criteria restricted enrollment to 16%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT05506410 | A Prospective Clinical Study of Hanlikang and BTK Inhibitors in the Treatment of Newly Diagnosed Mantle Cell Lymphoma |  | Oncology | Newly Diagnosed Mantle Cell Lymphoma | An open-label, single-arm, multicenter, prospective clinical study of Hanlikang and BTK inhibitors in the treatment of newly diagnosed mantle cell lymphoma | 1. Age 18-70, ECOG score 0-2; 2. Estimated survival time \>6 months; 3. Mantle cell lymphoma was confirmed by pathology. 4. Acceptable hematological indexes without chemotherapy contraindications; Neutrophil absolute value ≥1.0×10\^9 /L, PLT≥75×10\^9 /L, hemoglobin ≥80g/L (except patients with lymphoma bone marrow infiltration); 5. At least one measurable lesion. For intrnodal lesions, they were defined as long diameter ≥1.5cm and short diameter ≥1.0cm; For r extranodal lesions, the length should be ≥1.0cm; 7\. Liver function: TBIL≤1.5×ULN; ALT or AST ≤2.5 x ULN; Alkaline phosphatase ≤3×ULN in patients with non-bone invasion; 8\. Kidney function: serum creatinine ≤1.5×ULN; 9\. Excluding other major diseases, the heart function is normal; 10 Women and men of childbearing age and their spouses are willing to use adequate contraception throughout the study period, and women of childbearing age must have a negative serum pregnancy test within 7 days before the first dose; 11 Subjects voluntarily participated in the clinical trial, signed the informed consent form, and cooperated with the follow-up; 12\. There is no other relevant treatment including traditional Chinese medicine (anti-tumor), immunotherapy, biologic therapy (except anti-bone metastasis and other symptoms); | 1. Patients with definite neuropathy or psychosis, including dementia or seizures, a history of psychotropic substance abuse and inability to abstinence, or other substantial lesions that may increase CNS toxicity; 2. Participating in other clinical trials or participating in other clinical investigators 4 weeks before enrollment (except those not receiving treatment); 3. Systemic autoimmune disease or immune deficiency; 4. Refusing to collect blood samples; 5. Allergic to any drug in the protocol; 6. Pregnant and lactating women; 7. Major diseases that can cause test interference and uncontrolled active infected persons; 8. Primary or secondary central tumor; 9. Contraindications to chemotherapy; 10. Not considered suitable for inclusion. 11. Known active bacterial, viral, fungal, mycobacterial, parasitic, or other infections (other than nail bed skin fungal infections) or any major systemic infection event requiring intravenous antibiotic treatment or hospitalization (other than neoplastic fever) within 4 weeks prior to enrollment; 13\. Application of other antitumor therapies (such as radiotherapy, chemotherapy, hormone therapy, biotherapy, immunotherapy); 14\. Other serious medical conditions that may limit the subject's participation in the study, such as uncontrolled diabetes; Severe cardiac insufficiency (NYHA grade II or above); Acute coronary syndrome in the last 6 months; Coronary revascularization such as stenting, cabG, and other cardiac and macrovascular procedures within the last 6 months; Severe arrhythmias include frequent ventricular premature, ventricular tachycardia, rapid atrial fibrillation/flutter, and severe bradycardia. Uncontrolled hypertension: systolic blood pressure \>150mmHg, diastolic blood pressure \>100mmHg. Gastric ulcers (those identified by the investigators as being at risk for perforation); Active autoimmune diseases (e.g. systemic lupus erythematosus, rheumatoid arthritis, multiple sclerosis, Sjogren's syndrome, autoimmune thrombocytopenia, etc.); Severe respiratory diseases (e.g. obstructive pulmonary disease and history of bronchospasm), etc.; 15\. Hemophagocytic cell syndrome; 16\. Hepatitis B surface antigen (HBsAg) or hepatitis B core antibody (HBcAb) was positive, and the peripheral blood hepatitis B virus (HBV) DNA titer was not within the normal reference range; Hepatitis C virus (HCV) antibody positive and HCV RNA positive in peripheral blood; Human immunodeficiency virus (HIV) antibody positive; Cytomegalovirus (CMV) DNA test positive; Who tested positive for syphilis. | 100 | 70 | 2022-08-12 | 2026-12-30 | 53 | 53 | Protocol eligibility criteria restricted enrollment to 70%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06246110 | A Phase 2 Study of EIK1001 in Combination With Pembrolizumab and Chemotherapy in Patients With Stage 4 Non-Small Cell Lung Cancer | PHASE_II | Oncology | NSCLC | This is a multicenter open-label phase 2 trial that aim to assess the safety, tolerability, and efficacy of EIK1001 in combination with standard of care in participants with both confirmed stage 4 squamous and non-squamous NSCLC who have not received prior systemic therapy for the advanced disease. The study includes dose finding and evaluates adverse events and efficacy. | 1. be ≥ 18 years of age on the day of signing of informed consent. 2. confirmed Stage 4 NSCLC (squamous or non-squamous) and be considered for standard of care. 3. have confirmation that mutation-directed therapy is not indicated (documentation of absence of tumor activating mutations/fusions that are approved for first line therapy). 4. have at least 1 lesion with measurable disease at Baseline according to RECIST 1.1 as determined by the local site Investigator/radiology assessment. 5. have not received prior systemic treatment for advanced/metastatic NSCLC. 6. have an ECOG Performance Status of 0 to 1. 7. have adequate organ function. | 1. does not have predominantly squamous cell or non-squamous cell histology NSCLC. Mixed tumors will be categorized by the predominant cell type; if small cell elements are present, the participant is ineligible. 2. is currently participating in or has participated in a study of an investigational agent and received investigational therapy within 4 weeks or 5 half-lives (whichever is shorter) of administration of EIK1001. 3. prior to the first dose of EIK1001, has received prior systemic therapy for metastatic disease, or had major surgery (\< 3 weeks prior to the first dose). 4. has completed palliative radiotherapy within 7 days of the first dose of study drug administration. 5. has a known history of prior malignancy, except if the participant has undergone potentially curative therapy with no evidence of that disease recurrence for 5 years. 6. has an active infection requiring therapy. | 70 | 55 | 2024-02-06 | 2025-11-06 | 21 | 21 | Protocol eligibility criteria restricted enrollment to 79%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06945120 | Efficacy of an Asian Culture-tailored Lung Health (ACT) Intervention on Lung Cancer Screening and Smoking Cessation in Asian Americans |  | Oncology | Smoking Cessation | This two-arm stratified randomized clinical trial is to test a counseling and educational program designed to improve lung health through smoking cessation for Chinese and Korean American smokers at high risk for lung cancer. Participants will be randomized into one of two groups: Group A: ACT Lung Health Intervention versus Group B: Standard Care. Randomization means a participant is placed into a study group by chance. The research study procedures include screening for eligibility, questionnaires, and saliva tests. It is expected participation in this study will last about 6 months. About 50 participants are expected to take part in this research study. The National Cancer Institute is providing funding for this trial. | * Self-identify as either Chinese or Korean * Speak either Korean, Mandarin, or English * Are 18 years of age or older * Are current smokers (i.e., have smoked at least 100 traditional cigarettes ever and have smoked at least one traditional cigarette within the prior 30 days) * Will live in the United States for the next 12 months | * Hospitalization due to a serious mental illness (e.g., psychotic disorders) during the prior 6 months. * We will not include any of the following special populations: * Adults unable to consent. * Adults younger than 50 or older than 80 years * Individuals who are not yet adults (infants, children, teenagers) * Pregnant women * Prisoners | 50 | 0 | 2027-01-18 | 2029-07-18 | 30 | 30
NCT05133843 | Complete Functional Assessment of Intermediate Coronary Artery Stenosis Before and After Transcatheter Aortic Valve Implantation (TAVI) in Patients With Severe Symptomatic Aortic Valve Stenosis |  | Cardiovascular | Coronary Artery Stenosis | Prospective, single center, open-label study to 1. compare coronary flow reserve (CFR), index of microvascular resistance (IMR), fractional flow reserve (FFR) and resting full cycle ratio (RFR) values before TAVI and 6 months after TAVI 2. correlate testing of microcirculatory function (IMR) with measurements of functional testing (FFR and RFR) before and six months after TAVI 3. correlate functional testing (FFR and RFR) with computed tomography (CT) derived fractional flow reserve (CT-FFR) before and six months after TAVI. | * Age \>18 years * Willing to participate and able to understand, read and sign the informed consent document before the planned procedure * Severe symptomatic aortic stenosis with indication for TAVI according to current guidelines deemed by the Heart Team * Patients who have undergone coronary CT angiography before TAVI in which CAD could not be ruled out * CAD in one or more native major epicardial vessels or their branches by coronary angiogram with visually assessed coronary stenosis, in which the physiological severity of the lesion is in question (typically 40-90% diameter stenosis). * Eligible for invasive coronary angiography and functional assessment (FFR, RFR, CFR and IMR) * Eligible for coronary CT-angiography and functional assessment (CT-FFR) | * Patients whose CT-angiography was determined to be non-diagnostic/unreadable during its evaluation * Previous coronary artery bypass grafting with patent grafts to the interrogated vessel * Patients with severe lesions with a diameter stenosis ≥ 90%, flow-limiting lesions, or a significant left main coronary artery stenosis * Critical coronary artery disease deemed by the Heart Team to require immediate revascularization * Contraindication to adenosine (e.g. bronchial asthma) * Chronic renal impairment with severe reduction of glomerular filtration rate (eGFR \<30 ml/min) * Presence of cardiogenic shock * Participation in another interventional study involving the left heart or coronary arteries | 50 | 41 | 2021-09-29 | 2025-09-30 | 49 | 49 | Enrollment reached 82% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06916520 | Prasugrel Monotherapy Reduced Dose in Acute and Chronic Coronary Syndrome Patients After Percutaneous Coronary Intervention | PHASE_IV | Cardiovascular | Coronary Arterial Disease (CAD) | Rationale: Dual antiplatelet therapy, consisting of aspirin and a P2Y12-inhibitor, reduces the risk of stent-related and non-stent-related ischemic events after percutaneous coronary intervention (PCI). However, this therapy is also associated with a higher risk of bleeding. Given the advances in stent technology and pharmacology, it may be possible to treat patients undergoing PCI with low dose prasugrel as single antiplatelet therapy, regardless of medical history, age or body weight. Objective: Assess the feasibility and safety of a single antiplatelet strategy with a reduced dose of prasugrel 5 mg after PCI in acute and chronic coronary syndrome patients (ACS and CCS). Study design: Open-label, single-centre, randomized controlled trial. Study population: Patients undergoing successful PCI due to acute or chronic coronary syndrome. Intervention: A once-daily reduced dose of 5 mg prasugrel for 6 months in CCS patients and for 12 months in ACS patients, preceded by a loading dose of 60 mg prasugrel after PCI, administered without concomitant use of aspirin. Main study parameters/endpoints: The primary endpoint is Net Adverse Clinical Events (NACE), a composite of all-cause death, myocardial infarction, definite stent thrombosis, ischemic stroke, clinically relevant non-major bleeding or major bleeding defined as Bleeding Academic Research Consortium type 2, 3 or 5. | * Acute Coronary Syndrome * Chronic Coronary Syndrome * Successful PCI | * Known allergy or contraindication for prasugrel, including Active pathological bleeding Severe liver disease (defined as Child Pugh class C) * Current indication for oral anticoagulant therapy (OAC) * Indication for ongoing DAPT (e.g. PCI ≤ 6 months for CCS or ACS ≤ 12 months) * Pregnancy or breast-feeding women * Participation in another trial with an investigational drug or device * Recent or ongoing use of CYP2B6 substrates with a narrow therapeutic window (e.g. cyclophosphamide, efavirenz) | 300 | 12 | 2025-11-13 | 2029-06-13 | 44 | 44 | Protocol eligibility criteria restricted enrollment to 4%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06435585 | Responders and Non-responders in the Management of Heart Failure - Significance of Genetic Influence and Identification of Novel Informative Biomarkers |  | Cardiovascular | Heart Failure | The national heart failure quality registry SwedeHF started in 2003. It is the world's largest continuous HF registry enrolling clinician-judged HF (regardless of LVEF) at time of hospital or clinical visit. Eighty variables are entered into an electronic database managed by the Uppsala Clinical Research Center (UCR). There are \>140,000 registrations from \>110,000 unique patients from 70 hospitals in Sweden. University hospitals in Sweden with access to central biobanking will collect a high-quality biobank linked to SwedeHF consisting of blood plasma, whole blood and urine enabling genetic, proteomic and metabolomic analyses as well as analyses of different biomarkers of interest for HF patients. This will provide unique opportunities for future research within the national SwedeHF registry. | 1. Written informed consent 2. Heart failure defined by symptoms and signs of heart failure as judged by the local investigator 3. Registered in SwedeHF | 1. Plasma donation within 1 month of enrolment or any blood donation/blood loss \>500 mL during the 3 months prior to enrolment 2. Previous allogeneic bone marrow transplant (genetics) 3. In the opinion of the investigator, condition/s that may either put the patient at risk on participation or influence the results or the patient's ability to participate in the study. | 5000 | 2480 | 2021-02-17 | 2030-12-31 | 120 | 120 | Protocol eligibility criteria restricted enrollment to 50%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT07286643 | Point-of-care Echocardiogram (POCUS) Guided Resuscitation Versus Conventional Goal- Directed Therapy in the Management of Cirrhosis With Severe Sepsis or Septic Shock: A Randomised Controlled Trial |  | Cardiovascular | Cirrhosis, Liver | * Patients with cirrhosis requiring intensive care for severe sepsis carry a risk of high mortality due to altered hemodynamics with reduced effective arterial volume, portal hypertension, presence of ascites, and risk of complications like acute variceal bleeding (AVB), acute kidney injury (AKI) and circulatory failure(3-5). The main principles for management of severe sepsis include early recognition, control of the source of infection, appropriate and timely administration of antimicrobial agents, and resuscitation with intravenous fluids +/- vasoactive drugs, if needed (6). * Due to portal hypertension, these patients have a hyperdynamic circulation, increased capillary permeability, splanchnic arteriolar vasodilation, and may have latent cirrhotic cardiomyopathy (CCM) (7). Hence assessment of volume status and cardiac reserve using conventional central venous pressure (CVP) or mean arterial pressure (MAP) remains difficult (8). Although inferior vena cava (IVC) dynamics and IVC collapsibility index are reasonable accurate for ventilated patients, their use in spontaneously breathing subjects or those with tense ascites are not defined(9). Even measures like passive leg raising and Valsalva manoeuvre are difficult to perform in cirrhotic patients with tense ascites. * Early goal directed therapy (EGDT) improved outcomes in a randomized trial in patients with severe sepsis(10). Thereafter EGDT was incorporated into the 6-hour resuscitation bundle of the surviving sepsis campaign guidelines, but did not incorporate patients with cirrhosis(11-13). Following the early EGDT trials, studies focussed choice of resuscitation fluid i.e., albumin versus normal saline or balanced salt solution (BSS), concerns about potential risks of volume overload and pulmonary edema and lack of generalisability in subsequent trials showed that there was no associated survival benefit with an aggressive fluid protocol(14, 15). In the ALBIOS study, 1818 patients with severe sepsis or sept | 1. Critically ill patient with cirrhosis of any etiology 2. Sepsis-related Hypotension (MAP \<65mmHg or SBP \<90mmHg) 3. 18-65 yrs of age - | 1. Already on vasopressors/inotropes 2. Severe pre-existing cardiopulmonary disease like porto-pulmonary hypertension (PPH), known coronary artery disease, congenital or valvular heart disease, prosthetic cardiac valves, dilated or restrictive cardiomyopathy. 3. Poor chest wall window due to left pleural effusion, left pneumothorax, small intercostal spaces that restrict performance of a POCUS. 4. Active bleeding like variceal bleed 5. Cerebrovascular events 6. Chronic renal disease - End Stage Renal Disease (ESRD)/ patient on renal replacement therapy 7. Admission to ICU following liver transplantation, burns, cardiac surgery 8. Previous transjugular intra hepatic portosystemic shunt (TIPS), 9. Hepatocellular carcinoma 10. Pregnant or lactating women 11. Informed consent refused by patient or attendants 12. Active COVID-19 infection | 140 | 5 | 2026-01-01 | 2028-12-30 | 36 | 36 | Protocol eligibility criteria restricted enrollment to 4%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06992089 | Pacemaker Implantation in Patients With Heart Failure With Preserved Ejection Fraction, Chronotropic Incompetence and Small Ventricular Volume. The SHOP-HF Trial |  | Cardiovascular | Heart Failure With Preserved Ejection Fraction | This study is designed as a multicenter, prospective, controlled, randomized, two-arms, cross-over, two parallel cohorts, efficacy Clinical research with CE-marked medical device . The crossover trial will be performed in a blind fashion, so each participant will be evaluated during both blinded pacing-on and pacing-off phases, each of which will last 3 months. The population includes patients with the diagnosis of stable HFpEF according to criteria of the European Society of Cardiology and New York Heart Association (NYHA) functional class II-III/IV, left ventricular hypertrophy with small ventricular volume, sinus rhythm with low basal heart rate and chronotropic incompetence (CI). All patients will undergo pacemaker implantation, and computer-generated randomization sequence previously designed will be used to allocate participants (in a 1:1 ratio) to receive: (a) programming of the pacemaker with pacing On followed by pacing Off in two periods of 3 months; or (b) programming of the pacemaker with pacing Off followed by pacing On in two periods of 3 months. The study will be conducted in three centers in Spain. Discounting the time due to staggered entry, the total duration of a patient's follow-up will be 7 months. | * Stable symptomatic heart failure (NYHA functional class ≥II) during the last month. * Diagnosis criteria of HFpEF according to ESC guidelines: 1. symptoms and signs of HF. 2. left ventricular ejection fraction ≥50% by Simpson method. 3. proBNP \>125 pg/mL in the last month. 4. at least one additional criterion: 1. relevant structural heart disease (left ventricular hypertrophy and/or left atrial enlargement); and/or 2. Diastolic dysfunction. * Left ventricular hypertrophy was defined as wall thickness \> 10 mm. * Small ventricular volume was defined as indexed left ventricular end diastolic volume \< 45 ml/m2. * Adults ≥18 years old. * Previous admission for acute heart failure. * Chronotropic incompetence assessed by CPET, defined as: \[(HRmax - HRrest)\]/\[(220 - age) - (HRrest)\] \< 0.62. * Resting heart rate \< 65 bpm in sinus rhythm or 70 bmp in atrial fibrillation. | * Inability to perform a valid baseline exercise test. * Significant primary pulmonary disease; including pulmonary arterial hypertension, chronic thromboembolic pulmonary disease or chronic obstructive pulmonary disease. * Patient with prior history of left ventricular ejection fraction \<50%. * History of an acute coronary syndrome in the previous 12 months. * Effort angina or signs of ischemia during CPET. * RER threshold at \<1.05 at the CPET. * Significant primary moderate to severe valvular disease. * Any other comorbidity with a life expectancy lower than 1 year. * Heart rate at rest \> 75 lpm. * Other pacemaker indication. * Pregnant women. * Baseline rhythm different from sinus rhythm or atrial fibrillation. * Active treatment with beta-blockers, digitalis or non dihidropiridine calcium channel blockers. | 30 | 15 | 2025-06-17 | 2026-12-17 | 18 | 18 | Protocol eligibility criteria restricted enrollment to 50%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT03586518 | Validating the Accuracy of Novel, Non-contrast, Cardiac Magnetic resOnaNce Imaging in Defining Myocardial FIbRosis in Patients With End-stage Renal Disease on haeModialysis: the CONFIRM Study |  | Cardiovascular | End Stage Kidney Disease | Native T1 mapping is a novel, non-contrast, cardiac MRI technique that characterises myocardial tissue by exploiting the different water content of tissues. It correlates well with histo-pathological levels of myocardial fibrosis in diseases of pressure overload such as aortic stenosis. There is growing evidence to demonstrate the potential of native T1 mapping as an imaging biomarker of myocardial fibrosis in patients with ESRD; myocardial native T1 values are higher in patients with ESRD than controls, and associate with measures of myocardial strain and circulating markers of cardiac dysfunction. Although native T1 times are affected by water content of tissues, our group has shown that native T1 times are not influenced by clinical changes in fluid status in HD patients and that the inter-study reproducibility and intra- and inter-observer variability of native T1 are outstanding. Native T1 mapping is a promising, non-invasive imaging biomarker of myocardial fibrosis in patients with advanced renal disease. It is essential that the technique is validated against histology before further use in clinical studies. The aim of this study is to directly assess the relationship between native T1 mapping and levels of MF examined at post-mortem in haemodialysis patients. | * Prevalent haemodialysis patient (more than 3 months) * Active on the supportive care register with anticipated death in the subsequent 12 months * Able to give informed consent * Consent to donation of heart for research following death * Able to understand written and verbal explanations in English | * Contraindication to MRI scan (e.g. pacemaker, incompatible metallic implants, claustrophobia) * Patients with expected or potential infiltrative cardiomyopathy (e.g. amyloidosis) * Unable to give informed consent * Unable to understand written and verbal explanations in English | 9 | 0 | 2026-12-18 | 2029-09-18 | 34 | 34
NCT06906276 | Walking and Thinking - Brain Activity During Complex Walking in Atypical Parkinsonian Syndromes |  | Neurology | Gait Disorders, Neurologic | Every-day life means being part of a complex environment and performing complex tasks that usually involve a combination of motor and cognitive skills. However, the process of aging or the sequelae of neurological diseases such as atypical Parkinson's disease (APD) compromises motor-cognitive interaction necessary for an independent lifestyle. While motor-cognitive performance has been identified as an important goal for sustained health across different clinical populations, little is known about underlying brain function leading to these difficulties and how to best target these motor-cognitive difficulties in the context of rehabilitation and exercise interventions. The challenge of improving treatments of motor-cognitive difficulties (such as dual-tasking and navigation) is daunting, and an important step is arriving at a method that accurately portrays these impairments in an ecologically valid state. The investigators aim therefore to explore brain function during complex walking in healthy and APD by investigating the effects of age and neurological disease on motor-cognitive performance and its neural correlates during three conditions of complex walking (dual-task walking, navigation and a combination of both) using non-invasive measures of brain activity (functional near infrared spectrometry, fNIRS) and advanced gait analysis in real time in older healthy adults and people with APD. | * clinical diagnosis of PSP according to Movement Disorder Society (MDS) (2017) or * MSA according to MDS criteria (2022) * the ability to walk with or without a mobility device for ≤5 minutes continuously | * cognitive difficulties affecting the ability to understand and/or follow verbal/written - instructions * severe freezing of gait * Severe hearing or visual impairments that affect participation in the assessments * Other neurological diseases * Other diseases that can affect gait or balance. | 30 | 8 | 2025-03-14 | 2027-12-31 | 34 | 34 | Protocol eligibility criteria restricted enrollment to 27%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06106893 | A Single-center Clinical Study Evaluating the Safety and Efficacy of CD19 Universal CAR-γδT Cells in Active Systemic Lupus Erythematosus | PHASE_I | Immunology | Systemic Lupus Erythematosus | The prognosis of patients with active systemic lupus erythematosus (SLE) remains poor, due to two major therapeutic obstacles: (1) current treatment strategies including glucocorticoids, immunosuppressive agents, biological agents, are still difficult to achieve disease control, making the disease condition of some patients continue to be active or even worse; (2) some patients are unable to wean themselves off glucocorticoid and face the risk of numerous adverse effects caused by long-term glucocorticoid dependence, such as glucocorticoid-related diabetes, femoral head necrosis, hypertension, stress ulcers, and infection, etc. Therefore, there is a strong unmet clinical need for more effective treatment for patients suffering from active SLE. Several preclinical studies have shown the efficacy of CAR-T cell treatment in SLE. The aim of this study is to investigate the safety, tolerability, preliminary efficacy, pharmacokinetics (PK), and pharmacodynamics (PD) of CD19 Universal CAR-γδT cells therapy in active SLE. Patients with active SLE will be invited to participate in the study, to receive CD19 Universal CAR-γδT cells intravenous infusion and follow-up visits of up to 2 years after enrollment. | 1. Participants or their guardians understand and voluntarily sign the informed consent form, and be able to complete all the documents, procedures, follow-up examinations and treatments specified in the study protocol, with good compliance; 2. Age range from 18 to 70 years old, regardless of gender; 3. Body weight ≥ 40kg; 4. Participants diagnosed with SLE according to the American College of Rheumatology (ACR) 1997 revised criteria for SLE at least 24 weeks prior to signing the informed consent form; 5. active SLE needs to meet the following criteria at screening: SELENA-SLEDAI score ≥ 6 points; PGA ≥ 1 points; 6. Have received at least 8 weeks of standardized treatment for SLE prior to screening; 7. Female participants need to have a negative pregnancy test, and participants agree to take effective contraceptive measures throughout the study. | 1. Known hypersensitivity to prednisone, immunosuppressive agents; 2. Diagnosis of active severe lupus nephritis within 8 weeks prior to screening, requiring medications prohibited by the research protocol for active nephritis, hemodialysis or prednisone ≥ 100 mg/d, or equivalent glucocorticoid therapy for ≥14 days; 3. Suicidal ideation within the past 6 months based on assessment by Columbia-Suicide Severity Rating Scale (C-SSRS) at screening; or any suicidal behaviors within the past 12 months or recurrent suicidal behaviors during the subject's lifetime; 4. Presence of SLE or non-SLE related central nervous system diseases or pathological changes within 8 weeks prior to screening; 5. Existence of other lupus crisis within 8 weeks prior to screening; 6. Previous or current diagnosis of non-SLE-related inflammatory arthropathy or skin diseases; 7. Previous or current diagnosis of severe vasculitis due to other diseases excluding SLE; 8. History of vital organ transplantation or hematopoietic stem cell/or bone marrow transplantation; 9. Have received plasmapheresis, hemodialysis, intravenous immunoglobulin within 14 days prior to screening; 10. Other autoimmune diseases requiring systemic therapy; 11. Active or latent tuberculosis at screening (can be enrolled if appropriately treated); 12. Any of severe laboratory abnormalities in liver function, renal function, bone marrow function, coagulation function, pulmonary function, cardiac function at screening; 13. History of severe allergy or known hypersensitivity to any of the active ingredients of the drugs, excipients, or rodent-derived products, xenoproteins included in this trial, or subjects with allergic constitution; 14. Severe heart diseases; 15. Severe hepatobiliary disease; 16. Presence of medical conditions that are obviously unstable or not effectively treated; 17. Presence of uncontrollable bacterial, fungal, viral or other infections, requiring antibiotic therapy; 18. Have received live/attenuated vaccination within 4 weeks prior to screening or plan to receive live/attenuated vaccination throughout the study; 19. Have received any commercially available Janus kinase inhibitor or Bruton tyrosine kinase inhibitor within 3 half-lives prior to screening; 20. Have received B-cell targeted therapy prior to screening; 21. Have received a biologic agent other than B-cell targeted therapy within 5 half-lives prior to screening; 22. Previous received therapies with CAR-T cells or other genetically modified T cells; 23. Have received therapeutic dose of corticosteroids within 7 days prior to leukapheresis or within 72 hours prior to infusion; 24. Subjects that have undergone major surgery within 4 weeks prior to lymph depletion or those who are scheduled to undergo major surgery during the study period, or whose surgical wounds have not fully healed prior to enrollment; 25. Subjects that have donated blood for ≥ 400mL or had significant blood loss equivalent to at least 400mL within 4 weeks prior to screening, or have received a blood transfusion within 8 weeks, or plan to donate blood during the study period; 26. History of ≥ grade 2 bleeding within 4 weeks prior to screening or need for long-term continuous anticoagulant therapy; 27. Subjects with severe mental illness; 28. Alcoholics or subjects with a history of drug abuse; 29. Female subjects who are pregnant or lactating, or intend to pursue pregnancy within 2 years after the cell infusion; male patients whose female sexual partners intend to conceive within 2 years after the cell infusion; 30. History of malignancy； 31. Patients that have contraindications to any of the study procedures or have other medical conditions that may expose them to unacceptable risk, in the judgment of the investigators and/or clinical criteria. | 15 | 12 | 2024-01-12 | 2026-09-12 | 32 | 32 | Enrollment reached 80% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT07213648 | Modification of Threat Interpretation Bias to Reduce Anxiety in Neurodegenerative Movement Disorders (Aim 3) |  | Neurology | Huntington Disease | The investigators will conduct a pilot randomized controlled trial of the MindTrails-Movement CBM-I app in patients with Huntington's disease and Parkinson's disease (N=136). Participants randomly assigned to the intervention group (N=68) will be asked to download the MindTrails-Movement mobile app and to complete daily CBM-I training sessions and nightly surveys, in addition to surveys at baseline and every 2 weeks for the duration of the 6-week intervention and at 4-week follow-up (week 10). Participants assigned to the waitlist control group will download a control version of the app without CBM-I training sessions. They will be asked to complete surveys in the app at baseline and every 2 weeks for the duration of the 6-week intervention and at 4-week follow-up (week 10). After 10 weeks, they will be offered the opportunity to access the version of MindTrails-Movement with CBM-I training content. | * Clinical diagnosis of Huntington's disease or Parkinson's disease (genetic diagnosis of HD also acceptable) * With anxiety symptoms (NeuroQoL Anxiety ≥12) | * Cognitive decline precluding ability to consent or complete the intervention (MoCA 5 min/telephone ≤11) * Unable to read and understand English * Does not have regular access to an internet-connected device, capable of downloading and installing the mobile application (i.e., tablet or iPhone running iOS 10 or later or an Android phone running Android 5.0 or later) * Not located in the USA * \<21 years old * Active suicidality based on the answer "yes" to questions 4, 5, or 6b of the Columbia-Suicide Severity Rating Scale (Screen version) | 136 | 12 | 2025-11-20 | 2028-02-20 | 27 | 27 | Protocol eligibility criteria restricted enrollment to 9%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06893055 | Strength-Endurance Circuit Training in Parkinson's Disease: Effects on Disease Severity, Physical Performance, Blood Biomarkers and Quality of Life. |  | Neurology | Parkinson Disease, Idiopathic | The goal of this clinical trial is to determine whether adding strength training to aerobic training has a comparable or greater effect on the clinical status of Parkinson's disease patients than a standalone aerobic training. \- Does combined strength-endurance circuit training provide added benefits to physical performance, disease severity, blood biomarkers, and quality of life in PD patients compared to standalone aerobic training? Participants will: * undergo outcome measurements before and after the 12-week intervention and a 3-month follow-up measurement, * visit the clinic twice a week for 1-hour training sessions. * selected patients will be given a smartwatch with a pedometer that will count their average number of steps before, during and after the training period | * age ≥18 years * diagnosis of idiopathic Parkinson´s disease * Hoehn-Yahr Scale ≤ 2,5 * stable dopaminergic medication | * age ≥75 years * Hoehn-Yahr Scale ≥ 2,5 * deep brain stimulation * presence of freezing * Camptocormia * inability to walk without support * inability to perform study procedures * limiting co-morbidities * attendance at training sessions below 70% | 90 | 45 | 2025-03-03 | 2027-07-03 | 28 | 28 | Protocol eligibility criteria restricted enrollment to 50%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT07032350 | E-Tailored Pain Management Support for Dementia Family Caregivers |  | Neurology | Care Giving Burden | This randomized controlled trial will assess the feasibility, usability, and preliminary efficacy of the Pain Control Enhancement App (PACE-app), a web-based intervention designed to support family caregivers of persons with dementia in managing pain. The trial will also explore mechanisms through which the PACE-app may affect caregiver and care recipient outcomes. Uncontrolled pain is common in people with dementia and presents unique challenges for caregivers, particularly those with limited access to specialized healthcare services. Family caregivers often lack adequate knowledge, skills, and support to manage pain effectively, contributing to suboptimal outcomes for both caregivers and care recipients. The PACE-app provides tailored, technology-based pain management support that includes: Screening of caregiver-specific challenges in pain management; Personalized pain management strategies based on the screening results; Communication tools to facilitate interactions with healthcare providers; A digital pain diary for tracking care recipients' pain experiences. A total of 60 family caregivers of people with dementia and chronic pain will be randomized 1:1 to either the PACE-app intervention group or a usual-care control group. Participants in the intervention arm will use the app for 1 month and complete outcome assessments at baseline, 1 month (post-intervention), and 2 months (follow-up). Participants in the control arm will continue their usual caregiving practices and complete assessments on the same schedule. Primary outcomes include feasibility (recruitment, retention, adherence to study protocol) and acceptability (measured by app usage analytics and qualitative interviews). Secondary outcomes include changes in caregiver self-efficacy in pain management, adherence to prescribed pain treatments, caregiver burden, stress, depression, and communication with healthcare providers. The study will also examine potential mediators (caregiver knowledge, c | * Be a primary caregiver - (a family member, relative, or friend) of a person with dementia (or cognitive impairment) and chronic pain (lasting \>3 months)' * Be responsible for managing the care recipient's pain and pain treatments (including interpreting verbal or non-verbal pain communication). * Be age 18 - 100. * Be able to read and speak English. * Have regular access to an electronic device (tablet, laptop, or computer) with internet connectivity (for using the app and participating in data collection). * Be accessible by phone or email to schedule meetings. * Be willing to commit to the full study duration and protocol. | * Currently participating in another research study that could interfere with this intervention. | 60 | 8 | 2025-05-22 | 2028-04-22 | 36 | 36 | Protocol eligibility criteria restricted enrollment to 13%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT04786821 | Feasibility Study for a Randomised Control Trial for the Acceptability of Exoskeleton Assisted Walking Compared to Standard Exercise Training for Persons With Mobility Issues Due to Multiple Sclerosis |  | Neurology | Multiple Sclerosis | Multiple sclerosis (MS) is a chronic, inflammatory disease of the central nervous system. Lack of physical activity is common in people with MS (pwMS). This can lead to several comorbid conditions such as obesity, metabolic syndrome, osteoporosis, hypertension, diabetes and worse prognosis. An increasing number of studies suggest that physical exercise can play an important role in managing symptoms, preventing complications and comorbidities in pwMS, and may possibly be neuroprotective. However, doing exercise can be very challenging for pwMS who have moderate/severe mobility disability and who have problems with walking. In this project, the investigators will explore the use of a powered Exoskeleton as an exercise tool for people with moderate to severe difficulty walking due to MS. Powered Exoskeletons are wearable robots that offer opportunity to persons with lower limb weakness to stand and walk. The Exoskeleton-assisted training provides active training with potentially much less intervention needed from therapists. However, it is not clear whether pwMS can walk with a powered Exoskeleton at speeds and intensities sufficient to positively affect health and fitness outcomes. Thus, in this study, the investigators aim to explore whether using an Exoskeleton will enable people with MS to exercise at a moderate intensity and whether people with MS find this acceptable and safe to do on a regular basis. The investigators will also explore whether training with an Exoskeleton can improve walking. The investigators will train 12 patients with MS to walk with an Exoskeleton twice a week for 8 weeks. The investigators will compare the effects with another group of 12 patients who will do exercises with a fitness instructor twice a week for 8 weeks. The investigators will study whether walking with Exoskeleton is better than fitness training in terms of fitness outcomes, walking and cognitive, psychological factors. | * Diagnosis of MS as per the McDonald criteria (Polman et al., 2011). * Age 18 years or older. * Cognitive ability to give consent and participate in the protocol. * Walking limitations with Expanded Disability Status Scale (EDSS) scores ranging from 5.0 to 7.5. * Enough strength in hands and shoulders to support themselves standing and walking using crutches or a walker. * Meet the general requirements to fit with the Phoenix Exoskeleton (160-190.5 cm in height, weight below 80 Kg, hip width no greater than 42.7 cm measured when sitting, healthy skin where it touches Phoenix Exoskeleton). * Able to tolerate exercise twice per week as judged by the PI during screening. | * Any illness, other than MS, affecting walking and exercise performance. * Severe cognitive or behavioral impairment. * Relapses 3 months prior to enrolment. * Change in disease modifying drugs for MS 6 months before enrolment. * Botulin toxin injections for the lower limbs the previous 3 months. * Any medical contraindications to assisted walking (e.g., cardiovascular condition, weight-bearing restrictions, osteoporosis or other fracture risk, pregnancy, uncontrolled seizure). * Significant flexion contractures limited to 35 degrees at the hip and 20 degrees at the knee that precluded Phoenix Exoskeleton fit. * Psychopathology or other health conditions that the physiotherapist, in his or her clinical judgement, considers to be exclusionary to safely use an Exoskeleton. * Living more than 20 miles away from the experiment location to reduce burden on patients due to the number of planned study visits. | 24 | 24 | 2022-06-23 | 2024-10-30 | 29 | 29 | Enrollment exceeded target in Neurology; strong site engagement and pre-screening drove performance. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06426316 | Immune System, Inflammation, Migraine - The Role of Cytokines and Regulatory T Lymphocytes in Migraine Pathophysiology |  | Neurology | Migraine Disorders | Migraine is the 6th most frequent disease (14% of the population) and the second leading cause of disability worldwide. From puberty and onward, migraine is 2 to 3 times more frequent in women, which also suffer from more severe attacks. Migraine is also up to twice as prevalent in patients suffering from autoimmune or inflammatory diseases such as multiple sclerosis (MS), rheumatoid arthritis (RA), Crohn disease (CD), systemic lupus erythematosus (SLE) and endometriosis, whereas patients with long standing type 1 diabetes mellitus (T1DM) - an autoimmune but non inflammatory disease - seem to be less affected compared to the general population. Despite the identification of the role of peptides such as CGRP in migraine pathophysiology and the development of targetted anti-CGRP treatments, many patients remain unresponsive and the mechanisms behind migraine are still unclear. The trigemino-vascular system is involved in the perception of migraine pain. Migraine occurs with trigemino-cervical neuron sensitization, leading to peptide secretion (such as CGRP, PACAP-38 and VIP), which induce neurogenic inflammation that is responsible for vasodilation, capillary leakage, oedema and further sensitization of the trigemino-vascular system, leading to amplified perception of migraine pain. CGRP, PACAP-38 and VIP infusions all induce migraine attacks in migraine patients, and only mild or no headache in healthy volunteers. Sex hormones, prolactin and insulin are also involved in migraine pathophysiology, and the immune system, through cytokine production and immune cell dysregulations seems to also play a role in the pathogenesis of migraine. Both are closely related as sex hormone levels may have an influence on the levels of certain immune cell subtypes. Several pro-inflammatory cytokines (tumor necrosis factor (TNF)-alpha, interferon (IFN)-gamma and interleukin (IL)-6) were shown to be elevated in migraine patients but also inflammatory diseases such as MS and endometri | * female * 18 - 50 years of age * at least 50 kg * autoimmune/inflammatory disease groups : with a diagnosis of multiple sclerosis, systemic lupus erythematous, rheumatoid arthritis, Crohn's disease, type 1 diabetes or endometriosis * migraine group : with a diagnosis of migraine with at least 4 headache days per month | * BMI \< or = 17 ou \> or = 30kg/m² * type 2 diabetes, immune deficit, other chronic autoimmune or inflammatory disease * non-migraine headache, except for tension type headache of less than 4 days/month * pregnancy, delivery, miscarriage, breast-feeding, participation in a medically assisted human reproduction program (ovary stimulation/hormone therapy) \< 3 months before blood sampling * Menopause, hysterectomy, or bilateral oophorectomy * Hormone therapy (besides contraception and treatment of endometriosis) * bone marrow or solid organ transplant * guardianship, curatorship, safeguard of justice or deprivation of liberty * for patients : diagnosis of several autoimmune or inflammatory diseases * for controls : diagnosis of an autoimmune or inflammatory disease * for non-migraine participants : migraine | 396 | 0 | 2027-01-18 | 2029-03-18 | 26 | 26
NCT03003572 | Autoreactive Anti-Ro/SSA IgE To Determine Primary SjögRen's Syndrome's Disease Activity |  | Immunology | Primary Sjögren's Syndrome | Primary Sjögren's syndrome (pSS) can affect various organs, sometimes leads to life-threatening conditions and is always responsible for a decreased quality of life. Its evolution is chronic, with flares and relapses, and the need for reliable biomarkers to be carried out routinely is major in patients' follow-up. Because of the existence of autoreactive immunoglobulins E (IgE) in autoimmune diseases, the recently described role for anti-Ro/SSA antibodies in inducing interferon alpha (IFNα) signaling and the specific pharmacologic properties of IgE, anti-Ro/SSA IgE should be an interesting biomarker to determine pSS's activity. The aim of the study is to evaluate whether the proportion of anti-Ro/SSA IgE positive patients is higher in patients with active disease (i.e. Eular Sjögren Syndrome Disease Activity Index≥ 5). All consecutive patients with pSS (new or already known diagnosis) will be included, Anti-Ro/SSA IgE titers will be determined, the disease's features will be collected (including Eular Sjögren Syndrome Disease Activity Index/Eular Sjogren's Syndrome Patient Reported Index). | * Primary Sjögren's syndrome according to the American-European Consensus Criteria) * Informed and having signed the study consent form | * Secondary Sjögren's syndrome * Other systemic autoimmune disease (e.g. rheumatoid arthritis, AntiNeutrophil Antibodies (ANCA) -associated vasculitis, mixed connective tissue disease…) * Incapacity or refusal to sign the informed consent form * Incapacity or refusal to perform the follow-up examinations required by the study * Has received abatacept, sifalimumab, rontalizumab, anifrolumab, belimumab, Tumor Necrosis Factor (TNF) antagonists or interferon during the 6 months prior to the inclusion * Has any current signs or symptoms of active infection | 185 | 185 | 2018-03-27 | 2020-12-27 | 34 | 34 | Enrollment exceeded target in Immunology; strong site engagement and pre-screening drove performance. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06618573 | Study on the Safety of Administering Isoniazid to Systemic Lupus Erythematosus Patients to Prevent Tuberculosis | PHASE_II | Immunology | Tuberculosis | Systemic Lupus Erythematosus (SLE) is a prototypical systemic autoimmune disease characterized by heterogeneity, multisystem involvement, and production of multiple autoantibodies. Clinical features can vary, from mild skin and joint involvement to severe and life-threatening conditions. The course of lupus is highly variable in the form of relapses and remissions, with mild and severe forms that can be life-threatening. Treatments for SLE includes steroids and immunosuppressants to control disease activity. Patients with lupus are more susceptible to infections, in addition to being immunocompromised, and due to the administration of corticosteroid and cytotoxic drugs. The presence of these infections is a cause of death in lupus disease in addition to the activity of the disease itself, especially in Asia-Pacific countries. One infection that often occurs in lupus is Tuberculosis (TB). Tuberculosis is still a problem especially in the Asian region, and Indonesia ranks 2nd with the most cases after India according to World Health Organization in 2019. TB infection is found in 10-11.4% of SLE patients in Asia. The incidence of TB in SLE is reported to range from 150/100,000 patients per year in Turkey to 2,450/100,000 patients per year in India. The annual risk of TB in SLE patients is higher than the normal population. Registry data at Hasan Sadikin Hospital Bandung showed that 11.4% or 93 out of 813 SLE patients were infected with TB after being diagnosed with SLE. Risk factors for increased TB infection in SLE patients, in addition to SLE disease activity itself (SLEDAI score \>12), renal involvement, lymphopenia, and cumulative dose of steroids used by the patient, are also due to long duration of illness and previous history of TB. Tuberculosis is also one of the infections that cause death in SLE patients. Mortality from TB in Asian countries ranged from 5-31%. A study in the Philippines found that 14.8% of SLE patients with TB died, those who died had dis | SLE patients with conditions of : * No signs and symptoms of active TB * Not under TB treatment * No History of TB, malignancy, HIV, liver function test abnormality * Not in pregnancy/lactation * No other active infections * Remission or low to moderate disease activity state * Consented to join the study completely | SLE patients with conditions of : * History of allergy to Isoniazid * Chronic liver disease, including chronic hepatitis B or C virus * Malignancy * Pregnancy | 60 | 60 | 2022-08-15 | 2025-12-01 | 40 | 40 | Enrollment exceeded target in Immunology; strong site engagement and pre-screening drove performance. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT05470569 | Prospective Registry of Patients With Systemic Lupus Erythematosus of the Argentinian Society of Rheumatology |  | Immunology | SLE | A longitudinal and multicenter cohort study of patients with systemic lupus erythematosus (SLE) is planned, with a follow-up of for 5 years. The data will be obtained from the clinical history of each patient. The responsible for data collection will always be a physician with experience in the management of patients with SLE and who has received training for data loading. The data will be collected through the an electronic case report form (eCRF) specially designed for this record and which in turn will facilitate the control of the data and the generation of inquiries to the researchers. STUDY VARIABLES Baseline visit: Sociodemographic data Classification criteria American College of Rheumatology (ACR 1982/1997), Systemic Lupus International Collaborating Clinics (SLICC 2012) and/or European League Against Rheumatism / American College of Rheumatology (EULAR / ACR 2019) History of SLE Access to specialized care Current clinical manifestations Activity and damage Scores Current treatments Patient-Reported Outcomes (PROs): Self-reported quality of life questionnaires EQ-5R; physician global assessment (PGA) and the patient Comorbidities Vaccination Habits Obstetric history Associated antiphospholipid syndrome Hospitalizations for adverse event, infections, or lupus activity Annual clinical follow-up visits Clinical follow-up of the patient Changes in clinical manifestations Changes in treatments Use of health services; hospitalizations; high cost treatments Activity and damage scores PROs Annual global and SLE-related mortality STUDY ENDPOINTS * Number of patients who achieved complete clinical remission or low disease activity status (LDAS) * Impact on the quality of life and working life measured by PROs and PGA * Mortality annual and global during the follow up period * Change in disease activity and damage scores * Health care resources used reported as number of hospitalizations, emergency visits and need of high cost treatment * Accessibility to high c | * Patients ≥ 18 years of age * Classified as SLE (according to the 1982/1997 American College of Rheumatology criteria and/or Systemic Lupus International Collaborating Clinics criteria for SLE) * Less than 5 years from meeting SLE criteria * Informed consent signature | * Diagnosis of other systemic autoimmune diseases or overlap syndromes * Patients who have been transferred to other centers | 1500 | 1270 | 2022-04-01 | 2027-04-01 | 61 | 61 | Enrollment reached 85% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06771427 | Systemic Proteomic Analysis of Plasma Exosomes to Explore the Immunomodulation Reflected to Sjogren's Syndrome and Dry Eye Syndrome |  | Immunology | Dry Eye Syndrome (DES) | Background: A 2015 survey in Taiwan revealed that the prevalence of Dry Eye Syndrome (DES) is 4.87%, with 4.8% of these cases likely to develop into Sjögren's Syndrome (SJS). An American study indicated that 11.6% of DES cases could be diagnosed as SJS, and SJS patients showed significantly more severe conjunctival and corneal staining, Schirmer's test results, clinical symptoms, anti-nuclear antibody, and rheumatoid factor compared to non-SJS patients. Various autoimmune diseases (such as SJS, SLE, RA, SSc, AS, etc.) also affect the severity of dry eye symptoms. Recent studies have employed exosome proteomics to investigate cell-to-cell communication, molecular mechanisms of diseases, and the development of new diagnostic markers and therapeutic targets. While these studies have significant research value for understanding disease mechanisms, diagnosis, and treatment, few have specifically focused on the impact of exosome proteomics in SJS and DES. Objective: By analyzing the differential proteins in exosomes, this study aims to understand the pathological mechanisms of SJS and DES, identify potential diagnostic and therapeutic methods, and advance the diagnosis and treatment of these diseases. Methods: This study will develope on previous research projects conducted at Taipei Veterans General Hospital (TBDESJS，V112C-190) and the National Science and Technology Council (ACUDES). TBDESJS focused on evaluating the use of a herbal tea TBDESJS for relieving dry eye and mouth symptoms in DES and SJS patients, and ACUDES explored the immediate and long-term effects of acupuncture on treating dry eye and mouth symptoms in DES and SJS patients by using the GB20 (Fengchi) and BL2 (Zanzhu) acupuncture points. 1. TBDESJS Study: Included 30 DES patients, 60 SJS patients, and 10 healthy controls (NHC) to evaluate the efficacy of the Traditional Chinese Medicine (TCM) herbal tea in improving dry eye and mouth symptoms. 2. ACUDES Study: Included 50 DES patients, 50 SJS patient | aged between 20 and 75 years Schirmer's test less than 10 mm/5 min | Pregnancy With eye inflammation or infectious eye disease Accepted operation of eye Sjögren's syndrome Inclusion Criteria: primary or secondary SS aged between 20 and 75 years fulfilled the 2002 American-European Consensus Criteria for SS (AECG) had no abnormal findings of immune, liver, kidney, or blood function evaluations. Exclusion Criteria: a history of alcohol abuse, diabetes mellitus, or major life-threatening condition pregnancy or breastfeeding steroid pulse therapy within three months prior to the commencement of our study. non AIDDES Healthy Controls Inclusion Criteria: aged between 20 and 75 years without any Chronic disease Exclusion Criteria: any Sjögren's syndrome or Dry eye syndrome. | 220 | 128 | 2025-01-16 | 2026-12-31 | 24 | 24 | Protocol eligibility criteria restricted enrollment to 58%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06513429 | Clinical Study on Evaluating the Efficacy and Safety of IM19 CAR-T Cell Therapy in Patients With Refractory Systemic Lupus Erythematosus |  | Immunology | Refractory Systemic Lupus Erythematosus | The study is a single-arm, open-label clinical trial intended to recruit 6 refractory SLE subjects who meet the inclusion and exclusion criteria. The subjects will receive IM19 CAR-T cell infusion therapy at a dose of 1×10\^6/kg or 1×10\^8 CAR-T cells . The primary endpoint is to evaluate the improvement in SLE disease activity (SLEDAI-2K) at 90 days and the occurrence of adverse events related to IM19 CAR-T cell infusion within 28 days post-infusion. Additionally, the long-term efficacy was evaluated, including the improvement of SLEDAI-2K score and achieving lupus low disease activity (LLDAS) at day 180 and day 360, and renal response at day 180 and day 360. The persistence and duration of IM19 CAR-T cells in the peripheral blood of subjects will also be evaluated. The study plan includes five phases: screening phase, cell collection phase, lymphodepletion pretreatment phase, cell infusion phase, and follow-up phase. | * 1)The subject was diagnosed with systemic lupus erythematosus and met the classification criteria of EULAR/ACR 2019 SLE (see Annex 2) * 2\) Age ≥ 18 years old, ≤ 65 years old * 3\) Weight ≥ 40 kg * 4\) Meets the current clinical standards for refractory systemic lupus erythematosus: the disease remains active or relapses and progresses after systemic treatment using the current standard treatment regimen, including steroids (sufficient or shock therapy), immunosuppressants (cyclophosphamide or mycophenolate mofetil), and biologics (belizumab or Rituximab) * 5\) Currently, one or more of the following stable dose standard therapies are being used to treat SLE: steroids, antimalarial drugs, immunosuppressants. If the subject is receiving steroids, the following conditions must be met: at screening time and during screening period, the maximum dose of steroids is 30mg/day prednisone (or equivalent dose). Before screening, the dose of steroids should remain stable for ≥ 7 days. During the screening period, the dose of steroids adjustment should not exceed 5mg/day prednisone (or equivalent dose). If the subject is receiving treatment with antimalarial drugs and/or conventional immunosuppressants: the start time of drug treatment must be ≥ 12 weeks before screening. Maintain a stable dose of medication for at least 8 weeks before and during screening. Before the screening period, if biological agents (such as belizumab or Telitacicept) are used, they need to be discontinued for at least 4 weeks before screening. * 6\) Disease activity score (SLEDAI-2K) with a score of 10 or above (refer to Attachment 3) * 7\) Women of childbearing age who tested negative for blood pregnancy before the start of the trial and agreed to take effective contraceptive measures during the trial period until the last follow-up * 8\) Male participants whose partners have fertility agree to take effective contraceptive measures during the trial period until the last follow-up * 9\) Those who voluntarily participate in this experiment and sign an informed consent form. | * 1\) After evaluation by researchers, it is determined that the subject has diseases that are not suitable for participation in this study, such as life-threatening conditions (e.g., catastrophic antiphospholipid syndrome, acute severe renal failure, acute severe central nervous system disease manifestations). * 2\) The research subject has a history of alcohol or drug abuse within the past 24 weeks. * 3\) The research subject has a history of malignant tumors other than B-cell lymphoma. * 4\) Major surgery (including joint surgery) was performed within 24 weeks prior to screening, or surgery is planned within 24 weeks after enrollment in the study. * 5\) The research subject has overlapping mixed connective tissue diseases and other syndromes that affect the judgment of disease activity. * 6\) The research subject has human immunodeficiency virus (HIV) infection, selective IgA deficiency, T-cell deficiency virus infection, chronic hepatitis B or C virus infection, or SARS-CoV-2 \[severe acute respiratory syndrome coronavirus 2\] infections. * 7\) The research subject has a known active tuberculosis (TB) infection or bacterial infection. * 8\) History of myocardial infarction, cardiac angioplasty or stent placement, unstable angina, active arrhythmia, or other clinically significant heart disease within 6 months prior to screening initiation. * 9\) History of symptomatic deep vein thrombosis or pulmonary embolism within 6 months prior to screening initiation. * 10\) The research subject's alanine aminotransferase (ALT), aspartate aminotransferase (AST), or alkaline phosphatase (ALP) levels are ≥3×ULN, or bilirubin \>1.5×ULN, excluding laboratory test abnormalities due to SLE hepatitis. * 11\) The research subject has stage 4 chronic kidney failure, indicated by an estimated glomerular filtration rate (eGFR) \<30 mL/min/1.73 m², or serum creatinine \>2.5 mg/dL. During the screening visit (V1), the research subject presents with any of the following significant hematological abnormalities: a. Hemoglobin \<7.0 g/dL b. CD4+ T lymphocytes \<200/mm³ c. Absolute neutrophil count \<500/mm³ d. CD4+ T lymphocytes \<500/mm³ with a neutrophil count \<1000/mm³ e. Platelets \<25,000/mm³. * 12\) Treatment with CD20 monoclonal antibodies was used within the past 6 months. * 13\) Conditions that the researcher considers unsuitable for inclusion in this clinical trial. | 6 | 0 | 2026-09-18 | 2029-06-18 | 33 | 33
NCT04624490 | Hyperpolarized 129Xe MR Imaging of Lung Function in Healthy Volunteers and Subjects With Pulmonary Disease | PHASE_I | Respiratory | Asthma | This is an unblinded, open-label study with \~160 subjects with diagnosed pulmonary disease and \~100 healthy controls. Subjects to be enrolled will include males and females 18-80 years old. Evaluation will be on an outpatient basis. Imaging will be done on a single day and will involve administration of up to four 1-liter doses of HP 129Xe plus one 129Xe calibration dose (\~300-400mL HP 129Xe). In addition to 129Xe MRI, a series of anatomical conventional 1H MR images will be collected including a localizer scan, breath-hold spin echo image, and breath-hold steady-state free precession image to highlight the vasculature. All subjects will be evaluated at one center: The University of Kansas Medical Center, KS USA. | Healthy Volunteers: * Subject has no diagnosed pulmonary conditions * Ability to read and understand English or Spanish Subjects with Lung Disease: * Subject has a diagnosis of pulmonary dysfunction made by a physician * No acute worsening of pulmonary function in the past 30 days * Ability to read and understand English or Spanish | * MRI is contraindicated based on responses to MRI screening questionnaire * Subject is pregnant or lactating * Subject does not fit into 129Xe vest coil used for MRI * Subject cannot hold his/her breath for 15-16 seconds * Subject deemed unlikely to be able to comply with instructions during imaging * Oxygen saturation \<88% on room air or with supplemental oxygen * Cognitive deficits that preclude ability to provide consent * Institutionalization | 260 | 143 | 2020-11-02 | 2028-10-26 | 97 | 97 | Protocol eligibility criteria restricted enrollment to 55%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT05720325 | Mechanistic Trial of Dupilumab in Adults With House Dust Mite-associated Asthma Using an Aeroallergen Challenge Chamber | PHASE_II | Respiratory | Asthma, Allergic | (i)Intervention #1: HDM exposures in the ACC This trial utilizes exposures to House dust mites (HDM) in the Aeroallergen Challenge Chamber (ACC) as a two-pronged tool for (i) precision phenotyping of HDM+PARC+AA+ persons to identify those with the adaptive and maladaptive phenotypes and (ii) assessment of symptoms intermittently throughout the clinical trial to monitor effects of dupilumab/placebo on symptom severity . (ii) Participants classifying to the adaptive and maladaptive phenotypes are then randomized to 18-weeks dupilumab vs. placebo, with ACC HDM visits during this phase. | 1. Will demonstrate understanding of the study and will provide a signed and dated informed consent. 2. Will be male or female, 18 to 65 years of age at the time of the screening visit. 3. Will have symptoms consistent with perennial nasal allergy for a minimum of 2 years prior to the screening visit. 4. Will have a positive standard skin prick test (SPT) to D. pteronyssinus within 24 months of screening. A positive SPT is defined as a wheal diameter of at least 5 mm larger than the negative control (normal saline). 5. Will have asthma with a documented FEV1 reversibility of ≥10% within 18 months of screening. 6. If a participant manifests symptoms suggestive of COVID-19, the participant must have a negative SARS-CoV-2 rapid antigen nasopharyngeal swab test before each HDM exposure visit. 7. A woman of childbearing potential, must have a negative urine pregnancy test at Visit 1 and prior to each exposure in the ACC. All women of childbearing potential must agree to a medically acceptable form of birth control throughout the study duration and for at least 2 months prior to Visit 1. Acceptable methods of birth control for this study include: 1. oral, patch, or intra-vaginal contraceptives 2. Norplant System® or other implant system 3. Depo-Provera® 4. IUD 5. double barrier method 6. abstinence 7. surgical sterility (hysterectomy, tubal ligation, or uterine ablation) Post-menopausal women defined as women without a menstrual cycle for at least 12 consecutive months qualify as non-childbearing for this study. 8. Will have never smoked or will be an ex-smoker (\<20 pack year history and no cigarette or smokeless tobacco use in the past year). | 1. Have a chronic lung disease other than asthma. 2. Have atopic dermatitis. 3. Have any ocular disease that is not associated with allergic rhinoconjunctivitis. 4. Are on home oxygen requirement. 5. Have a history of rebound nasal congestion (brought on by extended use of topical decongestants), chronic rhinosinusitis with or without nasal polyps, nasal septal perforation, or severe nasal tract malformations noted on physical exam. 6. Have FEV1 \<70% predicted as determined by pre-bronchodilator spirometry at visit 1. 7. Are unwilling/unable to withhold intranasal steroids or asthma medications before specified visits. 8. Are unwilling/unable to abstain from protocol-defined prohibited medications for the protocol-specified times before and during screening/selection and ACC HDM exposure visits. 9. Have received any oral or other form of systemic glucocorticosteroids within 1 month prior to the screening visit. 10. Have received JAK-1 inhibitors within 3 months prior to the screening visit. 11. Have known hypersensitivity to dupilumab or any of its excipients. 12. Have an ongoing helminth infection. 13. Have received a live vaccine within 30 days of screening or are planned to receive one during study participation.Note: Participant can receive a live vaccine \> 30 days after final study investigational product injection (visit 14) 14. Are pregnant or nursing. 15. Have a history of keratoconjunctivitis sicca. 16. Have indoor pet exposure causing upper or lower symptoms. 17. Have received allergen immunotherapy of any form within 12 months of screening visit. 18. Received biologics, other than anti-obesity or diabetes medications (such as tirzepatides, semaglutides), for any indication within 12 months of screening visit. 19. Have participated in a trial with an investigational drug in the past 30 days. 20. Have past or current medical problems or findings from physical examination or laboratory testing that are not listed above, that, in the opinion of the investigator, may pose additional risks from participation in the study, may interfere with the participant's ability to comply with study requirements, or may impact the quality or interpretation of the data obtained from the study. | 88 | 82 | 2023-03-29 | 2026-08-29 | 42 | 42 | Enrollment reached 93% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06903897 | Improving Chronic Disease Outcomes Across the Lifespan by Addressing Structural Racism |  | Respiratory | Hyperlipidemias | With a multidisciplinary team of social determinants of health (SDOH), implementation, antiracism, community-engaged, and practice-based researchers, the investigators will apply an antiracism framework to an existing evidence-based SDOH screening and referral system and develop a holistic implementation toolkit aimed at reducing bias and mitigating unequal treatment for families of color. The investigators will first conduct qualitative interviews with adult patients and caregivers to understand their experiences with racism and discrimination within the context of their experiences with screening and referral for SDOH; the investigators will then share their findings with stakeholders (e.g., clinic directors, community agency leaders, health system leaders, Medicaid leaders) and elicit their ideas on how best to address these issues within the systems they lead. Subsequently, the investigators will refine the WE CARE implementation protocol using this stakeholder input with the guidance of antiracism and implementation experts. The investigators will then implement the refined WE CARE protocol in family medicine clinics since adverse SDOH impact the whole family unit; it will also allow them to examine WE CARE's impact on improving health outcomes for racialized groups across the life course. The investigators will conduct a hybrid effectiveness-implementation study with a stepped wedge cluster RCT design in three large family medicine clinics (including 2 health centers) that serve racially/ethnically diverse low-income families from Worcester, Massachusetts. The specific aims are to: * Aim 1: Refine the WE CARE implementation protocol using an antiracism lens and community engagement approach to: (a) conduct key informant interviews with families to identify racism and discrimination related barriers to SDOH screening/referral; (b) present these barriers to systems-level stakeholders to elicit input on strategies to address patient concerns; and 3) create an an | * Adults and children with diagnosed chronic diseases (hypertension, diabetes mellitus, hyperlipidemia, asthma, or depression) who receive Family Medicine care at one of the study sites. * Children (\<18 years of age) with a diagnosis of asthma. * Adult patients (18 years or older) with a diagnosis of diabetes mellitus, hypertension, hyperlipidemia and/or depression. | * In adults (\>18 years of age), those without one or more of the following diagnoses as recorded by ICD-10 codes in their EHR: hypertension, hyperlipidemia, diabetes mellitus, or depression. * In children (\<18 years of age), those without a diagnosis of asthma. | 68000 | 5228 | 2025-10-08 | 2028-09-30 | 36 | 36 | Protocol eligibility criteria restricted enrollment to 8%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06441812 | A Multicenter, Single-group Phase II Clinical Study to Evaluate the Long-term Safety, Pharmacodynamics and Efficacy of Multiple Subcutaneous Injections of SHR-1703 in Eosinophilic Asthma Patients | PHASE_II | Respiratory | Eosinophilic Asthma Patients | The purpose of this study is to evaluation the long-term Safety, Pharmacodynamics and Efficacy of SHR-1703 in Eosinophilic Asthma Patients | 1. At least 18 years of age, Male or Femal. 2. A minimum weight of 40kg. 3. Subjects with the clinical features of asthma that meets the diagnostic criteria of the "Guidelines for the Prevention and Treatment of Bronchial Asthma (2020 Edition)" and has a medical history of at least 1 year. 4. Documentation of current asthma controller medication \[medium or high dose ICS and at least one of additional controller such as long-acting muscarinic antagonist (LAMA), long-acting beta2-agonist (LABA) and leukotriene receptor antagonist (LTRA)\] for at least 1 stable month before first administration of SHR-1703. 5. At least one confirmed history of exacerbation within one year of initial administration of SHR-1703, occurring during the use of medium and high daily dose ICS. 6. Absolute count of eosinophils must be ≥0.15×109/L at visit 0 and visit 1. 7. A pre-bronchodilator FEV1 \<85% and ≥30% predicted at visit 0 and visit 1. 8. Female subjects with fertility agree to have no plan pregnancy and voluntarily adopt high-efficiency contraception measures from signing the informed consent form to 14 months after the last dose of SHR-1703, and male subjects with fertility as partners agree to have no plan pregnancy and voluntarily adopt high-efficiency contraception measures between the first dose of SHR-1703 and the last visit in the study. 9. Subjects must be able to give written informed consent prior to participation in the study. | 1. Presence of a clinically important lung condition. This includes but is not limited to current infection, bronchiectasis, pulmonary fibrosis or a history of lung cancer. 2. A known immunodeficiency. 3. Presence of a clinically significant and uncontrolled serious cardiovascular and cerebrovascular disease, including but not limited to myocardial infarction, unstable angina, heart failure, stroke, and subarachnoid haemorrhage. 4. Within the first 4 weeks before visit 0, presence of exacerbation of allergic rhinitis or sinusitis, or a history of infections with clinical significance and/or requiring clinical intervention, including but not limited to respiratory infections. 5. A known parasitic infection within the first 6 months before visit 0. 6. A malignancy history within the first 5 years before visit 0 (Subjects that had localized basal carcinoma of the skin or cervical carcinoma in situ which was resected for cure will not be excluded). 7. Blood donation or significant blood loss (≥ 400ml) within the first 4 weeks before visit 0, or infusion of blood products or immunoglobulins. 8. Use systemic immunosuppressants (excluding systemic glucocorticoids used for asthma treatment and for non asthma treatment for less than 3 days) or immunomodulators, or biologics or Th2 cytokine inhibitors, including but not limited to methotrexate, cyclosporine, interferon-α, anti IL-5 monoclonal antibodies (including SHR-1703), anti IL-4R monoclonal antibodies, anti TSLP monoclonal antibodies, anti IgE monoclonal antibodies, metformin, etc., and within 5 half-lives of the drug before the first administration (refer to the longer drug instructions; for those with unknown half-lives, 12 weeks before the first administration shall prevail); 9. Subjects who have previously participated in any study and received Investigational Product within the first 30 days before visit 0. 10. There was a surgical plan or other treatment measures that the researcher believed may affect the subject's evaluation during the study period. 11. Laboratory examination shows obvious abnormalities at visit 0 and visit 1: 1. White blood cell count (WBC) \<3.0×109/L; 2. Hemoglobin≤90g/L； 3. Platelet\<100×109/L； 4. Alanine aminotransferase (ALT)\>2×ULN (upper limit of normal); 5. Aspartate aminotransferase (AST) \>2×ULN； 6. Total bilirubin (TBIL)\>1.5×ULN; 7. Prothrombin time (PT) \>ULN+3s； 8. Creatinin\>1.5×ULN; 9. Active hepatitis B (positive for hepatitis B virus deoxyribonucleic acid (HBV DNA) in peripheral blood), or positive for hepatitis C virus antibody, or positive for human immunodeficiency virus (HIV) antibody, or positive for treponema pallidum antibody； 12. ECG QTc\>450ms or other clinically significant abnormal results that may pose significant safety risks to the subjects at visit 0 or visit 1； 13. A history of drug addicts or substance abuse within 1 years prior to Visit 0； 14. Subjects who are pregnant (positive HCG test at visit 0 or visit 1) or breastfeeding should not be enrolled if they plan to become pregnant during the time of study participation； 15. Subjects with a known allergy or intolerance to anti IL-5 monoclonal antibody or other biologic； 16. Other reasons determined by the researcher as unsuitable for participation in the study. | 200 | 116 | 2024-07-19 | 2026-09-19 | 26 | 26 | Protocol eligibility criteria restricted enrollment to 58%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT07476703 | Expanded Studies of Risk Factors for Pulmonary-, Liver-, and Cardiovascular Disease in the SCAPIS 2 Stockholm Reexamination |  | Respiratory | Coronary Artery Disease | The Swedish CArdioPulmonary bioImage Study (SCAPIS) is a unique, large-scale national research initiative involving 30,000 randomly selected individuals aged 50-64, recruited between 2014 and 2018. The study is a collaborative effort among six university hospitals across Sweden. A follow-up study, SCAPIS 2, is conducted for half of the original participants. In Stockholm, 2,500 individuals will be re-examined at Danderyd University Hospital and Karolinska Institutet. SCAPIS 2 includes a core set of examinations involving blood sampling, questionnaires, and imaging. In addition to these, complementary local investigations are conducted to enable more detailed research questions. This protocol describes the additional studies conducted in the Stockholm cohort: EXTENDED SAMPLING: Saliva and Blood Samples with Blood Cell Isolation Additional blood samples will be collected to isolate blood cells for detailed immune system profiling, red blood cell function nd for lipid profiles and inflammatory markers. Saliva samples will be analyzed for inflammatory markers and microbial composition. EXTENDED QUESTIONNAIRES: Dyspnea, Sleep, Respiratory Infections, and Dental Health Participants will complete detailed questionnaires covering recent food, drink, and medication intake; oral hygiene; breathing and lung function; sleep quality and daytime somnolence; and history of respiratory infections, including COVID-19. EXTENDED IMAGING AND PHYSIOLOGICAL MEASUREMENTS: These investigations will be conducted during a separate visit, coordinated with the main study, and take approximately one hour. 1. Cardiac Ultrasound and Abdominal Aortic Measurements: cardiac structure and function, as well as the diameter of major arteries (e.g., the thoracic and abdominal aorta). 2. Liver Elastography: An ultrasound-based technique used to assess liver stiffness and fat content. 3. Vascular Stiffness: Blood pressure cuff-based pulse wave analysis with automated stiffness calculation. Photopleth | Subjects already included in the main / general SCAPIS reexamination study in Stockholm. | Inability to provide consent. | 1400 | 942 | 2024-04-08 | 2026-08-30 | 29 | 29 | Protocol eligibility criteria restricted enrollment to 67%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT07288554 | A Randomized, Double-Blind, Placebo-controlled, Single- and Multiple-ascending Dose Study to Evaluate the Safety, Tolerability, Pharmacokinetics, Immunogenicity, Pharmacodynamics and Clinical Activity of BBT002 in Healthy Volunteers and Participants With Chronic Obstructive Pulmonary Disease (COPD) | PHASE_I | Respiratory | Chronic Obstructive Pulmonary Disease (COPD) | The study consists of two parts: * Part A (single dose in HVs in sequential ascending dose cohorts, SAD in HVs part) * Part B (two repeated doses in patients with COPD, MAD in patients part) | ( A\&B) 1. Age of 18-65 years (HVs), 35-75 years (patients) 2. Body mass index between 18-32 kg/m², capped at 120 kg 3. Negative pregnancy tests for women of childbearing potential 4. Willingness to refrain from alcohol consumption for 24 hours prior to each study visit 5. Non-smokers, healthy current smokers (≤5 cigarettes/day), or ex-smokers 6. Adequate contraception use (for men and women of childbearing potential) 7. No clinically significant abnormalities or history of relevant diseases Key Inclusion Criteria (Part B only) 1. Documented history of COPD with a post-bronchodilator FEV1/FVC \< 0.70 2. FEV1 ≥ 50% and FEV1\<80% predicted at screening. | ( part A \& B) 1. Positive viral serology for human immunodeficiency virus (HlV), hepatitis C virus (HCV), or hepatitis B (HBV) 2. Immunodeficiencies, autoimmune diseases, or cancer, history of conditions predisposing to infections 3. History of major metabolic, dermatological, liver, kidney, hematological or other significant disorders 4. Clinically relevant abnormal lab results, including low blood counts, liver enzymes, or abnormal kidney function 5. Positive drug/alcohol tests or abnormal vital signs at screening or Day -1 6. Abnormal Electrocardiogram(ECG) findings 7. History of drug/alcohol abuse in the past 2 years 8. History of severe allergic reactions or hypersensitivity Key Exclusion Criteria for (Part B only) 1. Current diagnosis of other significant pulmonary disease 2. Significant or unstable cardiovascular diseases 3. Recent clinically significant infection 4. Inability to perform spirometry | 68 | 0 | 2027-01-18 | 2029-11-18 | 34 | 34
NCT06940531 | Identifying the Causes and Risk Factors of Pulmonary Exacerbations in Cystic Fibrosis |  | Rare Disease | Cystic Fibrosis (CF) | Participants will be recruited by staff within the care of UK CF centres. Initial discussions will occur either during routine outpatient reviews, telephone consultations or during admissions. Consent will take place prior to any other procedures. There will be four separate cohorts of participant 1. Group A participants will be 200 adults with CF (16 years or older) attending a UK adult CF centre taking part in the study 2. Group B participants will be 100 additional adults with CF attending one of the five core CF adult centres: Manchester, Leeds, Newcastle, Cardiff, Liverpool. 3. There will be a pilot study to test the practicalities of running the same protocol in a paediatric population. This will consist of up to 25 children with CF (5-16 years) attending a paediatric clinic in one of the five core centres. 4. In addition, the investigators will recruit up to 40 healthy volunteers to provide samples on a single occasion as controls. Group A participants will have a single in-person visit, at the start of the study. Clinical data, including lung function (spirometry), venous blood draw, sweat chloride, saliva sample and finger-prick dried blood spot sample, sputum, nasal liquid sample and urine sample and demographic data will be collected. The study will run for 12 months. Home sampling kit, consisting of 13 home sampling boxes and 3 additional exacerbation boxes, will be provided for participants to collect in-home sampling for the first 6 months fortnightly. The 3 additional exacerbation boxes will be provided for posting additional set of samples when unwell. There will be questionnaires to complete to remotely monitor the adherence to the protocol. Study app ("Watson") will be set up to provide reminders and aid study adherence and timely return of samples. Group B will only be offered at 5 specialist CF centres (Manchester, Cardiff, Newcastle, Leeds, Liverpool). This follows the same format as Group A but includes additional face to face visits at 1 a | For Adult Participants 1. Confirmed diagnosis of cystic fibrosis (CF), defined as presence of two pathogenic CF-causing CFTR mutations AND clinical features consistent with a diagnosis of CF, OR presence of at least one pathogenic CF-causing CFTR mutation AND sweat chloride (before use of CFTR modulators) \>60mmol/L AND clinical features consistent with a diagnosis of CF. 2. Age ≥ 16 years and receiving care from a UK Adult Cystic Fibrosis Centre for main study. 5-16yrs for Paediatric pilot study (see below). 3. Have had at least 1 previous exacerbation of CF lung disease, treated with oral or intravenous antibiotics, in the previous 12 months. 4. Able to understand the patient information sheet, willing to consent to study protocol and to returning home samples 5. Has a home spirometry device and able to use this For those taking part in Group-B, additional inclusion criteria include 6. Willing to attend for additional face to face visits at 4 weeks, 26 weeks, and if they become unwell For those taking part in home monitoring (as part of Group-B at Manchester) 7. Has wireless internet at home 8. Willing to allow to home access to set up monitoring devices, collect these back in at end of study, and to carry out other visits to perform calibration or intermittent home air sampling. For Paediatric Participants 1. Confirmed diagnosis of cystic fibrosis (CF), defined as presence of two pathogenic CF-causing CFTR mutations AND clinical features consistent with a diagnosis of CF, OR presence of at least one pathogenic CF-causing CFTR mutation AND sweat chloride (before use of CFTR modulators) \>60mmol/L AND clinical features consistent with a diagnosis of CF. 2. Receiving care from an eligible Paediatric CF Centre. 3. Age 5-16 years 4. Have had at least 1 previous exacerbation of CF lung disease, treated with antibiotics. 5. Able to understand the study and/or willing to assent to study protocol. 6. Parents or guardians able to understand the study and willing to consent to take part, including helping with home sampling 7. Has a home spirometry device and able to use this For Healthy Volunteers 1. Healthy subject, male or female, aged 16-65 years 2. No active lung condition, chronic inflammatory disorder or infection 3. Not been on antibiotics or anti-inflammatory agents of any sort (including inhaled or systemic corticosteroids) for at least 90 days. 4. No recent (defined as within the previous 4 weeks) acute viral symptoms 5. Willing to sign the consent form and provide the samples. | 1. Unable to produce sputum, spontaneous or induced, at visit 1. If subject is normally able to produce sputum and still wishes to take part, visit 1 can be repeated on up to two additional occasions if this is needed to obtain sputum sample. 2. For the first visit, participants should be clinically stable at the time of the visit. This is defined as no acute change in their baseline symptoms or presence of new viral symptoms. They should not be on additional antibiotics or anti-viral therapies for any reason (above their usual medications), and should have completed any such additional therapies at least 4 weeks prior to visit 1. 3. Subjects with infection with Mycobacteria tuberculosis 4. Subjects with active ABPA, defined as receiving treatment for ABPA currently or within the last 12 months, or those considered at risk of requiring treatment for ABPA in the next 12 months. 5. Subjects receiving long term oral steroids at an equivalent dose of 10mg or more per day of prednisolone. 6. Subjects receiving any other form of long term immune-suppressant therapy. 7. Subjects with non-tuberculous mycobacteria (NTM) infection who are undergoing active eradication therapy. Subjects with chronic NTM infection who are not on eradication therapy, and not expecting to start this within the next 12 months, are not excluded. 8. Subjects who are unable to complete home spirometry who have previously been shown poor adherence to home monitoring requests 9. Any other condition, co-morbidity or other feature that, in the opinion of the investigator would render the subject unable to complete the protocol or unsuitable for inclusion. 10. For home monitoring, any subject where the investigator or their team has concern about staff safety when performing home visits. Patients taking part in other long term trials or observational studies are eligible to take part in CF-Tracker. Local investigators should judge whether the burden of additional research visits will be manageable. | 300 | 25 | 2025-05-16 | 2029-12-31 | 56 | 56 | Protocol eligibility criteria restricted enrollment to 8%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT05341453 | The Effect of Intensive Hippotherapy on the Psychomotoric Development of Children With Spinal Muscular Atrophy |  | Rare Disease | Spinal Muscular Atrophy | Spinal muscular atrophy is rare neuromuscular disease, it is caused by gene mutation survival motor neuron 1 (SMN1). This gene encodes survival motor neuron(SMN) protein. This protein is most important to survive alfa-motoric neurons in spinal cord. When this protein doesn´t work, no signals go from brain to skeletal muscles and fazic muscles of body. In the end weakening breathing muscles and internal organs muscles. The first treatment is pharmacological treatment. There is a lot of research about medicament treatment, the famous treatment in Czech Republic is medicine Spinraze and from year 2020 medicine Zongelsma. This, however, more often puts more difficulty on complex rehabilitation. An empirical observation has found out that complex rehabilitation has positive effect on progress of disease and on self-sufficiency of people and children with SMA. Physiotherapy is one of the recommended rehabilitation types. The use of rehabilitation procedures is common in clinical practice. In a 2016 study, 105 adults with SMA were asked how many of them used physiotherapy. A total of 86% of respondents received these services, yet the authors of the article conclude that further research is needed to understand the impact of physiotherapy in SMA. Nevertheless, there is a lot of discussion if physiotherapy is really good for people and children with SMA. Some research shows us, that physiotherapy doesn´t worsen this disease. Researchers showed that strength training 3 times a week does not show side effects in children under 10 years of age, in some cases trends in improving muscle strength and motor functions have been observed. Because in physiotherapy therapists work primarily with muscles, and a lot of activity can cause fatigue of skeletal muscles and worsen their function. But from clinical work scientists know that the effect of physiotherapy is extensive. There is a research on mice which shows the effect of physiotherapy on the strength activities and the aerobi | * clinic diagnosis SMA (I, II, and III types) * no changing medicine 6 months at least * without another grave diseases | * hip subluxation * allergies to horses and the environment of horse stables * insurmountable fear of the horse | 16 | 13 | 2022-04-22 | 2025-10-22 | 43 | 43 | Enrollment reached 81% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT05504837 | KB407-02 A Phase 1 Study of Inhaled KB407, a Replication-Defective, Non-Integrating Vector Expressing Human Cystic Fibrosis Transmembrane Conductance Regulator, for the Treatment of Cystic Fibrosis | PHASE_I | Rare Disease | Cystic Fibrosis | This study will evaluate safety and tolerability of ascending doses of nebulized KB407 in adults with cystic fibrosis. | 1. The subject must have read, understood, and signed an Institutional Review Board/Ethics Committee (IRB/IEC) approved Informed Consent Form and must be able to and willing to follow study procedures and instructions 2. Subjects aged 18 years or older at the time of Informed Consent 3. A confirmed diagnosis of CF as defined by clinical signs and symptoms of CF and at least one of the following: * A historical sweat chloride value \>60 mmol/L * Two copies of a disease causing mutation in the CFTR gene 4. Clinically stable in the opinion of the Investigator 5. Percent predicted FEV1 ≥40% and ≤90% of the predicted normal for age, gender, and height at Screening 6. Resting oxygen saturation ≥92% on room air at Screening | 1. Initiation of any new chronic therapy (eg, CFTR modulator, hypertonic saline, inhaled antibiotic) or any change in chronic therapy (excluding pancreatic enzyme replacement therapy) within 28 days prior to the first dose 2. Hospitalization, sinopulmonary infection, CF exacerbation, or other clinically significant infection or illness 14 days prior to the first dose that, in the opinion of the Investigator, may confound study results 3. Treatment for Mycobacterium abscessus within 3 months prior to the first dose or more than two pulmonary exacerbations with a history of Burkholderia cenocepacia infection within 6 months prior to the first dose 4. Participation in another clinical study or treatment with an investigational agent 30 days or 5 half-lives, whichever is longer, prior to the first dose 5. History of or listed for solid organ transplantation 6. Any condition (including a history or current evidence of substance abuse or dependence, uncontrolled asthma, or is considered to be immunocompromised) that, in the opinion of the Investigator, would impact a subject's ability to complete all study-related procedures and/or poses an additional risk to the assessment of safety of KB407 7. An active oral herpes infection 30 days prior to the first dose 8. Women who are pregnant or nursing 9. Subject who is unwilling to comply with contraception requirements per protocol 10. Clinically significant abnormalities of hematology or chemistry testing at Screening that the Investigator believes may interfere with the assessment of safety and/or efficacy of the study treatment 11. Subject has a known hypersensitivity to inhaled glycerol 12. Subject is known to be noncompliant or is unlikely to comply with the requirements of the study protocol in the opinion of the Investigator 13. Bronchoscopy participants only: Unable to tolerate bronchoscopy procedure and airway sampling, in the opinion of the Investigator 14. Cohort 4 participants only: Subjects who are ineligible for, do not tolerate, or do not benefit from modulator therapy | 20 | 17 | 2023-06-30 | 2026-11-30 | 42 | 42 | Enrollment reached 85% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06152302 | Analysis of Mobility in the Bath for Infants Affected With Spinal Muscular Atrophy |  | Rare Disease | Infantile Spinal Muscular Atrophy | This is a multicenter research project coordinated by the Child Neuromuscular Unit at Raymond Poincaré Hospital. Additionally, two other pediatric neurology departments, part of the national neuromuscular network FILNEMUS (https://www.filnemus.fr/), will participate in the study: Necker Children's Hospital and Armand Trousseau Hospital. The study's population will include all infants diagnosed with spinal muscular atrophy (SMA), specifically SMA type 1, who have onset before 6 months of age and have been evaluated by the French Therapeutic Commission. Participation in the study will be contingent on parental or guardian consent during follow-up visits. Spinal muscular atrophy is a genetic neurodegenerative condition that affects spinal motor neurons, causing motor and respiratory paralysis and ultimately leading to death. As groundbreaking therapies emerge, there's an increasing need to refine the methods used to assess motor function, especially in infants with severe hypotonia due to SMA type 1. Traditional reference scales used on examination tables are limited in their accuracy because of gravitational effects. Consequently, there's growing interest in evaluating these children's motor skills in water to detect movements unburdened by gravity. Pediatric neurologists in France (SFNP) have already acknowledged the potential value of parental video recordings during infant baths. However, the lack of standardization in recording conditions, coupled with the subjective nature of video interpretations, underscores the necessity for a more standardized and quantifiable approach. Herein lies the application of our proposed evaluation utilizing inertial sensors. Utilizing inertial sensors to detect subtle movements can highlight still-active yet minimally functional motor neurons. Such detection can be pivotal in identifying children who, despite severe motor skill limitations in traditional settings, still possess developmental potential. Our study seeks to leverage | * Infants with muscle weakness (commonly referred to as floppy babies): * Confirmed diagnosis of SMA through gene mutation or deletion (SMN1 gene). * Receiving standard care. * Age less than 12 years and a height of less than 90 cm at the time of inclusion. * Patients enrolled in a social security scheme. * Informed consent signed by both parents of the child and the investigator. | * Patients presenting with lesions in the spinal cord or conditions affecting the cardiorespiratory system. * Patients covered under the French Aid in Health for Foreign People program (AME). | 15 | 8 | 2025-06-26 | 2027-03-26 | 21 | 21 | Protocol eligibility criteria restricted enrollment to 53%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT05200429 | Canadian Observational Study Evaluating the Long-term IMPACT of CFTR (Can-IMPACT CF) |  | Rare Disease | Cystic Fibrosis | This observational study intends to investigate health trends and data in cystic fibrosis patients all across Canada that are receiving modulator treatment so researchers can determine if CFTR treatments are effective over a long period of time and if so, which treatments work best for each individual. The study will collect clinical data from routine standard of care, patient reported outcomes via survey data and samples for a biobank. | * Prescribed a CFTR modulator therapy and planning to commence modulator therapy within 30 days OR planning to switch modulator therapies within 30 days * Participates in the Canadian Cystic Fibrosis Registry (CCFR) * Informed consent by participant, or parent/legal guardian or assent | * Known contraindications to CFTR modulator therapy | 500 | 413 | 2021-11-01 | 2027-12-31 | 75 | 75 | Enrollment reached 83% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06528418 | Exploration and Study on the Identification of Various Pulmonary Diseases Using Volatile Organic Compounds Biomarkers in Human Exhaled Breath |  | Rare Disease | Lung Cancer | This is a prospective, cross-sectional, observational cohort study aimed at recruiting 10,000 participants with multiple pulmonary disease, including lung cancer, lung infection, chronic obstructive pulmonary disease (COPD), bronchitis, pulmonary fibrosis, pulmonary embolism, pulmonary arterial hypertension, tuberculosis, lung abscess, emphysema, radioactive lung injury, cystic fibrosis of the lung, Bronchial Asthma, Bronchiectasis, interstitial lung disease (ILD), preserved ratio impaired spirometry (PRISm) etc . Exhaled breath samples from these participants will be collected and analyzed using Gas chromatography-mass spectrometry(GC-MS) and micro Gas Chromatography-photoionisation detector (μGC-PID) system. Upon obtaining the μGC-PID results, a comprehensive evaluation of the diagnostic capabilities of exhaled breath samples in differentiating various pulmonary diseases will be performed, leveraging clinical diagnostic results, CT examination data, and clinical data. | * Males or females, age must be 18 years old or above. * Patients must meet the CT imaging diagnostic criteria for different lung diseases, and patients must be able to provide electronic versions of CT image data. * Patients must have a clear clinical diagnosis. * All participants must sign a written informed consent form. | * Pregnant women. * Individuals with a history of cancer other than lung disease. * Individuals who have undergone organ transplants or non-autologous (allogeneic) bone marrow or stem cell transplants. * Individuals with other severe organic diseases or mental illnesses. * Individuals with metabolic diseases such as diabetes, hyperlipidemia, etc. * Any other condition that researchers deem unsuitable for participation in this clinical trial. | 10000 | 0 | 2026-08-18 | 2028-02-18 | 18 | 18

## Protocol Sites
id | protocol_id | site_id | site_name | country | target_enrollment | actual_enrollment | performance_tier
436 | NCT06567015 | NCT06567015-S01 | Sarah Cannon Research Institute (SCRI) (The SCRI Oncology Research Consortium) | United States
437 | NCT06567015 | NCT06567015-S02 | Oncology Consultants (OC) - Texas Medical Center - Cancer Center | United States
438 | NCT06567015 | NCT06567015-S03 | Shanghai East Hospital, Tongji University | China
439 | NCT06567015 | NCT06567015-S04 | Tianjin Medical University Cancer Institute and Hospital | China
440 | NCT06567015 | NCT06567015-S05 | Centre Léon Bérard | France
441 | NCT06567015 | NCT06567015-S06 | CHU Hôpital de la Timone | France
442 | NCT06567015 | NCT06567015-S07 | Institut de Cancérologie de l'Ouest (ICO) - René Gauducheau | France
443 | NCT06567015 | NCT06567015-S08 | Institut Universitaire du Cancer de Toulouse - Oncopole | France
444 | NCT05655078 | NCT05655078-S01 | East Sussex Healthcare NHS Trust - Eastbourne Hospital | United Kingdom
445 | NCT05655078 | NCT05655078-S02 | East Sussex Healthcare NHS Trust - Conquest Hospital | United Kingdom
446 | NCT05655078 | NCT05655078-S03 | Royal Berkshire Hospital | United Kingdom
447 | NCT05655078 | NCT05655078-S04 | Southend University Hospital | United Kingdom
448 | NCT05655078 | NCT05655078-S05 | Queen Alexandra Hospital | United Kingdom
449 | NCT05655078 | NCT05655078-S06 | Queen Elizabeth Hospital, King's Lynn | United Kingdom
450 | NCT05655078 | NCT05655078-S07 | Furness General Hospital | United Kingdom
451 | NCT05655078 | NCT05655078-S08 | Betsi Cadwaladr University Health Board -Glan Clwyd Hospital | United Kingdom
452 | NCT06793189 | NCT06793189-S01 | Shanghai Ruijin Hospital | China
453 | NCT06793189 | NCT06793189-S02 | Affiliated First Hospital of China Medical University | China
454 | NCT06793189 | NCT06793189-S03 | Peking University Third Hospital | China
455 | NCT05506410 | NCT05506410-S01 | Department of Oncology, The First Affiliated Hospital of Zhengzhou University | China
456 | NCT06246110 | NCT06246110-S01 | Southern Cancer Care | United States
457 | NCT06246110 | NCT06246110-S02 | Ironwood Cancer and Research Center | United States
458 | NCT06246110 | NCT06246110-S03 | California Cancer Care Associates for Research & Excellence | United States
459 | NCT06246110 | NCT06246110-S04 | California Research Institute | United States
460 | NCT06246110 | NCT06246110-S05 | University of Southern California, Norris Comprehensive Cancer Center | United States
461 | NCT06246110 | NCT06246110-S06 | Providence St Joseph Hospital, Center for Cancer Prevention and Treatment | United States
462 | NCT06246110 | NCT06246110-S07 | Sutter Health Institute for Medical Research | United States
463 | NCT06246110 | NCT06246110-S08 | Rocky Mountain Cancer | United States
464 | NCT06945120 | NCT06945120-S01 | Dana-Farber Cancer Institute | United States
465 | NCT06945120 | NCT06945120-S02 | University of Massachusetts-Boston | United States
466 | NCT05133843 | NCT05133843-S01 | Heart Center Leipzig at University of Leipzig Department of Internal Medicine/Cardiology | Germany
467 | NCT06916520 | NCT06916520-S01 | Amsterdam UMC | Netherlands
468 | NCT06435585 | NCT06435585-S01 | Karolinska University hospital | Sweden
469 | NCT07286643 | NCT07286643-S01 | PGIMER Chandigarh | India
470 | NCT06992089 | NCT06992089-S01 | Hospital Clínico de la Comunidad Valenciana | Spain
471 | NCT03586518 | NCT03586518-S01 | University Hospitals of Leicester NHS Trust | United Kingdom
472 | NCT06906276 | NCT06906276-S01 | Karolinska Institutet | Sweden
473 | NCT07213648 | NCT07213648-S01 | Univeristy of Virginia School of Nursing | United States
474 | NCT06893055 | NCT06893055-S01 | Department of Neurology and Centre of Clinical Neuroscience First Faculty of Medicine, Charles University and General University Hospital in Prague | Czechia
475 | NCT07032350 | NCT07032350-S01 | College of Nursing | United States
476 | NCT04786821 | NCT04786821-S01 | sheffield teching hospital NHS foundation trust | United Kingdom
477 | NCT06426316 | NCT06426316-S01 | CHU de Clermont-Ferrand - Service de Neurologie | France
478 | NCT06106893 | NCT06106893-S01 | Wuhan Union Hospital | China
479 | NCT03003572 | NCT03003572-S01 | CH Pierre Oudot | France
480 | NCT03003572 | NCT03003572-S02 | CHU Estaing - Clermont Ferrand | France
481 | NCT03003572 | NCT03003572-S03 | CHU Grenoble Alpes | France
482 | NCT03003572 | NCT03003572-S04 | Hôpital de la Croix Rousse | France
483 | NCT03003572 | NCT03003572-S05 | CH Lyon Sud | France
484 | NCT03003572 | NCT03003572-S06 | Hôpital Edouard Herriot - CHU Lyon | France
485 | NCT03003572 | NCT03003572-S07 | CHU Reims | France
486 | NCT03003572 | NCT03003572-S08 | Chu Saint-Etienne | France
487 | NCT06618573 | NCT06618573-S01 | Rumah Sakit Dr Hasan Sadikin, Universitas Padjadjaran | Indonesia
488 | NCT05470569 | NCT05470569-S01 | Lucila Garcia | Argentina
489 | NCT06771427 | NCT06771427-S01 | Ching-Mao | Taiwan
490 | NCT06513429 | NCT06513429-S01 | Peking Universitiy Third Hospital | China
491 | NCT04624490 | NCT04624490-S01 | University of Kansas Medical Center | United States
492 | NCT05720325 | NCT05720325-S01 | Biogenics Research Chamber | United States
493 | NCT05720325 | NCT05720325-S02 | University of Texas Health Science Center at San Antonio | United States
494 | NCT06903897 | NCT06903897-S01 | (Benedict) UMass Memorial Medical Center - Adult Primary Care | United States
495 | NCT06903897 | NCT06903897-S02 | UMass Memorial Medical Center - Hahnemann Campus | United States
496 | NCT06903897 | NCT06903897-S03 | Family Health Center of Worcester | United States
497 | NCT06441812 | NCT06441812-S01 | West China Hospital of Sichuan University | China
498 | NCT07476703 | NCT07476703-S01 | Cardiovascular Research Lab, Dept Cardiology, Danderyd University Hospital | Sweden
499 | NCT07288554 | NCT07288554-S01 | The Second Hospital of Anhui Medical Univesity | China
500 | NCT07288554 | NCT07288554-S02 | The third affiliated hosptial of Guangzhou Medical University | China
501 | NCT07288554 | NCT07288554-S03 | The First Affiliated Hospital of Guangdong Medical University | China
502 | NCT07288554 | NCT07288554-S04 | Jiangmen Central Hospital | China
503 | NCT07288554 | NCT07288554-S05 | Qingyuan People's Hospital | China
504 | NCT07288554 | NCT07288554-S06 | The First People's Hospital of Xinxiang City | China
505 | NCT07288554 | NCT07288554-S07 | Yichang Central People's Hospital | China
506 | NCT07288554 | NCT07288554-S08 | The Affiliated Hospital of Xuzhou Medical University | China
507 | NCT06940531 | NCT06940531-S01 | Manchester Adult Cystic Fibrosis Centre | United Kingdom
508 | NCT06940531 | NCT06940531-S02 | Birmingham Heartlands Hospital | United Kingdom
509 | NCT06940531 | NCT06940531-S03 | Blackpool Teaching Hospitals | United Kingdom
510 | NCT06940531 | NCT06940531-S04 | Medical Research Unit, Bristol Royal Infirmary | United Kingdom
511 | NCT06940531 | NCT06940531-S05 | Cardiff and Vale University Health Board | United Kingdom
512 | NCT06940531 | NCT06940531-S06 | Royal Devon and Exeter Hospital (Wonford) | United Kingdom
513 | NCT06940531 | NCT06940531-S07 | NHS Greater Glasgow and Clyde | United Kingdom
514 | NCT06940531 | NCT06940531-S08 | Leeds Adult CF Centre | United Kingdom
515 | NCT05341453 | NCT05341453-S01 | Kamila Řasová | Czechia
516 | NCT05504837 | NCT05504837-S01 | University of Florida, Gainesville | United States
517 | NCT05504837 | NCT05504837-S02 | St. Lukes CF Center of Idaho | United States
518 | NCT05504837 | NCT05504837-S03 | The Cystic Fibrosis Institute | United States
519 | NCT05504837 | NCT05504837-S04 | New York Medical College/ Boston Children's Health Physicians | United States
520 | NCT05504837 | NCT05504837-S05 | Northwell Health Physicians | United States
521 | NCT05504837 | NCT05504837-S06 | Atrium Health Wake Forest Baptist Medical Center | United States
522 | NCT06152302 | NCT06152302-S01 | Infantile neuromuscular unity - Department of paediatric neurological care and intentive care unity, Raymond Poincaré Hospital - APHP | France
523 | NCT05200429 | NCT05200429-S01 | British Columbia Children's Hospital | Canada
524 | NCT05200429 | NCT05200429-S02 | St Paul's Hospital | Canada
525 | NCT06528418 | NCT06528418-S01 | The First Affiliated Hospital of Guangzhou Medical University | China

## Lessons Learned
id | protocol_id | category | description
95 | NCT06567015 | Operations | Protocol eligibility criteria restricted enrollment to 32%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
96 | NCT05655078 | Operations | Protocol eligibility criteria restricted enrollment to 29%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
97 | NCT06793189 | Operations | Protocol eligibility criteria restricted enrollment to 16%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
98 | NCT05506410 | Operations | Protocol eligibility criteria restricted enrollment to 70%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
99 | NCT06246110 | Operations | Protocol eligibility criteria restricted enrollment to 79%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
100 | NCT05133843 | Operations | Enrollment reached 82% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
101 | NCT06916520 | Operations | Protocol eligibility criteria restricted enrollment to 4%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
102 | NCT06435585 | Operations | Protocol eligibility criteria restricted enrollment to 50%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
103 | NCT07286643 | Operations | Protocol eligibility criteria restricted enrollment to 4%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
104 | NCT06992089 | Operations | Protocol eligibility criteria restricted enrollment to 50%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
105 | NCT06906276 | Operations | Protocol eligibility criteria restricted enrollment to 27%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
106 | NCT07213648 | Operations | Protocol eligibility criteria restricted enrollment to 9%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
107 | NCT06893055 | Operations | Protocol eligibility criteria restricted enrollment to 50%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
108 | NCT07032350 | Operations | Protocol eligibility criteria restricted enrollment to 13%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
109 | NCT04786821 | Operations | Enrollment exceeded target in Neurology; strong site engagement and pre-screening drove performance. Site coordinator training and regular performance reviews were key drivers of patient retention.
110 | NCT06106893 | Operations | Enrollment reached 80% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
111 | NCT03003572 | Operations | Enrollment exceeded target in Immunology; strong site engagement and pre-screening drove performance. Site coordinator training and regular performance reviews were key drivers of patient retention.
112 | NCT06618573 | Operations | Enrollment exceeded target in Immunology; strong site engagement and pre-screening drove performance. Site coordinator training and regular performance reviews were key drivers of patient retention.
113 | NCT05470569 | Operations | Enrollment reached 85% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
114 | NCT06771427 | Operations | Protocol eligibility criteria restricted enrollment to 58%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
115 | NCT04624490 | Operations | Protocol eligibility criteria restricted enrollment to 55%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
116 | NCT05720325 | Operations | Enrollment reached 93% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
117 | NCT06903897 | Operations | Protocol eligibility criteria restricted enrollment to 8%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
118 | NCT06441812 | Operations | Protocol eligibility criteria restricted enrollment to 58%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
119 | NCT07476703 | Operations | Protocol eligibility criteria restricted enrollment to 67%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
120 | NCT06940531 | Operations | Protocol eligibility criteria restricted enrollment to 8%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
121 | NCT05341453 | Operations | Enrollment reached 81% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
122 | NCT05504837 | Operations | Enrollment reached 85% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
123 | NCT06152302 | Operations | Protocol eligibility criteria restricted enrollment to 53%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
124 | NCT05200429 | Operations | Enrollment reached 83% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.