## Studies
study_id | title | phase | therapeutic_area | indication | portfolio | program | region | study_status | target_enrollment | actual_enrollment | enrollment_plan_percent | planned_fpi_date | planned_lpo_date | countries_count | sites_count | planned_velocity_per_week | actual_velocity_per_week | performance_status | study_stage | project_description | project_priority | project_status | partnership_type | activity_planning_status | project_id | asset_name | asset_number | launch_strategy | temp_budget_id | study_lifecycle_state | priority_study | priority_from | priority_to | not_part_of_uq_objectives | study_short_name | study_description | primary_indication | primary_subject_population | fso_model | fso_model_vendor | study_type | study_designation | business_area | funding_source | demographic_plan_in_scope | sponsor_company | study_sponsor | eligible_for_outsourcing | study_creation_date | country_list | asset_lead | sdl_name | clinical_scientist | medical_director | clinical_development_lead | org_therapy_area | csi_planned | csi_actual | cpa_planned | cpa_actual | fpa_planned | fpa_actual | fsa_planned | fsa_actual | fsfv_planned | fsfv_actual | lsfv_planned | lsfv_actual | lslv_planned | lslv_actual | dbl_planned | dbl_actual | sac_planned | sac_actual | rc_planned | rc_actual | epe_forecast_future_gbp | epe_forecast_this_year_gbp
ST-2024-013 | Validating the Accuracy of Novel, Non-contrast, Cardiac Magnetic resOnaNce Imaging in Defining Myocardial FIbRosis in Patients With End-stage Renal Disease on haeModialysis: the CONFIRM Study | PHASE_II | Cardiovascular | End Stage Kidney Disease | Cardiovascular Portfolio | APX-463 | APAC | PLANNED | 9 | 0 |  | 2026-12-18 | 2029-09-18 | 4 | 8 | 0.1 | 0 |  | Start-Up | Native T1 mapping is a novel, non-contrast, cardiac MRI technique that characterises myocardial tissue by exploiting the different water content of tissues. It correlates well with histo-pathological levels of myocardial fibrosis in diseases of pressure overload such as aortic stenosis. There is gro | Medium | Active | Investigator-Initiated | Planned | PRJ-0012 | APX-463 | ASS-0012 | US & EU Simultaneous | BUD-0012 | Pre-Activation | FALSE |  |  | FALSE | Validating the Accuracy of Novel, Non-contrast, Ca | Native T1 mapping is a novel, non-contrast, cardiac MRI technique that characterises myocardial tissue by exploiting the different water content of tissues. It correlates well with histo-pathological levels of myocardial fibrosis in diseases of pressure overload such as aortic stenosis. There is growing evidence to demonstrate the potential of native T1 mapping as an imaging biomarker of myocardial fibrosis in patients with ESRD; myocardial native T1 values are higher in patients with ESRD than controls, and associate with measures of myocardial strain and circulating markers of cardiac dysfunction. Although native T1 times are affected by water content of tissues, our group has shown that native T1 times are not influenced by clinical changes in fluid status in HD patients and that the inter-study reproducibility and intra- and inter-observer variability of native T1 are outstanding. Native T1 mapping is a promising, non-invasive imaging biomarker of myocardial fibrosis in patients with advanced renal disease. It is essential that the technique is validated against histology before further use in clinical studies. The aim of this study is to directly assess the relationship between native T1 mapping and levels of MF examined at post-mortem in haemodialysis patients. | End Stage Kidney Disease | Pediatric (2-17) | Hybrid | Parexel | Interventional | Breakthrough Therapy | Biologics | Internal R&D | FALSE | OmniPath Pharma | OmniPath Pharma | TRUE | 2026-06-21 | Brazil, Spain, Mexico, Sweden | Dr. David Harris | Dr. David Taylor | Dr. Emily White | Dr. Sarah Brown | Dr. Christopher Harris | Cardiovascular & Metabolism | 2026-10-19 |  | 2026-10-04 |  | 2026-08-20 |  | 2026-09-19 |  | 2026-12-18 |  | 2029-06-20 |  | 2029-09-18 |  | 2029-11-18 |  | 2030-02-18 |  | 2030-04-18 |  | 5773196 | 2496247
ST-2024-014 | Walking and Thinking - Brain Activity During Complex Walking in Atypical Parkinsonian Syndromes | PHASE_II | Neurology | Gait Disorders, Neurologic | Neurology Portfolio | NXG-793 | APAC | RECRUITING | 30 | 10 | 90.91 | 2025-03-14 | 2027-12-31 | 8 | 20 | 0.2 | 0.1 | AT_RISK | Enrolling | Every-day life means being part of a complex environment and performing complex tasks that usually involve a combination of motor and cognitive skills. However, the process of aging or the sequelae of neurological diseases such as atypical Parkinson's disease (APD) compromises motor-cognitive intera | Medium | Active | Investigator-Initiated | Completed | PRJ-0013 | NXG-793 | ASS-0013 | Global | BUD-0013 | Enrollment | FALSE |  |  | FALSE | Walking and Thinking - Brain Activity During Compl | Every-day life means being part of a complex environment and performing complex tasks that usually involve a combination of motor and cognitive skills. However, the process of aging or the sequelae of neurological diseases such as atypical Parkinson's disease (APD) compromises motor-cognitive interaction necessary for an independent lifestyle. While motor-cognitive performance has been identified as an important goal for sustained health across different clinical populations, little is known about underlying brain function leading to these difficulties and how to best target these motor-cognitive difficulties in the context of rehabilitation and exercise interventions. The challenge of improving treatments of motor-cognitive difficulties (such as dual-tasking and navigation) is daunting, and an important step is arriving at a method that accurately portrays these impairments in an ecologically valid state. The investigators aim therefore to explore brain function during complex walking in healthy and APD by investigating the effects of age and neurological disease on motor-cognitive performance and its neural correlates during three conditions of complex walking (dual-task walking, navigation and a combination of both) using non-invasive measures of brain activity (functional near infrared spectrometry, fNIRS) and advanced gait analysis in real time in older healthy adults and people with APD. | Gait Disorders, Neurologic | Adults (18-75) | In-House |  | Interventional | Fast Track | Biologics | Licensing Agreement | TRUE | Stellara Inc | Stellara Inc | FALSE | 2024-09-15 | United States, South Korea, Mexico, Saudi Arabia, United Kingdom, Germany, Canada, Turkey | Dr. Jennifer Garcia | Dr. Lisa Wilson | Dr. David Brown | Dr. Jennifer Johnson | Dr. Michelle Harris | Neuroscience & Rare Disease | 2025-01-13 | 2025-02-22 | 2024-12-29 | 2025-02-17 | 2024-11-14 | 2024-12-19 | 2024-12-14 | 2025-02-04 | 2025-03-14 | 2025-04-25 | 2027-10-02 |  | 2027-12-31 |  | 2028-02-28 |  | 2028-05-31 |  | 2028-07-31 |  | 18439477 | 4871997
ST-2025-021 | Autoreactive Anti-Ro/SSA IgE To Determine Primary SjögRen's Syndrome's Disease Activity | PHASE_II | Immunology | Primary Sjögren's Syndrome | Immunology Portfolio | GEN-769 | APAC | RECRUITING | 185 | 185 | 102.21 | 2018-03-27 | 2020-12-27 | 5 | 25 | 1.3 | 0.4 | ON_TRACK | Enrolling | Primary Sjögren's syndrome (pSS) can affect various organs, sometimes leads to life-threatening conditions and is always responsible for a decreased quality of life. Its evolution is chronic, with flares and relapses, and the need for reliable biomarkers to be carried out routinely is major in patie | High | Active | Commercial | In Progress | PRJ-0020 | GEN-769 | ASS-0020 | US & EU Simultaneous | BUD-0020 | Enrollment | TRUE | 2018-03-27 | 2020-12-27 | FALSE | Autoreactive Anti-Ro/SSA IgE To Determine Primary | Primary Sjögren's syndrome (pSS) can affect various organs, sometimes leads to life-threatening conditions and is always responsible for a decreased quality of life. Its evolution is chronic, with flares and relapses, and the need for reliable biomarkers to be carried out routinely is major in patients' follow-up. Because of the existence of autoreactive immunoglobulins E (IgE) in autoimmune diseases, the recently described role for anti-Ro/SSA antibodies in inducing interferon alpha (IFNα) signaling and the specific pharmacologic properties of IgE, anti-Ro/SSA IgE should be an interesting biomarker to determine pSS's activity. The aim of the study is to evaluate whether the proportion of anti-Ro/SSA IgE positive patients is higher in patients with active disease (i.e. Eular Sjögren Syndrome Disease Activity Index≥ 5). All consecutive patients with pSS (new or already known diagnosis) will be included, Anti-Ro/SSA IgE titers will be determined, the disease's features will be collected (including Eular Sjögren Syndrome Disease Activity Index/Eular Sjogren's Syndrome Patient Reported Index). | Primary Sjögren's Syndrome | Geriatric (65+) | Full Service Outsourcing (FSO) | PPD | Interventional | Fast Track | Gene Therapy | Licensing Agreement | FALSE | OmniPath Pharma | OmniPath Pharma | TRUE | 2017-09-28 | Chile, Switzerland, Turkey, Japan, Canada | Dr. Nicole Brown | Dr. Amanda Thompson | Dr. James Wilson | Dr. Jennifer Johnson | Dr. Robert Taylor | Immunology & Inflammation | 2018-01-26 | 2018-01-25 | 2018-01-11 | 2018-01-19 | 2017-11-27 | 2017-11-26 | 2017-12-27 | 2018-01-01 | 2018-03-27 | 2018-04-03 | 2020-09-28 |  | 2020-12-27 |  | 2021-02-27 |  | 2021-05-27 |  | 2021-07-27 |  | 4163229 | 918867
ST-2025-022 | Study on the Safety of Administering Isoniazid to Systemic Lupus Erythematosus Patients to Prevent Tuberculosis | PHASE_II | Immunology | Tuberculosis | Immunology Portfolio | APX-521 | North America | RECRUITING | 60 | 56 | 96.55 | 2022-08-15 | 2025-12-01 | 6 | 23 | 0.3 | 0.3 | ON_TRACK | Enrolling | Systemic Lupus Erythematosus (SLE) is a prototypical systemic autoimmune disease characterized by heterogeneity, multisystem involvement, and production of multiple autoantibodies. Clinical features can vary, from mild skin and joint involvement to severe and life-threatening conditions. The course | Medium | Active | Commercial | Completed | PRJ-0021 | APX-521 | ASS-0021 | Global | BUD-0021 | Enrollment | FALSE |  |  | FALSE | Study on the Safety of Administering Isoniazid to | Systemic Lupus Erythematosus (SLE) is a prototypical systemic autoimmune disease characterized by heterogeneity, multisystem involvement, and production of multiple autoantibodies. Clinical features can vary, from mild skin and joint involvement to severe and life-threatening conditions. The course of lupus is highly variable in the form of relapses and remissions, with mild and severe forms that can be life-threatening. Treatments for SLE includes steroids and immunosuppressants to control disease activity. Patients with lupus are more susceptible to infections, in addition to being immunocompromised, and due to the administration of corticosteroid and cytotoxic drugs. The presence of these infections is a cause of death in lupus disease in addition to the activity of the disease itself, especially in Asia-Pacific countries. One infection that often occurs in lupus is Tuberculosis (TB). Tuberculosis is still a problem especially in the Asian region, and Indonesia ranks 2nd with the most cases after India according to World Health Organization in 2019. TB infection is found in 10-11.4% of SLE patients in Asia. The incidence of TB in SLE is reported to range from 150/100,000 patients per year in Turkey to 2,450/100,000 patients per year in India. The annual risk of TB in SLE patients is higher than the normal population. Registry data at Hasan Sadikin Hospital Bandung showed that 11.4% or 93 out of 813 SLE patients were infected with TB after being diagnosed with SLE. Risk factors for increased TB infection in SLE patients, in addition to SLE disease activity itself (SLEDAI score \>12), renal involvement, lymphopenia, and cumulative dose of steroids used by the patient, are also due to long duration of illness and previous history of TB. Tuberculosis is also one of the infections that cause death in SLE patients. Mortality from TB in Asian countries ranged from 5-31%. A study in the Philippines found that 14.8% of SLE patients with TB died, those who died had dis | Tuberculosis | Adults (18+) | In-House |  | Interventional | Fast Track | Biologics | Internal R&D | FALSE | ApexBio Research | ApexBio Research | FALSE | 2022-02-16 | Japan, Italy, Saudi Arabia, Singapore, Belgium, China | Dr. Sarah Harris | Dr. Stephanie Thompson | Dr. Stephanie Wilson | Dr. James Martin | Dr. James Taylor | Immunology & Inflammation | 2022-06-16 | 2022-06-10 | 2022-06-01 | 2022-05-23 | 2022-04-17 | 2022-04-25 | 2022-05-17 | 2022-05-18 | 2022-08-15 | 2022-08-16 | 2025-09-02 |  | 2025-12-01 |  | 2026-02-01 |  | 2026-05-01 |  | 2026-07-01 |  | 12730931 | 3719737
ST-2024-010 | Responders and Non-responders in the Management of Heart Failure - Significance of Genetic Influence and Identification of Novel Informative Biomarkers | PHASE_II | Cardiovascular | Heart Failure | Cardiovascular Portfolio | APX-926 | APAC | RECRUITING | 5000 | 2432 | 85.91 | 2021-02-17 | 2030-12-31 | 3 | 6 | 9.7 | 9.1 | AT_RISK | Enrolling | The national heart failure quality registry SwedeHF started in 2003. It is the world's largest continuous HF registry enrolling clinician-judged HF (regardless of LVEF) at time of hospital or clinical visit. Eighty variables are entered into an electronic database managed by the Uppsala Clinical Res | Medium | Active | Investigator-Initiated | Completed | PRJ-0009 | APX-926 | ASS-0009 | EU First | BUD-0009 | Enrollment | FALSE |  |  | FALSE | Responders and Non-responders in the Management of | The national heart failure quality registry SwedeHF started in 2003. It is the world's largest continuous HF registry enrolling clinician-judged HF (regardless of LVEF) at time of hospital or clinical visit. Eighty variables are entered into an electronic database managed by the Uppsala Clinical Research Center (UCR). There are \>140,000 registrations from \>110,000 unique patients from 70 hospitals in Sweden. University hospitals in Sweden with access to central biobanking will collect a high-quality biobank linked to SwedeHF consisting of blood plasma, whole blood and urine enabling genetic, proteomic and metabolomic analyses as well as analyses of different biomarkers of interest for HF patients. This will provide unique opportunities for future research within the national SwedeHF registry. | Heart Failure | All Ages | In-House |  | Interventional | Breakthrough Therapy | Small Molecule | Government Grant | FALSE | ClinVita Sciences | ClinVita Sciences | FALSE | 2020-08-21 | United Kingdom, Australia, Turkey | Dr. Emily Brown | Dr. Lisa Thompson | Dr. James Johnson | Dr. James Davis | Dr. Sarah Martin | Cardiovascular & Metabolism | 2020-12-19 | 2020-12-17 | 2020-12-04 | 2020-12-10 | 2020-10-20 | 2020-10-26 | 2020-11-19 | 2020-11-14 | 2021-02-17 | 2021-02-18 | 2030-10-02 |  | 2030-12-31 |  | 2031-02-28 |  | 2031-05-31 |  | 2031-07-31 |  | 9860610 | 4157629
ST-2024-011 | Point-of-care Echocardiogram (POCUS) Guided Resuscitation Versus Conventional Goal- Directed Therapy in the Management of Cirrhosis With Severe Sepsis or Septic Shock: A Randomised Controlled Trial | PHASE_II | Cardiovascular | Cirrhosis, Liver | Cardiovascular Portfolio | MED-892 | MEA | RECRUITING | 140 | 5 | 71.43 | 2026-01-01 | 2028-12-30 | 4 | 17 | 0.9 | 0.2 | OFF_TRACK | Enrolling | * Patients with cirrhosis requiring intensive care for severe sepsis carry a risk of high mortality due to altered hemodynamics with reduced effective arterial volume, portal hypertension, presence of ascites, and risk of complications like acute variceal bleeding (AVB), acute kidney injury (AKI) an | High | Active | Consortium | In Progress | PRJ-0010 | MED-892 | ASS-0010 | EU First | BUD-0010 | Enrollment | TRUE | 2026-01-01 | 2028-12-30 | FALSE | Point-of-care Echocardiogram (POCUS) Guided Resusc | * Patients with cirrhosis requiring intensive care for severe sepsis carry a risk of high mortality due to altered hemodynamics with reduced effective arterial volume, portal hypertension, presence of ascites, and risk of complications like acute variceal bleeding (AVB), acute kidney injury (AKI) and circulatory failure(3-5). The main principles for management of severe sepsis include early recognition, control of the source of infection, appropriate and timely administration of antimicrobial agents, and resuscitation with intravenous fluids +/- vasoactive drugs, if needed (6). * Due to portal hypertension, these patients have a hyperdynamic circulation, increased capillary permeability, splanchnic arteriolar vasodilation, and may have latent cirrhotic cardiomyopathy (CCM) (7). Hence assessment of volume status and cardiac reserve using conventional central venous pressure (CVP) or mean arterial pressure (MAP) remains difficult (8). Although inferior vena cava (IVC) dynamics and IVC collapsibility index are reasonable accurate for ventilated patients, their use in spontaneously breathing subjects or those with tense ascites are not defined(9). Even measures like passive leg raising and Valsalva manoeuvre are difficult to perform in cirrhotic patients with tense ascites. * Early goal directed therapy (EGDT) improved outcomes in a randomized trial in patients with severe sepsis(10). Thereafter EGDT was incorporated into the 6-hour resuscitation bundle of the surviving sepsis campaign guidelines, but did not incorporate patients with cirrhosis(11-13). Following the early EGDT trials, studies focussed choice of resuscitation fluid i.e., albumin versus normal saline or balanced salt solution (BSS), concerns about potential risks of volume overload and pulmonary edema and lack of generalisability in subsequent trials showed that there was no associated survival benefit with an aggressive fluid protocol(14, 15). In the ALBIOS study, 1818 patients with severe sepsis or sept | Cirrhosis, Liver | Adults (18-75) | Hybrid | Parexel | Interventional | Priority Review | Gene Therapy | Partnership | TRUE | PharmaNova Inc | PharmaNova Inc | TRUE | 2025-07-05 | Brazil, United Kingdom, Colombia, Spain | Dr. Michelle Thomas | Dr. Lisa Garcia | Dr. Charles Anderson | Dr. Jessica Jones | Dr. Jennifer Smith | Cardiovascular & Metabolism | 2025-11-02 | 2025-11-11 | 2025-10-18 | 2025-10-18 | 2025-09-03 | 2025-08-24 | 2025-10-03 | 2025-09-29 | 2026-01-01 | 2025-12-26 | 2028-10-01 |  | 2028-12-30 |  | 2029-02-28 |  | 2029-05-30 |  | 2029-07-30 |  | 13290277 | 2567561
ST-2024-002 | Phase I/II First-In-Human Open-label Trial to Assess Safety and Efficacy of STX-241 in Participants With Locally Advanced or Metastatic Non-small Cell Lung Cancer (NSCLC) Resistant to EGFR Tyrosine Ki | PHASE_I | Oncology | Non-small Cell Lung Cancer (NSCLC) | Oncology Portfolio | ZPH-505 | LATAM | RECRUITING | 171 | 58 | 78.38 | 2024-09-17 | 2028-05-17 | 5 | 16 | 0.9 | 0.6 | OFF_TRACK | Enrolling | The goal of this First-In-Human (FIH) Phase I/II trial is to establish the safety profile, determine the Recommended Phase II Dose (RP2D), explore the pharmacokinetic (PK) exposure and pharmacodynamic (PD) properties as well as assess the efficacy of STX-241/PFL-241, a mutant selective Central Nervo | High | Active | Investigator-Initiated | In Progress | PRJ-0001 | ZPH-505 | ASS-0001 | US First | BUD-0001 | Enrollment | TRUE | 2024-09-17 | 2028-05-17 | FALSE | Phase I/II First-In-Human Open-label Trial to Asse | The goal of this First-In-Human (FIH) Phase I/II trial is to establish the safety profile, determine the Recommended Phase II Dose (RP2D), explore the pharmacokinetic (PK) exposure and pharmacodynamic (PD) properties as well as assess the efficacy of STX-241/PFL-241, a mutant selective Central Nervous System (CNS)-penetrant fourth generation EGFR TKI, in participants with locally advanced or metastatic NSCLC that progressed during or following third generation EGFR TKI such as osimertinib due to C797X double acquired (secondary) mutations. | Non-small Cell Lung Cancer (NSCLC) | Geriatric (65+) | Hybrid | IQVIA | Interventional | Priority Review | Pharmaceuticals | Internal R&D | TRUE | OmniPath Pharma | OmniPath Pharma | TRUE | 2024-03-21 | Belgium, Australia, Netherlands, Japan, Mexico | Dr. Robert Garcia | Dr. Stephanie Williams | Dr. Charles Jackson | Dr. Christopher Thompson | Dr. William Moore | Oncology & Hematology | 2024-07-19 | 2024-08-24 | 2024-07-04 | 2024-08-15 | 2024-05-20 | 2024-06-25 | 2024-06-19 | 2024-08-03 | 2024-09-17 | 2024-11-03 | 2028-02-17 |  | 2028-05-17 |  | 2028-07-17 |  | 2028-10-17 |  | 2028-12-17 |  | 4559701 | 2198150
ST-2024-003 | Hemithoracic Irradiation With Proton Therapy in Malignant Pleural Mesothelioma | PHASE_II | Oncology | Malignant Pleural Mesothelioma | Oncology Portfolio | OMP-770 | LATAM | RECRUITING | 148 | 49 | 106.52 | 2024-03-28 | 2029-09-30 | 6 | 30 | 0.5 | 0.4 | ON_TRACK | Enrolling | Study design: Randomised phase III clinical trial for patients with unilateral MPM. Primary endpoint: Progression free survival (PFS) and overall survival (OS), defined as the time from randomisation to the date of progression and death from any cause. Secondary Endpoints: Safety and Tolerability, | Low | Active | Academic | Completed | PRJ-0002 | OMP-770 | ASS-0002 | Global | BUD-0002 | Enrollment | FALSE |  |  | FALSE | Hemithoracic Irradiation With Proton Therapy in Ma | Study design: Randomised phase III clinical trial for patients with unilateral MPM. Primary endpoint: Progression free survival (PFS) and overall survival (OS), defined as the time from randomisation to the date of progression and death from any cause. Secondary Endpoints: Safety and Tolerability, Health related Quality of Life (QOL): EuroQoL EQ-5D-3L, Locoregional Control. Randomisation and stratification: 1:1 randomisation. Patients with be stratified for histology (epithelioid versus non-epithelioid), potential PBT centre (UCLH or The Christie) , laterality (left or right sided) and time since diagnosis (\<1 year or \> 1 year) Treatment: Experimental Arm: Patients in the experimental arm will receive PBT to the hemithorax to a dose of 50Gy in 25 fractions with a boost to 60Gy for the visible tumour (gross tumour volume-GTV). Treatment is given daily Monday-Friday over 5 weeks. Following completion of treatment in the experimental arm patients will have 2 years of follow-up from time of randomisation at the local recruiting/referring centre. Control Arm: The patients in the control arm would be under standard of care surveillance i.e. "watch and wait", with no treatment or other intervention. Patients will have 2 years of follow-up from time of randomisation at the local recruiting/referring centre. If the disease progresses, the patient will receive SOC treatment i.e. immunotherapy with nivolumab and ipilimumab, or chemotherapy at the clinician's discretion. Statistical analysis plan: The sample size is 148 patients (74 patients per arm). This is to detect a OS hazard ratio of 0.58, equivalent to an improvement in 2-year OS from 30% to 50%, with 85% power and 5% two-sided alpha. Recruitment to complete in 3 years across 20 UK centres with 2 years of additional follow-up and up to 5% dropout. Interim analyses for OS efficacy will be performed when 50, 75 and 110 patients have been randomised at around 1.5, 2.0 and 2.5 years respectively. Using a fixed-se | Malignant Pleural Mesothelioma | Geriatric (65+) | Full Service Outsourcing (FSO) | PRA Health Sciences | Interventional | Fast Track | Pharmaceuticals | Government Grant | FALSE | ApexBio Research | ApexBio Research | TRUE | 2023-09-30 | South Africa, Norway, Taiwan, Spain, Australia, Japan | Dr. Lisa Miller | Dr. Robert Smith | Dr. Sarah Davis | Dr. Nicole Williams | Dr. Christopher White | Oncology & Hematology | 2024-01-28 | 2024-02-06 | 2024-01-13 | 2024-01-08 | 2023-11-29 | 2023-12-01 | 2023-12-29 | 2024-01-06 | 2024-03-28 | 2024-03-27 | 2029-07-02 |  | 2029-09-30 |  | 2029-11-30 |  | 2030-02-28 |  | 2030-04-30 |  | 12044891 | 3151460
ST-2024-004 | A Prospective Study to Evaluate the Efficacy and Safety of MZL-IPI Risk-adapted Targeted Therapy in Patients With Untreated Marginal Zone B-cell Lymphoma | PHASE_II | Oncology | Marginal Zone Lymphoma(MZL) | Oncology Portfolio | GEN-330 | LATAM | RECRUITING | 145 | 26 | 76.47 | 2025-01-23 | 2028-12-31 | 7 | 27 | 0.7 | 0.3 | OFF_TRACK | Enrolling | Marginal zone lymphoma (MZL) is a common type of indolent lymphoma that originates from the marginal zone of lymphoid follicles. This study aims to evaluate targeted therapy based on the prognostic risk stratification of MZL-IPI in newly diagnosed MZL cases requiring systemic treatment, and provides | Medium | Active | Consortium | In Progress | PRJ-0003 | GEN-330 | ASS-0003 | US & EU Simultaneous | BUD-0003 | Enrollment | FALSE |  |  | TRUE | A Prospective Study to Evaluate the Efficacy and S | Marginal zone lymphoma (MZL) is a common type of indolent lymphoma that originates from the marginal zone of lymphoid follicles. This study aims to evaluate targeted therapy based on the prognostic risk stratification of MZL-IPI in newly diagnosed MZL cases requiring systemic treatment, and provides a basis for precision treatment of MZL. | Marginal Zone Lymphoma(MZL) | Adults (18-75) | In-House |  | Interventional | Priority Review | Biologics | Licensing Agreement | TRUE | PharmaNova Inc | PharmaNova Inc | FALSE | 2024-07-27 | Italy, Singapore, Chile, United Kingdom, Japan, New Zealand, Belgium | Dr. Daniel Jones | Dr. Michael Wilson | Dr. Stephanie Taylor | Dr. Daniel Wilson | Dr. James Anderson | Oncology & Hematology | 2024-11-24 | 2024-11-14 | 2024-11-09 | 2024-11-02 | 2024-09-25 | 2024-09-30 | 2024-10-25 | 2024-11-04 | 2025-01-23 | 2025-02-01 | 2028-10-02 |  | 2028-12-31 |  | 2029-02-28 |  | 2029-05-31 |  | 2029-07-31 |  | 11413424 | 4013620
ST-2024-005 | A Prospective Clinical Study of Hanlikang and BTK Inhibitors in the Treatment of Newly Diagnosed Mantle Cell Lymphoma | PHASE_II | Oncology | Newly Diagnosed Mantle Cell Lymphoma | Oncology Portfolio | PHX-873 | North America | RECRUITING | 100 | 71 | 75.53 | 2022-08-12 | 2026-12-30 | 6 | 20 | 0.4 | 0.4 | OFF_TRACK | Enrolling | An open-label, single-arm, multicenter, prospective clinical study of Hanlikang and BTK inhibitors in the treatment of newly diagnosed mantle cell lymphoma | Medium | Active | Investigator-Initiated | Completed | PRJ-0004 | PHX-873 | ASS-0004 | EU First | BUD-0004 | Enrollment | FALSE |  |  | FALSE | A Prospective Clinical Study of Hanlikang and BTK | An open-label, single-arm, multicenter, prospective clinical study of Hanlikang and BTK inhibitors in the treatment of newly diagnosed mantle cell lymphoma | Newly Diagnosed Mantle Cell Lymphoma | Adults (18-75) | Hybrid | Syneos Health | Interventional | Priority Review | Pharmaceuticals | Internal R&D | TRUE | Astellion Biosciences | Astellion Biosciences | TRUE | 2022-02-13 | New Zealand, Denmark, Germany, Belgium, Taiwan, Mexico | Dr. Jessica Miller | Dr. Robert Wilson | Dr. Jessica Taylor | Dr. Emily Smith | Dr. Nicole White | Oncology & Hematology | 2022-06-13 | 2022-06-22 | 2022-05-29 | 2022-05-24 | 2022-04-14 | 2022-04-08 | 2022-05-14 | 2022-05-05 | 2022-08-12 | 2022-08-04 | 2026-10-01 |  | 2026-12-30 |  | 2027-02-28 |  | 2027-05-30 |  | 2027-07-30 |  | 15516017 | 5780085
ST-2024-006 | A Phase 2 Study of EIK1001 in Combination With Pembrolizumab and Chemotherapy in Patients With Stage 4 Non-Small Cell Lung Cancer | PHASE_II | Oncology | NSCLC | Oncology Portfolio | NXG-810 | Europe | RECRUITING | 70 | 53 | 77.94 | 2024-02-06 | 2025-11-06 | 4 | 17 | 0.8 | 0.5 | OFF_TRACK | Enrolling | This is a multicenter open-label phase 2 trial that aim to assess the safety, tolerability, and efficacy of EIK1001 in combination with standard of care in participants with both confirmed stage 4 squamous and non-squamous NSCLC who have not received prior systemic therapy for the advanced disease. | Medium | Active | Academic | Completed | PRJ-0005 | NXG-810 | ASS-0005 | US & EU Simultaneous | BUD-0005 | Enrollment | FALSE |  |  | FALSE | A Phase 2 Study of EIK1001 in Combination With Pem | This is a multicenter open-label phase 2 trial that aim to assess the safety, tolerability, and efficacy of EIK1001 in combination with standard of care in participants with both confirmed stage 4 squamous and non-squamous NSCLC who have not received prior systemic therapy for the advanced disease. The study includes dose finding and evaluates adverse events and efficacy. | NSCLC | Pediatric (2-17) | In-House |  | Interventional | Fast Track | Pharmaceuticals | Partnership | FALSE | Nexagen Pharmaceuticals | Nexagen Pharmaceuticals | FALSE | 2023-08-10 | Italy, Netherlands, United Kingdom, South Africa | Dr. Jennifer Garcia | Dr. Amanda Thompson | Dr. Lisa Brown | Dr. David Jones | Dr. Lisa Martin | Oncology & Hematology | 2023-12-08 | 2023-12-14 | 2023-11-23 | 2023-11-28 | 2023-10-09 | 2023-10-04 | 2023-11-08 | 2023-11-10 | 2024-02-06 | 2024-02-13 | 2025-08-08 |  | 2025-11-06 |  | 2026-01-06 |  | 2026-04-06 |  | 2026-06-06 |  | 9739961 | 3993914
ST-2024-007 | Efficacy of an Asian Culture-tailored Lung Health (ACT) Intervention on Lung Cancer Screening and Smoking Cessation in Asian Americans | PHASE_II | Oncology | Smoking Cessation | Oncology Portfolio | CRX-255 | Europe | PLANNED | 50 | 0 |  | 2027-01-18 | 2029-07-18 | 6 | 22 | 0.4 | 0 |  | Start-Up | This two-arm stratified randomized clinical trial is to test a counseling and educational program designed to improve lung health through smoking cessation for Chinese and Korean American smokers at high risk for lung cancer. Participants will be randomized into one of two groups: Group A: ACT Lung | High | Active | Commercial | Completed | PRJ-0006 | CRX-255 | ASS-0006 | US First | BUD-0006 | Pre-Activation | TRUE | 2027-01-18 | 2029-07-18 | FALSE | Efficacy of an Asian Culture-tailored Lung Health | This two-arm stratified randomized clinical trial is to test a counseling and educational program designed to improve lung health through smoking cessation for Chinese and Korean American smokers at high risk for lung cancer. Participants will be randomized into one of two groups: Group A: ACT Lung Health Intervention versus Group B: Standard Care. Randomization means a participant is placed into a study group by chance. The research study procedures include screening for eligibility, questionnaires, and saliva tests. It is expected participation in this study will last about 6 months. About 50 participants are expected to take part in this research study. The National Cancer Institute is providing funding for this trial. | Smoking Cessation | Geriatric (65+) | In-House |  | Interventional | Fast Track | Gene Therapy | Licensing Agreement | FALSE | ClinVita Sciences | ClinVita Sciences | FALSE | 2026-07-22 | Chile, Australia, Argentina, India, Japan, Brazil | Dr. Jennifer Harris | Dr. Michelle Taylor | Dr. Michelle Thomas | Dr. William Martin | Dr. David Davis | Oncology & Hematology | 2026-11-19 |  | 2026-11-04 |  | 2026-09-20 |  | 2026-10-20 |  | 2027-01-18 |  | 2029-04-19 |  | 2029-07-18 |  | 2029-09-18 |  | 2029-12-18 |  | 2030-02-18 |  | 7052872 | 1634609
ST-2024-008 | Complete Functional Assessment of Intermediate Coronary Artery Stenosis Before and After Transcatheter Aortic Valve Implantation (TAVI) in Patients With Severe Symptomatic Aortic Valve Stenosis | PHASE_II | Cardiovascular | Coronary Artery Stenosis | Cardiovascular Portfolio | VRD-698 | LATAM | RECRUITING | 50 | 41 | 83.67 | 2021-09-29 | 2025-09-30 | 3 | 10 | 0.2 | 0.2 | AT_RISK | Enrolling | Prospective, single center, open-label study to 1. compare coronary flow reserve (CFR), index of microvascular resistance (IMR), fractional flow reserve (FFR) and resting full cycle ratio (RFR) values before TAVI and 6 months after TAVI 2. correlate testing of microcirculatory function (IMR) with m | High | Active | Consortium | Planned | PRJ-0007 | VRD-698 | ASS-0007 | US & EU Simultaneous | BUD-0007 | Enrollment | TRUE | 2021-09-29 | 2025-09-30 | FALSE | Complete Functional Assessment of Intermediate Cor | Prospective, single center, open-label study to 1. compare coronary flow reserve (CFR), index of microvascular resistance (IMR), fractional flow reserve (FFR) and resting full cycle ratio (RFR) values before TAVI and 6 months after TAVI 2. correlate testing of microcirculatory function (IMR) with measurements of functional testing (FFR and RFR) before and six months after TAVI 3. correlate functional testing (FFR and RFR) with computed tomography (CT) derived fractional flow reserve (CT-FFR) before and six months after TAVI. | Coronary Artery Stenosis | All Ages | Hybrid | Syneos Health | Interventional | Fast Track | Small Molecule | Licensing Agreement | FALSE | Veridon Therapeutics | Veridon Therapeutics | TRUE | 2021-04-02 | China, Belgium, Poland | Dr. Christopher Garcia | Dr. Amanda Garcia | Dr. Robert Moore | Dr. Nicole Garcia | Dr. Michelle Johnson | Cardiovascular & Metabolism | 2021-07-31 | 2021-07-31 | 2021-07-16 | 2021-07-21 | 2021-06-01 | 2021-05-25 | 2021-07-01 | 2021-06-27 | 2021-09-29 | 2021-09-30 | 2025-07-02 |  | 2025-09-30 |  | 2025-11-30 |  | 2026-02-28 |  | 2026-04-30 |  | 8719046 | 3705680
ST-2024-009 | Prasugrel Monotherapy Reduced Dose in Acute and Chronic Coronary Syndrome Patients After Percutaneous Coronary Intervention | PHASE_IV | Cardiovascular | Coronary Arterial Disease (CAD) | Cardiovascular Portfolio | GEN-887 | APAC | RECRUITING | 300 | 14 | 77.78 | 2025-11-13 | 2029-06-13 | 5 | 12 | 1.6 | 0.4 | OFF_TRACK | Enrolling | Rationale: Dual antiplatelet therapy, consisting of aspirin and a P2Y12-inhibitor, reduces the risk of stent-related and non-stent-related ischemic events after percutaneous coronary intervention (PCI). However, this therapy is also associated with a higher risk of bleeding. Given the advances in st | Medium | Active | Commercial | Planned | PRJ-0008 | GEN-887 | ASS-0008 | Global | BUD-0008 | Enrollment | FALSE |  |  | FALSE | Prasugrel Monotherapy Reduced Dose in Acute and Ch | Rationale: Dual antiplatelet therapy, consisting of aspirin and a P2Y12-inhibitor, reduces the risk of stent-related and non-stent-related ischemic events after percutaneous coronary intervention (PCI). However, this therapy is also associated with a higher risk of bleeding. Given the advances in stent technology and pharmacology, it may be possible to treat patients undergoing PCI with low dose prasugrel as single antiplatelet therapy, regardless of medical history, age or body weight. Objective: Assess the feasibility and safety of a single antiplatelet strategy with a reduced dose of prasugrel 5 mg after PCI in acute and chronic coronary syndrome patients (ACS and CCS). Study design: Open-label, single-centre, randomized controlled trial. Study population: Patients undergoing successful PCI due to acute or chronic coronary syndrome. Intervention: A once-daily reduced dose of 5 mg prasugrel for 6 months in CCS patients and for 12 months in ACS patients, preceded by a loading dose of 60 mg prasugrel after PCI, administered without concomitant use of aspirin. Main study parameters/endpoints: The primary endpoint is Net Adverse Clinical Events (NACE), a composite of all-cause death, myocardial infarction, definite stent thrombosis, ischemic stroke, clinically relevant non-major bleeding or major bleeding defined as Bleeding Academic Research Consortium type 2, 3 or 5. | Coronary Arterial Disease (CAD) | Adults (18-75) | Full Service Outsourcing (FSO) | PRA Health Sciences | Interventional | Breakthrough Therapy | Gene Therapy | Partnership | FALSE | MedPath Sciences | MedPath Sciences | TRUE | 2025-05-17 | Sweden, Mexico, Colombia, Taiwan, Mexico | Dr. Christopher Thompson | Dr. Robert Thomas | Dr. James Martin | Dr. Emily Anderson | Dr. Stephanie Williams | Cardiovascular & Metabolism | 2025-09-14 | 2025-09-23 | 2025-08-30 | 2025-09-03 | 2025-07-16 | 2025-07-08 | 2025-08-15 | 2025-08-20 | 2025-11-13 | 2025-11-21 | 2029-03-15 |  | 2029-06-13 |  | 2029-08-13 |  | 2029-11-13 |  | 2030-01-13 |  | 12628175 | 4407667
ST-2024-012 | Pacemaker Implantation in Patients With Heart Failure With Preserved Ejection Fraction, Chronotropic Incompetence and Small Ventricular Volume. The SHOP-HF Trial | PHASE_II | Cardiovascular | Heart Failure With Preserved Ejection Fraction | Cardiovascular Portfolio | CRX-750 | North America | RECRUITING | 30 | 17 | 73.91 | 2025-06-17 | 2026-12-17 | 6 | 28 | 0.4 | 0.3 | OFF_TRACK | Enrolling | This study is designed as a multicenter, prospective, controlled, randomized, two-arms, cross-over, two parallel cohorts, efficacy Clinical research with CE-marked medical device . The crossover trial will be performed in a blind fashion, so each participant will be evaluated during both blinded pac | Low | Active | Investigator-Initiated | Completed | PRJ-0011 | CRX-750 | ASS-0011 | EU First | BUD-0011 | Enrollment | FALSE |  |  | FALSE | Pacemaker Implantation in Patients With Heart Fail | This study is designed as a multicenter, prospective, controlled, randomized, two-arms, cross-over, two parallel cohorts, efficacy Clinical research with CE-marked medical device . The crossover trial will be performed in a blind fashion, so each participant will be evaluated during both blinded pacing-on and pacing-off phases, each of which will last 3 months. The population includes patients with the diagnosis of stable HFpEF according to criteria of the European Society of Cardiology and New York Heart Association (NYHA) functional class II-III/IV, left ventricular hypertrophy with small ventricular volume, sinus rhythm with low basal heart rate and chronotropic incompetence (CI). All patients will undergo pacemaker implantation, and computer-generated randomization sequence previously designed will be used to allocate participants (in a 1:1 ratio) to receive: (a) programming of the pacemaker with pacing On followed by pacing Off in two periods of 3 months; or (b) programming of the pacemaker with pacing Off followed by pacing On in two periods of 3 months. The study will be conducted in three centers in Spain. Discounting the time due to staggered entry, the total duration of a patient's follow-up will be 7 months. | Heart Failure With Preserved Ejection Fraction | Adults (18-75) | Full Service Outsourcing (FSO) | IQVIA | Interventional | Fast Track | Pharmaceuticals | Partnership | TRUE | PharmaNova Inc | PharmaNova Inc | TRUE | 2024-12-19 | Japan, Switzerland, Turkey, India, Norway, France | Dr. Charles Johnson | Dr. Jennifer Miller | Dr. Lisa Davis | Dr. David Wilson | Dr. Stephanie Thompson | Cardiovascular & Metabolism | 2025-04-18 | 2025-04-09 | 2025-04-03 | 2025-03-30 | 2025-02-17 | 2025-02-13 | 2025-03-19 | 2025-03-16 | 2025-06-17 | 2025-06-08 | 2026-09-18 |  | 2026-12-17 |  | 2027-02-17 |  | 2027-05-17 |  | 2027-07-17 |  | 9288796 | 2392219
ST-2024-015 | Modification of Threat Interpretation Bias to Reduce Anxiety in Neurodegenerative Movement Disorders (Aim 3) | PHASE_II | Neurology | Huntington Disease | Neurology Portfolio | CRX-271 | North America | RECRUITING | 136 | 15 | 88.24 | 2025-11-20 | 2028-02-20 | 7 | 28 | 1.2 | 0.5 | AT_RISK | Enrolling | The investigators will conduct a pilot randomized controlled trial of the MindTrails-Movement CBM-I app in patients with Huntington's disease and Parkinson's disease (N=136). Participants randomly assigned to the intervention group (N=68) will be asked to download the MindTrails-Movement mobile app | Low | Active | Commercial | Planned | PRJ-0014 | CRX-271 | ASS-0014 | US First | BUD-0014 | Enrollment | FALSE |  |  | TRUE | Modification of Threat Interpretation Bias to Redu | The investigators will conduct a pilot randomized controlled trial of the MindTrails-Movement CBM-I app in patients with Huntington's disease and Parkinson's disease (N=136). Participants randomly assigned to the intervention group (N=68) will be asked to download the MindTrails-Movement mobile app and to complete daily CBM-I training sessions and nightly surveys, in addition to surveys at baseline and every 2 weeks for the duration of the 6-week intervention and at 4-week follow-up (week 10). Participants assigned to the waitlist control group will download a control version of the app without CBM-I training sessions. They will be asked to complete surveys in the app at baseline and every 2 weeks for the duration of the 6-week intervention and at 4-week follow-up (week 10). After 10 weeks, they will be offered the opportunity to access the version of MindTrails-Movement with CBM-I training content. | Huntington Disease | Adults (18+) | Full Service Outsourcing (FSO) | ICON plc | Interventional | Standard | Pharmaceuticals | Licensing Agreement | TRUE | Genetika Therapeutics | Genetika Therapeutics | TRUE | 2025-05-24 | Netherlands, Brazil, Italy, Taiwan, Turkey, Saudi Arabia, New Zealand | Dr. James Jackson | Dr. Daniel Williams | Dr. Emily Wilson | Dr. Robert Williams | Dr. Charles Anderson | Neuroscience & Rare Disease | 2025-09-21 | 2025-10-31 | 2025-09-06 | 2025-10-15 | 2025-07-23 | 2025-08-20 | 2025-08-22 | 2025-09-23 | 2025-11-20 | 2025-12-18 | 2027-11-22 |  | 2028-02-20 |  | 2028-04-20 |  | 2028-07-20 |  | 2028-09-20 |  | 12037286 | 5148503
ST-2024-016 | Strength-Endurance Circuit Training in Parkinson's Disease: Effects on Disease Severity, Physical Performance, Blood Biomarkers and Quality of Life. | PHASE_II | Neurology | Parkinson Disease, Idiopathic | Neurology Portfolio | APX-563 | LATAM | RECRUITING | 90 | 45 | 88.24 | 2025-03-03 | 2027-07-03 | 7 | 22 | 0.7 | 0.7 | AT_RISK | Enrolling | The goal of this clinical trial is to determine whether adding strength training to aerobic training has a comparable or greater effect on the clinical status of Parkinson's disease patients than a standalone aerobic training. \- Does combined strength-endurance circuit training provide added benef | Medium | Active | Academic | In Progress | PRJ-0015 | APX-563 | ASS-0015 | Global | BUD-0015 | Enrollment | FALSE |  |  | FALSE | Strength-Endurance Circuit Training in Parkinson's | The goal of this clinical trial is to determine whether adding strength training to aerobic training has a comparable or greater effect on the clinical status of Parkinson's disease patients than a standalone aerobic training. \- Does combined strength-endurance circuit training provide added benefits to physical performance, disease severity, blood biomarkers, and quality of life in PD patients compared to standalone aerobic training? Participants will: * undergo outcome measurements before and after the 12-week intervention and a 3-month follow-up measurement, * visit the clinic twice a week for 1-hour training sessions. * selected patients will be given a smartwatch with a pedometer that will count their average number of steps before, during and after the training period | Parkinson Disease, Idiopathic | Adults (18-75) | In-House |  | Interventional | Breakthrough Therapy | Small Molecule | Internal R&D | FALSE | Nexagen Pharmaceuticals | Nexagen Pharmaceuticals | FALSE | 2024-09-04 | United States, Brazil, Canada, Belgium, India, Turkey, Australia | Dr. Michelle Thompson | Dr. Michelle Jones | Dr. Emily Johnson | Dr. Christopher Thomas | Dr. Robert Jones | Neuroscience & Rare Disease | 2025-01-02 | 2025-02-26 | 2024-12-18 | 2025-02-04 | 2024-11-03 | 2024-12-19 | 2024-12-03 | 2025-01-20 | 2025-03-03 | 2025-04-17 | 2027-04-04 |  | 2027-07-03 |  | 2027-09-03 |  | 2027-12-03 |  | 2028-02-03 |  | 9437981 | 2740256
ST-2024-017 | E-Tailored Pain Management Support for Dementia Family Caregivers | PHASE_II | Neurology | Care Giving Burden | Neurology Portfolio | VRD-384 | MEA | RECRUITING | 60 | 9 | 64.29 | 2025-05-22 | 2028-04-22 | 3 | 9 | 0.4 | 0.2 | OFF_TRACK | Enrolling | This randomized controlled trial will assess the feasibility, usability, and preliminary efficacy of the Pain Control Enhancement App (PACE-app), a web-based intervention designed to support family caregivers of persons with dementia in managing pain. The trial will also explore mechanisms through w | Medium | Active | Academic | Planned | PRJ-0016 | VRD-384 | ASS-0016 | EU First | BUD-0016 | Enrollment | FALSE |  |  | FALSE | E-Tailored Pain Management Support for Dementia Fa | This randomized controlled trial will assess the feasibility, usability, and preliminary efficacy of the Pain Control Enhancement App (PACE-app), a web-based intervention designed to support family caregivers of persons with dementia in managing pain. The trial will also explore mechanisms through which the PACE-app may affect caregiver and care recipient outcomes. Uncontrolled pain is common in people with dementia and presents unique challenges for caregivers, particularly those with limited access to specialized healthcare services. Family caregivers often lack adequate knowledge, skills, and support to manage pain effectively, contributing to suboptimal outcomes for both caregivers and care recipients. The PACE-app provides tailored, technology-based pain management support that includes: Screening of caregiver-specific challenges in pain management; Personalized pain management strategies based on the screening results; Communication tools to facilitate interactions with healthcare providers; A digital pain diary for tracking care recipients' pain experiences. A total of 60 family caregivers of people with dementia and chronic pain will be randomized 1:1 to either the PACE-app intervention group or a usual-care control group. Participants in the intervention arm will use the app for 1 month and complete outcome assessments at baseline, 1 month (post-intervention), and 2 months (follow-up). Participants in the control arm will continue their usual caregiving practices and complete assessments on the same schedule. Primary outcomes include feasibility (recruitment, retention, adherence to study protocol) and acceptability (measured by app usage analytics and qualitative interviews). Secondary outcomes include changes in caregiver self-efficacy in pain management, adherence to prescribed pain treatments, caregiver burden, stress, depression, and communication with healthcare providers. The study will also examine potential mediators (caregiver knowledge, c | Care Giving Burden | Adults (18-75) | Full Service Outsourcing (FSO) | Syneos Health | Interventional | Standard | Small Molecule | Partnership | TRUE | Veridon Therapeutics | Veridon Therapeutics | TRUE | 2024-11-23 | Denmark, Germany, Switzerland | Dr. Sarah Brown | Dr. Stephanie Garcia | Dr. Jennifer Anderson | Dr. Michelle Garcia | Dr. Christopher Thomas | Neuroscience & Rare Disease | 2025-03-23 | 2025-05-12 | 2025-03-08 | 2025-05-01 | 2025-01-22 | 2025-02-26 | 2025-02-21 | 2025-04-04 | 2025-05-22 | 2025-07-02 | 2028-01-23 |  | 2028-04-22 |  | 2028-06-22 |  | 2028-09-22 |  | 2028-11-22 |  | 5593137 | 2071249
ST-2024-018 | Feasibility Study for a Randomised Control Trial for the Acceptability of Exoskeleton Assisted Walking Compared to Standard Exercise Training for Persons With Mobility Issues Due to Multiple Sclerosis | PHASE_II | Neurology | Multiple Sclerosis | Neurology Portfolio | OMP-574 | MEA | RECRUITING | 24 | 24 | 104.35 | 2022-06-23 | 2024-10-30 | 3 | 15 | 0.2 | 0.1 | ON_TRACK | Enrolling | Multiple sclerosis (MS) is a chronic, inflammatory disease of the central nervous system. Lack of physical activity is common in people with MS (pwMS). This can lead to several comorbid conditions such as obesity, metabolic syndrome, osteoporosis, hypertension, diabetes and worse prognosis. An incre | Medium | Active | Consortium | In Progress | PRJ-0017 | OMP-574 | ASS-0017 | Global | BUD-0017 | Enrollment | FALSE |  |  | FALSE | Feasibility Study for a Randomised Control Trial f | Multiple sclerosis (MS) is a chronic, inflammatory disease of the central nervous system. Lack of physical activity is common in people with MS (pwMS). This can lead to several comorbid conditions such as obesity, metabolic syndrome, osteoporosis, hypertension, diabetes and worse prognosis. An increasing number of studies suggest that physical exercise can play an important role in managing symptoms, preventing complications and comorbidities in pwMS, and may possibly be neuroprotective. However, doing exercise can be very challenging for pwMS who have moderate/severe mobility disability and who have problems with walking. In this project, the investigators will explore the use of a powered Exoskeleton as an exercise tool for people with moderate to severe difficulty walking due to MS. Powered Exoskeletons are wearable robots that offer opportunity to persons with lower limb weakness to stand and walk. The Exoskeleton-assisted training provides active training with potentially much less intervention needed from therapists. However, it is not clear whether pwMS can walk with a powered Exoskeleton at speeds and intensities sufficient to positively affect health and fitness outcomes. Thus, in this study, the investigators aim to explore whether using an Exoskeleton will enable people with MS to exercise at a moderate intensity and whether people with MS find this acceptable and safe to do on a regular basis. The investigators will also explore whether training with an Exoskeleton can improve walking. The investigators will train 12 patients with MS to walk with an Exoskeleton twice a week for 8 weeks. The investigators will compare the effects with another group of 12 patients who will do exercises with a fitness instructor twice a week for 8 weeks. The investigators will study whether walking with Exoskeleton is better than fitness training in terms of fitness outcomes, walking and cognitive, psychological factors. | Multiple Sclerosis | Geriatric (65+) | In-House |  | Interventional | Priority Review | Small Molecule | Licensing Agreement | TRUE | ApexBio Research | ApexBio Research | FALSE | 2021-12-25 | Spain, South Africa, Switzerland | Dr. Michael Miller | Dr. Robert Smith | Dr. Robert Jones | Dr. Christopher Moore | Dr. Jessica Jackson | Neuroscience & Rare Disease | 2022-04-24 | 2022-05-01 | 2022-04-09 | 2022-04-09 | 2022-02-23 | 2022-03-03 | 2022-03-25 | 2022-03-22 | 2022-06-23 | 2022-06-18 | 2024-08-01 |  | 2024-10-30 |  | 2024-12-30 |  | 2025-03-30 |  | 2025-05-30 |  | 16565577 | 7700984
ST-2024-019 | Immune System, Inflammation, Migraine - The Role of Cytokines and Regulatory T Lymphocytes in Migraine Pathophysiology | PHASE_II | Neurology | Migraine Disorders | Neurology Portfolio | PHX-851 | MEA | PLANNED | 396 | 0 |  | 2027-01-18 | 2029-03-18 | 6 | 26 | 3.5 | 0 |  | Start-Up | Migraine is the 6th most frequent disease (14% of the population) and the second leading cause of disability worldwide. From puberty and onward, migraine is 2 to 3 times more frequent in women, which also suffer from more severe attacks. Migraine is also up to twice as prevalent in patients sufferin | Low | Active | Consortium | Completed | PRJ-0018 | PHX-851 | ASS-0018 | Global | BUD-0018 | Pre-Activation | FALSE |  |  | FALSE | Immune System, Inflammation, Migraine - The Role o | Migraine is the 6th most frequent disease (14% of the population) and the second leading cause of disability worldwide. From puberty and onward, migraine is 2 to 3 times more frequent in women, which also suffer from more severe attacks. Migraine is also up to twice as prevalent in patients suffering from autoimmune or inflammatory diseases such as multiple sclerosis (MS), rheumatoid arthritis (RA), Crohn disease (CD), systemic lupus erythematosus (SLE) and endometriosis, whereas patients with long standing type 1 diabetes mellitus (T1DM) - an autoimmune but non inflammatory disease - seem to be less affected compared to the general population. Despite the identification of the role of peptides such as CGRP in migraine pathophysiology and the development of targetted anti-CGRP treatments, many patients remain unresponsive and the mechanisms behind migraine are still unclear. The trigemino-vascular system is involved in the perception of migraine pain. Migraine occurs with trigemino-cervical neuron sensitization, leading to peptide secretion (such as CGRP, PACAP-38 and VIP), which induce neurogenic inflammation that is responsible for vasodilation, capillary leakage, oedema and further sensitization of the trigemino-vascular system, leading to amplified perception of migraine pain. CGRP, PACAP-38 and VIP infusions all induce migraine attacks in migraine patients, and only mild or no headache in healthy volunteers. Sex hormones, prolactin and insulin are also involved in migraine pathophysiology, and the immune system, through cytokine production and immune cell dysregulations seems to also play a role in the pathogenesis of migraine. Both are closely related as sex hormone levels may have an influence on the levels of certain immune cell subtypes. Several pro-inflammatory cytokines (tumor necrosis factor (TNF)-alpha, interferon (IFN)-gamma and interleukin (IL)-6) were shown to be elevated in migraine patients but also inflammatory diseases such as MS and endometri | Migraine Disorders | Adults (18+) | Hybrid | Covance | Interventional | Standard | Gene Therapy | Internal R&D | TRUE | OmniPath Pharma | OmniPath Pharma | TRUE | 2026-07-22 | Poland, Australia, Sweden, Taiwan, New Zealand, France | Dr. Christopher Thomas | Dr. Lisa Anderson | Dr. William Miller | Dr. Sarah Smith | Dr. Michael Johnson | Neuroscience & Rare Disease | 2026-11-19 |  | 2026-11-04 |  | 2026-09-20 |  | 2026-10-20 |  | 2027-01-18 |  | 2028-12-18 |  | 2029-03-18 |  | 2029-05-18 |  | 2029-08-18 |  | 2029-10-18 |  | 9757117 | 3810803
ST-2024-020 | A Single-center Clinical Study Evaluating the Safety and Efficacy of CD19 Universal CAR-γδT Cells in Active Systemic Lupus Erythematosus | PHASE_I | Immunology | Systemic Lupus Erythematosus | Immunology Portfolio | VRD-975 | North America | RECRUITING | 15 | 12 | 85.71 | 2024-01-12 | 2026-09-12 | 4 | 17 | 0.1 | 0.1 | AT_RISK | Enrolling | The prognosis of patients with active systemic lupus erythematosus (SLE) remains poor, due to two major therapeutic obstacles: (1) current treatment strategies including glucocorticoids, immunosuppressive agents, biological agents, are still difficult to achieve disease control, making the disease c | Medium | Active | Investigator-Initiated | In Progress | PRJ-0019 | VRD-975 | ASS-0019 | Global | BUD-0019 | Enrollment | FALSE |  |  | TRUE | A Single-center Clinical Study Evaluating the Safe | The prognosis of patients with active systemic lupus erythematosus (SLE) remains poor, due to two major therapeutic obstacles: (1) current treatment strategies including glucocorticoids, immunosuppressive agents, biological agents, are still difficult to achieve disease control, making the disease condition of some patients continue to be active or even worse; (2) some patients are unable to wean themselves off glucocorticoid and face the risk of numerous adverse effects caused by long-term glucocorticoid dependence, such as glucocorticoid-related diabetes, femoral head necrosis, hypertension, stress ulcers, and infection, etc. Therefore, there is a strong unmet clinical need for more effective treatment for patients suffering from active SLE. Several preclinical studies have shown the efficacy of CAR-T cell treatment in SLE. The aim of this study is to investigate the safety, tolerability, preliminary efficacy, pharmacokinetics (PK), and pharmacodynamics (PD) of CD19 Universal CAR-γδT cells therapy in active SLE. Patients with active SLE will be invited to participate in the study, to receive CD19 Universal CAR-γδT cells intravenous infusion and follow-up visits of up to 2 years after enrollment. | Systemic Lupus Erythematosus | Adults (18-75) | In-House |  | Interventional | Breakthrough Therapy | Small Molecule | Licensing Agreement | TRUE | MedPath Sciences | MedPath Sciences | FALSE | 2023-07-16 | Chile, Turkey, Denmark, Saudi Arabia | Dr. Robert Smith | Dr. Stephanie Johnson | Dr. Sarah Martin | Dr. Daniel Johnson | Dr. Stephanie Thompson | Immunology & Inflammation | 2023-11-13 | 2023-11-10 | 2023-10-29 | 2023-10-29 | 2023-09-14 | 2023-09-09 | 2023-10-14 | 2023-10-13 | 2024-01-12 | 2024-01-21 | 2026-06-14 |  | 2026-09-12 |  | 2026-11-12 |  | 2027-02-12 |  | 2027-04-12 |  | 4848213 | 2503712
ST-2025-023 | Prospective Registry of Patients With Systemic Lupus Erythematosus of the Argentinian Society of Rheumatology | PHASE_II | Immunology | SLE | Immunology Portfolio | APX-126 | North America | RECRUITING | 1500 | 1223 | 87.86 | 2022-04-01 | 2027-04-01 | 6 | 15 | 5.7 | 5.9 | AT_RISK | Enrolling | A longitudinal and multicenter cohort study of patients with systemic lupus erythematosus (SLE) is planned, with a follow-up of for 5 years. The data will be obtained from the clinical history of each patient. The responsible for data collection will always be a physician with experience in the mana | Medium | Active | Academic | Planned | PRJ-0022 | APX-126 | ASS-0022 | Global | BUD-0022 | Enrollment | FALSE |  |  | TRUE | Prospective Registry of Patients With Systemic Lup | A longitudinal and multicenter cohort study of patients with systemic lupus erythematosus (SLE) is planned, with a follow-up of for 5 years. The data will be obtained from the clinical history of each patient. The responsible for data collection will always be a physician with experience in the management of patients with SLE and who has received training for data loading. The data will be collected through the an electronic case report form (eCRF) specially designed for this record and which in turn will facilitate the control of the data and the generation of inquiries to the researchers. STUDY VARIABLES Baseline visit: Sociodemographic data Classification criteria American College of Rheumatology (ACR 1982/1997), Systemic Lupus International Collaborating Clinics (SLICC 2012) and/or European League Against Rheumatism / American College of Rheumatology (EULAR / ACR 2019) History of SLE Access to specialized care Current clinical manifestations Activity and damage Scores Current treatments Patient-Reported Outcomes (PROs): Self-reported quality of life questionnaires EQ-5R; physician global assessment (PGA) and the patient Comorbidities Vaccination Habits Obstetric history Associated antiphospholipid syndrome Hospitalizations for adverse event, infections, or lupus activity Annual clinical follow-up visits Clinical follow-up of the patient Changes in clinical manifestations Changes in treatments Use of health services; hospitalizations; high cost treatments Activity and damage scores PROs Annual global and SLE-related mortality STUDY ENDPOINTS * Number of patients who achieved complete clinical remission or low disease activity status (LDAS) * Impact on the quality of life and working life measured by PROs and PGA * Mortality annual and global during the follow up period * Change in disease activity and damage scores * Health care resources used reported as number of hospitalizations, emergency visits and need of high cost treatment * Accessibility to high c | SLE | All Ages | In-House |  | Interventional | Priority Review | Small Molecule | Internal R&D | FALSE | TrialSync Pharma | TrialSync Pharma | FALSE | 2021-10-03 | Colombia, Switzerland, China, Germany, Chile, Sweden | Dr. Sarah Harris | Dr. Thomas Jones | Dr. David Johnson | Dr. Jessica Taylor | Dr. Sarah Williams | Immunology & Inflammation | 2022-01-31 | 2022-02-22 | 2022-01-16 | 2022-01-26 | 2021-12-02 | 2021-12-24 | 2022-01-01 | 2022-01-05 | 2022-04-01 | 2022-04-21 | 2027-01-01 |  | 2027-04-01 |  | 2027-06-01 |  | 2027-09-01 |  | 2027-11-01 |  | 6068360 | 1509810
ST-2025-024 | Systemic Proteomic Analysis of Plasma Exosomes to Explore the Immunomodulation Reflected to Sjogren's Syndrome and Dry Eye Syndrome | PHASE_II | Immunology | Dry Eye Syndrome (DES) | Immunology Portfolio | PHX-287 | LATAM | RECRUITING | 220 | 135 | 72.97 | 2025-01-16 | 2026-12-31 | 5 | 19 | 2.2 | 1.8 | OFF_TRACK | Enrolling | Background: A 2015 survey in Taiwan revealed that the prevalence of Dry Eye Syndrome (DES) is 4.87%, with 4.8% of these cases likely to develop into Sjögren's Syndrome (SJS). An American study indicated that 11.6% of DES cases could be diagnosed as SJS, and SJS patients showed significantly more sev | Medium | Active | Investigator-Initiated | In Progress | PRJ-0023 | PHX-287 | ASS-0023 | EU First | BUD-0023 | Enrollment | FALSE |  |  | TRUE | Systemic Proteomic Analysis of Plasma Exosomes to | Background: A 2015 survey in Taiwan revealed that the prevalence of Dry Eye Syndrome (DES) is 4.87%, with 4.8% of these cases likely to develop into Sjögren's Syndrome (SJS). An American study indicated that 11.6% of DES cases could be diagnosed as SJS, and SJS patients showed significantly more severe conjunctival and corneal staining, Schirmer's test results, clinical symptoms, anti-nuclear antibody, and rheumatoid factor compared to non-SJS patients. Various autoimmune diseases (such as SJS, SLE, RA, SSc, AS, etc.) also affect the severity of dry eye symptoms. Recent studies have employed exosome proteomics to investigate cell-to-cell communication, molecular mechanisms of diseases, and the development of new diagnostic markers and therapeutic targets. While these studies have significant research value for understanding disease mechanisms, diagnosis, and treatment, few have specifically focused on the impact of exosome proteomics in SJS and DES. Objective: By analyzing the differential proteins in exosomes, this study aims to understand the pathological mechanisms of SJS and DES, identify potential diagnostic and therapeutic methods, and advance the diagnosis and treatment of these diseases. Methods: This study will develope on previous research projects conducted at Taipei Veterans General Hospital (TBDESJS，V112C-190) and the National Science and Technology Council (ACUDES). TBDESJS focused on evaluating the use of a herbal tea TBDESJS for relieving dry eye and mouth symptoms in DES and SJS patients, and ACUDES explored the immediate and long-term effects of acupuncture on treating dry eye and mouth symptoms in DES and SJS patients by using the GB20 (Fengchi) and BL2 (Zanzhu) acupuncture points. 1. TBDESJS Study: Included 30 DES patients, 60 SJS patients, and 10 healthy controls (NHC) to evaluate the efficacy of the Traditional Chinese Medicine (TCM) herbal tea in improving dry eye and mouth symptoms. 2. ACUDES Study: Included 50 DES patients, 50 SJS patient | Dry Eye Syndrome (DES) | Pediatric (2-17) | In-House |  | Interventional | Priority Review | Gene Therapy | Government Grant | TRUE | Stellara Inc | Stellara Inc | FALSE | 2024-07-20 | United States, Italy, New Zealand, United Kingdom, Mexico | Dr. Daniel Harris | Dr. Christopher Harris | Dr. Robert Taylor | Dr. Michael White | Dr. Charles Davis | Immunology & Inflammation | 2024-11-17 | 2024-11-22 | 2024-11-02 | 2024-11-01 | 2024-09-18 | 2024-09-17 | 2024-10-18 | 2024-10-08 | 2025-01-16 | 2025-01-10 | 2026-10-02 |  | 2026-12-31 |  | 2027-02-28 |  | 2027-05-31 |  | 2027-07-31 |  | 16092692 | 3059123
ST-2025-025 | Clinical Study on Evaluating the Efficacy and Safety of IM19 CAR-T Cell Therapy in Patients With Refractory Systemic Lupus Erythematosus | PHASE_II | Immunology | Refractory Systemic Lupus Erythematosus | Immunology Portfolio | MED-158 | MEA | PLANNED | 6 | 0 |  | 2026-09-18 | 2029-06-18 | 8 | 37 | 0 | 0 |  | Start-Up | The study is a single-arm, open-label clinical trial intended to recruit 6 refractory SLE subjects who meet the inclusion and exclusion criteria. The subjects will receive IM19 CAR-T cell infusion therapy at a dose of 1×10\^6/kg or 1×10\^8 CAR-T cells . The primary endpoint is to evaluate the improv | Medium | Active | Consortium | Planned | PRJ-0024 | MED-158 | ASS-0024 | US & EU Simultaneous | BUD-0024 | Pre-Activation | FALSE |  |  | TRUE | Clinical Study on Evaluating the Efficacy and Safe | The study is a single-arm, open-label clinical trial intended to recruit 6 refractory SLE subjects who meet the inclusion and exclusion criteria. The subjects will receive IM19 CAR-T cell infusion therapy at a dose of 1×10\^6/kg or 1×10\^8 CAR-T cells . The primary endpoint is to evaluate the improvement in SLE disease activity (SLEDAI-2K) at 90 days and the occurrence of adverse events related to IM19 CAR-T cell infusion within 28 days post-infusion. Additionally, the long-term efficacy was evaluated, including the improvement of SLEDAI-2K score and achieving lupus low disease activity (LLDAS) at day 180 and day 360, and renal response at day 180 and day 360. The persistence and duration of IM19 CAR-T cells in the peripheral blood of subjects will also be evaluated. The study plan includes five phases: screening phase, cell collection phase, lymphodepletion pretreatment phase, cell infusion phase, and follow-up phase. | Refractory Systemic Lupus Erythematosus | Geriatric (65+) | Hybrid | Covance | Interventional | Fast Track | Small Molecule | Partnership | FALSE | MedPath Sciences | MedPath Sciences | TRUE | 2026-03-22 | Germany, Denmark, Switzerland, Spain, South Africa, Singapore, Mexico, Mexico | Dr. Thomas Garcia | Dr. Emily Harris | Dr. Sarah Martin | Dr. Lisa Smith | Dr. Lisa Davis | Immunology & Inflammation | 2026-07-20 |  | 2026-07-05 |  | 2026-05-21 |  | 2026-06-20 |  | 2026-09-18 |  | 2029-03-20 |  | 2029-06-18 |  | 2029-08-18 |  | 2029-11-18 |  | 2030-01-18 |  | 3934747 | 1336434
ST-2025-026 | Hyperpolarized 129Xe MR Imaging of Lung Function in Healthy Volunteers and Subjects With Pulmonary Disease | PHASE_I | Respiratory | Asthma | Respiratory Portfolio | MED-384 | North America | RECRUITING | 260 | 148 | 69.48 | 2020-11-02 | 2028-10-26 | 6 | 22 | 0.6 | 0.5 | OFF_TRACK | Enrolling | This is an unblinded, open-label study with \~160 subjects with diagnosed pulmonary disease and \~100 healthy controls. Subjects to be enrolled will include males and females 18-80 years old. Evaluation will be on an outpatient basis. Imaging will be done on a single day and will involve administrat | High | Active | Academic | Completed | PRJ-0025 | MED-384 | ASS-0025 | EU First | BUD-0025 | Enrollment | TRUE | 2020-11-02 | 2028-10-26 | FALSE | Hyperpolarized 129Xe MR Imaging of Lung Function i | This is an unblinded, open-label study with \~160 subjects with diagnosed pulmonary disease and \~100 healthy controls. Subjects to be enrolled will include males and females 18-80 years old. Evaluation will be on an outpatient basis. Imaging will be done on a single day and will involve administration of up to four 1-liter doses of HP 129Xe plus one 129Xe calibration dose (\~300-400mL HP 129Xe). In addition to 129Xe MRI, a series of anatomical conventional 1H MR images will be collected including a localizer scan, breath-hold spin echo image, and breath-hold steady-state free precession image to highlight the vasculature. All subjects will be evaluated at one center: The University of Kansas Medical Center, KS USA. | Asthma | Adults (18-75) | In-House |  | Interventional | Breakthrough Therapy | Pharmaceuticals | Government Grant | TRUE | ApexBio Research | ApexBio Research | FALSE | 2020-05-06 | Chile, Singapore, Turkey, Belgium, Argentina, United States | Dr. Charles Thompson | Dr. Thomas Garcia | Dr. Christopher Smith | Dr. Michael Martin | Dr. Michael Miller | Respiratory & Allergy | 2020-09-03 | 2020-08-28 | 2020-08-19 | 2020-08-15 | 2020-07-05 | 2020-07-04 | 2020-08-04 | 2020-08-06 | 2020-11-02 | 2020-10-29 | 2028-07-28 |  | 2028-10-26 |  | 2028-12-26 |  | 2029-03-26 |  | 2029-05-26 |  | 4577129 | 2439889
ST-2025-027 | Mechanistic Trial of Dupilumab in Adults With House Dust Mite-associated Asthma Using an Aeroallergen Challenge Chamber | PHASE_II | Respiratory | Asthma, Allergic | Respiratory Portfolio | MED-515 | North America | RECRUITING | 88 | 86 | 101.18 | 2023-03-29 | 2026-08-29 | 8 | 33 | 0.5 | 0.5 | ON_TRACK | Enrolling | (i)Intervention #1: HDM exposures in the ACC This trial utilizes exposures to House dust mites (HDM) in the Aeroallergen Challenge Chamber (ACC) as a two-pronged tool for (i) precision phenotyping of HDM+PARC+AA+ persons to identify those with the adaptive and maladaptive phenotypes and (ii) assessm | Medium | Active | Commercial | Completed | PRJ-0026 | MED-515 | ASS-0026 | Global | BUD-0026 | Enrollment | FALSE |  |  | FALSE | Mechanistic Trial of Dupilumab in Adults With Hous | (i)Intervention #1: HDM exposures in the ACC This trial utilizes exposures to House dust mites (HDM) in the Aeroallergen Challenge Chamber (ACC) as a two-pronged tool for (i) precision phenotyping of HDM+PARC+AA+ persons to identify those with the adaptive and maladaptive phenotypes and (ii) assessment of symptoms intermittently throughout the clinical trial to monitor effects of dupilumab/placebo on symptom severity . (ii) Participants classifying to the adaptive and maladaptive phenotypes are then randomized to 18-weeks dupilumab vs. placebo, with ACC HDM visits during this phase. | Asthma, Allergic | Adults (18+) | Full Service Outsourcing (FSO) | Covance | Interventional | Breakthrough Therapy | Biologics | Internal R&D | FALSE | Stellara Inc | Stellara Inc | TRUE | 2022-09-30 | Colombia, South Korea, Chile, Saudi Arabia, Turkey, Mexico, Australia, Japan | Dr. Thomas Brown | Dr. Sarah Jones | Dr. David Garcia | Dr. Michael Moore | Dr. William Johnson | Respiratory & Allergy | 2023-01-28 | 2023-01-30 | 2023-01-13 | 2023-01-08 | 2022-11-29 | 2022-12-07 | 2022-12-29 | 2023-01-03 | 2023-03-29 | 2023-04-08 | 2026-05-31 |  | 2026-08-29 |  | 2026-10-29 |  | 2027-01-29 |  | 2027-03-29 |  | 6543924 | 1792770
ST-2025-028 | Improving Chronic Disease Outcomes Across the Lifespan by Addressing Structural Racism | PHASE_II | Respiratory | Hyperlipidemias | Respiratory Portfolio | VRD-853 | North America | RECRUITING | 68000 | 6573 | 98.87 | 2025-10-08 | 2028-09-30 | 3 | 7 | 438.7 | 163.4 | ON_TRACK | Enrolling | With a multidisciplinary team of social determinants of health (SDOH), implementation, antiracism, community-engaged, and practice-based researchers, the investigators will apply an antiracism framework to an existing evidence-based SDOH screening and referral system and develop a holistic implement | Low | Active | Investigator-Initiated | Planned | PRJ-0027 | VRD-853 | ASS-0027 | EU First | BUD-0027 | Enrollment | FALSE |  |  | FALSE | Improving Chronic Disease Outcomes Across the Life | With a multidisciplinary team of social determinants of health (SDOH), implementation, antiracism, community-engaged, and practice-based researchers, the investigators will apply an antiracism framework to an existing evidence-based SDOH screening and referral system and develop a holistic implementation toolkit aimed at reducing bias and mitigating unequal treatment for families of color. The investigators will first conduct qualitative interviews with adult patients and caregivers to understand their experiences with racism and discrimination within the context of their experiences with screening and referral for SDOH; the investigators will then share their findings with stakeholders (e.g., clinic directors, community agency leaders, health system leaders, Medicaid leaders) and elicit their ideas on how best to address these issues within the systems they lead. Subsequently, the investigators will refine the WE CARE implementation protocol using this stakeholder input with the guidance of antiracism and implementation experts. The investigators will then implement the refined WE CARE protocol in family medicine clinics since adverse SDOH impact the whole family unit; it will also allow them to examine WE CARE's impact on improving health outcomes for racialized groups across the life course. The investigators will conduct a hybrid effectiveness-implementation study with a stepped wedge cluster RCT design in three large family medicine clinics (including 2 health centers) that serve racially/ethnically diverse low-income families from Worcester, Massachusetts. The specific aims are to: * Aim 1: Refine the WE CARE implementation protocol using an antiracism lens and community engagement approach to: (a) conduct key informant interviews with families to identify racism and discrimination related barriers to SDOH screening/referral; (b) present these barriers to systems-level stakeholders to elicit input on strategies to address patient concerns; and 3) create an an | Hyperlipidemias | All Ages | Hybrid | PPD | Interventional | Breakthrough Therapy | Biologics | Internal R&D | FALSE | ApexBio Research | ApexBio Research | TRUE | 2025-04-11 | Poland, Netherlands, Saudi Arabia | Dr. Michelle Brown | Dr. James Johnson | Dr. Emily Moore | Dr. Jessica Brown | Dr. Daniel White | Respiratory & Allergy | 2025-08-09 | 2025-08-03 | 2025-07-25 | 2025-07-16 | 2025-06-10 | 2025-06-20 | 2025-07-10 | 2025-07-07 | 2025-10-08 | 2025-09-30 | 2028-07-02 |  | 2028-09-30 |  | 2028-11-30 |  | 2029-02-28 |  | 2029-04-30 |  | 3770776 | 1682104
ST-2025-029 | A Multicenter, Single-group Phase II Clinical Study to Evaluate the Long-term Safety, Pharmacodynamics and Efficacy of Multiple Subcutaneous Injections of SHR-1703 in Eosinophilic Asthma Patients | PHASE_II | Respiratory | Eosinophilic Asthma Patients | Respiratory Portfolio | PHX-501 | MEA | RECRUITING | 200 | 122 | 63.87 | 2024-07-19 | 2026-09-19 | 6 | 13 | 1.8 | 1.2 | OFF_TRACK | Enrolling | The purpose of this study is to evaluation the long-term Safety, Pharmacodynamics and Efficacy of SHR-1703 in Eosinophilic Asthma Patients | Medium | Active | Investigator-Initiated | In Progress | PRJ-0028 | PHX-501 | ASS-0028 | US First | BUD-0028 | Enrollment | FALSE |  |  | FALSE | A Multicenter, Single-group Phase II Clinical Stud | The purpose of this study is to evaluation the long-term Safety, Pharmacodynamics and Efficacy of SHR-1703 in Eosinophilic Asthma Patients | Eosinophilic Asthma Patients | Pediatric (2-17) | Hybrid | IQVIA | Interventional | Priority Review | Biologics | Partnership | TRUE | Genetika Therapeutics | Genetika Therapeutics | TRUE | 2024-01-21 | United Kingdom, Chile, New Zealand, Norway, Japan, Sweden | Dr. Emily Williams | Dr. Amanda Taylor | Dr. James Davis | Dr. Jessica Garcia | Dr. Michelle Brown | Respiratory & Allergy | 2024-05-20 | 2024-05-31 | 2024-05-05 | 2024-05-18 | 2024-03-21 | 2024-04-10 | 2024-04-20 | 2024-05-07 | 2024-07-19 | 2024-07-28 | 2026-06-21 |  | 2026-09-19 |  | 2026-11-19 |  | 2027-02-19 |  | 2027-04-19 |  | 6451776 | 2747002
ST-2025-030 | Expanded Studies of Risk Factors for Pulmonary-, Liver-, and Cardiovascular Disease in the SCAPIS 2 Stockholm Reexamination | PHASE_II | Respiratory | Coronary Artery Disease | Respiratory Portfolio | ZPH-863 | LATAM | RECRUITING | 1400 | 900 | 67.01 | 2024-04-08 | 2026-08-30 | 8 | 25 | 11.2 | 8.6 | OFF_TRACK | Enrolling | The Swedish CArdioPulmonary bioImage Study (SCAPIS) is a unique, large-scale national research initiative involving 30,000 randomly selected individuals aged 50-64, recruited between 2014 and 2018. The study is a collaborative effort among six university hospitals across Sweden. A follow-up study, S | Low | Active | Consortium | In Progress | PRJ-0029 | ZPH-863 | ASS-0029 | Global | BUD-0029 | Enrollment | FALSE |  |  | FALSE | Expanded Studies of Risk Factors for Pulmonary-, L | The Swedish CArdioPulmonary bioImage Study (SCAPIS) is a unique, large-scale national research initiative involving 30,000 randomly selected individuals aged 50-64, recruited between 2014 and 2018. The study is a collaborative effort among six university hospitals across Sweden. A follow-up study, SCAPIS 2, is conducted for half of the original participants. In Stockholm, 2,500 individuals will be re-examined at Danderyd University Hospital and Karolinska Institutet. SCAPIS 2 includes a core set of examinations involving blood sampling, questionnaires, and imaging. In addition to these, complementary local investigations are conducted to enable more detailed research questions. This protocol describes the additional studies conducted in the Stockholm cohort: EXTENDED SAMPLING: Saliva and Blood Samples with Blood Cell Isolation Additional blood samples will be collected to isolate blood cells for detailed immune system profiling, red blood cell function nd for lipid profiles and inflammatory markers. Saliva samples will be analyzed for inflammatory markers and microbial composition. EXTENDED QUESTIONNAIRES: Dyspnea, Sleep, Respiratory Infections, and Dental Health Participants will complete detailed questionnaires covering recent food, drink, and medication intake; oral hygiene; breathing and lung function; sleep quality and daytime somnolence; and history of respiratory infections, including COVID-19. EXTENDED IMAGING AND PHYSIOLOGICAL MEASUREMENTS: These investigations will be conducted during a separate visit, coordinated with the main study, and take approximately one hour. 1. Cardiac Ultrasound and Abdominal Aortic Measurements: cardiac structure and function, as well as the diameter of major arteries (e.g., the thoracic and abdominal aorta). 2. Liver Elastography: An ultrasound-based technique used to assess liver stiffness and fat content. 3. Vascular Stiffness: Blood pressure cuff-based pulse wave analysis with automated stiffness calculation. Photopleth | Coronary Artery Disease | Adults (18-75) | In-House |  | Interventional | Breakthrough Therapy | Gene Therapy | Licensing Agreement | FALSE | Nexagen Pharmaceuticals | Nexagen Pharmaceuticals | FALSE | 2023-10-11 | Colombia, Israel, Spain, Netherlands, France, Saudi Arabia, Taiwan, New Zealand | Dr. Stephanie Wilson | Dr. Thomas Brown | Dr. Charles White | Dr. David Thomas | Dr. Amanda Williams | Respiratory & Allergy | 2024-02-08 | 2024-02-06 | 2024-01-24 | 2024-01-18 | 2023-12-10 | 2023-12-02 | 2024-01-09 | 2024-01-07 | 2024-04-08 | 2024-04-13 | 2026-06-01 |  | 2026-08-30 |  | 2026-10-30 |  | 2027-01-30 |  | 2027-03-30 |  | 11826821 | 4868689
ST-2025-031 | A Randomized, Double-Blind, Placebo-controlled, Single- and Multiple-ascending Dose Study to Evaluate the Safety, Tolerability, Pharmacokinetics, Immunogenicity, Pharmacodynamics and Clinical Activity | PHASE_I | Respiratory | Chronic Obstructive Pulmonary Disease (COPD) | Respiratory Portfolio | APX-570 | Europe | PLANNED | 68 | 0 |  | 2027-01-18 | 2029-11-18 | 8 | 34 | 0.5 | 0 |  | Start-Up | The study consists of two parts: * Part A (single dose in HVs in sequential ascending dose cohorts, SAD in HVs part) * Part B (two repeated doses in patients with COPD, MAD in patients part) | High | Active | Investigator-Initiated | In Progress | PRJ-0030 | APX-570 | ASS-0030 | US & EU Simultaneous | BUD-0030 | Pre-Activation | TRUE | 2027-01-18 | 2029-11-18 | FALSE | A Randomized, Double-Blind, Placebo-controlled, Si | The study consists of two parts: * Part A (single dose in HVs in sequential ascending dose cohorts, SAD in HVs part) * Part B (two repeated doses in patients with COPD, MAD in patients part) | Chronic Obstructive Pulmonary Disease (COPD) | Geriatric (65+) | In-House |  | Interventional | Fast Track | Biologics | Partnership | FALSE | Stellara Inc | Stellara Inc | FALSE | 2026-07-22 | South Korea, Colombia, Argentina, Taiwan, Belgium, Poland, Mexico, Singapore | Dr. Charles Williams | Dr. Sarah Smith | Dr. Jennifer Davis | Dr. Emily Brown | Dr. Nicole Martin | Respiratory & Allergy | 2026-11-19 |  | 2026-11-04 |  | 2026-09-20 |  | 2026-10-20 |  | 2027-01-18 |  | 2029-08-20 |  | 2029-11-18 |  | 2030-01-18 |  | 2030-04-18 |  | 2030-06-18 |  | 2549425 | 720633
ST-2025-032 | Identifying the Causes and Risk Factors of Pulmonary Exacerbations in Cystic Fibrosis | PHASE_II | Rare Disease | Cystic Fibrosis (CF) | Rare Disease Portfolio | PHX-540 | APAC | RECRUITING | 300 | 28 | 90.32 | 2025-05-16 | 2029-12-31 | 4 | 8 | 1.2 | 0.5 | AT_RISK | Enrolling | Participants will be recruited by staff within the care of UK CF centres. Initial discussions will occur either during routine outpatient reviews, telephone consultations or during admissions. Consent will take place prior to any other procedures. There will be four separate cohorts of participant | Medium | Active | Academic | Planned | PRJ-0031 | PHX-540 | ASS-0031 | EU First | BUD-0031 | Enrollment | FALSE |  |  | FALSE | Identifying the Causes and Risk Factors of Pulmona | Participants will be recruited by staff within the care of UK CF centres. Initial discussions will occur either during routine outpatient reviews, telephone consultations or during admissions. Consent will take place prior to any other procedures. There will be four separate cohorts of participant 1. Group A participants will be 200 adults with CF (16 years or older) attending a UK adult CF centre taking part in the study 2. Group B participants will be 100 additional adults with CF attending one of the five core CF adult centres: Manchester, Leeds, Newcastle, Cardiff, Liverpool. 3. There will be a pilot study to test the practicalities of running the same protocol in a paediatric population. This will consist of up to 25 children with CF (5-16 years) attending a paediatric clinic in one of the five core centres. 4. In addition, the investigators will recruit up to 40 healthy volunteers to provide samples on a single occasion as controls. Group A participants will have a single in-person visit, at the start of the study. Clinical data, including lung function (spirometry), venous blood draw, sweat chloride, saliva sample and finger-prick dried blood spot sample, sputum, nasal liquid sample and urine sample and demographic data will be collected. The study will run for 12 months. Home sampling kit, consisting of 13 home sampling boxes and 3 additional exacerbation boxes, will be provided for participants to collect in-home sampling for the first 6 months fortnightly. The 3 additional exacerbation boxes will be provided for posting additional set of samples when unwell. There will be questionnaires to complete to remotely monitor the adherence to the protocol. Study app ("Watson") will be set up to provide reminders and aid study adherence and timely return of samples. Group B will only be offered at 5 specialist CF centres (Manchester, Cardiff, Newcastle, Leeds, Liverpool). This follows the same format as Group A but includes additional face to face visits at 1 a | Cystic Fibrosis (CF) | All Ages | Full Service Outsourcing (FSO) | Covance | Interventional | Priority Review | Biologics | Government Grant | FALSE | Astellion Biosciences | Astellion Biosciences | TRUE | 2024-11-17 | Singapore, Spain, New Zealand, China | Dr. William Brown | Dr. Lisa Wilson | Dr. Robert Brown | Dr. David Moore | Dr. Daniel Garcia | Neuroscience & Rare Disease | 2025-03-17 | 2025-03-23 | 2025-03-02 | 2025-03-08 | 2025-01-16 | 2025-01-24 | 2025-02-15 | 2025-02-23 | 2025-05-16 | 2025-05-22 | 2029-10-02 |  | 2029-12-31 |  | 2030-02-28 |  | 2030-05-31 |  | 2030-07-31 |  | 10959892 | 4729821
ST-2025-033 | The Effect of Intensive Hippotherapy on the Psychomotoric Development of Children With Spinal Muscular Atrophy | PHASE_II | Rare Disease | Spinal Muscular Atrophy | Rare Disease Portfolio | APX-588 | North America | RECRUITING | 16 | 13 | 86.67 | 2022-04-22 | 2025-10-22 | 4 | 15 | 0.1 | 0.1 | AT_RISK | Enrolling | Spinal muscular atrophy is rare neuromuscular disease, it is caused by gene mutation survival motor neuron 1 (SMN1). This gene encodes survival motor neuron(SMN) protein. This protein is most important to survive alfa-motoric neurons in spinal cord. When this protein doesn´t work, no signals go from | Medium | Active | Commercial | Completed | PRJ-0032 | APX-588 | ASS-0032 | US First | BUD-0032 | Enrollment | FALSE |  |  | FALSE | The Effect of Intensive Hippotherapy on the Psycho | Spinal muscular atrophy is rare neuromuscular disease, it is caused by gene mutation survival motor neuron 1 (SMN1). This gene encodes survival motor neuron(SMN) protein. This protein is most important to survive alfa-motoric neurons in spinal cord. When this protein doesn´t work, no signals go from brain to skeletal muscles and fazic muscles of body. In the end weakening breathing muscles and internal organs muscles. The first treatment is pharmacological treatment. There is a lot of research about medicament treatment, the famous treatment in Czech Republic is medicine Spinraze and from year 2020 medicine Zongelsma. This, however, more often puts more difficulty on complex rehabilitation. An empirical observation has found out that complex rehabilitation has positive effect on progress of disease and on self-sufficiency of people and children with SMA. Physiotherapy is one of the recommended rehabilitation types. The use of rehabilitation procedures is common in clinical practice. In a 2016 study, 105 adults with SMA were asked how many of them used physiotherapy. A total of 86% of respondents received these services, yet the authors of the article conclude that further research is needed to understand the impact of physiotherapy in SMA. Nevertheless, there is a lot of discussion if physiotherapy is really good for people and children with SMA. Some research shows us, that physiotherapy doesn´t worsen this disease. Researchers showed that strength training 3 times a week does not show side effects in children under 10 years of age, in some cases trends in improving muscle strength and motor functions have been observed. Because in physiotherapy therapists work primarily with muscles, and a lot of activity can cause fatigue of skeletal muscles and worsen their function. But from clinical work scientists know that the effect of physiotherapy is extensive. There is a research on mice which shows the effect of physiotherapy on the strength activities and the aerobi | Spinal Muscular Atrophy | All Ages | In-House |  | Interventional | Breakthrough Therapy | Pharmaceuticals | Government Grant | FALSE | Veridon Therapeutics | Veridon Therapeutics | FALSE | 2021-10-24 | India, Taiwan, Belgium, France | Dr. Nicole Thompson | Dr. Lisa Johnson | Dr. Nicole Wilson | Dr. Stephanie Anderson | Dr. Thomas Jones | Neuroscience & Rare Disease | 2022-02-21 | 2022-02-28 | 2022-02-06 | 2022-02-07 | 2021-12-23 | 2021-12-25 | 2022-01-22 | 2022-01-15 | 2022-04-22 | 2022-04-26 | 2025-07-24 |  | 2025-10-22 |  | 2025-12-22 |  | 2026-03-22 |  | 2026-05-22 |  | 4496223 | 1339009
ST-2025-034 | KB407-02 A Phase 1 Study of Inhaled KB407, a Replication-Defective, Non-Integrating Vector Expressing Human Cystic Fibrosis Transmembrane Conductance Regulator, for the Treatment of Cystic Fibrosis | PHASE_I | Rare Disease | Cystic Fibrosis | Rare Disease Portfolio | ZPH-190 | North America | RECRUITING | 20 | 17 | 94.44 | 2023-06-30 | 2026-11-30 | 3 | 15 | 0.1 | 0.1 | AT_RISK | Enrolling | This study will evaluate safety and tolerability of ascending doses of nebulized KB407 in adults with cystic fibrosis. | Medium | Active | Commercial | Planned | PRJ-0033 | ZPH-190 | ASS-0033 | Global | BUD-0033 | Enrollment | FALSE |  |  | FALSE | KB407-02 A Phase 1 Study of Inhaled KB407, a Repli | This study will evaluate safety and tolerability of ascending doses of nebulized KB407 in adults with cystic fibrosis. | Cystic Fibrosis | Pediatric (2-17) | In-House |  | Interventional | Priority Review | Pharmaceuticals | Government Grant | FALSE | PharmaNova Inc | PharmaNova Inc | FALSE | 2023-01-01 | Switzerland, France, Singapore | Dr. David Jones | Dr. Jessica Johnson | Dr. Charles Anderson | Dr. Jennifer Wilson | Dr. Robert Taylor | Neuroscience & Rare Disease | 2023-05-01 | 2023-06-13 | 2023-04-16 | 2023-05-30 | 2023-03-02 | 2023-04-06 | 2023-04-01 | 2023-05-23 | 2023-06-30 | 2023-08-15 | 2026-09-01 |  | 2026-11-30 |  | 2027-01-30 |  | 2027-04-30 |  | 2027-06-30 |  | 4619807 | 2146375
ST-2025-035 | Analysis of Mobility in the Bath for Infants Affected With Spinal Muscular Atrophy | PHASE_II | Rare Disease | Infantile Spinal Muscular Atrophy | Rare Disease Portfolio | CRX-889 | APAC | RECRUITING | 15 | 9 | 100 | 2025-06-26 | 2027-03-26 | 8 | 28 | 0.2 | 0.2 | ON_TRACK | Enrolling | This is a multicenter research project coordinated by the Child Neuromuscular Unit at Raymond Poincaré Hospital. Additionally, two other pediatric neurology departments, part of the national neuromuscular network FILNEMUS (https://www.filnemus.fr/), will participate in the study: Necker Children's H | Medium | Active | Consortium | In Progress | PRJ-0034 | CRX-889 | ASS-0034 | EU First | BUD-0034 | Enrollment | FALSE |  |  | FALSE | Analysis of Mobility in the Bath for Infants Affec | This is a multicenter research project coordinated by the Child Neuromuscular Unit at Raymond Poincaré Hospital. Additionally, two other pediatric neurology departments, part of the national neuromuscular network FILNEMUS (https://www.filnemus.fr/), will participate in the study: Necker Children's Hospital and Armand Trousseau Hospital. The study's population will include all infants diagnosed with spinal muscular atrophy (SMA), specifically SMA type 1, who have onset before 6 months of age and have been evaluated by the French Therapeutic Commission. Participation in the study will be contingent on parental or guardian consent during follow-up visits. Spinal muscular atrophy is a genetic neurodegenerative condition that affects spinal motor neurons, causing motor and respiratory paralysis and ultimately leading to death. As groundbreaking therapies emerge, there's an increasing need to refine the methods used to assess motor function, especially in infants with severe hypotonia due to SMA type 1. Traditional reference scales used on examination tables are limited in their accuracy because of gravitational effects. Consequently, there's growing interest in evaluating these children's motor skills in water to detect movements unburdened by gravity. Pediatric neurologists in France (SFNP) have already acknowledged the potential value of parental video recordings during infant baths. However, the lack of standardization in recording conditions, coupled with the subjective nature of video interpretations, underscores the necessity for a more standardized and quantifiable approach. Herein lies the application of our proposed evaluation utilizing inertial sensors. Utilizing inertial sensors to detect subtle movements can highlight still-active yet minimally functional motor neurons. Such detection can be pivotal in identifying children who, despite severe motor skill limitations in traditional settings, still possess developmental potential. Our study seeks to leverage | Infantile Spinal Muscular Atrophy | Adults (18+) | Full Service Outsourcing (FSO) | Parexel | Interventional | Breakthrough Therapy | Gene Therapy | Licensing Agreement | TRUE | BioMed Corp | BioMed Corp | TRUE | 2024-12-28 | Mexico, Netherlands, Brazil, Singapore, Germany, India, Colombia, Norway | Dr. Robert Smith | Dr. Thomas Wilson | Dr. David Thompson | Dr. Christopher White | Dr. Sarah Harris | Neuroscience & Rare Disease | 2025-04-27 | 2025-05-22 | 2025-04-12 | 2025-05-02 | 2025-02-26 | 2025-03-30 | 2025-03-28 | 2025-04-27 | 2025-06-26 | 2025-07-20 | 2026-12-26 |  | 2027-03-26 |  | 2027-05-26 |  | 2027-08-26 |  | 2027-10-26 |  | 15328463 | 5983667
ST-2025-036 | Canadian Observational Study Evaluating the Long-term IMPACT of CFTR (Can-IMPACT CF) | PHASE_II | Rare Disease | Cystic Fibrosis | Rare Disease Portfolio | VRD-673 | Europe | RECRUITING | 500 | 412 | 95.15 | 2021-11-01 | 2027-12-31 | 6 | 22 | 1.6 | 1.7 | ON_TRACK | Enrolling | This observational study intends to investigate health trends and data in cystic fibrosis patients all across Canada that are receiving modulator treatment so researchers can determine if CFTR treatments are effective over a long period of time and if so, which treatments work best for each individu | Low | Active | Commercial | Planned | PRJ-0035 | VRD-673 | ASS-0035 | US First | BUD-0035 | Enrollment | FALSE |  |  | FALSE | Canadian Observational Study Evaluating the Long-t | This observational study intends to investigate health trends and data in cystic fibrosis patients all across Canada that are receiving modulator treatment so researchers can determine if CFTR treatments are effective over a long period of time and if so, which treatments work best for each individual. The study will collect clinical data from routine standard of care, patient reported outcomes via survey data and samples for a biobank. | Cystic Fibrosis | Pediatric (2-17) | Hybrid | Covance | Interventional | Priority Review | Gene Therapy | Internal R&D | FALSE | Stellara Inc | Stellara Inc | TRUE | 2021-05-05 | Denmark, India, Australia, Norway, Mexico, Netherlands | Dr. Nicole Davis | Dr. William Jackson | Dr. Sarah Brown | Dr. Sarah Taylor | Dr. William Moore | Neuroscience & Rare Disease | 2021-09-02 | 2021-08-23 | 2021-08-18 | 2021-08-16 | 2021-07-04 | 2021-07-08 | 2021-08-03 | 2021-07-30 | 2021-11-01 | 2021-10-28 | 2027-10-02 |  | 2027-12-31 |  | 2028-02-28 |  | 2028-05-31 |  | 2028-07-31 |  | 4552366 | 1242169
ST-2025-037 | Exploration and Study on the Identification of Various Pulmonary Diseases Using Volatile Organic Compounds Biomarkers in Human Exhaled Breath | PHASE_II | Rare Disease | Lung Cancer | Rare Disease Portfolio | GEN-899 | LATAM | PLANNED | 10000 | 0 |  | 2026-08-18 | 2028-02-18 | 8 | 24 | 128.2 | 0 |  | Start-Up | This is a prospective, cross-sectional, observational cohort study aimed at recruiting 10,000 participants with multiple pulmonary disease, including lung cancer, lung infection, chronic obstructive pulmonary disease (COPD), bronchitis, pulmonary fibrosis, pulmonary embolism, pulmonary arterial hype | Medium | Active | Commercial | Completed | PRJ-0036 | GEN-899 | ASS-0036 | Global | BUD-0036 | Pre-Activation | FALSE |  |  | FALSE | Exploration and Study on the Identification of Var | This is a prospective, cross-sectional, observational cohort study aimed at recruiting 10,000 participants with multiple pulmonary disease, including lung cancer, lung infection, chronic obstructive pulmonary disease (COPD), bronchitis, pulmonary fibrosis, pulmonary embolism, pulmonary arterial hypertension, tuberculosis, lung abscess, emphysema, radioactive lung injury, cystic fibrosis of the lung, Bronchial Asthma, Bronchiectasis, interstitial lung disease (ILD), preserved ratio impaired spirometry (PRISm) etc . Exhaled breath samples from these participants will be collected and analyzed using Gas chromatography-mass spectrometry(GC-MS) and micro Gas Chromatography-photoionisation detector (μGC-PID) system. Upon obtaining the μGC-PID results, a comprehensive evaluation of the diagnostic capabilities of exhaled breath samples in differentiating various pulmonary diseases will be performed, leveraging clinical diagnostic results, CT examination data, and clinical data. | Lung Cancer | Adults (18+) | Full Service Outsourcing (FSO) | PPD | Interventional | Breakthrough Therapy | Small Molecule | Licensing Agreement | FALSE | Stellara Inc | Stellara Inc | TRUE | 2026-02-19 | Argentina, India, Australia, Mexico, Taiwan, Poland, Canada, Saudi Arabia | Dr. Sarah Thomas | Dr. Christopher Harris | Dr. Daniel Johnson | Dr. Charles White | Dr. James Miller | Neuroscience & Rare Disease | 2026-06-19 |  | 2026-06-04 |  | 2026-04-20 |  | 2026-05-20 |  | 2026-08-18 |  | 2027-11-20 |  | 2028-02-18 |  | 2028-04-18 |  | 2028-07-18 |  | 2028-09-18 |  | 9095006 | 3333547

## Enrollment Timeline
id | study_id | period_date | planned_cumulative | actual_cumulative | forecast_cumulative | enrolled_this_period | below_plan_flag
12055 | ST-2024-002 | 2024-09-01 | 3 | 2 | 2 | 2 | TRUE
12056 | ST-2024-002 | 2024-10-01 | 4 | 3 | 3 | 1 | TRUE
12057 | ST-2024-002 | 2024-11-01 | 5 | 4 | 4 | 1 | TRUE
12058 | ST-2024-002 | 2024-12-01 | 6 | 5 | 5 | 1 | TRUE
12059 | ST-2024-002 | 2025-01-01 | 7 | 5 | 5 | 0 | TRUE
12060 | ST-2024-002 | 2025-02-01 | 8 | 6 | 6 | 1 | TRUE
12061 | ST-2024-002 | 2025-03-01 | 10 | 8 | 8 | 2 | TRUE
12062 | ST-2024-002 | 2025-04-01 | 12 | 9 | 9 | 1 | TRUE
12063 | ST-2024-002 | 2025-05-01 | 14 | 11 | 11 | 2 | TRUE
12064 | ST-2024-002 | 2025-06-01 | 16 | 13 | 13 | 2 | TRUE
12065 | ST-2024-002 | 2025-07-01 | 19 | 16 | 16 | 3 | TRUE
12066 | ST-2024-002 | 2025-08-01 | 22 | 18 | 18 | 2 | TRUE
12067 | ST-2024-002 | 2025-09-01 | 26 | 20 | 20 | 2 | TRUE
12068 | ST-2024-002 | 2025-10-01 | 30 | 24 | 24 | 4 | TRUE
12069 | ST-2024-002 | 2025-11-01 | 35 | 27 | 28 | 3 | TRUE
12070 | ST-2024-002 | 2025-12-01 | 40 | 34 | 35 | 7 | TRUE
12071 | ST-2024-002 | 2026-01-01 | 46 | 39 | 40 | 5 | TRUE
12072 | ST-2024-002 | 2026-02-01 | 53 | 42 | 43 | 3 | TRUE
12073 | ST-2024-002 | 2026-03-01 | 59 | 49 | 50 | 7 | TRUE
12074 | ST-2024-002 | 2026-04-01 | 66 | 54 | 56 | 5 | TRUE
12075 | ST-2024-002 | 2026-05-01 | 74 | 58 | 60 | 4 | TRUE
12076 | ST-2024-002 | 2026-06-01 | 81 |  | 72 |  | FALSE
12077 | ST-2024-002 | 2026-07-01 | 89 |  | 80 |  | FALSE
12078 | ST-2024-002 | 2026-08-01 | 96 |  | 86 |  | FALSE
12079 | ST-2024-002 | 2026-09-01 | 104 |  | 93 |  | FALSE
12080 | ST-2024-002 | 2026-10-01 | 111 |  | 99 |  | FALSE
12081 | ST-2024-002 | 2026-11-01 | 117 |  | 105 |  | FALSE
12082 | ST-2024-002 | 2026-12-01 | 124 |  | 111 |  | FALSE
12083 | ST-2024-002 | 2027-01-01 | 130 |  | 117 |  | FALSE
12084 | ST-2024-002 | 2027-02-01 | 135 |  | 121 |  | FALSE
12085 | ST-2024-002 | 2027-03-01 | 140 |  | 126 |  | FALSE
12086 | ST-2024-002 | 2027-04-01 | 144 |  | 129 |  | FALSE
12087 | ST-2024-002 | 2027-05-01 | 148 |  | 133 |  | FALSE
12088 | ST-2024-002 | 2027-06-01 | 151 |  | 135 |  | FALSE
12089 | ST-2024-002 | 2027-07-01 | 154 |  | 138 |  | FALSE
12090 | ST-2024-002 | 2027-08-01 | 156 |  | 140 |  | FALSE
12091 | ST-2024-002 | 2027-09-01 | 158 |  | 142 |  | FALSE
12092 | ST-2024-002 | 2027-10-01 | 160 |  | 144 |  | FALSE
12093 | ST-2024-002 | 2027-11-01 | 162 |  | 145 |  | FALSE
12094 | ST-2024-002 | 2027-12-01 | 163 |  | 146 |  | FALSE
12095 | ST-2024-002 | 2028-01-01 | 164 |  | 147 |  | FALSE
12096 | ST-2024-002 | 2028-02-01 | 165 |  | 148 |  | FALSE
12097 | ST-2024-002 | 2028-03-01 | 166 |  | 149 |  | FALSE
12098 | ST-2024-002 | 2028-04-01 | 167 |  | 150 |  | FALSE
12099 | ST-2024-002 | 2028-05-01 | 167 |  | 150 |  | FALSE
12100 | ST-2024-002 | 2028-06-01 | 167 |  | 150 |  | FALSE
12101 | ST-2024-002 | 2028-07-01 | 167 |  | 150 |  | FALSE
12102 | ST-2024-002 | 2028-08-01 | 167 |  | 150 |  | FALSE
12103 | ST-2024-003 | 2024-03-01 | 2 | 2 | 2 | 2 | FALSE
12104 | ST-2024-003 | 2024-04-01 | 3 | 3 | 3 | 1 | FALSE
12105 | ST-2024-003 | 2024-05-01 | 3 | 3 | 3 | 0 | FALSE
12106 | ST-2024-003 | 2024-06-01 | 4 | 4 | 4 | 1 | FALSE
12107 | ST-2024-003 | 2024-07-01 | 4 | 4 | 4 | 0 | FALSE
12108 | ST-2024-003 | 2024-08-01 | 5 | 4 | 4 | 0 | TRUE
12109 | ST-2024-003 | 2024-09-01 | 5 | 5 | 5 | 1 | FALSE
12110 | ST-2024-003 | 2024-10-01 | 6 | 6 | 6 | 1 | FALSE
12111 | ST-2024-003 | 2024-11-01 | 7 | 7 | 7 | 1 | FALSE
12112 | ST-2024-003 | 2024-12-01 | 8 | 8 | 8 | 1 | FALSE
12113 | ST-2024-003 | 2025-01-01 | 9 | 9 | 9 | 1 | FALSE
12114 | ST-2024-003 | 2025-02-01 | 10 | 9 | 9 | 0 | TRUE
12115 | ST-2024-003 | 2025-03-01 | 11 | 11 | 11 | 2 | FALSE
12116 | ST-2024-003 | 2025-04-01 | 13 | 13 | 13 | 2 | FALSE
12117 | ST-2024-003 | 2025-05-01 | 14 | 14 | 14 | 1 | FALSE
12118 | ST-2024-003 | 2025-06-01 | 16 | 16 | 16 | 2 | FALSE
12119 | ST-2024-003 | 2025-07-01 | 18 | 19 | 19 | 3 | FALSE
12120 | ST-2024-003 | 2025-08-01 | 20 | 19 | 19 | 0 | TRUE
12121 | ST-2024-003 | 2025-09-01 | 22 | 21 | 21 | 2 | TRUE
12122 | ST-2024-003 | 2025-10-01 | 24 | 24 | 24 | 3 | FALSE
12123 | ST-2024-003 | 2025-11-01 | 27 | 27 | 28 | 3 | FALSE
12124 | ST-2024-003 | 2025-12-01 | 29 | 30 | 31 | 3 | FALSE
12125 | ST-2024-003 | 2026-01-01 | 32 | 32 | 33 | 2 | FALSE
12126 | ST-2024-003 | 2026-02-01 | 36 | 38 | 39 | 6 | FALSE
12127 | ST-2024-003 | 2026-03-01 | 39 | 39 | 40 | 1 | FALSE
12128 | ST-2024-003 | 2026-04-01 | 42 | 44 | 45 | 5 | FALSE
12129 | ST-2024-003 | 2026-05-01 | 46 | 49 | 50 | 5 | FALSE
12130 | ST-2024-003 | 2026-06-01 | 50 |  | 52 |  | FALSE
12131 | ST-2024-003 | 2026-07-01 | 54 |  | 56 |  | FALSE
12132 | ST-2024-003 | 2026-08-01 | 58 |  | 60 |  | FALSE
12133 | ST-2024-003 | 2026-09-01 | 63 |  | 66 |  | FALSE
12134 | ST-2024-003 | 2026-10-01 | 67 |  | 70 |  | FALSE
12135 | ST-2024-003 | 2026-11-01 | 71 |  | 74 |  | FALSE
12136 | ST-2024-003 | 2026-12-01 | 76 |  | 79 |  | FALSE
12137 | ST-2024-003 | 2027-01-01 | 80 |  | 84 |  | FALSE
12138 | ST-2024-003 | 2027-02-01 | 84 |  | 88 |  | FALSE
12139 | ST-2024-003 | 2027-03-01 | 89 |  | 93 |  | FALSE
12140 | ST-2024-003 | 2027-04-01 | 93 |  | 97 |  | FALSE
12141 | ST-2024-003 | 2027-05-01 | 97 |  | 101 |  | FALSE
12142 | ST-2024-003 | 2027-06-01 | 101 |  | 106 |  | FALSE
12143 | ST-2024-003 | 2027-07-01 | 105 |  | 110 |  | FALSE
12144 | ST-2024-003 | 2027-08-01 | 108 |  | 113 |  | FALSE
12145 | ST-2024-003 | 2027-09-01 | 111 |  | 116 |  | FALSE
12146 | ST-2024-003 | 2027-10-01 | 115 |  | 120 |  | FALSE
12147 | ST-2024-003 | 2027-11-01 | 118 |  | 123 |  | FALSE
12148 | ST-2024-003 | 2027-12-01 | 120 |  | 126 |  | FALSE
12149 | ST-2024-003 | 2028-01-01 | 123 |  | 129 |  | FALSE
12150 | ST-2024-003 | 2028-02-01 | 125 |  | 131 |  | FALSE
12151 | ST-2024-003 | 2028-03-01 | 127 |  | 133 |  | FALSE
12152 | ST-2024-003 | 2028-04-01 | 129 |  | 135 |  | FALSE
12153 | ST-2024-003 | 2028-05-01 | 131 |  | 137 |  | FALSE
12154 | ST-2024-003 | 2028-06-01 | 133 |  | 139 |  | FALSE
12155 | ST-2024-003 | 2028-07-01 | 134 |  | 140 |  | FALSE
12156 | ST-2024-003 | 2028-08-01 | 136 |  | 142 |  | FALSE
12157 | ST-2024-003 | 2028-09-01 | 137 |  | 143 |  | FALSE
12158 | ST-2024-003 | 2028-10-01 | 138 |  | 144 |  | FALSE
12159 | ST-2024-003 | 2028-11-01 | 139 |  | 145 |  | FALSE
12160 | ST-2024-003 | 2028-12-01 | 140 |  | 147 |  | FALSE
12161 | ST-2024-003 | 2029-01-01 | 141 |  | 148 |  | FALSE
12162 | ST-2024-003 | 2029-02-01 | 142 |  | 148 |  | FALSE
12163 | ST-2024-003 | 2029-03-01 | 142 |  | 148 |  | FALSE
12164 | ST-2024-003 | 2029-04-01 | 143 |  | 148 |  | FALSE
12165 | ST-2024-003 | 2029-05-01 | 143 |  | 148 |  | FALSE
12166 | ST-2024-003 | 2029-06-01 | 144 |  | 148 |  | FALSE
12167 | ST-2024-003 | 2029-07-01 | 144 |  | 148 |  | FALSE
12168 | ST-2024-003 | 2029-08-01 | 145 |  | 148 |  | FALSE
12169 | ST-2024-003 | 2029-09-01 | 145 |  | 148 |  | FALSE
12170 | ST-2024-003 | 2029-10-01 | 145 |  | 148 |  | FALSE
12171 | ST-2024-003 | 2029-11-01 | 145 |  | 148 |  | FALSE
12172 | ST-2024-003 | 2029-12-01 | 145 |  | 148 |  | FALSE
12173 | ST-2024-004 | 2025-01-01 | 3 | 2 | 2 | 2 | TRUE
12174 | ST-2024-004 | 2025-02-01 | 3 | 2 | 2 | 0 | TRUE
12175 | ST-2024-004 | 2025-03-01 | 4 | 3 | 3 | 1 | TRUE
12176 | ST-2024-004 | 2025-04-01 | 4 | 3 | 3 | 0 | TRUE
12177 | ST-2024-004 | 2025-05-01 | 5 | 4 | 4 | 1 | TRUE
12178 | ST-2024-004 | 2025-06-01 | 6 | 4 | 4 | 0 | TRUE
12179 | ST-2024-004 | 2025-07-01 | 8 | 6 | 6 | 2 | TRUE
12180 | ST-2024-004 | 2025-08-01 | 9 | 6 | 6 | 0 | TRUE
12181 | ST-2024-004 | 2025-09-01 | 10 | 7 | 7 | 1 | TRUE
12182 | ST-2024-004 | 2025-10-01 | 12 | 9 | 9 | 2 | TRUE
12183 | ST-2024-004 | 2025-11-01 | 14 | 11 | 11 | 2 | TRUE
12184 | ST-2024-004 | 2025-12-01 | 17 | 13 | 13 | 2 | TRUE
12185 | ST-2024-004 | 2026-01-01 | 19 | 15 | 15 | 2 | TRUE
12186 | ST-2024-004 | 2026-02-01 | 23 | 17 | 17 | 2 | TRUE
12187 | ST-2024-004 | 2026-03-01 | 26 | 19 | 19 | 2 | TRUE
12188 | ST-2024-004 | 2026-04-01 | 30 | 24 | 24 | 5 | TRUE
12189 | ST-2024-004 | 2026-05-01 | 34 | 26 | 27 | 2 | TRUE
12190 | ST-2024-004 | 2026-06-01 | 38 |  | 34 |  | FALSE
12191 | ST-2024-004 | 2026-07-01 | 43 |  | 38 |  | FALSE
12192 | ST-2024-004 | 2026-08-01 | 49 |  | 44 |  | FALSE
12193 | ST-2024-004 | 2026-09-01 | 54 |  | 48 |  | FALSE
12194 | ST-2024-004 | 2026-10-01 | 60 |  | 54 |  | FALSE
12195 | ST-2024-004 | 2026-11-01 | 66 |  | 59 |  | FALSE
12196 | ST-2024-004 | 2026-12-01 | 72 |  | 64 |  | FALSE
12197 | ST-2024-004 | 2027-01-01 | 78 |  | 70 |  | FALSE
12198 | ST-2024-004 | 2027-02-01 | 84 |  | 75 |  | FALSE
12199 | ST-2024-004 | 2027-03-01 | 90 |  | 81 |  | FALSE
12200 | ST-2024-004 | 2027-04-01 | 95 |  | 85 |  | FALSE
12201 | ST-2024-004 | 2027-05-01 | 101 |  | 90 |  | FALSE
12202 | ST-2024-004 | 2027-06-01 | 106 |  | 95 |  | FALSE
12203 | ST-2024-004 | 2027-07-01 | 110 |  | 99 |  | FALSE
12204 | ST-2024-004 | 2027-08-01 | 114 |  | 102 |  | FALSE
12205 | ST-2024-004 | 2027-09-01 | 118 |  | 106 |  | FALSE
12206 | ST-2024-004 | 2027-10-01 | 121 |  | 108 |  | FALSE
12207 | ST-2024-004 | 2027-11-01 | 125 |  | 112 |  | FALSE
12208 | ST-2024-004 | 2027-12-01 | 127 |  | 114 |  | FALSE
12209 | ST-2024-004 | 2028-01-01 | 130 |  | 117 |  | FALSE
12210 | ST-2024-004 | 2028-02-01 | 132 |  | 118 |  | FALSE
12211 | ST-2024-004 | 2028-03-01 | 134 |  | 120 |  | FALSE
12212 | ST-2024-004 | 2028-04-01 | 135 |  | 121 |  | FALSE
12213 | ST-2024-004 | 2028-05-01 | 136 |  | 122 |  | FALSE
12214 | ST-2024-004 | 2028-06-01 | 138 |  | 124 |  | FALSE
12215 | ST-2024-004 | 2028-07-01 | 139 |  | 125 |  | FALSE
12216 | ST-2024-004 | 2028-08-01 | 140 |  | 126 |  | FALSE
12217 | ST-2024-004 | 2028-09-01 | 140 |  | 126 |  | FALSE
12218 | ST-2024-004 | 2028-10-01 | 141 |  | 126 |  | FALSE
12219 | ST-2024-004 | 2028-11-01 | 141 |  | 126 |  | FALSE
12220 | ST-2024-004 | 2028-12-01 | 142 |  | 127 |  | FALSE
12221 | ST-2024-004 | 2029-01-01 | 142 |  | 127 |  | FALSE
12222 | ST-2024-004 | 2029-02-01 | 142 |  | 127 |  | FALSE
12223 | ST-2024-004 | 2029-03-01 | 142 |  | 127 |  | FALSE
12224 | ST-2024-005 | 2022-08-01 | 2 | 1 | 1 | 1 | TRUE
12225 | ST-2024-005 | 2022-09-01 | 2 | 1 | 1 | 0 | TRUE
12226 | ST-2024-005 | 2022-10-01 | 2 | 1 | 1 | 0 | TRUE
12227 | ST-2024-005 | 2022-11-01 | 3 | 2 | 2 | 1 | TRUE
12228 | ST-2024-005 | 2022-12-01 | 3 | 2 | 2 | 0 | TRUE
12229 | ST-2024-005 | 2023-01-01 | 4 | 3 | 3 | 1 | TRUE
12230 | ST-2024-005 | 2023-02-01 | 5 | 3 | 3 | 0 | TRUE
12231 | ST-2024-005 | 2023-03-01 | 5 | 3 | 3 | 0 | TRUE
12232 | ST-2024-005 | 2023-04-01 | 6 | 4 | 4 | 1 | TRUE
12233 | ST-2024-005 | 2023-05-01 | 7 | 4 | 4 | 0 | TRUE
12234 | ST-2024-005 | 2023-06-01 | 8 | 6 | 6 | 2 | TRUE
12235 | ST-2024-005 | 2023-07-01 | 10 | 7 | 7 | 1 | TRUE
12236 | ST-2024-005 | 2023-08-01 | 11 | 8 | 8 | 1 | TRUE
12237 | ST-2024-005 | 2023-09-01 | 13 | 9 | 9 | 1 | TRUE
12238 | ST-2024-005 | 2023-10-01 | 14 | 10 | 10 | 1 | TRUE
12239 | ST-2024-005 | 2023-11-01 | 17 | 12 | 12 | 2 | TRUE
12240 | ST-2024-005 | 2023-12-01 | 19 | 13 | 13 | 1 | TRUE
12241 | ST-2024-005 | 2024-01-01 | 21 | 14 | 14 | 1 | TRUE
12242 | ST-2024-005 | 2024-02-01 | 24 | 17 | 17 | 3 | TRUE
12243 | ST-2024-005 | 2024-03-01 | 27 | 20 | 20 | 3 | TRUE
12244 | ST-2024-005 | 2024-04-01 | 30 | 22 | 22 | 2 | TRUE
12245 | ST-2024-005 | 2024-05-01 | 33 | 25 | 26 | 3 | TRUE
12246 | ST-2024-005 | 2024-06-01 | 37 | 28 | 29 | 3 | TRUE
12247 | ST-2024-005 | 2024-07-01 | 40 | 28 | 29 | 0 | TRUE
12248 | ST-2024-005 | 2024-08-01 | 44 | 33 | 34 | 5 | TRUE
12249 | ST-2024-005 | 2024-09-01 | 48 | 34 | 35 | 1 | TRUE
12250 | ST-2024-005 | 2024-10-01 | 51 | 38 | 39 | 4 | TRUE
12251 | ST-2024-005 | 2024-11-01 | 55 | 40 | 41 | 2 | TRUE
12252 | ST-2024-005 | 2024-12-01 | 59 | 43 | 44 | 3 | TRUE
12253 | ST-2024-005 | 2025-01-01 | 62 | 45 | 46 | 2 | TRUE
12254 | ST-2024-005 | 2025-02-01 | 66 | 48 | 49 | 3 | TRUE
12255 | ST-2024-005 | 2025-03-01 | 69 | 50 | 52 | 2 | TRUE
12256 | ST-2024-005 | 2025-04-01 | 72 | 51 | 53 | 1 | TRUE
12257 | ST-2024-005 | 2025-05-01 | 75 | 55 | 57 | 4 | TRUE
12258 | ST-2024-005 | 2025-06-01 | 78 | 55 | 57 | 0 | TRUE
12259 | ST-2024-005 | 2025-07-01 | 80 | 59 | 61 | 4 | TRUE
12260 | ST-2024-005 | 2025-08-01 | 82 | 63 | 65 | 4 | TRUE
12261 | ST-2024-005 | 2025-09-01 | 85 | 62 | 64 | 0 | TRUE
12262 | ST-2024-005 | 2025-10-01 | 86 | 65 | 67 | 3 | TRUE
12263 | ST-2024-005 | 2025-11-01 | 88 | 67 | 69 | 2 | TRUE
12264 | ST-2024-005 | 2025-12-01 | 89 | 68 | 70 | 1 | TRUE
12265 | ST-2024-005 | 2026-01-01 | 91 | 65 | 67 | 0 | TRUE
12266 | ST-2024-005 | 2026-02-01 | 92 | 65 | 67 | 0 | TRUE
12267 | ST-2024-005 | 2026-03-01 | 93 | 66 | 68 | 1 | TRUE
12268 | ST-2024-005 | 2026-04-01 | 94 | 70 | 72 | 4 | TRUE
12269 | ST-2024-005 | 2026-05-01 | 94 | 71 | 73 | 1 | TRUE
12270 | ST-2024-005 | 2026-06-01 | 95 |  | 85 |  | FALSE
12271 | ST-2024-005 | 2026-07-01 | 96 |  | 86 |  | FALSE
12272 | ST-2024-005 | 2026-08-01 | 96 |  | 86 |  | FALSE
12273 | ST-2024-005 | 2026-09-01 | 97 |  | 87 |  | FALSE
12274 | ST-2024-005 | 2026-10-01 | 97 |  | 87 |  | FALSE
12275 | ST-2024-005 | 2026-11-01 | 97 |  | 87 |  | FALSE
12276 | ST-2024-005 | 2026-12-01 | 98 |  | 88 |  | FALSE
12277 | ST-2024-005 | 2027-01-01 | 98 |  | 88 |  | FALSE
12278 | ST-2024-005 | 2027-02-01 | 98 |  | 88 |  | FALSE
12279 | ST-2024-005 | 2027-03-01 | 98 |  | 88 |  | FALSE
12280 | ST-2024-006 | 2024-02-01 | 1 | 0 | 0 | 0 | TRUE
12281 | ST-2024-006 | 2024-03-01 | 2 | 1 | 1 | 1 | TRUE
12282 | ST-2024-006 | 2024-04-01 | 3 | 2 | 2 | 1 | TRUE
12283 | ST-2024-006 | 2024-05-01 | 5 | 4 | 4 | 2 | TRUE
12284 | ST-2024-006 | 2024-06-01 | 7 | 5 | 5 | 1 | TRUE
12285 | ST-2024-006 | 2024-07-01 | 10 | 7 | 7 | 2 | TRUE
12286 | ST-2024-006 | 2024-08-01 | 14 | 10 | 10 | 3 | TRUE
12287 | ST-2024-006 | 2024-09-01 | 19 | 14 | 14 | 4 | TRUE
12288 | ST-2024-006 | 2024-10-01 | 25 | 20 | 20 | 6 | TRUE
12289 | ST-2024-006 | 2024-11-01 | 31 | 25 | 26 | 5 | TRUE
12290 | ST-2024-006 | 2024-12-01 | 38 | 30 | 31 | 5 | TRUE
12291 | ST-2024-006 | 2025-01-01 | 44 | 35 | 36 | 5 | TRUE
12292 | ST-2024-006 | 2025-02-01 | 50 | 40 | 41 | 5 | TRUE
12293 | ST-2024-006 | 2025-03-01 | 55 | 41 | 42 | 1 | TRUE
12294 | ST-2024-006 | 2025-04-01 | 59 | 49 | 50 | 8 | TRUE
12295 | ST-2024-006 | 2025-05-01 | 62 | 49 | 50 | 0 | TRUE
12296 | ST-2024-006 | 2025-06-01 | 64 | 50 | 52 | 1 | TRUE
12297 | ST-2024-006 | 2025-07-01 | 66 | 53 | 55 | 3 | TRUE
12298 | ST-2024-006 | 2025-08-01 | 67 | 51 | 53 | 0 | TRUE
12299 | ST-2024-006 | 2025-09-01 | 68 | 55 | 57 | 4 | TRUE
12300 | ST-2024-006 | 2025-10-01 | 68 | 55 | 57 | 0 | TRUE
12301 | ST-2024-006 | 2025-11-01 | 68 | 54 | 56 | 0 | TRUE
12302 | ST-2024-006 | 2025-12-01 | 68 | 51 | 53 | 0 | TRUE
12303 | ST-2024-006 | 2026-01-01 | 68 | 56 | 58 | 5 | TRUE
12304 | ST-2024-006 | 2026-02-01 | 68 | 53 | 55 | 0 | TRUE
12305 | ST-2024-007 | 2027-01-01 | 1 |  | 0 |  | FALSE
12306 | ST-2024-007 | 2027-02-01 | 1 |  | 0 |  | FALSE
12307 | ST-2024-007 | 2027-03-01 | 1 |  | 0 |  | FALSE
12308 | ST-2024-007 | 2027-04-01 | 2 |  | 1 |  | FALSE
12309 | ST-2024-007 | 2027-05-01 | 3 |  | 2 |  | FALSE
12310 | ST-2024-007 | 2027-06-01 | 4 |  | 3 |  | FALSE
12311 | ST-2024-007 | 2027-07-01 | 5 |  | 4 |  | FALSE
12312 | ST-2024-007 | 2027-08-01 | 6 |  | 5 |  | FALSE
12313 | ST-2024-007 | 2027-09-01 | 8 |  | 7 |  | FALSE
12314 | ST-2024-007 | 2027-10-01 | 10 |  | 9 |  | FALSE
12315 | ST-2024-007 | 2027-11-01 | 12 |  | 10 |  | FALSE
12316 | ST-2024-007 | 2027-12-01 | 15 |  | 13 |  | FALSE
12317 | ST-2024-007 | 2028-01-01 | 18 |  | 16 |  | FALSE
12318 | ST-2024-007 | 2028-02-01 | 21 |  | 18 |  | FALSE
12319 | ST-2024-007 | 2028-03-01 | 25 |  | 22 |  | FALSE
12320 | ST-2024-007 | 2028-04-01 | 28 |  | 25 |  | FALSE
12321 | ST-2024-007 | 2028-05-01 | 31 |  | 27 |  | FALSE
12322 | ST-2024-007 | 2028-06-01 | 34 |  | 30 |  | FALSE
12323 | ST-2024-007 | 2028-07-01 | 37 |  | 33 |  | FALSE
12324 | ST-2024-007 | 2028-08-01 | 39 |  | 35 |  | FALSE
12325 | ST-2024-007 | 2028-09-01 | 41 |  | 36 |  | FALSE
12326 | ST-2024-007 | 2028-10-01 | 43 |  | 38 |  | FALSE
12327 | ST-2024-007 | 2028-11-01 | 44 |  | 39 |  | FALSE
12328 | ST-2024-007 | 2028-12-01 | 45 |  | 40 |  | FALSE
12329 | ST-2024-007 | 2029-01-01 | 46 |  | 41 |  | FALSE
12330 | ST-2024-007 | 2029-02-01 | 47 |  | 42 |  | FALSE
12331 | ST-2024-007 | 2029-03-01 | 48 |  | 43 |  | FALSE
12332 | ST-2024-007 | 2029-04-01 | 48 |  | 43 |  | FALSE
12333 | ST-2024-007 | 2029-05-01 | 48 |  | 43 |  | FALSE
12334 | ST-2024-007 | 2029-06-01 | 49 |  | 44 |  | FALSE
12335 | ST-2024-007 | 2029-07-01 | 49 |  | 44 |  | FALSE
12336 | ST-2024-007 | 2029-08-01 | 49 |  | 44 |  | FALSE
12337 | ST-2024-007 | 2029-09-01 | 49 |  | 44 |  | FALSE
12338 | ST-2024-007 | 2029-10-01 | 49 |  | 44 |  | FALSE
12339 | ST-2024-008 | 2021-09-01 | 1 | 0 | 0 | 0 | TRUE
12340 | ST-2024-008 | 2021-10-01 | 1 | 0 | 0 | 0 | TRUE
12341 | ST-2024-008 | 2021-11-01 | 1 | 0 | 0 | 0 | TRUE
12342 | ST-2024-008 | 2021-12-01 | 1 | 0 | 0 | 0 | TRUE
12343 | ST-2024-008 | 2022-01-01 | 1 | 0 | 0 | 0 | TRUE
12344 | ST-2024-008 | 2022-02-01 | 2 | 1 | 1 | 1 | TRUE
12345 | ST-2024-008 | 2022-03-01 | 2 | 1 | 1 | 0 | TRUE
12346 | ST-2024-008 | 2022-04-01 | 3 | 2 | 2 | 1 | TRUE
12347 | ST-2024-008 | 2022-05-01 | 3 | 2 | 2 | 0 | TRUE
12348 | ST-2024-008 | 2022-06-01 | 4 | 3 | 3 | 1 | TRUE
12349 | ST-2024-008 | 2022-07-01 | 4 | 3 | 3 | 0 | TRUE
12350 | ST-2024-008 | 2022-08-01 | 5 | 4 | 4 | 1 | TRUE
12351 | ST-2024-008 | 2022-09-01 | 6 | 4 | 4 | 0 | TRUE
12352 | ST-2024-008 | 2022-10-01 | 7 | 5 | 5 | 1 | TRUE
12353 | ST-2024-008 | 2022-11-01 | 8 | 7 | 7 | 2 | TRUE
12354 | ST-2024-008 | 2022-12-01 | 9 | 7 | 7 | 0 | TRUE
12355 | ST-2024-008 | 2023-01-01 | 11 | 9 | 9 | 2 | TRUE
12356 | ST-2024-008 | 2023-02-01 | 12 | 9 | 9 | 0 | TRUE
12357 | ST-2024-008 | 2023-03-01 | 14 | 11 | 11 | 2 | TRUE
12358 | ST-2024-008 | 2023-04-01 | 16 | 13 | 13 | 2 | TRUE
12359 | ST-2024-008 | 2023-05-01 | 18 | 14 | 14 | 1 | TRUE
12360 | ST-2024-008 | 2023-06-01 | 19 | 16 | 16 | 2 | TRUE
12361 | ST-2024-008 | 2023-07-01 | 21 | 17 | 17 | 1 | TRUE
12362 | ST-2024-008 | 2023-08-01 | 23 | 18 | 18 | 1 | TRUE
12363 | ST-2024-008 | 2023-09-01 | 26 | 21 | 21 | 3 | TRUE
12364 | ST-2024-008 | 2023-10-01 | 28 | 23 | 23 | 2 | TRUE
12365 | ST-2024-008 | 2023-11-01 | 30 | 24 | 24 | 1 | TRUE
12366 | ST-2024-008 | 2023-12-01 | 31 | 27 | 28 | 3 | TRUE
12367 | ST-2024-008 | 2024-01-01 | 33 | 26 | 27 | 0 | TRUE
12368 | ST-2024-008 | 2024-02-01 | 35 | 30 | 31 | 4 | TRUE
12369 | ST-2024-008 | 2024-03-01 | 37 | 30 | 31 | 0 | TRUE
12370 | ST-2024-008 | 2024-04-01 | 38 | 30 | 31 | 0 | TRUE
12371 | ST-2024-008 | 2024-05-01 | 40 | 33 | 34 | 3 | TRUE
12372 | ST-2024-008 | 2024-06-01 | 41 | 33 | 34 | 0 | TRUE
12373 | ST-2024-008 | 2024-07-01 | 42 | 34 | 35 | 1 | TRUE
12374 | ST-2024-008 | 2024-08-01 | 43 | 37 | 38 | 3 | TRUE
12375 | ST-2024-008 | 2024-09-01 | 44 | 35 | 36 | 0 | TRUE
12376 | ST-2024-008 | 2024-10-01 | 45 | 39 | 40 | 4 | TRUE
12377 | ST-2024-008 | 2024-11-01 | 45 | 37 | 38 | 0 | TRUE
12378 | ST-2024-008 | 2024-12-01 | 46 | 37 | 38 | 0 | TRUE
12379 | ST-2024-008 | 2025-01-01 | 46 | 39 | 40 | 2 | TRUE
12380 | ST-2024-008 | 2025-02-01 | 47 | 38 | 39 | 0 | TRUE
12381 | ST-2024-008 | 2025-03-01 | 47 | 40 | 41 | 2 | TRUE
12382 | ST-2024-008 | 2025-04-01 | 48 | 38 | 39 | 0 | TRUE
12383 | ST-2024-008 | 2025-05-01 | 48 | 42 | 43 | 4 | TRUE
12384 | ST-2024-008 | 2025-06-01 | 48 | 40 | 41 | 0 | TRUE
12385 | ST-2024-008 | 2025-07-01 | 48 | 37 | 38 | 0 | TRUE
12386 | ST-2024-008 | 2025-08-01 | 48 | 39 | 40 | 2 | TRUE
12387 | ST-2024-008 | 2025-09-01 | 49 | 40 | 41 | 1 | TRUE
12388 | ST-2024-008 | 2025-10-01 | 49 | 40 | 41 | 0 | TRUE
12389 | ST-2024-008 | 2025-11-01 | 49 | 41 | 42 | 1 | TRUE
12390 | ST-2024-008 | 2025-12-01 | 49 | 41 | 42 | 0 | TRUE
12391 | ST-2024-009 | 2025-11-01 | 6 | 4 | 4 | 4 | TRUE
12392 | ST-2024-009 | 2025-12-01 | 7 | 6 | 6 | 2 | TRUE
12393 | ST-2024-009 | 2026-01-01 | 9 | 7 | 7 | 1 | TRUE
12394 | ST-2024-009 | 2026-02-01 | 10 | 8 | 8 | 1 | TRUE
12395 | ST-2024-009 | 2026-03-01 | 13 | 10 | 10 | 2 | TRUE
12396 | ST-2024-009 | 2026-04-01 | 15 | 12 | 12 | 2 | TRUE
12397 | ST-2024-009 | 2026-05-01 | 18 | 14 | 14 | 2 | TRUE
12398 | ST-2024-009 | 2026-06-01 | 21 |  | 18 |  | FALSE
12399 | ST-2024-009 | 2026-07-01 | 25 |  | 22 |  | FALSE
12400 | ST-2024-009 | 2026-08-01 | 30 |  | 27 |  | FALSE
12401 | ST-2024-009 | 2026-09-01 | 35 |  | 31 |  | FALSE
12402 | ST-2024-009 | 2026-10-01 | 41 |  | 36 |  | FALSE
12403 | ST-2024-009 | 2026-11-01 | 48 |  | 43 |  | FALSE
12404 | ST-2024-009 | 2026-12-01 | 56 |  | 50 |  | FALSE
12405 | ST-2024-009 | 2027-01-01 | 65 |  | 58 |  | FALSE
12406 | ST-2024-009 | 2027-02-01 | 75 |  | 67 |  | FALSE
12407 | ST-2024-009 | 2027-03-01 | 86 |  | 77 |  | FALSE
12408 | ST-2024-009 | 2027-04-01 | 97 |  | 87 |  | FALSE
12409 | ST-2024-009 | 2027-05-01 | 110 |  | 99 |  | FALSE
12410 | ST-2024-009 | 2027-06-01 | 123 |  | 110 |  | FALSE
12411 | ST-2024-009 | 2027-07-01 | 136 |  | 122 |  | FALSE
12412 | ST-2024-009 | 2027-08-01 | 150 |  | 135 |  | FALSE
12413 | ST-2024-009 | 2027-09-01 | 163 |  | 146 |  | FALSE
12414 | ST-2024-009 | 2027-10-01 | 176 |  | 158 |  | FALSE
12415 | ST-2024-009 | 2027-11-01 | 189 |  | 170 |  | FALSE
12416 | ST-2024-009 | 2027-12-01 | 202 |  | 181 |  | FALSE
12417 | ST-2024-009 | 2028-01-01 | 213 |  | 191 |  | FALSE
12418 | ST-2024-009 | 2028-02-01 | 224 |  | 201 |  | FALSE
12419 | ST-2024-009 | 2028-03-01 | 234 |  | 210 |  | FALSE
12420 | ST-2024-009 | 2028-04-01 | 243 |  | 218 |  | FALSE
12421 | ST-2024-009 | 2028-05-01 | 251 |  | 225 |  | FALSE
12422 | ST-2024-009 | 2028-06-01 | 258 |  | 232 |  | FALSE
12423 | ST-2024-009 | 2028-07-01 | 264 |  | 237 |  | FALSE
12424 | ST-2024-009 | 2028-08-01 | 269 |  | 242 |  | FALSE
12425 | ST-2024-009 | 2028-09-01 | 274 |  | 246 |  | FALSE
12426 | ST-2024-009 | 2028-10-01 | 278 |  | 250 |  | FALSE
12427 | ST-2024-009 | 2028-11-01 | 281 |  | 252 |  | FALSE
12428 | ST-2024-009 | 2028-12-01 | 284 |  | 255 |  | FALSE
12429 | ST-2024-009 | 2029-01-01 | 286 |  | 257 |  | FALSE
12430 | ST-2024-009 | 2029-02-01 | 289 |  | 260 |  | FALSE
12431 | ST-2024-009 | 2029-03-01 | 290 |  | 261 |  | FALSE
12432 | ST-2024-009 | 2029-04-01 | 292 |  | 262 |  | FALSE
12433 | ST-2024-009 | 2029-05-01 | 293 |  | 263 |  | FALSE
12434 | ST-2024-009 | 2029-06-01 | 294 |  | 264 |  | FALSE
12435 | ST-2024-009 | 2029-07-01 | 294 |  | 264 |  | FALSE
12436 | ST-2024-009 | 2029-08-01 | 294 |  | 264 |  | FALSE
12437 | ST-2024-009 | 2029-09-01 | 294 |  | 264 |  | FALSE
12438 | ST-2024-010 | 2021-02-01 | 96 | 81 | 84 | 81 | TRUE
12439 | ST-2024-010 | 2021-03-01 | 102 | 92 | 95 | 11 | TRUE
12440 | ST-2024-010 | 2021-04-01 | 109 | 90 | 93 | 0 | TRUE
12441 | ST-2024-010 | 2021-05-01 | 116 | 105 | 109 | 15 | TRUE
12442 | ST-2024-010 | 2021-06-01 | 124 | 101 | 105 | 0 | TRUE
12443 | ST-2024-010 | 2021-07-01 | 132 | 117 | 121 | 16 | TRUE
12444 | ST-2024-010 | 2021-08-01 | 141 | 124 | 128 | 7 | TRUE
12445 | ST-2024-010 | 2021-09-01 | 151 | 132 | 137 | 8 | TRUE
12446 | ST-2024-010 | 2021-10-01 | 161 | 134 | 139 | 2 | TRUE
12447 | ST-2024-010 | 2021-11-01 | 172 | 144 | 149 | 10 | TRUE
12448 | ST-2024-010 | 2021-12-01 | 183 | 165 | 171 | 21 | TRUE
12449 | ST-2024-010 | 2022-01-01 | 195 | 164 | 170 | 0 | TRUE
12450 | ST-2024-010 | 2022-02-01 | 208 | 186 | 193 | 22 | TRUE
12451 | ST-2024-010 | 2022-03-01 | 222 | 193 | 200 | 7 | TRUE
12452 | ST-2024-010 | 2022-04-01 | 237 | 195 | 202 | 2 | TRUE
12453 | ST-2024-010 | 2022-05-01 | 252 | 221 | 229 | 26 | TRUE
12454 | ST-2024-010 | 2022-06-01 | 269 | 220 | 228 | 0 | TRUE
12455 | ST-2024-010 | 2022-07-01 | 286 | 239 | 248 | 19 | TRUE
12456 | ST-2024-010 | 2022-08-01 | 305 | 263 | 273 | 24 | TRUE
12457 | ST-2024-010 | 2022-09-01 | 324 | 265 | 275 | 2 | TRUE
12458 | ST-2024-010 | 2022-10-01 | 345 | 294 | 305 | 29 | TRUE
12459 | ST-2024-010 | 2022-11-01 | 367 | 330 | 343 | 36 | TRUE
12460 | ST-2024-010 | 2022-12-01 | 391 | 351 | 365 | 21 | TRUE
12461 | ST-2024-010 | 2023-01-01 | 415 | 369 | 383 | 18 | TRUE
12462 | ST-2024-010 | 2023-02-01 | 441 | 372 | 386 | 3 | TRUE
12463 | ST-2024-010 | 2023-03-01 | 469 | 386 | 401 | 14 | TRUE
12464 | ST-2024-010 | 2023-04-01 | 498 | 427 | 444 | 41 | TRUE
12465 | ST-2024-010 | 2023-05-01 | 529 | 449 | 466 | 22 | TRUE
12466 | ST-2024-010 | 2023-06-01 | 561 | 472 | 490 | 23 | TRUE
12467 | ST-2024-010 | 2023-07-01 | 596 | 530 | 551 | 58 | TRUE
12468 | ST-2024-010 | 2023-08-01 | 631 | 559 | 581 | 29 | TRUE
12469 | ST-2024-010 | 2023-09-01 | 669 | 560 | 582 | 1 | TRUE
12470 | ST-2024-010 | 2023-10-01 | 709 | 602 | 626 | 42 | TRUE
12471 | ST-2024-010 | 2023-11-01 | 750 | 681 | 708 | 79 | TRUE
12472 | ST-2024-010 | 2023-12-01 | 794 | 723 | 751 | 42 | TRUE
12473 | ST-2024-010 | 2024-01-01 | 839 | 746 | 775 | 23 | TRUE
12474 | ST-2024-010 | 2024-02-01 | 887 | 785 | 816 | 39 | TRUE
12475 | ST-2024-010 | 2024-03-01 | 937 | 812 | 844 | 27 | TRUE
12476 | ST-2024-010 | 2024-04-01 | 989 | 881 | 916 | 69 | TRUE
12477 | ST-2024-010 | 2024-05-01 | 1043 | 865 | 899 | 0 | TRUE
12478 | ST-2024-010 | 2024-06-01 | 1099 | 994 | 1033 | 129 | TRUE
12479 | ST-2024-010 | 2024-07-01 | 1157 | 945 | 982 | 0 | TRUE
12480 | ST-2024-010 | 2024-08-01 | 1217 | 1055 | 1097 | 110 | TRUE
12481 | ST-2024-010 | 2024-09-01 | 1280 | 1121 | 1165 | 66 | TRUE
12482 | ST-2024-010 | 2024-10-01 | 1344 | 1185 | 1232 | 64 | TRUE
12483 | ST-2024-010 | 2024-11-01 | 1411 | 1151 | 1197 | 0 | TRUE
12484 | ST-2024-010 | 2024-12-01 | 1479 | 1253 | 1303 | 102 | TRUE
12485 | ST-2024-010 | 2025-01-01 | 1550 | 1376 | 1431 | 123 | TRUE
12486 | ST-2024-010 | 2025-02-01 | 1622 | 1380 | 1435 | 4 | TRUE
12487 | ST-2024-010 | 2025-03-01 | 1696 | 1502 | 1562 | 122 | TRUE
12488 | ST-2024-010 | 2025-04-01 | 1771 | 1495 | 1554 | 0 | TRUE
12489 | ST-2024-010 | 2025-05-01 | 1848 | 1542 | 1603 | 47 | TRUE
12490 | ST-2024-010 | 2025-06-01 | 1927 | 1753 | 1823 | 211 | TRUE
12491 | ST-2024-010 | 2025-07-01 | 2006 | 1715 | 1783 | 0 | TRUE
12492 | ST-2024-010 | 2025-08-01 | 2087 | 1894 | 1969 | 179 | TRUE
12493 | ST-2024-010 | 2025-09-01 | 2168 | 1970 | 2048 | 76 | TRUE
12494 | ST-2024-010 | 2025-10-01 | 2250 | 1864 | 1938 | 0 | TRUE
12495 | ST-2024-010 | 2025-11-01 | 2333 | 1964 | 2042 | 100 | TRUE
12496 | ST-2024-010 | 2025-12-01 | 2416 | 1979 | 2058 | 15 | TRUE
12497 | ST-2024-010 | 2026-01-01 | 2500 | 2093 | 2176 | 114 | TRUE
12498 | ST-2024-010 | 2026-02-01 | 2583 | 2315 | 2407 | 222 | TRUE
12499 | ST-2024-010 | 2026-03-01 | 2666 | 2278 | 2369 | 0 | TRUE
12500 | ST-2024-010 | 2026-04-01 | 2749 | 2477 | 2576 | 199 | TRUE
12501 | ST-2024-010 | 2026-05-01 | 2831 | 2432 | 2529 | 0 | TRUE
12502 | ST-2024-010 | 2026-06-01 | 2912 |  | 2697 |  | FALSE
12503 | ST-2024-010 | 2026-07-01 | 2993 |  | 2772 |  | FALSE
12504 | ST-2024-010 | 2026-08-01 | 3072 |  | 2845 |  | FALSE
12505 | ST-2024-010 | 2026-09-01 | 3151 |  | 2918 |  | FALSE
12506 | ST-2024-010 | 2026-10-01 | 3228 |  | 2990 |  | FALSE
12507 | ST-2024-010 | 2026-11-01 | 3303 |  | 3059 |  | FALSE
12508 | ST-2024-010 | 2026-12-01 | 3377 |  | 3128 |  | FALSE
12509 | ST-2024-010 | 2027-01-01 | 3449 |  | 3194 |  | FALSE
12510 | ST-2024-010 | 2027-02-01 | 3520 |  | 3260 |  | FALSE
12511 | ST-2024-010 | 2027-03-01 | 3588 |  | 3323 |  | FALSE
12512 | ST-2024-010 | 2027-04-01 | 3655 |  | 3385 |  | FALSE
12513 | ST-2024-010 | 2027-05-01 | 3719 |  | 3444 |  | FALSE
12514 | ST-2024-010 | 2027-06-01 | 3782 |  | 3503 |  | FALSE
12515 | ST-2024-010 | 2027-07-01 | 3842 |  | 3558 |  | FALSE
12516 | ST-2024-010 | 2027-08-01 | 3900 |  | 3612 |  | FALSE
12517 | ST-2024-010 | 2027-09-01 | 3956 |  | 3664 |  | FALSE
12518 | ST-2024-010 | 2027-10-01 | 4010 |  | 3714 |  | FALSE
12519 | ST-2024-010 | 2027-11-01 | 4062 |  | 3762 |  | FALSE
12520 | ST-2024-010 | 2027-12-01 | 4112 |  | 3808 |  | FALSE
12521 | ST-2024-010 | 2028-01-01 | 4160 |  | 3853 |  | FALSE
12522 | ST-2024-010 | 2028-02-01 | 4205 |  | 3895 |  | FALSE
12523 | ST-2024-010 | 2028-03-01 | 4249 |  | 3935 |  | FALSE
12524 | ST-2024-010 | 2028-04-01 | 4290 |  | 3973 |  | FALSE
12525 | ST-2024-010 | 2028-05-01 | 4330 |  | 4010 |  | FALSE
12526 | ST-2024-010 | 2028-06-01 | 4368 |  | 4046 |  | FALSE
12527 | ST-2024-010 | 2028-07-01 | 4403 |  | 4078 |  | FALSE
12528 | ST-2024-010 | 2028-08-01 | 4438 |  | 4110 |  | FALSE
12529 | ST-2024-010 | 2028-09-01 | 4470 |  | 4140 |  | FALSE
12530 | ST-2024-010 | 2028-10-01 | 4501 |  | 4169 |  | FALSE
12531 | ST-2024-010 | 2028-11-01 | 4530 |  | 4196 |  | FALSE
12532 | ST-2024-010 | 2028-12-01 | 4558 |  | 4222 |  | FALSE
12533 | ST-2024-010 | 2029-01-01 | 4584 |  | 4246 |  | FALSE
12534 | ST-2024-010 | 2029-02-01 | 4608 |  | 4268 |  | FALSE
12535 | ST-2024-010 | 2029-03-01 | 4632 |  | 4290 |  | FALSE
12536 | ST-2024-010 | 2029-04-01 | 4654 |  | 4310 |  | FALSE
12537 | ST-2024-010 | 2029-05-01 | 4675 |  | 4330 |  | FALSE
12538 | ST-2024-010 | 2029-06-01 | 4694 |  | 4348 |  | FALSE
12539 | ST-2024-010 | 2029-07-01 | 4713 |  | 4365 |  | FALSE
12540 | ST-2024-010 | 2029-08-01 | 4730 |  | 4381 |  | FALSE
12541 | ST-2024-010 | 2029-09-01 | 4747 |  | 4397 |  | FALSE
12542 | ST-2024-010 | 2029-10-01 | 4762 |  | 4411 |  | FALSE
12543 | ST-2024-010 | 2029-11-01 | 4777 |  | 4424 |  | FALSE
12544 | ST-2024-010 | 2029-12-01 | 4791 |  | 4437 |  | FALSE
12545 | ST-2024-010 | 2030-01-01 | 4804 |  | 4449 |  | FALSE
12546 | ST-2024-010 | 2030-02-01 | 4816 |  | 4461 |  | FALSE
12547 | ST-2024-010 | 2030-03-01 | 4827 |  | 4471 |  | FALSE
12548 | ST-2024-010 | 2030-04-01 | 4838 |  | 4481 |  | FALSE
12549 | ST-2024-010 | 2030-05-01 | 4848 |  | 4490 |  | FALSE
12550 | ST-2024-010 | 2030-06-01 | 4858 |  | 4499 |  | FALSE
12551 | ST-2024-010 | 2030-07-01 | 4867 |  | 4508 |  | FALSE
12552 | ST-2024-010 | 2030-08-01 | 4875 |  | 4515 |  | FALSE
12553 | ST-2024-010 | 2030-09-01 | 4883 |  | 4523 |  | FALSE
12554 | ST-2024-010 | 2030-10-01 | 4890 |  | 4529 |  | FALSE
12555 | ST-2024-010 | 2030-11-01 | 4897 |  | 4536 |  | FALSE
12556 | ST-2024-010 | 2030-12-01 | 4903 |  | 4541 |  | FALSE
12557 | ST-2024-010 | 2031-01-01 | 4910 |  | 4548 |  | FALSE
12558 | ST-2024-010 | 2031-02-01 | 4910 |  | 4548 |  | FALSE
12559 | ST-2024-010 | 2031-03-01 | 4910 |  | 4548 |  | FALSE
12560 | ST-2024-011 | 2026-01-01 | 3 | 2 | 2 | 2 | TRUE
12561 | ST-2024-011 | 2026-02-01 | 3 | 2 | 2 | 0 | TRUE
12562 | ST-2024-011 | 2026-03-01 | 4 | 2 | 2 | 0 | TRUE
12563 | ST-2024-011 | 2026-04-01 | 5 | 3 | 3 | 1 | TRUE
12564 | ST-2024-011 | 2026-05-01 | 7 | 5 | 5 | 2 | TRUE
12565 | ST-2024-011 | 2026-06-01 | 9 |  | 8 |  | FALSE
12566 | ST-2024-011 | 2026-07-01 | 11 |  | 9 |  | FALSE
12567 | ST-2024-011 | 2026-08-01 | 13 |  | 11 |  | FALSE
12568 | ST-2024-011 | 2026-09-01 | 16 |  | 14 |  | FALSE
12569 | ST-2024-011 | 2026-10-01 | 20 |  | 18 |  | FALSE
12570 | ST-2024-011 | 2026-11-01 | 24 |  | 21 |  | FALSE
12571 | ST-2024-011 | 2026-12-01 | 29 |  | 26 |  | FALSE
12572 | ST-2024-011 | 2027-01-01 | 34 |  | 30 |  | FALSE
12573 | ST-2024-011 | 2027-02-01 | 40 |  | 36 |  | FALSE
12574 | ST-2024-011 | 2027-03-01 | 47 |  | 42 |  | FALSE
12575 | ST-2024-011 | 2027-04-01 | 54 |  | 48 |  | FALSE
12576 | ST-2024-011 | 2027-05-01 | 62 |  | 55 |  | FALSE
12577 | ST-2024-011 | 2027-06-01 | 70 |  | 63 |  | FALSE
12578 | ST-2024-011 | 2027-07-01 | 77 |  | 69 |  | FALSE
12579 | ST-2024-011 | 2027-08-01 | 85 |  | 76 |  | FALSE
12580 | ST-2024-011 | 2027-09-01 | 92 |  | 82 |  | FALSE
12581 | ST-2024-011 | 2027-10-01 | 99 |  | 89 |  | FALSE
12582 | ST-2024-011 | 2027-11-01 | 105 |  | 94 |  | FALSE
12583 | ST-2024-011 | 2027-12-01 | 110 |  | 99 |  | FALSE
12584 | ST-2024-011 | 2028-01-01 | 115 |  | 103 |  | FALSE
12585 | ST-2024-011 | 2028-02-01 | 119 |  | 107 |  | FALSE
12586 | ST-2024-011 | 2028-03-01 | 123 |  | 110 |  | FALSE
12587 | ST-2024-011 | 2028-04-01 | 126 |  | 113 |  | FALSE
12588 | ST-2024-011 | 2028-05-01 | 128 |  | 115 |  | FALSE
12589 | ST-2024-011 | 2028-06-01 | 130 |  | 117 |  | FALSE
12590 | ST-2024-011 | 2028-07-01 | 132 |  | 118 |  | FALSE
12591 | ST-2024-011 | 2028-08-01 | 134 |  | 120 |  | FALSE
12592 | ST-2024-011 | 2028-09-01 | 135 |  | 121 |  | FALSE
12593 | ST-2024-011 | 2028-10-01 | 136 |  | 122 |  | FALSE
12594 | ST-2024-011 | 2028-11-01 | 136 |  | 122 |  | FALSE
12595 | ST-2024-011 | 2028-12-01 | 137 |  | 123 |  | FALSE
12596 | ST-2024-011 | 2029-01-01 | 137 |  | 123 |  | FALSE
12597 | ST-2024-011 | 2029-02-01 | 137 |  | 123 |  | FALSE
12598 | ST-2024-011 | 2029-03-01 | 137 |  | 123 |  | FALSE
12599 | ST-2024-012 | 2025-06-01 | 0 | 0 | 0 | 0 | FALSE
12600 | ST-2024-012 | 2025-07-01 | 1 | 0 | 0 | 0 | TRUE
12601 | ST-2024-012 | 2025-08-01 | 1 | 0 | 0 | 0 | TRUE
12602 | ST-2024-012 | 2025-09-01 | 2 | 1 | 1 | 1 | TRUE
12603 | ST-2024-012 | 2025-10-01 | 4 | 2 | 2 | 1 | TRUE
12604 | ST-2024-012 | 2025-11-01 | 6 | 4 | 4 | 2 | TRUE
12605 | ST-2024-012 | 2025-12-01 | 8 | 5 | 5 | 1 | TRUE
12606 | ST-2024-012 | 2026-01-01 | 11 | 7 | 7 | 2 | TRUE
12607 | ST-2024-012 | 2026-02-01 | 15 | 10 | 10 | 3 | TRUE
12608 | ST-2024-012 | 2026-03-01 | 18 | 13 | 13 | 3 | TRUE
12609 | ST-2024-012 | 2026-04-01 | 21 | 14 | 14 | 1 | TRUE
12610 | ST-2024-012 | 2026-05-01 | 23 | 17 | 17 | 3 | TRUE
12611 | ST-2024-012 | 2026-06-01 | 25 |  | 22 |  | FALSE
12612 | ST-2024-012 | 2026-07-01 | 27 |  | 24 |  | FALSE
12613 | ST-2024-012 | 2026-08-01 | 28 |  | 25 |  | FALSE
12614 | ST-2024-012 | 2026-09-01 | 28 |  | 25 |  | FALSE
12615 | ST-2024-012 | 2026-10-01 | 29 |  | 26 |  | FALSE
12616 | ST-2024-012 | 2026-11-01 | 29 |  | 26 |  | FALSE
12617 | ST-2024-012 | 2026-12-01 | 29 |  | 26 |  | FALSE
12618 | ST-2024-012 | 2027-01-01 | 29 |  | 26 |  | FALSE
12619 | ST-2024-012 | 2027-02-01 | 29 |  | 26 |  | FALSE
12620 | ST-2024-012 | 2027-03-01 | 29 |  | 26 |  | FALSE
12621 | ST-2024-013 | 2026-12-01 | 0 |  | 0 |  | FALSE
12622 | ST-2024-013 | 2027-01-01 | 0 |  | 0 |  | FALSE
12623 | ST-2024-013 | 2027-02-01 | 0 |  | 0 |  | FALSE
12624 | ST-2024-013 | 2027-03-01 | 0 |  | 0 |  | FALSE
12625 | ST-2024-013 | 2027-04-01 | 0 |  | 0 |  | FALSE
12626 | ST-2024-013 | 2027-05-01 | 0 |  | 0 |  | FALSE
12627 | ST-2024-013 | 2027-06-01 | 0 |  | 0 |  | FALSE
12628 | ST-2024-013 | 2027-07-01 | 0 |  | 0 |  | FALSE
12629 | ST-2024-013 | 2027-08-01 | 1 |  | 1 |  | FALSE
12630 | ST-2024-013 | 2027-09-01 | 1 |  | 1 |  | FALSE
12631 | ST-2024-013 | 2027-10-01 | 1 |  | 1 |  | FALSE
12632 | ST-2024-013 | 2027-11-01 | 2 |  | 2 |  | FALSE
12633 | ST-2024-013 | 2027-12-01 | 2 |  | 2 |  | FALSE
12634 | ST-2024-013 | 2028-01-01 | 2 |  | 2 |  | FALSE
12635 | ST-2024-013 | 2028-02-01 | 3 |  | 3 |  | FALSE
12636 | ST-2024-013 | 2028-03-01 | 3 |  | 3 |  | FALSE
12637 | ST-2024-013 | 2028-04-01 | 4 |  | 4 |  | FALSE
12638 | ST-2024-013 | 2028-05-01 | 5 |  | 5 |  | FALSE
12639 | ST-2024-013 | 2028-06-01 | 5 |  | 5 |  | FALSE
12640 | ST-2024-013 | 2028-07-01 | 6 |  | 6 |  | FALSE
12641 | ST-2024-013 | 2028-08-01 | 6 |  | 6 |  | FALSE
12642 | ST-2024-013 | 2028-09-01 | 6 |  | 6 |  | FALSE
12643 | ST-2024-013 | 2028-10-01 | 7 |  | 7 |  | FALSE
12644 | ST-2024-013 | 2028-11-01 | 7 |  | 7 |  | FALSE
12645 | ST-2024-013 | 2028-12-01 | 7 |  | 7 |  | FALSE
12646 | ST-2024-013 | 2029-01-01 | 8 |  | 8 |  | FALSE
12647 | ST-2024-013 | 2029-02-01 | 8 |  | 8 |  | FALSE
12648 | ST-2024-013 | 2029-03-01 | 8 |  | 8 |  | FALSE
12649 | ST-2024-013 | 2029-04-01 | 8 |  | 8 |  | FALSE
12650 | ST-2024-013 | 2029-05-01 | 8 |  | 8 |  | FALSE
12651 | ST-2024-013 | 2029-06-01 | 8 |  | 8 |  | FALSE
12652 | ST-2024-013 | 2029-07-01 | 8 |  | 8 |  | FALSE
12653 | ST-2024-013 | 2029-08-01 | 8 |  | 8 |  | FALSE
12654 | ST-2024-013 | 2029-09-01 | 8 |  | 8 |  | FALSE
12655 | ST-2024-013 | 2029-10-01 | 8 |  | 8 |  | FALSE
12656 | ST-2024-013 | 2029-11-01 | 8 |  | 8 |  | FALSE
12657 | ST-2024-013 | 2029-12-01 | 8 |  | 8 |  | FALSE
12658 | ST-2024-014 | 2025-03-01 | 0 | 0 | 0 | 0 | FALSE
12659 | ST-2024-014 | 2025-04-01 | 0 | 0 | 0 | 0 | FALSE
12660 | ST-2024-014 | 2025-05-01 | 1 | 0 | 0 | 0 | TRUE
12661 | ST-2024-014 | 2025-06-01 | 1 | 0 | 0 | 0 | TRUE
12662 | ST-2024-014 | 2025-07-01 | 1 | 0 | 0 | 0 | TRUE
12663 | ST-2024-014 | 2025-08-01 | 2 | 1 | 1 | 1 | TRUE
12664 | ST-2024-014 | 2025-09-01 | 2 | 2 | 2 | 1 | FALSE
12665 | ST-2024-014 | 2025-10-01 | 3 | 2 | 2 | 0 | TRUE
12666 | ST-2024-014 | 2025-11-01 | 3 | 2 | 2 | 0 | TRUE
12667 | ST-2024-014 | 2025-12-01 | 4 | 3 | 3 | 1 | TRUE
12668 | ST-2024-014 | 2026-01-01 | 5 | 4 | 4 | 1 | TRUE
12669 | ST-2024-014 | 2026-02-01 | 7 | 6 | 6 | 2 | TRUE
12670 | ST-2024-014 | 2026-03-01 | 8 | 7 | 7 | 1 | TRUE
12671 | ST-2024-014 | 2026-04-01 | 9 | 8 | 8 | 1 | TRUE
12672 | ST-2024-014 | 2026-05-01 | 11 | 10 | 10 | 2 | TRUE
12673 | ST-2024-014 | 2026-06-01 | 13 |  | 13 |  | FALSE
12674 | ST-2024-014 | 2026-07-01 | 15 |  | 15 |  | FALSE
12675 | ST-2024-014 | 2026-08-01 | 16 |  | 16 |  | FALSE
12676 | ST-2024-014 | 2026-09-01 | 18 |  | 18 |  | FALSE
12677 | ST-2024-014 | 2026-10-01 | 20 |  | 20 |  | FALSE
12678 | ST-2024-014 | 2026-11-01 | 21 |  | 21 |  | FALSE
12679 | ST-2024-014 | 2026-12-01 | 22 |  | 22 |  | FALSE
12680 | ST-2024-014 | 2027-01-01 | 24 |  | 24 |  | FALSE
12681 | ST-2024-014 | 2027-02-01 | 25 |  | 25 |  | FALSE
12682 | ST-2024-014 | 2027-03-01 | 26 |  | 26 |  | FALSE
12683 | ST-2024-014 | 2027-04-01 | 26 |  | 26 |  | FALSE
12684 | ST-2024-014 | 2027-05-01 | 27 |  | 27 |  | FALSE
12685 | ST-2024-014 | 2027-06-01 | 27 |  | 27 |  | FALSE
12686 | ST-2024-014 | 2027-07-01 | 28 |  | 28 |  | FALSE
12687 | ST-2024-014 | 2027-08-01 | 28 |  | 28 |  | FALSE
12688 | ST-2024-014 | 2027-09-01 | 28 |  | 28 |  | FALSE
12689 | ST-2024-014 | 2027-10-01 | 29 |  | 29 |  | FALSE
12690 | ST-2024-014 | 2027-11-01 | 29 |  | 29 |  | FALSE
12691 | ST-2024-014 | 2027-12-01 | 29 |  | 29 |  | FALSE
12692 | ST-2024-014 | 2028-01-01 | 29 |  | 29 |  | FALSE
12693 | ST-2024-014 | 2028-02-01 | 29 |  | 29 |  | FALSE
12694 | ST-2024-014 | 2028-03-01 | 29 |  | 29 |  | FALSE
12695 | ST-2024-015 | 2025-11-01 | 3 | 2 | 2 | 2 | TRUE
12696 | ST-2024-015 | 2025-12-01 | 4 | 3 | 3 | 1 | TRUE
12697 | ST-2024-015 | 2026-01-01 | 5 | 4 | 4 | 1 | TRUE
12698 | ST-2024-015 | 2026-02-01 | 7 | 6 | 6 | 2 | TRUE
12699 | ST-2024-015 | 2026-03-01 | 10 | 9 | 9 | 3 | TRUE
12700 | ST-2024-015 | 2026-04-01 | 13 | 12 | 12 | 3 | TRUE
12701 | ST-2024-015 | 2026-05-01 | 17 | 15 | 15 | 3 | TRUE
12702 | ST-2024-015 | 2026-06-01 | 22 |  | 22 |  | FALSE
12703 | ST-2024-015 | 2026-07-01 | 28 |  | 28 |  | FALSE
12704 | ST-2024-015 | 2026-08-01 | 35 |  | 36 |  | FALSE
12705 | ST-2024-015 | 2026-09-01 | 43 |  | 44 |  | FALSE
12706 | ST-2024-015 | 2026-10-01 | 53 |  | 54 |  | FALSE
12707 | ST-2024-015 | 2026-11-01 | 62 |  | 64 |  | FALSE
12708 | ST-2024-015 | 2026-12-01 | 73 |  | 75 |  | FALSE
12709 | ST-2024-015 | 2027-01-01 | 82 |  | 84 |  | FALSE
12710 | ST-2024-015 | 2027-02-01 | 92 |  | 95 |  | FALSE
12711 | ST-2024-015 | 2027-03-01 | 100 |  | 103 |  | FALSE
12712 | ST-2024-015 | 2027-04-01 | 107 |  | 110 |  | FALSE
12713 | ST-2024-015 | 2027-05-01 | 113 |  | 116 |  | FALSE
12714 | ST-2024-015 | 2027-06-01 | 118 |  | 121 |  | FALSE
12715 | ST-2024-015 | 2027-07-01 | 122 |  | 126 |  | FALSE
12716 | ST-2024-015 | 2027-08-01 | 125 |  | 129 |  | FALSE
12717 | ST-2024-015 | 2027-09-01 | 128 |  | 132 |  | FALSE
12718 | ST-2024-015 | 2027-10-01 | 130 |  | 134 |  | FALSE
12719 | ST-2024-015 | 2027-11-01 | 131 |  | 135 |  | FALSE
12720 | ST-2024-015 | 2027-12-01 | 132 |  | 136 |  | FALSE
12721 | ST-2024-015 | 2028-01-01 | 133 |  | 136 |  | FALSE
12722 | ST-2024-015 | 2028-02-01 | 133 |  | 136 |  | FALSE
12723 | ST-2024-015 | 2028-03-01 | 133 |  | 136 |  | FALSE
12724 | ST-2024-015 | 2028-04-01 | 133 |  | 136 |  | FALSE
12725 | ST-2024-015 | 2028-05-01 | 133 |  | 136 |  | FALSE
12726 | ST-2024-016 | 2025-03-01 | 2 | 1 | 1 | 1 | TRUE
12727 | ST-2024-016 | 2025-04-01 | 2 | 1 | 1 | 0 | TRUE
12728 | ST-2024-016 | 2025-05-01 | 3 | 2 | 2 | 1 | TRUE
12729 | ST-2024-016 | 2025-06-01 | 4 | 3 | 3 | 1 | TRUE
12730 | ST-2024-016 | 2025-07-01 | 6 | 5 | 5 | 2 | TRUE
12731 | ST-2024-016 | 2025-08-01 | 8 | 7 | 7 | 2 | TRUE
12732 | ST-2024-016 | 2025-09-01 | 10 | 8 | 8 | 1 | TRUE
12733 | ST-2024-016 | 2025-10-01 | 13 | 10 | 10 | 2 | TRUE
12734 | ST-2024-016 | 2025-11-01 | 17 | 14 | 14 | 4 | TRUE
12735 | ST-2024-016 | 2025-12-01 | 21 | 17 | 17 | 3 | TRUE
12736 | ST-2024-016 | 2026-01-01 | 26 | 22 | 22 | 5 | TRUE
12737 | ST-2024-016 | 2026-02-01 | 32 | 27 | 28 | 5 | TRUE
12738 | ST-2024-016 | 2026-03-01 | 38 | 34 | 35 | 7 | TRUE
12739 | ST-2024-016 | 2026-04-01 | 45 | 40 | 41 | 6 | TRUE
12740 | ST-2024-016 | 2026-05-01 | 51 | 45 | 46 | 5 | TRUE
12741 | ST-2024-016 | 2026-06-01 | 57 |  | 53 |  | FALSE
12742 | ST-2024-016 | 2026-07-01 | 63 |  | 58 |  | FALSE
12743 | ST-2024-016 | 2026-08-01 | 68 |  | 63 |  | FALSE
12744 | ST-2024-016 | 2026-09-01 | 72 |  | 67 |  | FALSE
12745 | ST-2024-016 | 2026-10-01 | 76 |  | 70 |  | FALSE
12746 | ST-2024-016 | 2026-11-01 | 79 |  | 73 |  | FALSE
12747 | ST-2024-016 | 2026-12-01 | 81 |  | 75 |  | FALSE
12748 | ST-2024-016 | 2027-01-01 | 83 |  | 77 |  | FALSE
12749 | ST-2024-016 | 2027-02-01 | 85 |  | 79 |  | FALSE
12750 | ST-2024-016 | 2027-03-01 | 86 |  | 80 |  | FALSE
12751 | ST-2024-016 | 2027-04-01 | 87 |  | 81 |  | FALSE
12752 | ST-2024-016 | 2027-05-01 | 87 |  | 81 |  | FALSE
12753 | ST-2024-016 | 2027-06-01 | 88 |  | 82 |  | FALSE
12754 | ST-2024-016 | 2027-07-01 | 88 |  | 82 |  | FALSE
12755 | ST-2024-016 | 2027-08-01 | 88 |  | 82 |  | FALSE
12756 | ST-2024-016 | 2027-09-01 | 88 |  | 82 |  | FALSE
12757 | ST-2024-016 | 2027-10-01 | 88 |  | 82 |  | FALSE
12758 | ST-2024-017 | 2025-05-01 | 1 | 0 | 0 | 0 | TRUE
12759 | ST-2024-017 | 2025-06-01 | 1 | 0 | 0 | 0 | TRUE
12760 | ST-2024-017 | 2025-07-01 | 2 | 1 | 1 | 1 | TRUE
12761 | ST-2024-017 | 2025-08-01 | 2 | 1 | 1 | 0 | TRUE
12762 | ST-2024-017 | 2025-09-01 | 3 | 2 | 2 | 1 | TRUE
12763 | ST-2024-017 | 2025-10-01 | 3 | 1 | 1 | 0 | TRUE
12764 | ST-2024-017 | 2025-11-01 | 4 | 2 | 2 | 1 | TRUE
12765 | ST-2024-017 | 2025-12-01 | 5 | 3 | 3 | 1 | TRUE
12766 | ST-2024-017 | 2026-01-01 | 7 | 4 | 4 | 1 | TRUE
12767 | ST-2024-017 | 2026-02-01 | 8 | 5 | 5 | 1 | TRUE
12768 | ST-2024-017 | 2026-03-01 | 10 | 7 | 7 | 2 | TRUE
12769 | ST-2024-017 | 2026-04-01 | 12 | 8 | 8 | 1 | TRUE
12770 | ST-2024-017 | 2026-05-01 | 14 | 9 | 9 | 1 | TRUE
12771 | ST-2024-017 | 2026-06-01 | 17 |  | 15 |  | FALSE
12772 | ST-2024-017 | 2026-07-01 | 20 |  | 18 |  | FALSE
12773 | ST-2024-017 | 2026-08-01 | 23 |  | 20 |  | FALSE
12774 | ST-2024-017 | 2026-09-01 | 26 |  | 23 |  | FALSE
12775 | ST-2024-017 | 2026-10-01 | 30 |  | 27 |  | FALSE
12776 | ST-2024-017 | 2026-11-01 | 33 |  | 29 |  | FALSE
12777 | ST-2024-017 | 2026-12-01 | 36 |  | 32 |  | FALSE
12778 | ST-2024-017 | 2027-01-01 | 39 |  | 35 |  | FALSE
12779 | ST-2024-017 | 2027-02-01 | 42 |  | 37 |  | FALSE
12780 | ST-2024-017 | 2027-03-01 | 45 |  | 40 |  | FALSE
12781 | ST-2024-017 | 2027-04-01 | 47 |  | 42 |  | FALSE
12782 | ST-2024-017 | 2027-05-01 | 49 |  | 44 |  | FALSE
12783 | ST-2024-017 | 2027-06-01 | 51 |  | 45 |  | FALSE
12784 | ST-2024-017 | 2027-07-01 | 52 |  | 46 |  | FALSE
12785 | ST-2024-017 | 2027-08-01 | 54 |  | 48 |  | FALSE
12786 | ST-2024-017 | 2027-09-01 | 55 |  | 49 |  | FALSE
12787 | ST-2024-017 | 2027-10-01 | 56 |  | 50 |  | FALSE
12788 | ST-2024-017 | 2027-11-01 | 56 |  | 50 |  | FALSE
12789 | ST-2024-017 | 2027-12-01 | 57 |  | 51 |  | FALSE
12790 | ST-2024-017 | 2028-01-01 | 57 |  | 51 |  | FALSE
12791 | ST-2024-017 | 2028-02-01 | 58 |  | 52 |  | FALSE
12792 | ST-2024-017 | 2028-03-01 | 58 |  | 52 |  | FALSE
12793 | ST-2024-017 | 2028-04-01 | 58 |  | 52 |  | FALSE
12794 | ST-2024-017 | 2028-05-01 | 58 |  | 52 |  | FALSE
12795 | ST-2024-017 | 2028-06-01 | 58 |  | 52 |  | FALSE
12796 | ST-2024-017 | 2028-07-01 | 58 |  | 52 |  | FALSE
12797 | ST-2024-018 | 2022-06-01 | 0 | 0 | 0 | 0 | FALSE
12798 | ST-2024-018 | 2022-07-01 | 0 | 0 | 0 | 0 | FALSE
12799 | ST-2024-018 | 2022-08-01 | 0 | 0 | 0 | 0 | FALSE
12800 | ST-2024-018 | 2022-09-01 | 1 | 1 | 1 | 1 | FALSE
12801 | ST-2024-018 | 2022-10-01 | 1 | 1 | 1 | 0 | FALSE
12802 | ST-2024-018 | 2022-11-01 | 2 | 2 | 2 | 1 | FALSE
12803 | ST-2024-018 | 2022-12-01 | 2 | 2 | 2 | 0 | FALSE
12804 | ST-2024-018 | 2023-01-01 | 3 | 3 | 3 | 1 | FALSE
12805 | ST-2024-018 | 2023-02-01 | 4 | 4 | 4 | 1 | FALSE
12806 | ST-2024-018 | 2023-03-01 | 5 | 5 | 5 | 1 | FALSE
12807 | ST-2024-018 | 2023-04-01 | 6 | 6 | 6 | 1 | FALSE
12808 | ST-2024-018 | 2023-05-01 | 8 | 9 | 9 | 3 | FALSE
12809 | ST-2024-018 | 2023-06-01 | 9 | 9 | 9 | 0 | FALSE
12810 | ST-2024-018 | 2023-07-01 | 11 | 11 | 11 | 2 | FALSE
12811 | ST-2024-018 | 2023-08-01 | 12 | 12 | 12 | 1 | FALSE
12812 | ST-2024-018 | 2023-09-01 | 14 | 15 | 15 | 3 | FALSE
12813 | ST-2024-018 | 2023-10-01 | 15 | 16 | 16 | 1 | FALSE
12814 | ST-2024-018 | 2023-11-01 | 17 | 17 | 17 | 1 | FALSE
12815 | ST-2024-018 | 2023-12-01 | 18 | 20 | 20 | 3 | FALSE
12816 | ST-2024-018 | 2024-01-01 | 19 | 21 | 21 | 1 | FALSE
12817 | ST-2024-018 | 2024-02-01 | 20 | 20 | 20 | 0 | FALSE
12818 | ST-2024-018 | 2024-03-01 | 21 | 22 | 22 | 2 | FALSE
12819 | ST-2024-018 | 2024-04-01 | 21 | 23 | 23 | 1 | FALSE
12820 | ST-2024-018 | 2024-05-01 | 22 | 22 | 22 | 0 | FALSE
12821 | ST-2024-018 | 2024-06-01 | 22 | 22 | 22 | 0 | FALSE
12822 | ST-2024-018 | 2024-07-01 | 23 | 23 | 23 | 1 | FALSE
12823 | ST-2024-018 | 2024-08-01 | 23 | 24 | 24 | 1 | FALSE
12824 | ST-2024-018 | 2024-09-01 | 23 | 24 | 24 | 0 | FALSE
12825 | ST-2024-018 | 2024-10-01 | 23 | 24 | 24 | 0 | FALSE
12826 | ST-2024-018 | 2024-11-01 | 23 | 24 | 24 | 0 | FALSE
12827 | ST-2024-018 | 2024-12-01 | 23 | 24 | 24 | 0 | FALSE
12828 | ST-2024-018 | 2025-01-01 | 23 | 24 | 24 | 0 | FALSE
12829 | ST-2024-019 | 2027-01-01 | 9 |  | 8 |  | FALSE
12830 | ST-2024-019 | 2027-02-01 | 12 |  | 11 |  | FALSE
12831 | ST-2024-019 | 2027-03-01 | 17 |  | 16 |  | FALSE
12832 | ST-2024-019 | 2027-04-01 | 23 |  | 22 |  | FALSE
12833 | ST-2024-019 | 2027-05-01 | 31 |  | 29 |  | FALSE
12834 | ST-2024-019 | 2027-06-01 | 41 |  | 39 |  | FALSE
12835 | ST-2024-019 | 2027-07-01 | 53 |  | 51 |  | FALSE
12836 | ST-2024-019 | 2027-08-01 | 69 |  | 66 |  | FALSE
12837 | ST-2024-019 | 2027-09-01 | 89 |  | 85 |  | FALSE
12838 | ST-2024-019 | 2027-10-01 | 112 |  | 107 |  | FALSE
12839 | ST-2024-019 | 2027-11-01 | 138 |  | 132 |  | FALSE
12840 | ST-2024-019 | 2027-12-01 | 167 |  | 160 |  | FALSE
12841 | ST-2024-019 | 2028-01-01 | 198 |  | 190 |  | FALSE
12842 | ST-2024-019 | 2028-02-01 | 228 |  | 219 |  | FALSE
12843 | ST-2024-019 | 2028-03-01 | 257 |  | 247 |  | FALSE
12844 | ST-2024-019 | 2028-04-01 | 283 |  | 272 |  | FALSE
12845 | ST-2024-019 | 2028-05-01 | 306 |  | 294 |  | FALSE
12846 | ST-2024-019 | 2028-06-01 | 326 |  | 314 |  | FALSE
12847 | ST-2024-019 | 2028-07-01 | 342 |  | 329 |  | FALSE
12848 | ST-2024-019 | 2028-08-01 | 354 |  | 341 |  | FALSE
12849 | ST-2024-019 | 2028-09-01 | 364 |  | 350 |  | FALSE
12850 | ST-2024-019 | 2028-10-01 | 372 |  | 358 |  | FALSE
12851 | ST-2024-019 | 2028-11-01 | 378 |  | 364 |  | FALSE
12852 | ST-2024-019 | 2028-12-01 | 383 |  | 368 |  | FALSE
12853 | ST-2024-019 | 2029-01-01 | 386 |  | 371 |  | FALSE
12854 | ST-2024-019 | 2029-02-01 | 388 |  | 373 |  | FALSE
12855 | ST-2024-019 | 2029-03-01 | 388 |  | 373 |  | FALSE
12856 | ST-2024-019 | 2029-04-01 | 388 |  | 373 |  | FALSE
12857 | ST-2024-019 | 2029-05-01 | 388 |  | 373 |  | FALSE
12858 | ST-2024-019 | 2029-06-01 | 388 |  | 373 |  | FALSE
12859 | ST-2024-020 | 2024-01-01 | 0 | 0 | 0 | 0 | FALSE
12860 | ST-2024-020 | 2024-02-01 | 0 | 0 | 0 | 0 | FALSE
12861 | ST-2024-020 | 2024-03-01 | 0 | 0 | 0 | 0 | FALSE
12862 | ST-2024-020 | 2024-04-01 | 0 | 0 | 0 | 0 | FALSE
12863 | ST-2024-020 | 2024-05-01 | 0 | 0 | 0 | 0 | FALSE
12864 | ST-2024-020 | 2024-06-01 | 1 | 0 | 0 | 0 | TRUE
12865 | ST-2024-020 | 2024-07-01 | 1 | 0 | 0 | 0 | TRUE
12866 | ST-2024-020 | 2024-08-01 | 1 | 0 | 0 | 0 | TRUE
12867 | ST-2024-020 | 2024-09-01 | 2 | 1 | 1 | 1 | TRUE
12868 | ST-2024-020 | 2024-10-01 | 2 | 1 | 1 | 0 | TRUE
12869 | ST-2024-020 | 2024-11-01 | 3 | 2 | 2 | 1 | TRUE
12870 | ST-2024-020 | 2024-12-01 | 4 | 3 | 3 | 1 | TRUE
12871 | ST-2024-020 | 2025-01-01 | 4 | 3 | 3 | 0 | TRUE
12872 | ST-2024-020 | 2025-02-01 | 5 | 4 | 4 | 1 | TRUE
12873 | ST-2024-020 | 2025-03-01 | 6 | 5 | 5 | 1 | TRUE
12874 | ST-2024-020 | 2025-04-01 | 7 | 5 | 5 | 0 | TRUE
12875 | ST-2024-020 | 2025-05-01 | 8 | 7 | 7 | 2 | TRUE
12876 | ST-2024-020 | 2025-06-01 | 9 | 8 | 8 | 1 | TRUE
12877 | ST-2024-020 | 2025-07-01 | 10 | 8 | 8 | 0 | TRUE
12878 | ST-2024-020 | 2025-08-01 | 10 | 9 | 9 | 1 | TRUE
12879 | ST-2024-020 | 2025-09-01 | 11 | 9 | 9 | 0 | TRUE
12880 | ST-2024-020 | 2025-10-01 | 12 | 10 | 10 | 1 | TRUE
12881 | ST-2024-020 | 2025-11-01 | 12 | 10 | 10 | 0 | TRUE
12882 | ST-2024-020 | 2025-12-01 | 13 | 11 | 11 | 1 | TRUE
12883 | ST-2024-020 | 2026-01-01 | 13 | 11 | 11 | 0 | TRUE
12884 | ST-2024-020 | 2026-02-01 | 13 | 11 | 11 | 0 | TRUE
12885 | ST-2024-020 | 2026-03-01 | 14 | 12 | 12 | 1 | TRUE
12886 | ST-2024-020 | 2026-04-01 | 14 | 11 | 11 | 0 | TRUE
12887 | ST-2024-020 | 2026-05-01 | 14 | 12 | 12 | 1 | TRUE
12888 | ST-2024-020 | 2026-06-01 | 14 |  | 13 |  | FALSE
12889 | ST-2024-020 | 2026-07-01 | 14 |  | 13 |  | FALSE
12890 | ST-2024-020 | 2026-08-01 | 14 |  | 13 |  | FALSE
12891 | ST-2024-020 | 2026-09-01 | 14 |  | 13 |  | FALSE
12892 | ST-2024-020 | 2026-10-01 | 14 |  | 13 |  | FALSE
12893 | ST-2024-020 | 2026-11-01 | 14 |  | 13 |  | FALSE
12894 | ST-2024-020 | 2026-12-01 | 14 |  | 13 |  | FALSE
12895 | ST-2025-021 | 2018-03-01 | 4 | 4 | 4 | 4 | FALSE
12896 | ST-2025-021 | 2018-04-01 | 5 | 5 | 5 | 1 | FALSE
12897 | ST-2025-021 | 2018-05-01 | 6 | 6 | 6 | 1 | FALSE
12898 | ST-2025-021 | 2018-06-01 | 8 | 7 | 7 | 1 | TRUE
12899 | ST-2025-021 | 2018-07-01 | 10 | 10 | 10 | 3 | FALSE
12900 | ST-2025-021 | 2018-08-01 | 12 | 12 | 12 | 2 | FALSE
12901 | ST-2025-021 | 2018-09-01 | 16 | 17 | 17 | 5 | FALSE
12902 | ST-2025-021 | 2018-10-01 | 19 | 18 | 18 | 1 | TRUE
12903 | ST-2025-021 | 2018-11-01 | 24 | 24 | 24 | 6 | FALSE
12904 | ST-2025-021 | 2018-12-01 | 29 | 30 | 31 | 6 | FALSE
12905 | ST-2025-021 | 2019-01-01 | 36 | 35 | 36 | 5 | TRUE
12906 | ST-2025-021 | 2019-02-01 | 43 | 43 | 44 | 8 | FALSE
12907 | ST-2025-021 | 2019-03-01 | 51 | 53 | 55 | 10 | FALSE
12908 | ST-2025-021 | 2019-04-01 | 61 | 65 | 67 | 12 | FALSE
12909 | ST-2025-021 | 2019-05-01 | 71 | 74 | 76 | 9 | FALSE
12910 | ST-2025-021 | 2019-06-01 | 81 | 80 | 83 | 6 | TRUE
12911 | ST-2025-021 | 2019-07-01 | 92 | 93 | 96 | 13 | FALSE
12912 | ST-2025-021 | 2019-08-01 | 103 | 104 | 108 | 11 | FALSE
12913 | ST-2025-021 | 2019-09-01 | 113 | 121 | 125 | 17 | FALSE
12914 | ST-2025-021 | 2019-10-01 | 123 | 131 | 136 | 10 | FALSE
12915 | ST-2025-021 | 2019-11-01 | 133 | 134 | 139 | 3 | FALSE
12916 | ST-2025-021 | 2019-12-01 | 141 | 149 | 154 | 15 | FALSE
12917 | ST-2025-021 | 2020-01-01 | 148 | 150 | 156 | 1 | FALSE
12918 | ST-2025-021 | 2020-02-01 | 155 | 161 | 167 | 11 | FALSE
12919 | ST-2025-021 | 2020-03-01 | 160 | 162 | 168 | 1 | FALSE
12920 | ST-2025-021 | 2020-04-01 | 165 | 164 | 170 | 2 | TRUE
12921 | ST-2025-021 | 2020-05-01 | 168 | 166 | 172 | 2 | TRUE
12922 | ST-2025-021 | 2020-06-01 | 172 | 173 | 179 | 7 | FALSE
12923 | ST-2025-021 | 2020-07-01 | 174 | 185 | 185 | 12 | FALSE
12924 | ST-2025-021 | 2020-08-01 | 176 | 180 | 185 | 0 | FALSE
12925 | ST-2025-021 | 2020-09-01 | 178 | 185 | 185 | 5 | FALSE
12926 | ST-2025-021 | 2020-10-01 | 179 | 178 | 185 | 0 | TRUE
12927 | ST-2025-021 | 2020-11-01 | 180 | 180 | 185 | 2 | FALSE
12928 | ST-2025-021 | 2020-12-01 | 181 | 185 | 185 | 5 | FALSE
12929 | ST-2025-021 | 2021-01-01 | 181 | 185 | 185 | 0 | FALSE
12930 | ST-2025-021 | 2021-02-01 | 181 | 185 | 185 | 0 | FALSE
12931 | ST-2025-021 | 2021-03-01 | 181 | 185 | 185 | 0 | FALSE
12932 | ST-2025-022 | 2022-08-01 | 1 | 0 | 0 | 0 | TRUE
12933 | ST-2025-022 | 2022-09-01 | 1 | 0 | 0 | 0 | TRUE
12934 | ST-2025-022 | 2022-10-01 | 1 | 1 | 1 | 1 | FALSE
12935 | ST-2025-022 | 2022-11-01 | 2 | 2 | 2 | 1 | FALSE
12936 | ST-2025-022 | 2022-12-01 | 2 | 1 | 1 | 0 | TRUE
12937 | ST-2025-022 | 2023-01-01 | 3 | 3 | 3 | 2 | FALSE
12938 | ST-2025-022 | 2023-02-01 | 4 | 3 | 3 | 0 | TRUE
12939 | ST-2025-022 | 2023-03-01 | 4 | 4 | 4 | 1 | FALSE
12940 | ST-2025-022 | 2023-04-01 | 5 | 5 | 5 | 1 | FALSE
12941 | ST-2025-022 | 2023-05-01 | 7 | 6 | 6 | 1 | TRUE
12942 | ST-2025-022 | 2023-06-01 | 8 | 8 | 8 | 2 | FALSE
12943 | ST-2025-022 | 2023-07-01 | 10 | 9 | 9 | 1 | TRUE
12944 | ST-2025-022 | 2023-08-01 | 11 | 11 | 11 | 2 | FALSE
12945 | ST-2025-022 | 2023-09-01 | 13 | 13 | 13 | 2 | FALSE
12946 | ST-2025-022 | 2023-10-01 | 16 | 16 | 16 | 3 | FALSE
12947 | ST-2025-022 | 2023-11-01 | 18 | 18 | 18 | 2 | FALSE
12948 | ST-2025-022 | 2023-12-01 | 21 | 22 | 22 | 4 | FALSE
12949 | ST-2025-022 | 2024-01-01 | 24 | 24 | 24 | 2 | FALSE
12950 | ST-2025-022 | 2024-02-01 | 27 | 26 | 27 | 2 | TRUE
12951 | ST-2025-022 | 2024-03-01 | 30 | 28 | 29 | 2 | TRUE
12952 | ST-2025-022 | 2024-04-01 | 32 | 34 | 35 | 6 | FALSE
12953 | ST-2025-022 | 2024-05-01 | 35 | 34 | 35 | 0 | TRUE
12954 | ST-2025-022 | 2024-06-01 | 38 | 37 | 38 | 3 | TRUE
12955 | ST-2025-022 | 2024-07-01 | 41 | 42 | 43 | 5 | FALSE
12956 | ST-2025-022 | 2024-08-01 | 43 | 41 | 42 | 0 | TRUE
12957 | ST-2025-022 | 2024-09-01 | 46 | 48 | 49 | 7 | FALSE
12958 | ST-2025-022 | 2024-10-01 | 48 | 46 | 47 | 0 | TRUE
12959 | ST-2025-022 | 2024-11-01 | 49 | 48 | 49 | 2 | TRUE
12960 | ST-2025-022 | 2024-12-01 | 51 | 49 | 50 | 1 | TRUE
12961 | ST-2025-022 | 2025-01-01 | 52 | 54 | 56 | 5 | FALSE
12962 | ST-2025-022 | 2025-02-01 | 54 | 54 | 56 | 0 | FALSE
12963 | ST-2025-022 | 2025-03-01 | 55 | 53 | 55 | 0 | TRUE
12964 | ST-2025-022 | 2025-04-01 | 55 | 57 | 59 | 4 | FALSE
12965 | ST-2025-022 | 2025-05-01 | 56 | 57 | 59 | 0 | FALSE
12966 | ST-2025-022 | 2025-06-01 | 57 | 56 | 58 | 0 | TRUE
12967 | ST-2025-022 | 2025-07-01 | 57 | 59 | 60 | 3 | FALSE
12968 | ST-2025-022 | 2025-08-01 | 58 | 58 | 60 | 0 | FALSE
12969 | ST-2025-022 | 2025-09-01 | 58 | 58 | 60 | 0 | FALSE
12970 | ST-2025-022 | 2025-10-01 | 58 | 56 | 58 | 0 | TRUE
12971 | ST-2025-022 | 2025-11-01 | 58 | 57 | 59 | 1 | TRUE
12972 | ST-2025-022 | 2025-12-01 | 58 | 59 | 60 | 2 | FALSE
12973 | ST-2025-022 | 2026-01-01 | 58 | 58 | 60 | 0 | FALSE
12974 | ST-2025-022 | 2026-02-01 | 58 | 60 | 60 | 2 | FALSE
12975 | ST-2025-022 | 2026-03-01 | 58 | 56 | 58 | 0 | TRUE
12976 | ST-2025-023 | 2022-04-01 | 30 | 27 | 28 | 27 | TRUE
12977 | ST-2025-023 | 2022-05-01 | 34 | 30 | 31 | 3 | TRUE
12978 | ST-2025-023 | 2022-06-01 | 39 | 33 | 34 | 3 | TRUE
12979 | ST-2025-023 | 2022-07-01 | 45 | 39 | 40 | 6 | TRUE
12980 | ST-2025-023 | 2022-08-01 | 51 | 44 | 45 | 5 | TRUE
12981 | ST-2025-023 | 2022-09-01 | 58 | 53 | 55 | 9 | TRUE
12982 | ST-2025-023 | 2022-10-01 | 65 | 57 | 59 | 4 | TRUE
12983 | ST-2025-023 | 2022-11-01 | 74 | 62 | 64 | 5 | TRUE
12984 | ST-2025-023 | 2022-12-01 | 84 | 73 | 75 | 11 | TRUE
12985 | ST-2025-023 | 2023-01-01 | 95 | 84 | 87 | 11 | TRUE
12986 | ST-2025-023 | 2023-02-01 | 107 | 95 | 98 | 11 | TRUE
12987 | ST-2025-023 | 2023-03-01 | 121 | 110 | 114 | 15 | TRUE
12988 | ST-2025-023 | 2023-04-01 | 137 | 129 | 134 | 19 | TRUE
12989 | ST-2025-023 | 2023-05-01 | 154 | 133 | 138 | 4 | TRUE
12990 | ST-2025-023 | 2023-06-01 | 173 | 152 | 158 | 19 | TRUE
12991 | ST-2025-023 | 2023-07-01 | 194 | 180 | 187 | 28 | TRUE
12992 | ST-2025-023 | 2023-08-01 | 218 | 201 | 209 | 21 | TRUE
12993 | ST-2025-023 | 2023-09-01 | 243 | 228 | 237 | 27 | TRUE
12994 | ST-2025-023 | 2023-10-01 | 271 | 254 | 264 | 26 | TRUE
12995 | ST-2025-023 | 2023-11-01 | 302 | 274 | 284 | 20 | TRUE
12996 | ST-2025-023 | 2023-12-01 | 335 | 296 | 307 | 22 | TRUE
12997 | ST-2025-023 | 2024-01-01 | 370 | 317 | 329 | 21 | TRUE
12998 | ST-2025-023 | 2024-02-01 | 408 | 361 | 375 | 44 | TRUE
12999 | ST-2025-023 | 2024-03-01 | 448 | 389 | 404 | 28 | TRUE
13000 | ST-2025-023 | 2024-04-01 | 490 | 437 | 454 | 48 | TRUE
13001 | ST-2025-023 | 2024-05-01 | 534 | 474 | 492 | 37 | TRUE
13002 | ST-2025-023 | 2024-06-01 | 580 | 508 | 528 | 34 | TRUE
13003 | ST-2025-023 | 2024-07-01 | 628 | 570 | 592 | 62 | TRUE
13004 | ST-2025-023 | 2024-08-01 | 676 | 579 | 602 | 9 | TRUE
13005 | ST-2025-023 | 2024-09-01 | 725 | 646 | 671 | 67 | TRUE
13006 | ST-2025-023 | 2024-10-01 | 774 | 685 | 712 | 39 | TRUE
13007 | ST-2025-023 | 2024-11-01 | 823 | 714 | 742 | 29 | TRUE
13008 | ST-2025-023 | 2024-12-01 | 871 | 794 | 825 | 80 | TRUE
13009 | ST-2025-023 | 2025-01-01 | 919 | 788 | 819 | 0 | TRUE
13010 | ST-2025-023 | 2025-02-01 | 965 | 868 | 902 | 80 | TRUE
13011 | ST-2025-023 | 2025-03-01 | 1009 | 955 | 993 | 87 | TRUE
13012 | ST-2025-023 | 2025-04-01 | 1051 | 963 | 1001 | 8 | TRUE
13013 | ST-2025-023 | 2025-05-01 | 1091 | 997 | 1036 | 34 | TRUE
13014 | ST-2025-023 | 2025-06-01 | 1129 | 1039 | 1080 | 42 | TRUE
13015 | ST-2025-023 | 2025-07-01 | 1164 | 1096 | 1139 | 57 | TRUE
13016 | ST-2025-023 | 2025-08-01 | 1197 | 1079 | 1122 | 0 | TRUE
13017 | ST-2025-023 | 2025-09-01 | 1228 | 1122 | 1166 | 43 | TRUE
13018 | ST-2025-023 | 2025-10-01 | 1256 | 1076 | 1119 | 0 | TRUE
13019 | ST-2025-023 | 2025-11-01 | 1281 | 1147 | 1192 | 71 | TRUE
13020 | ST-2025-023 | 2025-12-01 | 1305 | 1118 | 1162 | 0 | TRUE
13021 | ST-2025-023 | 2026-01-01 | 1326 | 1232 | 1281 | 114 | TRUE
13022 | ST-2025-023 | 2026-02-01 | 1345 | 1182 | 1229 | 0 | TRUE
13023 | ST-2025-023 | 2026-03-01 | 1362 | 1290 | 1341 | 108 | TRUE
13024 | ST-2025-023 | 2026-04-01 | 1378 | 1264 | 1314 | 0 | TRUE
13025 | ST-2025-023 | 2026-05-01 | 1392 | 1223 | 1271 | 0 | TRUE
13026 | ST-2025-023 | 2026-06-01 | 1404 |  | 1351 |  | FALSE
13027 | ST-2025-023 | 2026-07-01 | 1415 |  | 1362 |  | FALSE
13028 | ST-2025-023 | 2026-08-01 | 1425 |  | 1372 |  | FALSE
13029 | ST-2025-023 | 2026-09-01 | 1434 |  | 1380 |  | FALSE
13030 | ST-2025-023 | 2026-10-01 | 1441 |  | 1387 |  | FALSE
13031 | ST-2025-023 | 2026-11-01 | 1448 |  | 1394 |  | FALSE
13032 | ST-2025-023 | 2026-12-01 | 1454 |  | 1399 |  | FALSE
13033 | ST-2025-023 | 2027-01-01 | 1460 |  | 1405 |  | FALSE
13034 | ST-2025-023 | 2027-02-01 | 1465 |  | 1410 |  | FALSE
13035 | ST-2025-023 | 2027-03-01 | 1469 |  | 1414 |  | FALSE
13036 | ST-2025-023 | 2027-04-01 | 1473 |  | 1418 |  | FALSE
13037 | ST-2025-023 | 2027-05-01 | 1473 |  | 1418 |  | FALSE
13038 | ST-2025-023 | 2027-06-01 | 1473 |  | 1418 |  | FALSE
13039 | ST-2025-023 | 2027-07-01 | 1473 |  | 1418 |  | FALSE
13040 | ST-2025-024 | 2025-01-01 | 5 | 3 | 3 | 3 | TRUE
13041 | ST-2025-024 | 2025-02-01 | 7 | 5 | 5 | 2 | TRUE
13042 | ST-2025-024 | 2025-03-01 | 10 | 6 | 6 | 1 | TRUE
13043 | ST-2025-024 | 2025-04-01 | 14 | 10 | 10 | 4 | TRUE
13044 | ST-2025-024 | 2025-05-01 | 19 | 13 | 13 | 3 | TRUE
13045 | ST-2025-024 | 2025-06-01 | 26 | 18 | 18 | 5 | TRUE
13046 | ST-2025-024 | 2025-07-01 | 34 | 23 | 23 | 5 | TRUE
13047 | ST-2025-024 | 2025-08-01 | 45 | 31 | 32 | 8 | TRUE
13048 | ST-2025-024 | 2025-09-01 | 59 | 40 | 41 | 9 | TRUE
13049 | ST-2025-024 | 2025-10-01 | 74 | 54 | 56 | 14 | TRUE
13050 | ST-2025-024 | 2025-11-01 | 91 | 68 | 70 | 14 | TRUE
13051 | ST-2025-024 | 2025-12-01 | 110 | 78 | 81 | 10 | TRUE
13052 | ST-2025-024 | 2026-01-01 | 128 | 94 | 97 | 16 | TRUE
13053 | ST-2025-024 | 2026-02-01 | 145 | 107 | 111 | 13 | TRUE
13054 | ST-2025-024 | 2026-03-01 | 160 | 111 | 115 | 4 | TRUE
13055 | ST-2025-024 | 2026-04-01 | 174 | 133 | 138 | 22 | TRUE
13056 | ST-2025-024 | 2026-05-01 | 185 | 135 | 140 | 2 | TRUE
13057 | ST-2025-024 | 2026-06-01 | 193 |  | 173 |  | FALSE
13058 | ST-2025-024 | 2026-07-01 | 200 |  | 180 |  | FALSE
13059 | ST-2025-024 | 2026-08-01 | 205 |  | 184 |  | FALSE
13060 | ST-2025-024 | 2026-09-01 | 209 |  | 188 |  | FALSE
13061 | ST-2025-024 | 2026-10-01 | 212 |  | 190 |  | FALSE
13062 | ST-2025-024 | 2026-11-01 | 214 |  | 192 |  | FALSE
13063 | ST-2025-024 | 2026-12-01 | 216 |  | 194 |  | FALSE
13064 | ST-2025-024 | 2027-01-01 | 216 |  | 194 |  | FALSE
13065 | ST-2025-024 | 2027-02-01 | 216 |  | 194 |  | FALSE
13066 | ST-2025-024 | 2027-03-01 | 216 |  | 194 |  | FALSE
13067 | ST-2025-025 | 2026-09-01 | 0 |  | 0 |  | FALSE
13068 | ST-2025-025 | 2026-10-01 | 0 |  | 0 |  | FALSE
13069 | ST-2025-025 | 2026-11-01 | 0 |  | 0 |  | FALSE
13070 | ST-2025-025 | 2026-12-01 | 0 |  | 0 |  | FALSE
13071 | ST-2025-025 | 2027-01-01 | 0 |  | 0 |  | FALSE
13072 | ST-2025-025 | 2027-02-01 | 0 |  | 0 |  | FALSE
13073 | ST-2025-025 | 2027-03-01 | 0 |  | 0 |  | FALSE
13074 | ST-2025-025 | 2027-04-01 | 0 |  | 0 |  | FALSE
13075 | ST-2025-025 | 2027-05-01 | 0 |  | 0 |  | FALSE
13076 | ST-2025-025 | 2027-06-01 | 1 |  | 1 |  | FALSE
13077 | ST-2025-025 | 2027-07-01 | 1 |  | 1 |  | FALSE
13078 | ST-2025-025 | 2027-08-01 | 1 |  | 1 |  | FALSE
13079 | ST-2025-025 | 2027-09-01 | 1 |  | 1 |  | FALSE
13080 | ST-2025-025 | 2027-10-01 | 2 |  | 2 |  | FALSE
13081 | ST-2025-025 | 2027-11-01 | 2 |  | 2 |  | FALSE
13082 | ST-2025-025 | 2027-12-01 | 2 |  | 2 |  | FALSE
13083 | ST-2025-025 | 2028-01-01 | 3 |  | 3 |  | FALSE
13084 | ST-2025-025 | 2028-02-01 | 3 |  | 3 |  | FALSE
13085 | ST-2025-025 | 2028-03-01 | 3 |  | 3 |  | FALSE
13086 | ST-2025-025 | 2028-04-01 | 4 |  | 4 |  | FALSE
13087 | ST-2025-025 | 2028-05-01 | 4 |  | 4 |  | FALSE
13088 | ST-2025-025 | 2028-06-01 | 4 |  | 4 |  | FALSE
13089 | ST-2025-025 | 2028-07-01 | 4 |  | 4 |  | FALSE
13090 | ST-2025-025 | 2028-08-01 | 5 |  | 5 |  | FALSE
13091 | ST-2025-025 | 2028-09-01 | 5 |  | 5 |  | FALSE
13092 | ST-2025-025 | 2028-10-01 | 5 |  | 5 |  | FALSE
13093 | ST-2025-025 | 2028-11-01 | 5 |  | 5 |  | FALSE
13094 | ST-2025-025 | 2028-12-01 | 5 |  | 5 |  | FALSE
13095 | ST-2025-025 | 2029-01-01 | 5 |  | 5 |  | FALSE
13096 | ST-2025-025 | 2029-02-01 | 5 |  | 5 |  | FALSE
13097 | ST-2025-025 | 2029-03-01 | 5 |  | 5 |  | FALSE
13098 | ST-2025-025 | 2029-04-01 | 5 |  | 5 |  | FALSE
13099 | ST-2025-025 | 2029-05-01 | 5 |  | 5 |  | FALSE
13100 | ST-2025-025 | 2029-06-01 | 5 |  | 5 |  | FALSE
13101 | ST-2025-025 | 2029-07-01 | 5 |  | 5 |  | FALSE
13102 | ST-2025-025 | 2029-08-01 | 5 |  | 5 |  | FALSE
13103 | ST-2025-025 | 2029-09-01 | 5 |  | 5 |  | FALSE
13104 | ST-2025-026 | 2020-11-01 | 5 | 3 | 3 | 3 | TRUE
13105 | ST-2025-026 | 2020-12-01 | 5 | 3 | 3 | 0 | TRUE
13106 | ST-2025-026 | 2021-01-01 | 5 | 3 | 3 | 0 | TRUE
13107 | ST-2025-026 | 2021-02-01 | 6 | 3 | 3 | 0 | TRUE
13108 | ST-2025-026 | 2021-03-01 | 6 | 3 | 3 | 0 | TRUE
13109 | ST-2025-026 | 2021-04-01 | 7 | 4 | 4 | 1 | TRUE
13110 | ST-2025-026 | 2021-05-01 | 8 | 5 | 5 | 1 | TRUE
13111 | ST-2025-026 | 2021-06-01 | 8 | 5 | 5 | 0 | TRUE
13112 | ST-2025-026 | 2021-07-01 | 9 | 5 | 5 | 0 | TRUE
13113 | ST-2025-026 | 2021-08-01 | 10 | 6 | 6 | 1 | TRUE
13114 | ST-2025-026 | 2021-09-01 | 11 | 7 | 7 | 1 | TRUE
13115 | ST-2025-026 | 2021-10-01 | 12 | 7 | 7 | 0 | TRUE
13116 | ST-2025-026 | 2021-11-01 | 13 | 8 | 8 | 1 | TRUE
13117 | ST-2025-026 | 2021-12-01 | 14 | 9 | 9 | 1 | TRUE
13118 | ST-2025-026 | 2022-01-01 | 15 | 10 | 10 | 1 | TRUE
13119 | ST-2025-026 | 2022-02-01 | 16 | 10 | 10 | 0 | TRUE
13120 | ST-2025-026 | 2022-03-01 | 18 | 12 | 12 | 2 | TRUE
13121 | ST-2025-026 | 2022-04-01 | 19 | 13 | 13 | 1 | TRUE
13122 | ST-2025-026 | 2022-05-01 | 20 | 12 | 12 | 0 | TRUE
13123 | ST-2025-026 | 2022-06-01 | 22 | 15 | 15 | 3 | TRUE
13124 | ST-2025-026 | 2022-07-01 | 24 | 15 | 15 | 0 | TRUE
13125 | ST-2025-026 | 2022-08-01 | 26 | 18 | 18 | 3 | TRUE
13126 | ST-2025-026 | 2022-09-01 | 28 | 18 | 18 | 0 | TRUE
13127 | ST-2025-026 | 2022-10-01 | 30 | 19 | 19 | 1 | TRUE
13128 | ST-2025-026 | 2022-11-01 | 32 | 21 | 21 | 2 | TRUE
13129 | ST-2025-026 | 2022-12-01 | 35 | 22 | 22 | 1 | TRUE
13130 | ST-2025-026 | 2023-01-01 | 37 | 24 | 24 | 2 | TRUE
13131 | ST-2025-026 | 2023-02-01 | 40 | 26 | 27 | 2 | TRUE
13132 | ST-2025-026 | 2023-03-01 | 43 | 27 | 28 | 1 | TRUE
13133 | ST-2025-026 | 2023-04-01 | 46 | 31 | 32 | 4 | TRUE
13134 | ST-2025-026 | 2023-05-01 | 49 | 32 | 33 | 1 | TRUE
13135 | ST-2025-026 | 2023-06-01 | 53 | 36 | 37 | 4 | TRUE
13136 | ST-2025-026 | 2023-07-01 | 56 | 36 | 37 | 0 | TRUE
13137 | ST-2025-026 | 2023-08-01 | 60 | 37 | 38 | 1 | TRUE
13138 | ST-2025-026 | 2023-09-01 | 64 | 44 | 45 | 7 | TRUE
13139 | ST-2025-026 | 2023-10-01 | 68 | 44 | 45 | 0 | TRUE
13140 | ST-2025-026 | 2023-11-01 | 72 | 47 | 48 | 3 | TRUE
13141 | ST-2025-026 | 2023-12-01 | 76 | 50 | 52 | 3 | TRUE
13142 | ST-2025-026 | 2024-01-01 | 81 | 51 | 53 | 1 | TRUE
13143 | ST-2025-026 | 2024-02-01 | 86 | 56 | 58 | 5 | TRUE
13144 | ST-2025-026 | 2024-03-01 | 91 | 58 | 60 | 2 | TRUE
13145 | ST-2025-026 | 2024-04-01 | 95 | 61 | 63 | 3 | TRUE
13146 | ST-2025-026 | 2024-05-01 | 101 | 67 | 69 | 6 | TRUE
13147 | ST-2025-026 | 2024-06-01 | 106 | 70 | 72 | 3 | TRUE
13148 | ST-2025-026 | 2024-07-01 | 111 | 72 | 74 | 2 | TRUE
13149 | ST-2025-026 | 2024-08-01 | 116 | 78 | 81 | 6 | TRUE
13150 | ST-2025-026 | 2024-09-01 | 121 | 77 | 80 | 0 | TRUE
13151 | ST-2025-026 | 2024-10-01 | 127 | 87 | 90 | 10 | TRUE
13152 | ST-2025-026 | 2024-11-01 | 132 | 82 | 85 | 0 | TRUE
13153 | ST-2025-026 | 2024-12-01 | 138 | 95 | 98 | 13 | TRUE
13154 | ST-2025-026 | 2025-01-01 | 143 | 97 | 100 | 2 | TRUE
13155 | ST-2025-026 | 2025-02-01 | 148 | 96 | 99 | 0 | TRUE
13156 | ST-2025-026 | 2025-03-01 | 153 | 100 | 104 | 4 | TRUE
13157 | ST-2025-026 | 2025-04-01 | 158 | 103 | 107 | 3 | TRUE
13158 | ST-2025-026 | 2025-05-01 | 164 | 107 | 111 | 4 | TRUE
13159 | ST-2025-026 | 2025-06-01 | 168 | 114 | 118 | 7 | TRUE
13160 | ST-2025-026 | 2025-07-01 | 173 | 113 | 117 | 0 | TRUE
13161 | ST-2025-026 | 2025-08-01 | 178 | 115 | 119 | 2 | TRUE
13162 | ST-2025-026 | 2025-09-01 | 183 | 127 | 132 | 12 | TRUE
13163 | ST-2025-026 | 2025-10-01 | 187 | 117 | 121 | 0 | TRUE
13164 | ST-2025-026 | 2025-11-01 | 191 | 131 | 136 | 14 | TRUE
13165 | ST-2025-026 | 2025-12-01 | 195 | 136 | 141 | 5 | TRUE
13166 | ST-2025-026 | 2026-01-01 | 199 | 126 | 131 | 0 | TRUE
13167 | ST-2025-026 | 2026-02-01 | 203 | 140 | 145 | 14 | TRUE
13168 | ST-2025-026 | 2026-03-01 | 206 | 131 | 136 | 0 | TRUE
13169 | ST-2025-026 | 2026-04-01 | 210 | 143 | 148 | 12 | TRUE
13170 | ST-2025-026 | 2026-05-01 | 213 | 148 | 153 | 5 | TRUE
13171 | ST-2025-026 | 2026-06-01 | 216 |  | 194 |  | FALSE
13172 | ST-2025-026 | 2026-07-01 | 219 |  | 197 |  | FALSE
13173 | ST-2025-026 | 2026-08-01 | 222 |  | 199 |  | FALSE
13174 | ST-2025-026 | 2026-09-01 | 224 |  | 201 |  | FALSE
13175 | ST-2025-026 | 2026-10-01 | 227 |  | 204 |  | FALSE
13176 | ST-2025-026 | 2026-11-01 | 229 |  | 206 |  | FALSE
13177 | ST-2025-026 | 2026-12-01 | 231 |  | 207 |  | FALSE
13178 | ST-2025-026 | 2027-01-01 | 233 |  | 209 |  | FALSE
13179 | ST-2025-026 | 2027-02-01 | 235 |  | 211 |  | FALSE
13180 | ST-2025-026 | 2027-03-01 | 237 |  | 213 |  | FALSE
13181 | ST-2025-026 | 2027-04-01 | 239 |  | 215 |  | FALSE
13182 | ST-2025-026 | 2027-05-01 | 240 |  | 216 |  | FALSE
13183 | ST-2025-026 | 2027-06-01 | 241 |  | 216 |  | FALSE
13184 | ST-2025-026 | 2027-07-01 | 243 |  | 218 |  | FALSE
13185 | ST-2025-026 | 2027-08-01 | 244 |  | 219 |  | FALSE
13186 | ST-2025-026 | 2027-09-01 | 245 |  | 220 |  | FALSE
13187 | ST-2025-026 | 2027-10-01 | 246 |  | 221 |  | FALSE
13188 | ST-2025-026 | 2027-11-01 | 247 |  | 222 |  | FALSE
13189 | ST-2025-026 | 2027-12-01 | 248 |  | 223 |  | FALSE
13190 | ST-2025-026 | 2028-01-01 | 249 |  | 224 |  | FALSE
13191 | ST-2025-026 | 2028-02-01 | 250 |  | 225 |  | FALSE
13192 | ST-2025-026 | 2028-03-01 | 251 |  | 225 |  | FALSE
13193 | ST-2025-026 | 2028-04-01 | 251 |  | 225 |  | FALSE
13194 | ST-2025-026 | 2028-05-01 | 252 |  | 226 |  | FALSE
13195 | ST-2025-026 | 2028-06-01 | 253 |  | 227 |  | FALSE
13196 | ST-2025-026 | 2028-07-01 | 253 |  | 227 |  | FALSE
13197 | ST-2025-026 | 2028-08-01 | 254 |  | 228 |  | FALSE
13198 | ST-2025-026 | 2028-09-01 | 254 |  | 228 |  | FALSE
13199 | ST-2025-026 | 2028-10-01 | 254 |  | 228 |  | FALSE
13200 | ST-2025-026 | 2028-11-01 | 255 |  | 229 |  | FALSE
13201 | ST-2025-026 | 2028-12-01 | 255 |  | 229 |  | FALSE
13202 | ST-2025-026 | 2029-01-01 | 255 |  | 229 |  | FALSE
13203 | ST-2025-027 | 2023-03-01 | 1 | 0 | 0 | 0 | TRUE
13204 | ST-2025-027 | 2023-04-01 | 2 | 1 | 1 | 1 | TRUE
13205 | ST-2025-027 | 2023-05-01 | 2 | 1 | 1 | 0 | TRUE
13206 | ST-2025-027 | 2023-06-01 | 3 | 3 | 3 | 2 | FALSE
13207 | ST-2025-027 | 2023-07-01 | 3 | 2 | 2 | 0 | TRUE
13208 | ST-2025-027 | 2023-08-01 | 4 | 4 | 4 | 2 | FALSE
13209 | ST-2025-027 | 2023-09-01 | 5 | 4 | 4 | 0 | TRUE
13210 | ST-2025-027 | 2023-10-01 | 6 | 5 | 5 | 1 | TRUE
13211 | ST-2025-027 | 2023-11-01 | 8 | 7 | 7 | 2 | TRUE
13212 | ST-2025-027 | 2023-12-01 | 9 | 9 | 9 | 2 | FALSE
13213 | ST-2025-027 | 2024-01-01 | 11 | 11 | 11 | 2 | FALSE
13214 | ST-2025-027 | 2024-02-01 | 13 | 12 | 12 | 1 | TRUE
13215 | ST-2025-027 | 2024-03-01 | 15 | 14 | 14 | 2 | TRUE
13216 | ST-2025-027 | 2024-04-01 | 18 | 16 | 16 | 2 | TRUE
13217 | ST-2025-027 | 2024-05-01 | 21 | 20 | 20 | 4 | TRUE
13218 | ST-2025-027 | 2024-06-01 | 24 | 22 | 22 | 2 | TRUE
13219 | ST-2025-027 | 2024-07-01 | 28 | 28 | 29 | 6 | FALSE
13220 | ST-2025-027 | 2024-08-01 | 31 | 31 | 32 | 3 | FALSE
13221 | ST-2025-027 | 2024-09-01 | 35 | 34 | 35 | 3 | TRUE
13222 | ST-2025-027 | 2024-10-01 | 39 | 37 | 38 | 3 | TRUE
13223 | ST-2025-027 | 2024-11-01 | 44 | 43 | 44 | 6 | TRUE
13224 | ST-2025-027 | 2024-12-01 | 48 | 47 | 48 | 4 | TRUE
13225 | ST-2025-027 | 2025-01-01 | 52 | 47 | 48 | 0 | TRUE
13226 | ST-2025-027 | 2025-02-01 | 56 | 51 | 53 | 4 | TRUE
13227 | ST-2025-027 | 2025-03-01 | 59 | 54 | 56 | 3 | TRUE
13228 | ST-2025-027 | 2025-04-01 | 63 | 63 | 65 | 9 | FALSE
13229 | ST-2025-027 | 2025-05-01 | 66 | 61 | 63 | 0 | TRUE
13230 | ST-2025-027 | 2025-06-01 | 69 | 64 | 66 | 3 | TRUE
13231 | ST-2025-027 | 2025-07-01 | 72 | 70 | 72 | 6 | TRUE
13232 | ST-2025-027 | 2025-08-01 | 74 | 72 | 74 | 2 | TRUE
13233 | ST-2025-027 | 2025-09-01 | 76 | 71 | 73 | 0 | TRUE
13234 | ST-2025-027 | 2025-10-01 | 78 | 77 | 80 | 6 | TRUE
13235 | ST-2025-027 | 2025-11-01 | 79 | 75 | 78 | 0 | TRUE
13236 | ST-2025-027 | 2025-12-01 | 81 | 78 | 81 | 3 | TRUE
13237 | ST-2025-027 | 2026-01-01 | 82 | 77 | 80 | 0 | TRUE
13238 | ST-2025-027 | 2026-02-01 | 83 | 81 | 84 | 4 | TRUE
13239 | ST-2025-027 | 2026-03-01 | 84 | 78 | 81 | 0 | TRUE
13240 | ST-2025-027 | 2026-04-01 | 84 | 80 | 83 | 2 | TRUE
13241 | ST-2025-027 | 2026-05-01 | 85 | 86 | 88 | 6 | FALSE
13242 | ST-2025-027 | 2026-06-01 | 85 |  | 87 |  | FALSE
13243 | ST-2025-027 | 2026-07-01 | 86 |  | 88 |  | FALSE
13244 | ST-2025-027 | 2026-08-01 | 86 |  | 88 |  | FALSE
13245 | ST-2025-027 | 2026-09-01 | 86 |  | 88 |  | FALSE
13246 | ST-2025-027 | 2026-10-01 | 86 |  | 88 |  | FALSE
13247 | ST-2025-027 | 2026-11-01 | 86 |  | 88 |  | FALSE
13248 | ST-2025-028 | 2025-10-01 | 1520 | 1384 | 1439 | 1384 | TRUE
13249 | ST-2025-028 | 2025-11-01 | 1888 | 1873 | 1947 | 489 | TRUE
13250 | ST-2025-028 | 2025-12-01 | 2342 | 2103 | 2187 | 230 | TRUE
13251 | ST-2025-028 | 2026-01-01 | 2900 | 2728 | 2837 | 625 | TRUE
13252 | ST-2025-028 | 2026-02-01 | 3583 | 3264 | 3394 | 536 | TRUE
13253 | ST-2025-028 | 2026-03-01 | 4417 | 4262 | 4432 | 998 | TRUE
13254 | ST-2025-028 | 2026-04-01 | 5429 | 4992 | 5191 | 730 | TRUE
13255 | ST-2025-028 | 2026-05-01 | 6648 | 6573 | 6835 | 1581 | TRUE
13256 | ST-2025-028 | 2026-06-01 | 8105 |  | 8210 |  | FALSE
13257 | ST-2025-028 | 2026-07-01 | 9831 |  | 9959 |  | FALSE
13258 | ST-2025-028 | 2026-08-01 | 11851 |  | 12005 |  | FALSE
13259 | ST-2025-028 | 2026-09-01 | 14185 |  | 14369 |  | FALSE
13260 | ST-2025-028 | 2026-10-01 | 16841 |  | 17060 |  | FALSE
13261 | ST-2025-028 | 2026-11-01 | 19811 |  | 20069 |  | FALSE
13262 | ST-2025-028 | 2026-12-01 | 23068 |  | 23368 |  | FALSE
13263 | ST-2025-028 | 2027-01-01 | 26566 |  | 26912 |  | FALSE
13264 | ST-2025-028 | 2027-02-01 | 30237 |  | 30631 |  | FALSE
13265 | ST-2025-028 | 2027-03-01 | 34000 |  | 34443 |  | FALSE
13266 | ST-2025-028 | 2027-04-01 | 37762 |  | 38254 |  | FALSE
13267 | ST-2025-028 | 2027-05-01 | 41433 |  | 41973 |  | FALSE
13268 | ST-2025-028 | 2027-06-01 | 44931 |  | 45516 |  | FALSE
13269 | ST-2025-028 | 2027-07-01 | 48188 |  | 48816 |  | FALSE
13270 | ST-2025-028 | 2027-08-01 | 51158 |  | 51825 |  | FALSE
13271 | ST-2025-028 | 2027-09-01 | 53814 |  | 54515 |  | FALSE
13272 | ST-2025-028 | 2027-10-01 | 56148 |  | 56880 |  | FALSE
13273 | ST-2025-028 | 2027-11-01 | 58168 |  | 58926 |  | FALSE
13274 | ST-2025-028 | 2027-12-01 | 59894 |  | 60675 |  | FALSE
13275 | ST-2025-028 | 2028-01-01 | 61351 |  | 62151 |  | FALSE
13276 | ST-2025-028 | 2028-02-01 | 62570 |  | 63385 |  | FALSE
13277 | ST-2025-028 | 2028-03-01 | 63582 |  | 64411 |  | FALSE
13278 | ST-2025-028 | 2028-04-01 | 64416 |  | 65256 |  | FALSE
13279 | ST-2025-028 | 2028-05-01 | 65099 |  | 65947 |  | FALSE
13280 | ST-2025-028 | 2028-06-01 | 65657 |  | 66513 |  | FALSE
13281 | ST-2025-028 | 2028-07-01 | 66111 |  | 66973 |  | FALSE
13282 | ST-2025-028 | 2028-08-01 | 66479 |  | 67345 |  | FALSE
13283 | ST-2025-028 | 2028-09-01 | 66776 |  | 67646 |  | FALSE
13284 | ST-2025-028 | 2028-10-01 | 66776 |  | 67646 |  | FALSE
13285 | ST-2025-028 | 2028-11-01 | 66776 |  | 67646 |  | FALSE
13286 | ST-2025-028 | 2028-12-01 | 66776 |  | 67646 |  | FALSE
13287 | ST-2025-029 | 2024-07-01 | 4 | 2 | 2 | 2 | TRUE
13288 | ST-2025-029 | 2024-08-01 | 6 | 3 | 3 | 1 | TRUE
13289 | ST-2025-029 | 2024-09-01 | 8 | 5 | 5 | 2 | TRUE
13290 | ST-2025-029 | 2024-10-01 | 11 | 6 | 6 | 1 | TRUE
13291 | ST-2025-029 | 2024-11-01 | 15 | 9 | 9 | 3 | TRUE
13292 | ST-2025-029 | 2024-12-01 | 20 | 12 | 12 | 3 | TRUE
13293 | ST-2025-029 | 2025-01-01 | 27 | 15 | 15 | 3 | TRUE
13294 | ST-2025-029 | 2025-02-01 | 35 | 20 | 20 | 5 | TRUE
13295 | ST-2025-029 | 2025-03-01 | 45 | 28 | 29 | 8 | TRUE
13296 | ST-2025-029 | 2025-04-01 | 56 | 34 | 35 | 6 | TRUE
13297 | ST-2025-029 | 2025-05-01 | 70 | 42 | 43 | 8 | TRUE
13298 | ST-2025-029 | 2025-06-01 | 84 | 52 | 54 | 10 | TRUE
13299 | ST-2025-029 | 2025-07-01 | 100 | 57 | 59 | 5 | TRUE
13300 | ST-2025-029 | 2025-08-01 | 115 | 68 | 70 | 11 | TRUE
13301 | ST-2025-029 | 2025-09-01 | 129 | 82 | 85 | 14 | TRUE
13302 | ST-2025-029 | 2025-10-01 | 143 | 82 | 85 | 0 | TRUE
13303 | ST-2025-029 | 2025-11-01 | 154 | 92 | 95 | 10 | TRUE
13304 | ST-2025-029 | 2025-12-01 | 164 | 97 | 100 | 5 | TRUE
13305 | ST-2025-029 | 2026-01-01 | 172 | 103 | 107 | 6 | TRUE
13306 | ST-2025-029 | 2026-02-01 | 179 | 105 | 109 | 2 | TRUE
13307 | ST-2025-029 | 2026-03-01 | 184 | 115 | 119 | 10 | TRUE
13308 | ST-2025-029 | 2026-04-01 | 188 | 117 | 121 | 2 | TRUE
13309 | ST-2025-029 | 2026-05-01 | 191 | 122 | 126 | 5 | TRUE
13310 | ST-2025-029 | 2026-06-01 | 193 |  | 173 |  | FALSE
13311 | ST-2025-029 | 2026-07-01 | 195 |  | 175 |  | FALSE
13312 | ST-2025-029 | 2026-08-01 | 196 |  | 176 |  | FALSE
13313 | ST-2025-029 | 2026-09-01 | 196 |  | 176 |  | FALSE
13314 | ST-2025-029 | 2026-10-01 | 196 |  | 176 |  | FALSE
13315 | ST-2025-029 | 2026-11-01 | 196 |  | 176 |  | FALSE
13316 | ST-2025-029 | 2026-12-01 | 196 |  | 176 |  | FALSE
13317 | ST-2025-030 | 2024-04-01 | 32 | 21 | 21 | 21 | TRUE
13318 | ST-2025-030 | 2024-05-01 | 43 | 31 | 32 | 10 | TRUE
13319 | ST-2025-030 | 2024-06-01 | 56 | 40 | 41 | 9 | TRUE
13320 | ST-2025-030 | 2024-07-01 | 73 | 49 | 50 | 9 | TRUE
13321 | ST-2025-030 | 2024-08-01 | 94 | 64 | 66 | 15 | TRUE
13322 | ST-2025-030 | 2024-09-01 | 122 | 85 | 88 | 21 | TRUE
13323 | ST-2025-030 | 2024-10-01 | 157 | 113 | 117 | 28 | TRUE
13324 | ST-2025-030 | 2024-11-01 | 199 | 144 | 149 | 31 | TRUE
13325 | ST-2025-030 | 2024-12-01 | 251 | 174 | 180 | 30 | TRUE
13326 | ST-2025-030 | 2025-01-01 | 313 | 213 | 221 | 39 | TRUE
13327 | ST-2025-030 | 2025-02-01 | 386 | 255 | 265 | 42 | TRUE
13328 | ST-2025-030 | 2025-03-01 | 467 | 334 | 347 | 79 | TRUE
13329 | ST-2025-030 | 2025-04-01 | 557 | 382 | 397 | 48 | TRUE
13330 | ST-2025-030 | 2025-05-01 | 651 | 434 | 451 | 52 | TRUE
13331 | ST-2025-030 | 2025-06-01 | 748 | 502 | 522 | 68 | TRUE
13332 | ST-2025-030 | 2025-07-01 | 842 | 563 | 585 | 61 | TRUE
13333 | ST-2025-030 | 2025-08-01 | 932 | 635 | 660 | 72 | TRUE
13334 | ST-2025-030 | 2025-09-01 | 1013 | 672 | 698 | 37 | TRUE
13335 | ST-2025-030 | 2025-10-01 | 1086 | 735 | 764 | 63 | TRUE
13336 | ST-2025-030 | 2025-11-01 | 1148 | 750 | 780 | 15 | TRUE
13337 | ST-2025-030 | 2025-12-01 | 1200 | 847 | 880 | 97 | TRUE
13338 | ST-2025-030 | 2026-01-01 | 1242 | 879 | 914 | 32 | TRUE
13339 | ST-2025-030 | 2026-02-01 | 1277 | 854 | 888 | 0 | TRUE
13340 | ST-2025-030 | 2026-03-01 | 1305 | 909 | 945 | 55 | TRUE
13341 | ST-2025-030 | 2026-04-01 | 1326 | 898 | 933 | 0 | TRUE
13342 | ST-2025-030 | 2026-05-01 | 1343 | 900 | 936 | 2 | TRUE
13343 | ST-2025-030 | 2026-06-01 | 1356 |  | 1220 |  | FALSE
13344 | ST-2025-030 | 2026-07-01 | 1367 |  | 1230 |  | FALSE
13345 | ST-2025-030 | 2026-08-01 | 1374 |  | 1236 |  | FALSE
13346 | ST-2025-030 | 2026-09-01 | 1374 |  | 1236 |  | FALSE
13347 | ST-2025-030 | 2026-10-01 | 1374 |  | 1236 |  | FALSE
13348 | ST-2025-030 | 2026-11-01 | 1374 |  | 1236 |  | FALSE
13349 | ST-2025-031 | 2027-01-01 | 1 |  | 1 |  | FALSE
13350 | ST-2025-031 | 2027-02-01 | 1 |  | 1 |  | FALSE
13351 | ST-2025-031 | 2027-03-01 | 2 |  | 2 |  | FALSE
13352 | ST-2025-031 | 2027-04-01 | 3 |  | 3 |  | FALSE
13353 | ST-2025-031 | 2027-05-01 | 3 |  | 3 |  | FALSE
13354 | ST-2025-031 | 2027-06-01 | 4 |  | 4 |  | FALSE
13355 | ST-2025-031 | 2027-07-01 | 5 |  | 5 |  | FALSE
13356 | ST-2025-031 | 2027-08-01 | 7 |  | 7 |  | FALSE
13357 | ST-2025-031 | 2027-09-01 | 8 |  | 8 |  | FALSE
13358 | ST-2025-031 | 2027-10-01 | 10 |  | 10 |  | FALSE
13359 | ST-2025-031 | 2027-11-01 | 13 |  | 13 |  | FALSE
13360 | ST-2025-031 | 2027-12-01 | 16 |  | 16 |  | FALSE
13361 | ST-2025-031 | 2028-01-01 | 19 |  | 19 |  | FALSE
13362 | ST-2025-031 | 2028-02-01 | 22 |  | 22 |  | FALSE
13363 | ST-2025-031 | 2028-03-01 | 26 |  | 26 |  | FALSE
13364 | ST-2025-031 | 2028-04-01 | 30 |  | 30 |  | FALSE
13365 | ST-2025-031 | 2028-05-01 | 34 |  | 34 |  | FALSE
13366 | ST-2025-031 | 2028-06-01 | 37 |  | 37 |  | FALSE
13367 | ST-2025-031 | 2028-07-01 | 41 |  | 41 |  | FALSE
13368 | ST-2025-031 | 2028-08-01 | 45 |  | 45 |  | FALSE
13369 | ST-2025-031 | 2028-09-01 | 48 |  | 48 |  | FALSE
13370 | ST-2025-031 | 2028-10-01 | 51 |  | 51 |  | FALSE
13371 | ST-2025-031 | 2028-11-01 | 54 |  | 54 |  | FALSE
13372 | ST-2025-031 | 2028-12-01 | 57 |  | 57 |  | FALSE
13373 | ST-2025-031 | 2029-01-01 | 59 |  | 59 |  | FALSE
13374 | ST-2025-031 | 2029-02-01 | 60 |  | 60 |  | FALSE
13375 | ST-2025-031 | 2029-03-01 | 62 |  | 62 |  | FALSE
13376 | ST-2025-031 | 2029-04-01 | 63 |  | 63 |  | FALSE
13377 | ST-2025-031 | 2029-05-01 | 64 |  | 64 |  | FALSE
13378 | ST-2025-031 | 2029-06-01 | 64 |  | 64 |  | FALSE
13379 | ST-2025-031 | 2029-07-01 | 65 |  | 65 |  | FALSE
13380 | ST-2025-031 | 2029-08-01 | 66 |  | 66 |  | FALSE
13381 | ST-2025-031 | 2029-09-01 | 66 |  | 66 |  | FALSE
13382 | ST-2025-031 | 2029-10-01 | 66 |  | 66 |  | FALSE
13383 | ST-2025-031 | 2029-11-01 | 66 |  | 66 |  | FALSE
13384 | ST-2025-031 | 2029-12-01 | 66 |  | 66 |  | FALSE
13385 | ST-2025-031 | 2030-01-01 | 66 |  | 66 |  | FALSE
13386 | ST-2025-031 | 2030-02-01 | 66 |  | 66 |  | FALSE
13387 | ST-2025-032 | 2025-05-01 | 6 | 5 | 5 | 5 | TRUE
13388 | ST-2025-032 | 2025-06-01 | 7 | 6 | 6 | 1 | TRUE
13389 | ST-2025-032 | 2025-07-01 | 8 | 7 | 7 | 1 | TRUE
13390 | ST-2025-032 | 2025-08-01 | 9 | 8 | 8 | 1 | TRUE
13391 | ST-2025-032 | 2025-09-01 | 10 | 9 | 9 | 1 | TRUE
13392 | ST-2025-032 | 2025-10-01 | 12 | 10 | 10 | 1 | TRUE
13393 | ST-2025-032 | 2025-11-01 | 14 | 13 | 13 | 3 | TRUE
13394 | ST-2025-032 | 2025-12-01 | 16 | 13 | 13 | 0 | TRUE
13395 | ST-2025-032 | 2026-01-01 | 18 | 16 | 16 | 3 | TRUE
13396 | ST-2025-032 | 2026-02-01 | 21 | 20 | 20 | 4 | TRUE
13397 | ST-2025-032 | 2026-03-01 | 24 | 22 | 22 | 2 | TRUE
13398 | ST-2025-032 | 2026-04-01 | 27 | 25 | 26 | 3 | TRUE
13399 | ST-2025-032 | 2026-05-01 | 31 | 28 | 29 | 3 | TRUE
13400 | ST-2025-032 | 2026-06-01 | 35 |  | 34 |  | FALSE
13401 | ST-2025-032 | 2026-07-01 | 40 |  | 39 |  | FALSE
13402 | ST-2025-032 | 2026-08-01 | 45 |  | 44 |  | FALSE
13403 | ST-2025-032 | 2026-09-01 | 51 |  | 50 |  | FALSE
13404 | ST-2025-032 | 2026-10-01 | 57 |  | 56 |  | FALSE
13405 | ST-2025-032 | 2026-11-01 | 64 |  | 62 |  | FALSE
13406 | ST-2025-032 | 2026-12-01 | 72 |  | 70 |  | FALSE
13407 | ST-2025-032 | 2027-01-01 | 80 |  | 78 |  | FALSE
13408 | ST-2025-032 | 2027-02-01 | 89 |  | 87 |  | FALSE
13409 | ST-2025-032 | 2027-03-01 | 98 |  | 96 |  | FALSE
13410 | ST-2025-032 | 2027-04-01 | 108 |  | 106 |  | FALSE
13411 | ST-2025-032 | 2027-05-01 | 118 |  | 116 |  | FALSE
13412 | ST-2025-032 | 2027-06-01 | 128 |  | 125 |  | FALSE
13413 | ST-2025-032 | 2027-07-01 | 139 |  | 136 |  | FALSE
13414 | ST-2025-032 | 2027-08-01 | 150 |  | 147 |  | FALSE
13415 | ST-2025-032 | 2027-09-01 | 160 |  | 157 |  | FALSE
13416 | ST-2025-032 | 2027-10-01 | 171 |  | 168 |  | FALSE
13417 | ST-2025-032 | 2027-11-01 | 181 |  | 178 |  | FALSE
13418 | ST-2025-032 | 2027-12-01 | 191 |  | 187 |  | FALSE
13419 | ST-2025-032 | 2028-01-01 | 201 |  | 197 |  | FALSE
13420 | ST-2025-032 | 2028-02-01 | 210 |  | 206 |  | FALSE
13421 | ST-2025-032 | 2028-03-01 | 219 |  | 215 |  | FALSE
13422 | ST-2025-032 | 2028-04-01 | 227 |  | 223 |  | FALSE
13423 | ST-2025-032 | 2028-05-01 | 235 |  | 231 |  | FALSE
13424 | ST-2025-032 | 2028-06-01 | 242 |  | 238 |  | FALSE
13425 | ST-2025-032 | 2028-07-01 | 248 |  | 244 |  | FALSE
13426 | ST-2025-032 | 2028-08-01 | 254 |  | 249 |  | FALSE
13427 | ST-2025-032 | 2028-09-01 | 259 |  | 254 |  | FALSE
13428 | ST-2025-032 | 2028-10-01 | 264 |  | 259 |  | FALSE
13429 | ST-2025-032 | 2028-11-01 | 268 |  | 263 |  | FALSE
13430 | ST-2025-032 | 2028-12-01 | 272 |  | 267 |  | FALSE
13431 | ST-2025-032 | 2029-01-01 | 275 |  | 270 |  | FALSE
13432 | ST-2025-032 | 2029-02-01 | 278 |  | 273 |  | FALSE
13433 | ST-2025-032 | 2029-03-01 | 281 |  | 276 |  | FALSE
13434 | ST-2025-032 | 2029-04-01 | 283 |  | 278 |  | FALSE
13435 | ST-2025-032 | 2029-05-01 | 285 |  | 280 |  | FALSE
13436 | ST-2025-032 | 2029-06-01 | 287 |  | 282 |  | FALSE
13437 | ST-2025-032 | 2029-07-01 | 289 |  | 284 |  | FALSE
13438 | ST-2025-032 | 2029-08-01 | 290 |  | 285 |  | FALSE
13439 | ST-2025-032 | 2029-09-01 | 291 |  | 286 |  | FALSE
13440 | ST-2025-032 | 2029-10-01 | 292 |  | 287 |  | FALSE
13441 | ST-2025-032 | 2029-11-01 | 293 |  | 288 |  | FALSE
13442 | ST-2025-032 | 2029-12-01 | 294 |  | 289 |  | FALSE
13443 | ST-2025-032 | 2030-01-01 | 294 |  | 289 |  | FALSE
13444 | ST-2025-032 | 2030-02-01 | 294 |  | 289 |  | FALSE
13445 | ST-2025-032 | 2030-03-01 | 294 |  | 289 |  | FALSE
13446 | ST-2025-033 | 2022-04-01 | 0 | 0 | 0 | 0 | FALSE
13447 | ST-2025-033 | 2022-05-01 | 0 | 0 | 0 | 0 | FALSE
13448 | ST-2025-033 | 2022-06-01 | 0 | 0 | 0 | 0 | FALSE
13449 | ST-2025-033 | 2022-07-01 | 0 | 0 | 0 | 0 | FALSE
13450 | ST-2025-033 | 2022-08-01 | 0 | 0 | 0 | 0 | FALSE
13451 | ST-2025-033 | 2022-09-01 | 0 | 0 | 0 | 0 | FALSE
13452 | ST-2025-033 | 2022-10-01 | 1 | 0 | 0 | 0 | TRUE
13453 | ST-2025-033 | 2022-11-01 | 1 | 0 | 0 | 0 | TRUE
13454 | ST-2025-033 | 2022-12-01 | 1 | 0 | 0 | 0 | TRUE
13455 | ST-2025-033 | 2023-01-01 | 1 | 0 | 0 | 0 | TRUE
13456 | ST-2025-033 | 2023-02-01 | 1 | 0 | 0 | 0 | TRUE
13457 | ST-2025-033 | 2023-03-01 | 2 | 1 | 1 | 1 | TRUE
13458 | ST-2025-033 | 2023-04-01 | 2 | 1 | 1 | 0 | TRUE
13459 | ST-2025-033 | 2023-05-01 | 3 | 2 | 2 | 1 | TRUE
13460 | ST-2025-033 | 2023-06-01 | 3 | 2 | 2 | 0 | TRUE
13461 | ST-2025-033 | 2023-07-01 | 4 | 3 | 3 | 1 | TRUE
13462 | ST-2025-033 | 2023-08-01 | 4 | 3 | 3 | 0 | TRUE
13463 | ST-2025-033 | 2023-09-01 | 5 | 4 | 4 | 1 | TRUE
13464 | ST-2025-033 | 2023-10-01 | 6 | 5 | 5 | 1 | TRUE
13465 | ST-2025-033 | 2023-11-01 | 6 | 5 | 5 | 0 | TRUE
13466 | ST-2025-033 | 2023-12-01 | 7 | 5 | 5 | 0 | TRUE
13467 | ST-2025-033 | 2024-01-01 | 8 | 7 | 7 | 2 | TRUE
13468 | ST-2025-033 | 2024-02-01 | 9 | 7 | 7 | 0 | TRUE
13469 | ST-2025-033 | 2024-03-01 | 9 | 7 | 7 | 0 | TRUE
13470 | ST-2025-033 | 2024-04-01 | 10 | 9 | 9 | 2 | TRUE
13471 | ST-2025-033 | 2024-05-01 | 11 | 9 | 9 | 0 | TRUE
13472 | ST-2025-033 | 2024-06-01 | 11 | 10 | 10 | 1 | TRUE
13473 | ST-2025-033 | 2024-07-01 | 12 | 10 | 10 | 0 | TRUE
13474 | ST-2025-033 | 2024-08-01 | 12 | 10 | 10 | 0 | TRUE
13475 | ST-2025-033 | 2024-09-01 | 13 | 11 | 11 | 1 | TRUE
13476 | ST-2025-033 | 2024-10-01 | 13 | 10 | 10 | 0 | TRUE
13477 | ST-2025-033 | 2024-11-01 | 14 | 12 | 12 | 2 | TRUE
13478 | ST-2025-033 | 2024-12-01 | 14 | 12 | 12 | 0 | TRUE
13479 | ST-2025-033 | 2025-01-01 | 14 | 11 | 11 | 0 | TRUE
13480 | ST-2025-033 | 2025-02-01 | 14 | 11 | 11 | 0 | TRUE
13481 | ST-2025-033 | 2025-03-01 | 14 | 12 | 12 | 1 | TRUE
13482 | ST-2025-033 | 2025-04-01 | 15 | 13 | 13 | 1 | TRUE
13483 | ST-2025-033 | 2025-05-01 | 15 | 13 | 13 | 0 | TRUE
13484 | ST-2025-033 | 2025-06-01 | 15 | 12 | 12 | 0 | TRUE
13485 | ST-2025-033 | 2025-07-01 | 15 | 12 | 12 | 0 | TRUE
13486 | ST-2025-033 | 2025-08-01 | 15 | 13 | 13 | 1 | TRUE
13487 | ST-2025-033 | 2025-09-01 | 15 | 13 | 13 | 0 | TRUE
13488 | ST-2025-033 | 2025-10-01 | 15 | 12 | 12 | 0 | TRUE
13489 | ST-2025-033 | 2025-11-01 | 15 | 12 | 12 | 0 | TRUE
13490 | ST-2025-033 | 2025-12-01 | 15 | 13 | 13 | 1 | TRUE
13491 | ST-2025-033 | 2026-01-01 | 15 | 13 | 13 | 0 | TRUE
13492 | ST-2025-034 | 2023-06-01 | 0 | 0 | 0 | 0 | FALSE
13493 | ST-2025-034 | 2023-07-01 | 0 | 0 | 0 | 0 | FALSE
13494 | ST-2025-034 | 2023-08-01 | 0 | 0 | 0 | 0 | FALSE
13495 | ST-2025-034 | 2023-09-01 | 0 | 0 | 0 | 0 | FALSE
13496 | ST-2025-034 | 2023-10-01 | 0 | 0 | 0 | 0 | FALSE
13497 | ST-2025-034 | 2023-11-01 | 1 | 0 | 0 | 0 | TRUE
13498 | ST-2025-034 | 2023-12-01 | 1 | 0 | 0 | 0 | TRUE
13499 | ST-2025-034 | 2024-01-01 | 1 | 0 | 0 | 0 | TRUE
13500 | ST-2025-034 | 2024-02-01 | 1 | 0 | 0 | 0 | TRUE
13501 | ST-2025-034 | 2024-03-01 | 2 | 1 | 1 | 1 | TRUE
13502 | ST-2025-034 | 2024-04-01 | 2 | 2 | 2 | 1 | FALSE
13503 | ST-2025-034 | 2024-05-01 | 3 | 2 | 2 | 0 | TRUE
13504 | ST-2025-034 | 2024-06-01 | 3 | 3 | 3 | 1 | FALSE
13505 | ST-2025-034 | 2024-07-01 | 4 | 3 | 3 | 0 | TRUE
13506 | ST-2025-034 | 2024-08-01 | 4 | 3 | 3 | 0 | TRUE
13507 | ST-2025-034 | 2024-09-01 | 5 | 5 | 5 | 2 | FALSE
13508 | ST-2025-034 | 2024-10-01 | 6 | 5 | 5 | 0 | TRUE
13509 | ST-2025-034 | 2024-11-01 | 7 | 6 | 6 | 1 | TRUE
13510 | ST-2025-034 | 2024-12-01 | 8 | 7 | 7 | 1 | TRUE
13511 | ST-2025-034 | 2025-01-01 | 9 | 9 | 9 | 2 | FALSE
13512 | ST-2025-034 | 2025-02-01 | 10 | 9 | 9 | 0 | TRUE
13513 | ST-2025-034 | 2025-03-01 | 10 | 9 | 9 | 0 | TRUE
13514 | ST-2025-034 | 2025-04-01 | 11 | 10 | 10 | 1 | TRUE
13515 | ST-2025-034 | 2025-05-01 | 12 | 11 | 11 | 1 | TRUE
13516 | ST-2025-034 | 2025-06-01 | 13 | 12 | 12 | 1 | TRUE
13517 | ST-2025-034 | 2025-07-01 | 14 | 14 | 14 | 2 | FALSE
13518 | ST-2025-034 | 2025-08-01 | 15 | 14 | 14 | 0 | TRUE
13519 | ST-2025-034 | 2025-09-01 | 15 | 15 | 15 | 1 | FALSE
13520 | ST-2025-034 | 2025-10-01 | 16 | 15 | 15 | 0 | TRUE
13521 | ST-2025-034 | 2025-11-01 | 16 | 15 | 15 | 0 | TRUE
13522 | ST-2025-034 | 2025-12-01 | 17 | 16 | 16 | 1 | TRUE
13523 | ST-2025-034 | 2026-01-01 | 17 | 16 | 16 | 0 | TRUE
13524 | ST-2025-034 | 2026-02-01 | 18 | 17 | 17 | 1 | TRUE
13525 | ST-2025-034 | 2026-03-01 | 18 | 18 | 18 | 1 | FALSE
13526 | ST-2025-034 | 2026-04-01 | 18 | 17 | 17 | 0 | TRUE
13527 | ST-2025-034 | 2026-05-01 | 18 | 17 | 17 | 0 | TRUE
13528 | ST-2025-034 | 2026-06-01 | 19 |  | 19 |  | FALSE
13529 | ST-2025-034 | 2026-07-01 | 19 |  | 19 |  | FALSE
13530 | ST-2025-034 | 2026-08-01 | 19 |  | 19 |  | FALSE
13531 | ST-2025-034 | 2026-09-01 | 19 |  | 19 |  | FALSE
13532 | ST-2025-034 | 2026-10-01 | 19 |  | 19 |  | FALSE
13533 | ST-2025-034 | 2026-11-01 | 19 |  | 19 |  | FALSE
13534 | ST-2025-034 | 2026-12-01 | 19 |  | 19 |  | FALSE
13535 | ST-2025-034 | 2027-01-01 | 19 |  | 19 |  | FALSE
13536 | ST-2025-034 | 2027-02-01 | 19 |  | 19 |  | FALSE
13537 | ST-2025-035 | 2025-06-01 | 0 | 0 | 0 | 0 | FALSE
13538 | ST-2025-035 | 2025-07-01 | 0 | 0 | 0 | 0 | FALSE
13539 | ST-2025-035 | 2025-08-01 | 0 | 0 | 0 | 0 | FALSE
13540 | ST-2025-035 | 2025-09-01 | 1 | 1 | 1 | 1 | FALSE
13541 | ST-2025-035 | 2025-10-01 | 1 | 1 | 1 | 0 | FALSE
13542 | ST-2025-035 | 2025-11-01 | 2 | 2 | 2 | 1 | FALSE
13543 | ST-2025-035 | 2025-12-01 | 3 | 3 | 3 | 1 | FALSE
13544 | ST-2025-035 | 2026-01-01 | 4 | 4 | 4 | 1 | FALSE
13545 | ST-2025-035 | 2026-02-01 | 5 | 5 | 5 | 1 | FALSE
13546 | ST-2025-035 | 2026-03-01 | 6 | 6 | 6 | 1 | FALSE
13547 | ST-2025-035 | 2026-04-01 | 8 | 8 | 8 | 2 | FALSE
13548 | ST-2025-035 | 2026-05-01 | 9 | 9 | 9 | 1 | FALSE
13549 | ST-2025-035 | 2026-06-01 | 10 |  | 10 |  | FALSE
13550 | ST-2025-035 | 2026-07-01 | 11 |  | 11 |  | FALSE
13551 | ST-2025-035 | 2026-08-01 | 12 |  | 12 |  | FALSE
13552 | ST-2025-035 | 2026-09-01 | 13 |  | 13 |  | FALSE
13553 | ST-2025-035 | 2026-10-01 | 13 |  | 13 |  | FALSE
13554 | ST-2025-035 | 2026-11-01 | 14 |  | 14 |  | FALSE
13555 | ST-2025-035 | 2026-12-01 | 14 |  | 14 |  | FALSE
13556 | ST-2025-035 | 2027-01-01 | 14 |  | 14 |  | FALSE
13557 | ST-2025-035 | 2027-02-01 | 14 |  | 14 |  | FALSE
13558 | ST-2025-035 | 2027-03-01 | 14 |  | 14 |  | FALSE
13559 | ST-2025-035 | 2027-04-01 | 14 |  | 14 |  | FALSE
13560 | ST-2025-035 | 2027-05-01 | 14 |  | 14 |  | FALSE
13561 | ST-2025-035 | 2027-06-01 | 14 |  | 14 |  | FALSE
13562 | ST-2025-036 | 2021-11-01 | 9 | 8 | 8 | 8 | TRUE
13563 | ST-2025-036 | 2021-12-01 | 11 | 10 | 10 | 2 | TRUE
13564 | ST-2025-036 | 2022-01-01 | 12 | 10 | 10 | 0 | TRUE
13565 | ST-2025-036 | 2022-02-01 | 13 | 11 | 11 | 1 | TRUE
13566 | ST-2025-036 | 2022-03-01 | 15 | 14 | 14 | 3 | TRUE
13567 | ST-2025-036 | 2022-04-01 | 16 | 14 | 14 | 0 | TRUE
13568 | ST-2025-036 | 2022-05-01 | 18 | 17 | 17 | 3 | TRUE
13569 | ST-2025-036 | 2022-06-01 | 20 | 18 | 18 | 1 | TRUE
13570 | ST-2025-036 | 2022-07-01 | 22 | 19 | 19 | 1 | TRUE
13571 | ST-2025-036 | 2022-08-01 | 25 | 22 | 22 | 3 | TRUE
13572 | ST-2025-036 | 2022-09-01 | 27 | 24 | 24 | 2 | TRUE
13573 | ST-2025-036 | 2022-10-01 | 30 | 27 | 28 | 3 | TRUE
13574 | ST-2025-036 | 2022-11-01 | 34 | 30 | 31 | 3 | TRUE
13575 | ST-2025-036 | 2022-12-01 | 37 | 33 | 34 | 3 | TRUE
13576 | ST-2025-036 | 2023-01-01 | 41 | 38 | 39 | 5 | TRUE
13577 | ST-2025-036 | 2023-02-01 | 45 | 43 | 44 | 5 | TRUE
13578 | ST-2025-036 | 2023-03-01 | 50 | 45 | 46 | 2 | TRUE
13579 | ST-2025-036 | 2023-04-01 | 55 | 51 | 53 | 6 | TRUE
13580 | ST-2025-036 | 2023-05-01 | 61 | 55 | 57 | 4 | TRUE
13581 | ST-2025-036 | 2023-06-01 | 66 | 58 | 60 | 3 | TRUE
13582 | ST-2025-036 | 2023-07-01 | 73 | 70 | 72 | 12 | TRUE
13583 | ST-2025-036 | 2023-08-01 | 80 | 71 | 73 | 1 | TRUE
13584 | ST-2025-036 | 2023-09-01 | 87 | 84 | 87 | 13 | TRUE
13585 | ST-2025-036 | 2023-10-01 | 95 | 91 | 94 | 7 | TRUE
13586 | ST-2025-036 | 2023-11-01 | 104 | 95 | 98 | 4 | TRUE
13587 | ST-2025-036 | 2023-12-01 | 113 | 110 | 114 | 15 | TRUE
13588 | ST-2025-036 | 2024-01-01 | 123 | 120 | 124 | 10 | TRUE
13589 | ST-2025-036 | 2024-02-01 | 133 | 124 | 128 | 4 | TRUE
13590 | ST-2025-036 | 2024-03-01 | 143 | 140 | 145 | 16 | TRUE
13591 | ST-2025-036 | 2024-04-01 | 155 | 140 | 145 | 0 | TRUE
13592 | ST-2025-036 | 2024-05-01 | 166 | 155 | 161 | 15 | TRUE
13593 | ST-2025-036 | 2024-06-01 | 178 | 166 | 172 | 11 | TRUE
13594 | ST-2025-036 | 2024-07-01 | 191 | 176 | 183 | 10 | TRUE
13595 | ST-2025-036 | 2024-08-01 | 203 | 194 | 201 | 18 | TRUE
13596 | ST-2025-036 | 2024-09-01 | 216 | 207 | 215 | 13 | TRUE
13597 | ST-2025-036 | 2024-10-01 | 230 | 210 | 218 | 3 | TRUE
13598 | ST-2025-036 | 2024-11-01 | 243 | 234 | 243 | 24 | TRUE
13599 | ST-2025-036 | 2024-12-01 | 256 | 227 | 236 | 0 | TRUE
13600 | ST-2025-036 | 2025-01-01 | 269 | 242 | 251 | 15 | TRUE
13601 | ST-2025-036 | 2025-02-01 | 283 | 263 | 273 | 21 | TRUE
13602 | ST-2025-036 | 2025-03-01 | 296 | 274 | 284 | 11 | TRUE
13603 | ST-2025-036 | 2025-04-01 | 308 | 288 | 299 | 14 | TRUE
13604 | ST-2025-036 | 2025-05-01 | 321 | 286 | 297 | 0 | TRUE
13605 | ST-2025-036 | 2025-06-01 | 333 | 313 | 325 | 27 | TRUE
13606 | ST-2025-036 | 2025-07-01 | 344 | 338 | 351 | 25 | TRUE
13607 | ST-2025-036 | 2025-08-01 | 356 | 334 | 347 | 0 | TRUE
13608 | ST-2025-036 | 2025-09-01 | 366 | 325 | 338 | 0 | TRUE
13609 | ST-2025-036 | 2025-10-01 | 376 | 350 | 364 | 25 | TRUE
13610 | ST-2025-036 | 2025-11-01 | 386 | 343 | 356 | 0 | TRUE
13611 | ST-2025-036 | 2025-12-01 | 395 | 371 | 385 | 28 | TRUE
13612 | ST-2025-036 | 2026-01-01 | 404 | 392 | 407 | 21 | TRUE
13613 | ST-2025-036 | 2026-02-01 | 412 | 399 | 414 | 7 | TRUE
13614 | ST-2025-036 | 2026-03-01 | 419 | 393 | 408 | 0 | TRUE
13615 | ST-2025-036 | 2026-04-01 | 426 | 403 | 419 | 10 | TRUE
13616 | ST-2025-036 | 2026-05-01 | 433 | 412 | 428 | 9 | TRUE
13617 | ST-2025-036 | 2026-06-01 | 438 |  | 439 |  | FALSE
13618 | ST-2025-036 | 2026-07-01 | 444 |  | 445 |  | FALSE
13619 | ST-2025-036 | 2026-08-01 | 449 |  | 450 |  | FALSE
13620 | ST-2025-036 | 2026-09-01 | 454 |  | 455 |  | FALSE
13621 | ST-2025-036 | 2026-10-01 | 458 |  | 459 |  | FALSE
13622 | ST-2025-036 | 2026-11-01 | 462 |  | 463 |  | FALSE
13623 | ST-2025-036 | 2026-12-01 | 465 |  | 466 |  | FALSE
13624 | ST-2025-036 | 2027-01-01 | 469 |  | 470 |  | FALSE
13625 | ST-2025-036 | 2027-02-01 | 472 |  | 473 |  | FALSE
13626 | ST-2025-036 | 2027-03-01 | 474 |  | 475 |  | FALSE
13627 | ST-2025-036 | 2027-04-01 | 477 |  | 478 |  | FALSE
13628 | ST-2025-036 | 2027-05-01 | 479 |  | 480 |  | FALSE
13629 | ST-2025-036 | 2027-06-01 | 481 |  | 482 |  | FALSE
13630 | ST-2025-036 | 2027-07-01 | 483 |  | 484 |  | FALSE
13631 | ST-2025-036 | 2027-08-01 | 484 |  | 485 |  | FALSE
13632 | ST-2025-036 | 2027-09-01 | 486 |  | 487 |  | FALSE
13633 | ST-2025-036 | 2027-10-01 | 487 |  | 488 |  | FALSE
13634 | ST-2025-036 | 2027-11-01 | 488 |  | 489 |  | FALSE
13635 | ST-2025-036 | 2027-12-01 | 490 |  | 491 |  | FALSE
13636 | ST-2025-036 | 2028-01-01 | 491 |  | 492 |  | FALSE
13637 | ST-2025-036 | 2028-02-01 | 491 |  | 492 |  | FALSE
13638 | ST-2025-036 | 2028-03-01 | 491 |  | 492 |  | FALSE
13639 | ST-2025-037 | 2026-08-01 | 277 |  | 249 |  | FALSE
13640 | ST-2025-037 | 2026-09-01 | 426 |  | 383 |  | FALSE
13641 | ST-2025-037 | 2026-10-01 | 649 |  | 584 |  | FALSE
13642 | ST-2025-037 | 2026-11-01 | 977 |  | 879 |  | FALSE
13643 | ST-2025-037 | 2026-12-01 | 1445 |  | 1300 |  | FALSE
13644 | ST-2025-037 | 2027-01-01 | 2086 |  | 1877 |  | FALSE
13645 | ST-2025-037 | 2027-02-01 | 2913 |  | 2621 |  | FALSE
13646 | ST-2025-037 | 2027-03-01 | 3906 |  | 3515 |  | FALSE
13647 | ST-2025-037 | 2027-04-01 | 5000 |  | 4500 |  | FALSE
13648 | ST-2025-037 | 2027-05-01 | 6093 |  | 5483 |  | FALSE
13649 | ST-2025-037 | 2027-06-01 | 7086 |  | 6377 |  | FALSE
13650 | ST-2025-037 | 2027-07-01 | 7913 |  | 7121 |  | FALSE
13651 | ST-2025-037 | 2027-08-01 | 8554 |  | 7698 |  | FALSE
13652 | ST-2025-037 | 2027-09-01 | 9022 |  | 8119 |  | FALSE
13653 | ST-2025-037 | 2027-10-01 | 9350 |  | 8415 |  | FALSE
13654 | ST-2025-037 | 2027-11-01 | 9573 |  | 8615 |  | FALSE
13655 | ST-2025-037 | 2027-12-01 | 9722 |  | 8749 |  | FALSE
13656 | ST-2025-037 | 2028-01-01 | 9820 |  | 8838 |  | FALSE
13657 | ST-2025-037 | 2028-02-01 | 9820 |  | 8838 |  | FALSE
13658 | ST-2025-037 | 2028-03-01 | 9820 |  | 8838 |  | FALSE
13659 | ST-2025-037 | 2028-04-01 | 9820 |  | 8838 |  | FALSE
13660 | ST-2025-037 | 2028-05-01 | 9820 |  | 8838 |  | FALSE

## Enrollment Rate
id | study_id | period_date | planned_rate | actual_rate | below_plan_flag
6877 | ST-2024-002 | 2024-09-01 | 3 | 2 | TRUE
6878 | ST-2024-002 | 2024-10-01 | 1 | 1 | FALSE
6879 | ST-2024-002 | 2024-11-01 | 1 | 1 | FALSE
6880 | ST-2024-002 | 2024-12-01 | 1 | 1 | FALSE
6881 | ST-2024-002 | 2025-01-01 | 1 | 0 | TRUE
6882 | ST-2024-002 | 2025-02-01 | 1 | 1 | FALSE
6883 | ST-2024-002 | 2025-03-01 | 2 | 2 | FALSE
6884 | ST-2024-002 | 2025-04-01 | 2 | 1 | TRUE
6885 | ST-2024-002 | 2025-05-01 | 2 | 2 | FALSE
6886 | ST-2024-002 | 2025-06-01 | 2 | 2 | FALSE
6887 | ST-2024-002 | 2025-07-01 | 3 | 3 | FALSE
6888 | ST-2024-002 | 2025-08-01 | 3 | 2 | TRUE
6889 | ST-2024-002 | 2025-09-01 | 4 | 2 | TRUE
6890 | ST-2024-002 | 2025-10-01 | 4 | 4 | FALSE
6891 | ST-2024-002 | 2025-11-01 | 5 | 3 | TRUE
6892 | ST-2024-002 | 2025-12-01 | 5 | 7 | FALSE
6893 | ST-2024-002 | 2026-01-01 | 6 | 5 | TRUE
6894 | ST-2024-002 | 2026-02-01 | 7 | 3 | TRUE
6895 | ST-2024-002 | 2026-03-01 | 6 | 7 | FALSE
6896 | ST-2024-002 | 2026-04-01 | 7 | 5 | TRUE
6897 | ST-2024-002 | 2026-05-01 | 8 | 4 | TRUE
6898 | ST-2024-003 | 2024-03-01 | 2 | 2 | FALSE
6899 | ST-2024-003 | 2024-04-01 | 1 | 1 | FALSE
6900 | ST-2024-003 | 2024-05-01 | 0 | 0 | FALSE
6901 | ST-2024-003 | 2024-06-01 | 1 | 1 | FALSE
6902 | ST-2024-003 | 2024-07-01 | 0 | 0 | FALSE
6903 | ST-2024-003 | 2024-08-01 | 1 | 0 | TRUE
6904 | ST-2024-003 | 2024-09-01 | 0 | 1 | FALSE
6905 | ST-2024-003 | 2024-10-01 | 1 | 1 | FALSE
6906 | ST-2024-003 | 2024-11-01 | 1 | 1 | FALSE
6907 | ST-2024-003 | 2024-12-01 | 1 | 1 | FALSE
6908 | ST-2024-003 | 2025-01-01 | 1 | 1 | FALSE
6909 | ST-2024-003 | 2025-02-01 | 1 | 0 | TRUE
6910 | ST-2024-003 | 2025-03-01 | 1 | 2 | FALSE
6911 | ST-2024-003 | 2025-04-01 | 2 | 2 | FALSE
6912 | ST-2024-003 | 2025-05-01 | 1 | 1 | FALSE
6913 | ST-2024-003 | 2025-06-01 | 2 | 2 | FALSE
6914 | ST-2024-003 | 2025-07-01 | 2 | 3 | FALSE
6915 | ST-2024-003 | 2025-08-01 | 2 | 0 | TRUE
6916 | ST-2024-003 | 2025-09-01 | 2 | 2 | FALSE
6917 | ST-2024-003 | 2025-10-01 | 2 | 3 | FALSE
6918 | ST-2024-003 | 2025-11-01 | 3 | 3 | FALSE
6919 | ST-2024-003 | 2025-12-01 | 2 | 3 | FALSE
6920 | ST-2024-003 | 2026-01-01 | 3 | 2 | TRUE
6921 | ST-2024-003 | 2026-02-01 | 4 | 6 | FALSE
6922 | ST-2024-003 | 2026-03-01 | 3 | 1 | TRUE
6923 | ST-2024-003 | 2026-04-01 | 3 | 5 | FALSE
6924 | ST-2024-003 | 2026-05-01 | 4 | 5 | FALSE
6925 | ST-2024-004 | 2025-01-01 | 3 | 2 | TRUE
6926 | ST-2024-004 | 2025-02-01 | 0 | 0 | FALSE
6927 | ST-2024-004 | 2025-03-01 | 1 | 1 | FALSE
6928 | ST-2024-004 | 2025-04-01 | 0 | 0 | FALSE
6929 | ST-2024-004 | 2025-05-01 | 1 | 1 | FALSE
6930 | ST-2024-004 | 2025-06-01 | 1 | 0 | TRUE
6931 | ST-2024-004 | 2025-07-01 | 2 | 2 | FALSE
6932 | ST-2024-004 | 2025-08-01 | 1 | 0 | TRUE
6933 | ST-2024-004 | 2025-09-01 | 1 | 1 | FALSE
6934 | ST-2024-004 | 2025-10-01 | 2 | 2 | FALSE
6935 | ST-2024-004 | 2025-11-01 | 2 | 2 | FALSE
6936 | ST-2024-004 | 2025-12-01 | 3 | 2 | TRUE
6937 | ST-2024-004 | 2026-01-01 | 2 | 2 | FALSE
6938 | ST-2024-004 | 2026-02-01 | 4 | 2 | TRUE
6939 | ST-2024-004 | 2026-03-01 | 3 | 2 | TRUE
6940 | ST-2024-004 | 2026-04-01 | 4 | 5 | FALSE
6941 | ST-2024-004 | 2026-05-01 | 4 | 2 | TRUE
6942 | ST-2024-005 | 2022-08-01 | 2 | 1 | TRUE
6943 | ST-2024-005 | 2022-09-01 | 0 | 0 | FALSE
6944 | ST-2024-005 | 2022-10-01 | 0 | 0 | FALSE
6945 | ST-2024-005 | 2022-11-01 | 1 | 1 | FALSE
6946 | ST-2024-005 | 2022-12-01 | 0 | 0 | FALSE
6947 | ST-2024-005 | 2023-01-01 | 1 | 1 | FALSE
6948 | ST-2024-005 | 2023-02-01 | 1 | 0 | TRUE
6949 | ST-2024-005 | 2023-03-01 | 0 | 0 | FALSE
6950 | ST-2024-005 | 2023-04-01 | 1 | 1 | FALSE
6951 | ST-2024-005 | 2023-05-01 | 1 | 0 | TRUE
6952 | ST-2024-005 | 2023-06-01 | 1 | 2 | FALSE
6953 | ST-2024-005 | 2023-07-01 | 2 | 1 | TRUE
6954 | ST-2024-005 | 2023-08-01 | 1 | 1 | FALSE
6955 | ST-2024-005 | 2023-09-01 | 2 | 1 | TRUE
6956 | ST-2024-005 | 2023-10-01 | 1 | 1 | FALSE
6957 | ST-2024-005 | 2023-11-01 | 3 | 2 | TRUE
6958 | ST-2024-005 | 2023-12-01 | 2 | 1 | TRUE
6959 | ST-2024-005 | 2024-01-01 | 2 | 1 | TRUE
6960 | ST-2024-005 | 2024-02-01 | 3 | 3 | FALSE
6961 | ST-2024-005 | 2024-03-01 | 3 | 3 | FALSE
6962 | ST-2024-005 | 2024-04-01 | 3 | 2 | TRUE
6963 | ST-2024-005 | 2024-05-01 | 3 | 3 | FALSE
6964 | ST-2024-005 | 2024-06-01 | 4 | 3 | TRUE
6965 | ST-2024-005 | 2024-07-01 | 3 | 0 | TRUE
6966 | ST-2024-005 | 2024-08-01 | 4 | 5 | FALSE
6967 | ST-2024-005 | 2024-09-01 | 4 | 1 | TRUE
6968 | ST-2024-005 | 2024-10-01 | 3 | 4 | FALSE
6969 | ST-2024-005 | 2024-11-01 | 4 | 2 | TRUE
6970 | ST-2024-005 | 2024-12-01 | 4 | 3 | TRUE
6971 | ST-2024-005 | 2025-01-01 | 3 | 2 | TRUE
6972 | ST-2024-005 | 2025-02-01 | 4 | 3 | TRUE
6973 | ST-2024-005 | 2025-03-01 | 3 | 2 | TRUE
6974 | ST-2024-005 | 2025-04-01 | 3 | 1 | TRUE
6975 | ST-2024-005 | 2025-05-01 | 3 | 4 | FALSE
6976 | ST-2024-005 | 2025-06-01 | 3 | 0 | TRUE
6977 | ST-2024-005 | 2025-07-01 | 2 | 4 | FALSE
6978 | ST-2024-005 | 2025-08-01 | 2 | 4 | FALSE
6979 | ST-2024-005 | 2025-09-01 | 3 | 0 | TRUE
6980 | ST-2024-005 | 2025-10-01 | 1 | 3 | FALSE
6981 | ST-2024-005 | 2025-11-01 | 2 | 2 | FALSE
6982 | ST-2024-005 | 2025-12-01 | 1 | 1 | FALSE
6983 | ST-2024-005 | 2026-01-01 | 2 | 0 | TRUE
6984 | ST-2024-005 | 2026-02-01 | 1 | 0 | TRUE
6985 | ST-2024-005 | 2026-03-01 | 1 | 1 | FALSE
6986 | ST-2024-005 | 2026-04-01 | 1 | 4 | FALSE
6987 | ST-2024-005 | 2026-05-01 | 0 | 1 | FALSE
6988 | ST-2024-006 | 2024-02-01 | 1 | 0 | TRUE
6989 | ST-2024-006 | 2024-03-01 | 1 | 1 | FALSE
6990 | ST-2024-006 | 2024-04-01 | 1 | 1 | FALSE
6991 | ST-2024-006 | 2024-05-01 | 2 | 2 | FALSE
6992 | ST-2024-006 | 2024-06-01 | 2 | 1 | TRUE
6993 | ST-2024-006 | 2024-07-01 | 3 | 2 | TRUE
6994 | ST-2024-006 | 2024-08-01 | 4 | 3 | TRUE
6995 | ST-2024-006 | 2024-09-01 | 5 | 4 | TRUE
6996 | ST-2024-006 | 2024-10-01 | 6 | 6 | FALSE
6997 | ST-2024-006 | 2024-11-01 | 6 | 5 | TRUE
6998 | ST-2024-006 | 2024-12-01 | 7 | 5 | TRUE
6999 | ST-2024-006 | 2025-01-01 | 6 | 5 | TRUE
7000 | ST-2024-006 | 2025-02-01 | 6 | 5 | TRUE
7001 | ST-2024-006 | 2025-03-01 | 5 | 1 | TRUE
7002 | ST-2024-006 | 2025-04-01 | 4 | 8 | FALSE
7003 | ST-2024-006 | 2025-05-01 | 3 | 0 | TRUE
7004 | ST-2024-006 | 2025-06-01 | 2 | 1 | TRUE
7005 | ST-2024-006 | 2025-07-01 | 2 | 3 | FALSE
7006 | ST-2024-006 | 2025-08-01 | 1 | 0 | TRUE
7007 | ST-2024-006 | 2025-09-01 | 1 | 4 | FALSE
7008 | ST-2024-006 | 2025-10-01 | 0 | 0 | FALSE
7009 | ST-2024-006 | 2025-11-01 | 0 | 0 | FALSE
7010 | ST-2024-006 | 2025-12-01 | 0 | 0 | FALSE
7011 | ST-2024-006 | 2026-01-01 | 0 | 5 | FALSE
7012 | ST-2024-006 | 2026-02-01 | 0 | 0 | FALSE
7013 | ST-2024-008 | 2021-09-01 | 1 | 0 | TRUE
7014 | ST-2024-008 | 2021-10-01 | 0 | 0 | FALSE
7015 | ST-2024-008 | 2021-11-01 | 0 | 0 | FALSE
7016 | ST-2024-008 | 2021-12-01 | 0 | 0 | FALSE
7017 | ST-2024-008 | 2022-01-01 | 0 | 0 | FALSE
7018 | ST-2024-008 | 2022-02-01 | 1 | 1 | FALSE
7019 | ST-2024-008 | 2022-03-01 | 0 | 0 | FALSE
7020 | ST-2024-008 | 2022-04-01 | 1 | 1 | FALSE
7021 | ST-2024-008 | 2022-05-01 | 0 | 0 | FALSE
7022 | ST-2024-008 | 2022-06-01 | 1 | 1 | FALSE
7023 | ST-2024-008 | 2022-07-01 | 0 | 0 | FALSE
7024 | ST-2024-008 | 2022-08-01 | 1 | 1 | FALSE
7025 | ST-2024-008 | 2022-09-01 | 1 | 0 | TRUE
7026 | ST-2024-008 | 2022-10-01 | 1 | 1 | FALSE
7027 | ST-2024-008 | 2022-11-01 | 1 | 2 | FALSE
7028 | ST-2024-008 | 2022-12-01 | 1 | 0 | TRUE
7029 | ST-2024-008 | 2023-01-01 | 2 | 2 | FALSE
7030 | ST-2024-008 | 2023-02-01 | 1 | 0 | TRUE
7031 | ST-2024-008 | 2023-03-01 | 2 | 2 | FALSE
7032 | ST-2024-008 | 2023-04-01 | 2 | 2 | FALSE
7033 | ST-2024-008 | 2023-05-01 | 2 | 1 | TRUE
7034 | ST-2024-008 | 2023-06-01 | 1 | 2 | FALSE
7035 | ST-2024-008 | 2023-07-01 | 2 | 1 | TRUE
7036 | ST-2024-008 | 2023-08-01 | 2 | 1 | TRUE
7037 | ST-2024-008 | 2023-09-01 | 3 | 3 | FALSE
7038 | ST-2024-008 | 2023-10-01 | 2 | 2 | FALSE
7039 | ST-2024-008 | 2023-11-01 | 2 | 1 | TRUE
7040 | ST-2024-008 | 2023-12-01 | 1 | 3 | FALSE
7041 | ST-2024-008 | 2024-01-01 | 2 | 0 | TRUE
7042 | ST-2024-008 | 2024-02-01 | 2 | 4 | FALSE
7043 | ST-2024-008 | 2024-03-01 | 2 | 0 | TRUE
7044 | ST-2024-008 | 2024-04-01 | 1 | 0 | TRUE
7045 | ST-2024-008 | 2024-05-01 | 2 | 3 | FALSE
7046 | ST-2024-008 | 2024-06-01 | 1 | 0 | TRUE
7047 | ST-2024-008 | 2024-07-01 | 1 | 1 | FALSE
7048 | ST-2024-008 | 2024-08-01 | 1 | 3 | FALSE
7049 | ST-2024-008 | 2024-09-01 | 1 | 0 | TRUE
7050 | ST-2024-008 | 2024-10-01 | 1 | 4 | FALSE
7051 | ST-2024-008 | 2024-11-01 | 0 | 0 | FALSE
7052 | ST-2024-008 | 2024-12-01 | 1 | 0 | TRUE
7053 | ST-2024-008 | 2025-01-01 | 0 | 2 | FALSE
7054 | ST-2024-008 | 2025-02-01 | 1 | 0 | TRUE
7055 | ST-2024-008 | 2025-03-01 | 0 | 2 | FALSE
7056 | ST-2024-008 | 2025-04-01 | 1 | 0 | TRUE
7057 | ST-2024-008 | 2025-05-01 | 0 | 4 | FALSE
7058 | ST-2024-008 | 2025-06-01 | 0 | 0 | FALSE
7059 | ST-2024-008 | 2025-07-01 | 0 | 0 | FALSE
7060 | ST-2024-008 | 2025-08-01 | 0 | 2 | FALSE
7061 | ST-2024-008 | 2025-09-01 | 1 | 1 | FALSE
7062 | ST-2024-008 | 2025-10-01 | 0 | 0 | FALSE
7063 | ST-2024-008 | 2025-11-01 | 0 | 1 | FALSE
7064 | ST-2024-008 | 2025-12-01 | 0 | 0 | FALSE
7065 | ST-2024-009 | 2025-11-01 | 6 | 4 | TRUE
7066 | ST-2024-009 | 2025-12-01 | 1 | 2 | FALSE
7067 | ST-2024-009 | 2026-01-01 | 2 | 1 | TRUE
7068 | ST-2024-009 | 2026-02-01 | 1 | 1 | FALSE
7069 | ST-2024-009 | 2026-03-01 | 3 | 2 | TRUE
7070 | ST-2024-009 | 2026-04-01 | 2 | 2 | FALSE
7071 | ST-2024-009 | 2026-05-01 | 3 | 2 | TRUE
7072 | ST-2024-010 | 2021-02-01 | 96 | 81 | TRUE
7073 | ST-2024-010 | 2021-03-01 | 6 | 11 | FALSE
7074 | ST-2024-010 | 2021-04-01 | 7 | 0 | TRUE
7075 | ST-2024-010 | 2021-05-01 | 7 | 15 | FALSE
7076 | ST-2024-010 | 2021-06-01 | 8 | 0 | TRUE
7077 | ST-2024-010 | 2021-07-01 | 8 | 16 | FALSE
7078 | ST-2024-010 | 2021-08-01 | 9 | 7 | TRUE
7079 | ST-2024-010 | 2021-09-01 | 10 | 8 | TRUE
7080 | ST-2024-010 | 2021-10-01 | 10 | 2 | TRUE
7081 | ST-2024-010 | 2021-11-01 | 11 | 10 | TRUE
7082 | ST-2024-010 | 2021-12-01 | 11 | 21 | FALSE
7083 | ST-2024-010 | 2022-01-01 | 12 | 0 | TRUE
7084 | ST-2024-010 | 2022-02-01 | 13 | 22 | FALSE
7085 | ST-2024-010 | 2022-03-01 | 14 | 7 | TRUE
7086 | ST-2024-010 | 2022-04-01 | 15 | 2 | TRUE
7087 | ST-2024-010 | 2022-05-01 | 15 | 26 | FALSE
7088 | ST-2024-010 | 2022-06-01 | 17 | 0 | TRUE
7089 | ST-2024-010 | 2022-07-01 | 17 | 19 | FALSE
7090 | ST-2024-010 | 2022-08-01 | 19 | 24 | FALSE
7091 | ST-2024-010 | 2022-09-01 | 19 | 2 | TRUE
7092 | ST-2024-010 | 2022-10-01 | 21 | 29 | FALSE
7093 | ST-2024-010 | 2022-11-01 | 22 | 36 | FALSE
7094 | ST-2024-010 | 2022-12-01 | 24 | 21 | TRUE
7095 | ST-2024-010 | 2023-01-01 | 24 | 18 | TRUE
7096 | ST-2024-010 | 2023-02-01 | 26 | 3 | TRUE
7097 | ST-2024-010 | 2023-03-01 | 28 | 14 | TRUE
7098 | ST-2024-010 | 2023-04-01 | 29 | 41 | FALSE
7099 | ST-2024-010 | 2023-05-01 | 31 | 22 | TRUE
7100 | ST-2024-010 | 2023-06-01 | 32 | 23 | TRUE
7101 | ST-2024-010 | 2023-07-01 | 35 | 58 | FALSE
7102 | ST-2024-010 | 2023-08-01 | 35 | 29 | TRUE
7103 | ST-2024-010 | 2023-09-01 | 38 | 1 | TRUE
7104 | ST-2024-010 | 2023-10-01 | 40 | 42 | FALSE
7105 | ST-2024-010 | 2023-11-01 | 41 | 79 | FALSE
7106 | ST-2024-010 | 2023-12-01 | 44 | 42 | TRUE
7107 | ST-2024-010 | 2024-01-01 | 45 | 23 | TRUE
7108 | ST-2024-010 | 2024-02-01 | 48 | 39 | TRUE
7109 | ST-2024-010 | 2024-03-01 | 50 | 27 | TRUE
7110 | ST-2024-010 | 2024-04-01 | 52 | 69 | FALSE
7111 | ST-2024-010 | 2024-05-01 | 54 | 0 | TRUE
7112 | ST-2024-010 | 2024-06-01 | 56 | 129 | FALSE
7113 | ST-2024-010 | 2024-07-01 | 58 | 0 | TRUE
7114 | ST-2024-010 | 2024-08-01 | 60 | 110 | FALSE
7115 | ST-2024-010 | 2024-09-01 | 63 | 66 | FALSE
7116 | ST-2024-010 | 2024-10-01 | 64 | 64 | FALSE
7117 | ST-2024-010 | 2024-11-01 | 67 | 0 | TRUE
7118 | ST-2024-010 | 2024-12-01 | 68 | 102 | FALSE
7119 | ST-2024-010 | 2025-01-01 | 71 | 123 | FALSE
7120 | ST-2024-010 | 2025-02-01 | 72 | 4 | TRUE
7121 | ST-2024-010 | 2025-03-01 | 74 | 122 | FALSE
7122 | ST-2024-010 | 2025-04-01 | 75 | 0 | TRUE
7123 | ST-2024-010 | 2025-05-01 | 77 | 47 | TRUE
7124 | ST-2024-010 | 2025-06-01 | 79 | 211 | FALSE
7125 | ST-2024-010 | 2025-07-01 | 79 | 0 | TRUE
7126 | ST-2024-010 | 2025-08-01 | 81 | 179 | FALSE
7127 | ST-2024-010 | 2025-09-01 | 81 | 76 | TRUE
7128 | ST-2024-010 | 2025-10-01 | 82 | 0 | TRUE
7129 | ST-2024-010 | 2025-11-01 | 83 | 100 | FALSE
7130 | ST-2024-010 | 2025-12-01 | 83 | 15 | TRUE
7131 | ST-2024-010 | 2026-01-01 | 84 | 114 | FALSE
7132 | ST-2024-010 | 2026-02-01 | 83 | 222 | FALSE
7133 | ST-2024-010 | 2026-03-01 | 83 | 0 | TRUE
7134 | ST-2024-010 | 2026-04-01 | 83 | 199 | FALSE
7135 | ST-2024-010 | 2026-05-01 | 82 | 0 | TRUE
7136 | ST-2024-011 | 2026-01-01 | 3 | 2 | TRUE
7137 | ST-2024-011 | 2026-02-01 | 0 | 0 | FALSE
7138 | ST-2024-011 | 2026-03-01 | 1 | 0 | TRUE
7139 | ST-2024-011 | 2026-04-01 | 1 | 1 | FALSE
7140 | ST-2024-011 | 2026-05-01 | 2 | 2 | FALSE
7141 | ST-2024-012 | 2025-06-01 | 0 | 0 | FALSE
7142 | ST-2024-012 | 2025-07-01 | 1 | 0 | TRUE
7143 | ST-2024-012 | 2025-08-01 | 0 | 0 | FALSE
7144 | ST-2024-012 | 2025-09-01 | 1 | 1 | FALSE
7145 | ST-2024-012 | 2025-10-01 | 2 | 1 | TRUE
7146 | ST-2024-012 | 2025-11-01 | 2 | 2 | FALSE
7147 | ST-2024-012 | 2025-12-01 | 2 | 1 | TRUE
7148 | ST-2024-012 | 2026-01-01 | 3 | 2 | TRUE
7149 | ST-2024-012 | 2026-02-01 | 4 | 3 | TRUE
7150 | ST-2024-012 | 2026-03-01 | 3 | 3 | FALSE
7151 | ST-2024-012 | 2026-04-01 | 3 | 1 | TRUE
7152 | ST-2024-012 | 2026-05-01 | 2 | 3 | FALSE
7153 | ST-2024-014 | 2025-03-01 | 0 | 0 | FALSE
7154 | ST-2024-014 | 2025-04-01 | 0 | 0 | FALSE
7155 | ST-2024-014 | 2025-05-01 | 1 | 0 | TRUE
7156 | ST-2024-014 | 2025-06-01 | 0 | 0 | FALSE
7157 | ST-2024-014 | 2025-07-01 | 0 | 0 | FALSE
7158 | ST-2024-014 | 2025-08-01 | 1 | 1 | FALSE
7159 | ST-2024-014 | 2025-09-01 | 0 | 1 | FALSE
7160 | ST-2024-014 | 2025-10-01 | 1 | 0 | TRUE
7161 | ST-2024-014 | 2025-11-01 | 0 | 0 | FALSE
7162 | ST-2024-014 | 2025-12-01 | 1 | 1 | FALSE
7163 | ST-2024-014 | 2026-01-01 | 1 | 1 | FALSE
7164 | ST-2024-014 | 2026-02-01 | 2 | 2 | FALSE
7165 | ST-2024-014 | 2026-03-01 | 1 | 1 | FALSE
7166 | ST-2024-014 | 2026-04-01 | 1 | 1 | FALSE
7167 | ST-2024-014 | 2026-05-01 | 2 | 2 | FALSE
7168 | ST-2024-015 | 2025-11-01 | 3 | 2 | TRUE
7169 | ST-2024-015 | 2025-12-01 | 1 | 1 | FALSE
7170 | ST-2024-015 | 2026-01-01 | 1 | 1 | FALSE
7171 | ST-2024-015 | 2026-02-01 | 2 | 2 | FALSE
7172 | ST-2024-015 | 2026-03-01 | 3 | 3 | FALSE
7173 | ST-2024-015 | 2026-04-01 | 3 | 3 | FALSE
7174 | ST-2024-015 | 2026-05-01 | 4 | 3 | TRUE
7175 | ST-2024-016 | 2025-03-01 | 2 | 1 | TRUE
7176 | ST-2024-016 | 2025-04-01 | 0 | 0 | FALSE
7177 | ST-2024-016 | 2025-05-01 | 1 | 1 | FALSE
7178 | ST-2024-016 | 2025-06-01 | 1 | 1 | FALSE
7179 | ST-2024-016 | 2025-07-01 | 2 | 2 | FALSE
7180 | ST-2024-016 | 2025-08-01 | 2 | 2 | FALSE
7181 | ST-2024-016 | 2025-09-01 | 2 | 1 | TRUE
7182 | ST-2024-016 | 2025-10-01 | 3 | 2 | TRUE
7183 | ST-2024-016 | 2025-11-01 | 4 | 4 | FALSE
7184 | ST-2024-016 | 2025-12-01 | 4 | 3 | TRUE
7185 | ST-2024-016 | 2026-01-01 | 5 | 5 | FALSE
7186 | ST-2024-016 | 2026-02-01 | 6 | 5 | TRUE
7187 | ST-2024-016 | 2026-03-01 | 6 | 7 | FALSE
7188 | ST-2024-016 | 2026-04-01 | 7 | 6 | TRUE
7189 | ST-2024-016 | 2026-05-01 | 6 | 5 | TRUE
7190 | ST-2024-017 | 2025-05-01 | 1 | 0 | TRUE
7191 | ST-2024-017 | 2025-06-01 | 0 | 0 | FALSE
7192 | ST-2024-017 | 2025-07-01 | 1 | 1 | FALSE
7193 | ST-2024-017 | 2025-08-01 | 0 | 0 | FALSE
7194 | ST-2024-017 | 2025-09-01 | 1 | 1 | FALSE
7195 | ST-2024-017 | 2025-10-01 | 0 | 0 | FALSE
7196 | ST-2024-017 | 2025-11-01 | 1 | 1 | FALSE
7197 | ST-2024-017 | 2025-12-01 | 1 | 1 | FALSE
7198 | ST-2024-017 | 2026-01-01 | 2 | 1 | TRUE
7199 | ST-2024-017 | 2026-02-01 | 1 | 1 | FALSE
7200 | ST-2024-017 | 2026-03-01 | 2 | 2 | FALSE
7201 | ST-2024-017 | 2026-04-01 | 2 | 1 | TRUE
7202 | ST-2024-017 | 2026-05-01 | 2 | 1 | TRUE
7203 | ST-2024-018 | 2022-06-01 | 0 | 0 | FALSE
7204 | ST-2024-018 | 2022-07-01 | 0 | 0 | FALSE
7205 | ST-2024-018 | 2022-08-01 | 0 | 0 | FALSE
7206 | ST-2024-018 | 2022-09-01 | 1 | 1 | FALSE
7207 | ST-2024-018 | 2022-10-01 | 0 | 0 | FALSE
7208 | ST-2024-018 | 2022-11-01 | 1 | 1 | FALSE
7209 | ST-2024-018 | 2022-12-01 | 0 | 0 | FALSE
7210 | ST-2024-018 | 2023-01-01 | 1 | 1 | FALSE
7211 | ST-2024-018 | 2023-02-01 | 1 | 1 | FALSE
7212 | ST-2024-018 | 2023-03-01 | 1 | 1 | FALSE
7213 | ST-2024-018 | 2023-04-01 | 1 | 1 | FALSE
7214 | ST-2024-018 | 2023-05-01 | 2 | 3 | FALSE
7215 | ST-2024-018 | 2023-06-01 | 1 | 0 | TRUE
7216 | ST-2024-018 | 2023-07-01 | 2 | 2 | FALSE
7217 | ST-2024-018 | 2023-08-01 | 1 | 1 | FALSE
7218 | ST-2024-018 | 2023-09-01 | 2 | 3 | FALSE
7219 | ST-2024-018 | 2023-10-01 | 1 | 1 | FALSE
7220 | ST-2024-018 | 2023-11-01 | 2 | 1 | TRUE
7221 | ST-2024-018 | 2023-12-01 | 1 | 3 | FALSE
7222 | ST-2024-018 | 2024-01-01 | 1 | 1 | FALSE
7223 | ST-2024-018 | 2024-02-01 | 1 | 0 | TRUE
7224 | ST-2024-018 | 2024-03-01 | 1 | 2 | FALSE
7225 | ST-2024-018 | 2024-04-01 | 0 | 1 | FALSE
7226 | ST-2024-018 | 2024-05-01 | 1 | 0 | TRUE
7227 | ST-2024-018 | 2024-06-01 | 0 | 0 | FALSE
7228 | ST-2024-018 | 2024-07-01 | 1 | 1 | FALSE
7229 | ST-2024-018 | 2024-08-01 | 0 | 1 | FALSE
7230 | ST-2024-018 | 2024-09-01 | 0 | 0 | FALSE
7231 | ST-2024-018 | 2024-10-01 | 0 | 0 | FALSE
7232 | ST-2024-018 | 2024-11-01 | 0 | 0 | FALSE
7233 | ST-2024-018 | 2024-12-01 | 0 | 0 | FALSE
7234 | ST-2024-018 | 2025-01-01 | 0 | 0 | FALSE
7235 | ST-2024-020 | 2024-01-01 | 0 | 0 | FALSE
7236 | ST-2024-020 | 2024-02-01 | 0 | 0 | FALSE
7237 | ST-2024-020 | 2024-03-01 | 0 | 0 | FALSE
7238 | ST-2024-020 | 2024-04-01 | 0 | 0 | FALSE
7239 | ST-2024-020 | 2024-05-01 | 0 | 0 | FALSE
7240 | ST-2024-020 | 2024-06-01 | 1 | 0 | TRUE
7241 | ST-2024-020 | 2024-07-01 | 0 | 0 | FALSE
7242 | ST-2024-020 | 2024-08-01 | 0 | 0 | FALSE
7243 | ST-2024-020 | 2024-09-01 | 1 | 1 | FALSE
7244 | ST-2024-020 | 2024-10-01 | 0 | 0 | FALSE
7245 | ST-2024-020 | 2024-11-01 | 1 | 1 | FALSE
7246 | ST-2024-020 | 2024-12-01 | 1 | 1 | FALSE
7247 | ST-2024-020 | 2025-01-01 | 0 | 0 | FALSE
7248 | ST-2024-020 | 2025-02-01 | 1 | 1 | FALSE
7249 | ST-2024-020 | 2025-03-01 | 1 | 1 | FALSE
7250 | ST-2024-020 | 2025-04-01 | 1 | 0 | TRUE
7251 | ST-2024-020 | 2025-05-01 | 1 | 2 | FALSE
7252 | ST-2024-020 | 2025-06-01 | 1 | 1 | FALSE
7253 | ST-2024-020 | 2025-07-01 | 1 | 0 | TRUE
7254 | ST-2024-020 | 2025-08-01 | 0 | 1 | FALSE
7255 | ST-2024-020 | 2025-09-01 | 1 | 0 | TRUE
7256 | ST-2024-020 | 2025-10-01 | 1 | 1 | FALSE
7257 | ST-2024-020 | 2025-11-01 | 0 | 0 | FALSE
7258 | ST-2024-020 | 2025-12-01 | 1 | 1 | FALSE
7259 | ST-2024-020 | 2026-01-01 | 0 | 0 | FALSE
7260 | ST-2024-020 | 2026-02-01 | 0 | 0 | FALSE
7261 | ST-2024-020 | 2026-03-01 | 1 | 1 | FALSE
7262 | ST-2024-020 | 2026-04-01 | 0 | 0 | FALSE
7263 | ST-2024-020 | 2026-05-01 | 0 | 1 | FALSE
7264 | ST-2025-021 | 2018-03-01 | 4 | 4 | FALSE
7265 | ST-2025-021 | 2018-04-01 | 1 | 1 | FALSE
7266 | ST-2025-021 | 2018-05-01 | 1 | 1 | FALSE
7267 | ST-2025-021 | 2018-06-01 | 2 | 1 | TRUE
7268 | ST-2025-021 | 2018-07-01 | 2 | 3 | FALSE
7269 | ST-2025-021 | 2018-08-01 | 2 | 2 | FALSE
7270 | ST-2025-021 | 2018-09-01 | 4 | 5 | FALSE
7271 | ST-2025-021 | 2018-10-01 | 3 | 1 | TRUE
7272 | ST-2025-021 | 2018-11-01 | 5 | 6 | FALSE
7273 | ST-2025-021 | 2018-12-01 | 5 | 6 | FALSE
7274 | ST-2025-021 | 2019-01-01 | 7 | 5 | TRUE
7275 | ST-2025-021 | 2019-02-01 | 7 | 8 | FALSE
7276 | ST-2025-021 | 2019-03-01 | 8 | 10 | FALSE
7277 | ST-2025-021 | 2019-04-01 | 10 | 12 | FALSE
7278 | ST-2025-021 | 2019-05-01 | 10 | 9 | TRUE
7279 | ST-2025-021 | 2019-06-01 | 10 | 6 | TRUE
7280 | ST-2025-021 | 2019-07-01 | 11 | 13 | FALSE
7281 | ST-2025-021 | 2019-08-01 | 11 | 11 | FALSE
7282 | ST-2025-021 | 2019-09-01 | 10 | 17 | FALSE
7283 | ST-2025-021 | 2019-10-01 | 10 | 10 | FALSE
7284 | ST-2025-021 | 2019-11-01 | 10 | 3 | TRUE
7285 | ST-2025-021 | 2019-12-01 | 8 | 15 | FALSE
7286 | ST-2025-021 | 2020-01-01 | 7 | 1 | TRUE
7287 | ST-2025-021 | 2020-02-01 | 7 | 11 | FALSE
7288 | ST-2025-021 | 2020-03-01 | 5 | 1 | TRUE
7289 | ST-2025-021 | 2020-04-01 | 5 | 2 | TRUE
7290 | ST-2025-021 | 2020-05-01 | 3 | 2 | TRUE
7291 | ST-2025-021 | 2020-06-01 | 4 | 7 | FALSE
7292 | ST-2025-021 | 2020-07-01 | 2 | 12 | FALSE
7293 | ST-2025-021 | 2020-08-01 | 2 | 0 | TRUE
7294 | ST-2025-021 | 2020-09-01 | 2 | 5 | FALSE
7295 | ST-2025-021 | 2020-10-01 | 1 | 0 | TRUE
7296 | ST-2025-021 | 2020-11-01 | 1 | 2 | FALSE
7297 | ST-2025-021 | 2020-12-01 | 1 | 5 | FALSE
7298 | ST-2025-021 | 2021-01-01 | 0 | 0 | FALSE
7299 | ST-2025-021 | 2021-02-01 | 0 | 0 | FALSE
7300 | ST-2025-021 | 2021-03-01 | 0 | 0 | FALSE
7301 | ST-2025-022 | 2022-08-01 | 1 | 0 | TRUE
7302 | ST-2025-022 | 2022-09-01 | 0 | 0 | FALSE
7303 | ST-2025-022 | 2022-10-01 | 0 | 1 | FALSE
7304 | ST-2025-022 | 2022-11-01 | 1 | 1 | FALSE
7305 | ST-2025-022 | 2022-12-01 | 0 | 0 | FALSE
7306 | ST-2025-022 | 2023-01-01 | 1 | 2 | FALSE
7307 | ST-2025-022 | 2023-02-01 | 1 | 0 | TRUE
7308 | ST-2025-022 | 2023-03-01 | 0 | 1 | FALSE
7309 | ST-2025-022 | 2023-04-01 | 1 | 1 | FALSE
7310 | ST-2025-022 | 2023-05-01 | 2 | 1 | TRUE
7311 | ST-2025-022 | 2023-06-01 | 1 | 2 | FALSE
7312 | ST-2025-022 | 2023-07-01 | 2 | 1 | TRUE
7313 | ST-2025-022 | 2023-08-01 | 1 | 2 | FALSE
7314 | ST-2025-022 | 2023-09-01 | 2 | 2 | FALSE
7315 | ST-2025-022 | 2023-10-01 | 3 | 3 | FALSE
7316 | ST-2025-022 | 2023-11-01 | 2 | 2 | FALSE
7317 | ST-2025-022 | 2023-12-01 | 3 | 4 | FALSE
7318 | ST-2025-022 | 2024-01-01 | 3 | 2 | TRUE
7319 | ST-2025-022 | 2024-02-01 | 3 | 2 | TRUE
7320 | ST-2025-022 | 2024-03-01 | 3 | 2 | TRUE
7321 | ST-2025-022 | 2024-04-01 | 2 | 6 | FALSE
7322 | ST-2025-022 | 2024-05-01 | 3 | 0 | TRUE
7323 | ST-2025-022 | 2024-06-01 | 3 | 3 | FALSE
7324 | ST-2025-022 | 2024-07-01 | 3 | 5 | FALSE
7325 | ST-2025-022 | 2024-08-01 | 2 | 0 | TRUE
7326 | ST-2025-022 | 2024-09-01 | 3 | 7 | FALSE
7327 | ST-2025-022 | 2024-10-01 | 2 | 0 | TRUE
7328 | ST-2025-022 | 2024-11-01 | 1 | 2 | FALSE
7329 | ST-2025-022 | 2024-12-01 | 2 | 1 | TRUE
7330 | ST-2025-022 | 2025-01-01 | 1 | 5 | FALSE
7331 | ST-2025-022 | 2025-02-01 | 2 | 0 | TRUE
7332 | ST-2025-022 | 2025-03-01 | 1 | 0 | TRUE
7333 | ST-2025-022 | 2025-04-01 | 0 | 4 | FALSE
7334 | ST-2025-022 | 2025-05-01 | 1 | 0 | TRUE
7335 | ST-2025-022 | 2025-06-01 | 1 | 0 | TRUE
7336 | ST-2025-022 | 2025-07-01 | 0 | 3 | FALSE
7337 | ST-2025-022 | 2025-08-01 | 1 | 0 | TRUE
7338 | ST-2025-022 | 2025-09-01 | 0 | 0 | FALSE
7339 | ST-2025-022 | 2025-10-01 | 0 | 0 | FALSE
7340 | ST-2025-022 | 2025-11-01 | 0 | 1 | FALSE
7341 | ST-2025-022 | 2025-12-01 | 0 | 2 | FALSE
7342 | ST-2025-022 | 2026-01-01 | 0 | 0 | FALSE
7343 | ST-2025-022 | 2026-02-01 | 0 | 2 | FALSE
7344 | ST-2025-022 | 2026-03-01 | 0 | 0 | FALSE
7345 | ST-2025-023 | 2022-04-01 | 30 | 27 | TRUE
7346 | ST-2025-023 | 2022-05-01 | 4 | 3 | TRUE
7347 | ST-2025-023 | 2022-06-01 | 5 | 3 | TRUE
7348 | ST-2025-023 | 2022-07-01 | 6 | 6 | FALSE
7349 | ST-2025-023 | 2022-08-01 | 6 | 5 | TRUE
7350 | ST-2025-023 | 2022-09-01 | 7 | 9 | FALSE
7351 | ST-2025-023 | 2022-10-01 | 7 | 4 | TRUE
7352 | ST-2025-023 | 2022-11-01 | 9 | 5 | TRUE
7353 | ST-2025-023 | 2022-12-01 | 10 | 11 | FALSE
7354 | ST-2025-023 | 2023-01-01 | 11 | 11 | FALSE
7355 | ST-2025-023 | 2023-02-01 | 12 | 11 | TRUE
7356 | ST-2025-023 | 2023-03-01 | 14 | 15 | FALSE
7357 | ST-2025-023 | 2023-04-01 | 16 | 19 | FALSE
7358 | ST-2025-023 | 2023-05-01 | 17 | 4 | TRUE
7359 | ST-2025-023 | 2023-06-01 | 19 | 19 | FALSE
7360 | ST-2025-023 | 2023-07-01 | 21 | 28 | FALSE
7361 | ST-2025-023 | 2023-08-01 | 24 | 21 | TRUE
7362 | ST-2025-023 | 2023-09-01 | 25 | 27 | FALSE
7363 | ST-2025-023 | 2023-10-01 | 28 | 26 | TRUE
7364 | ST-2025-023 | 2023-11-01 | 31 | 20 | TRUE
7365 | ST-2025-023 | 2023-12-01 | 33 | 22 | TRUE
7366 | ST-2025-023 | 2024-01-01 | 35 | 21 | TRUE
7367 | ST-2025-023 | 2024-02-01 | 38 | 44 | FALSE
7368 | ST-2025-023 | 2024-03-01 | 40 | 28 | TRUE
7369 | ST-2025-023 | 2024-04-01 | 42 | 48 | FALSE
7370 | ST-2025-023 | 2024-05-01 | 44 | 37 | TRUE
7371 | ST-2025-023 | 2024-06-01 | 46 | 34 | TRUE
7372 | ST-2025-023 | 2024-07-01 | 48 | 62 | FALSE
7373 | ST-2025-023 | 2024-08-01 | 48 | 9 | TRUE
7374 | ST-2025-023 | 2024-09-01 | 49 | 67 | FALSE
7375 | ST-2025-023 | 2024-10-01 | 49 | 39 | TRUE
7376 | ST-2025-023 | 2024-11-01 | 49 | 29 | TRUE
7377 | ST-2025-023 | 2024-12-01 | 48 | 80 | FALSE
7378 | ST-2025-023 | 2025-01-01 | 48 | 0 | TRUE
7379 | ST-2025-023 | 2025-02-01 | 46 | 80 | FALSE
7380 | ST-2025-023 | 2025-03-01 | 44 | 87 | FALSE
7381 | ST-2025-023 | 2025-04-01 | 42 | 8 | TRUE
7382 | ST-2025-023 | 2025-05-01 | 40 | 34 | TRUE
7383 | ST-2025-023 | 2025-06-01 | 38 | 42 | FALSE
7384 | ST-2025-023 | 2025-07-01 | 35 | 57 | FALSE
7385 | ST-2025-023 | 2025-08-01 | 33 | 0 | TRUE
7386 | ST-2025-023 | 2025-09-01 | 31 | 43 | FALSE
7387 | ST-2025-023 | 2025-10-01 | 28 | 0 | TRUE
7388 | ST-2025-023 | 2025-11-01 | 25 | 71 | FALSE
7389 | ST-2025-023 | 2025-12-01 | 24 | 0 | TRUE
7390 | ST-2025-023 | 2026-01-01 | 21 | 114 | FALSE
7391 | ST-2025-023 | 2026-02-01 | 19 | 0 | TRUE
7392 | ST-2025-023 | 2026-03-01 | 17 | 108 | FALSE
7393 | ST-2025-023 | 2026-04-01 | 16 | 0 | TRUE
7394 | ST-2025-023 | 2026-05-01 | 14 | 0 | TRUE
7395 | ST-2025-024 | 2025-01-01 | 5 | 3 | TRUE
7396 | ST-2025-024 | 2025-02-01 | 2 | 2 | FALSE
7397 | ST-2025-024 | 2025-03-01 | 3 | 1 | TRUE
7398 | ST-2025-024 | 2025-04-01 | 4 | 4 | FALSE
7399 | ST-2025-024 | 2025-05-01 | 5 | 3 | TRUE
7400 | ST-2025-024 | 2025-06-01 | 7 | 5 | TRUE
7401 | ST-2025-024 | 2025-07-01 | 8 | 5 | TRUE
7402 | ST-2025-024 | 2025-08-01 | 11 | 8 | TRUE
7403 | ST-2025-024 | 2025-09-01 | 14 | 9 | TRUE
7404 | ST-2025-024 | 2025-10-01 | 15 | 14 | TRUE
7405 | ST-2025-024 | 2025-11-01 | 17 | 14 | TRUE
7406 | ST-2025-024 | 2025-12-01 | 19 | 10 | TRUE
7407 | ST-2025-024 | 2026-01-01 | 18 | 16 | TRUE
7408 | ST-2025-024 | 2026-02-01 | 17 | 13 | TRUE
7409 | ST-2025-024 | 2026-03-01 | 15 | 4 | TRUE
7410 | ST-2025-024 | 2026-04-01 | 14 | 22 | FALSE
7411 | ST-2025-024 | 2026-05-01 | 11 | 2 | TRUE
7412 | ST-2025-026 | 2020-11-01 | 5 | 3 | TRUE
7413 | ST-2025-026 | 2020-12-01 | 0 | 0 | FALSE
7414 | ST-2025-026 | 2021-01-01 | 0 | 0 | FALSE
7415 | ST-2025-026 | 2021-02-01 | 1 | 0 | TRUE
7416 | ST-2025-026 | 2021-03-01 | 0 | 0 | FALSE
7417 | ST-2025-026 | 2021-04-01 | 1 | 1 | FALSE
7418 | ST-2025-026 | 2021-05-01 | 1 | 1 | FALSE
7419 | ST-2025-026 | 2021-06-01 | 0 | 0 | FALSE
7420 | ST-2025-026 | 2021-07-01 | 1 | 0 | TRUE
7421 | ST-2025-026 | 2021-08-01 | 1 | 1 | FALSE
7422 | ST-2025-026 | 2021-09-01 | 1 | 1 | FALSE
7423 | ST-2025-026 | 2021-10-01 | 1 | 0 | TRUE
7424 | ST-2025-026 | 2021-11-01 | 1 | 1 | FALSE
7425 | ST-2025-026 | 2021-12-01 | 1 | 1 | FALSE
7426 | ST-2025-026 | 2022-01-01 | 1 | 1 | FALSE
7427 | ST-2025-026 | 2022-02-01 | 1 | 0 | TRUE
7428 | ST-2025-026 | 2022-03-01 | 2 | 2 | FALSE
7429 | ST-2025-026 | 2022-04-01 | 1 | 1 | FALSE
7430 | ST-2025-026 | 2022-05-01 | 1 | 0 | TRUE
7431 | ST-2025-026 | 2022-06-01 | 2 | 3 | FALSE
7432 | ST-2025-026 | 2022-07-01 | 2 | 0 | TRUE
7433 | ST-2025-026 | 2022-08-01 | 2 | 3 | FALSE
7434 | ST-2025-026 | 2022-09-01 | 2 | 0 | TRUE
7435 | ST-2025-026 | 2022-10-01 | 2 | 1 | TRUE
7436 | ST-2025-026 | 2022-11-01 | 2 | 2 | FALSE
7437 | ST-2025-026 | 2022-12-01 | 3 | 1 | TRUE
7438 | ST-2025-026 | 2023-01-01 | 2 | 2 | FALSE
7439 | ST-2025-026 | 2023-02-01 | 3 | 2 | TRUE
7440 | ST-2025-026 | 2023-03-01 | 3 | 1 | TRUE
7441 | ST-2025-026 | 2023-04-01 | 3 | 4 | FALSE
7442 | ST-2025-026 | 2023-05-01 | 3 | 1 | TRUE
7443 | ST-2025-026 | 2023-06-01 | 4 | 4 | FALSE
7444 | ST-2025-026 | 2023-07-01 | 3 | 0 | TRUE
7445 | ST-2025-026 | 2023-08-01 | 4 | 1 | TRUE
7446 | ST-2025-026 | 2023-09-01 | 4 | 7 | FALSE
7447 | ST-2025-026 | 2023-10-01 | 4 | 0 | TRUE
7448 | ST-2025-026 | 2023-11-01 | 4 | 3 | TRUE
7449 | ST-2025-026 | 2023-12-01 | 4 | 3 | TRUE
7450 | ST-2025-026 | 2024-01-01 | 5 | 1 | TRUE
7451 | ST-2025-026 | 2024-02-01 | 5 | 5 | FALSE
7452 | ST-2025-026 | 2024-03-01 | 5 | 2 | TRUE
7453 | ST-2025-026 | 2024-04-01 | 4 | 3 | TRUE
7454 | ST-2025-026 | 2024-05-01 | 6 | 6 | FALSE
7455 | ST-2025-026 | 2024-06-01 | 5 | 3 | TRUE
7456 | ST-2025-026 | 2024-07-01 | 5 | 2 | TRUE
7457 | ST-2025-026 | 2024-08-01 | 5 | 6 | FALSE
7458 | ST-2025-026 | 2024-09-01 | 5 | 0 | TRUE
7459 | ST-2025-026 | 2024-10-01 | 6 | 10 | FALSE
7460 | ST-2025-026 | 2024-11-01 | 5 | 0 | TRUE
7461 | ST-2025-026 | 2024-12-01 | 6 | 13 | FALSE
7462 | ST-2025-026 | 2025-01-01 | 5 | 2 | TRUE
7463 | ST-2025-026 | 2025-02-01 | 5 | 0 | TRUE
7464 | ST-2025-026 | 2025-03-01 | 5 | 4 | TRUE
7465 | ST-2025-026 | 2025-04-01 | 5 | 3 | TRUE
7466 | ST-2025-026 | 2025-05-01 | 6 | 4 | TRUE
7467 | ST-2025-026 | 2025-06-01 | 4 | 7 | FALSE
7468 | ST-2025-026 | 2025-07-01 | 5 | 0 | TRUE
7469 | ST-2025-026 | 2025-08-01 | 5 | 2 | TRUE
7470 | ST-2025-026 | 2025-09-01 | 5 | 12 | FALSE
7471 | ST-2025-026 | 2025-10-01 | 4 | 0 | TRUE
7472 | ST-2025-026 | 2025-11-01 | 4 | 14 | FALSE
7473 | ST-2025-026 | 2025-12-01 | 4 | 5 | FALSE
7474 | ST-2025-026 | 2026-01-01 | 4 | 0 | TRUE
7475 | ST-2025-026 | 2026-02-01 | 4 | 14 | FALSE
7476 | ST-2025-026 | 2026-03-01 | 3 | 0 | TRUE
7477 | ST-2025-026 | 2026-04-01 | 4 | 12 | FALSE
7478 | ST-2025-026 | 2026-05-01 | 3 | 5 | FALSE
7479 | ST-2025-027 | 2023-03-01 | 1 | 0 | TRUE
7480 | ST-2025-027 | 2023-04-01 | 1 | 1 | FALSE
7481 | ST-2025-027 | 2023-05-01 | 0 | 0 | FALSE
7482 | ST-2025-027 | 2023-06-01 | 1 | 2 | FALSE
7483 | ST-2025-027 | 2023-07-01 | 0 | 0 | FALSE
7484 | ST-2025-027 | 2023-08-01 | 1 | 2 | FALSE
7485 | ST-2025-027 | 2023-09-01 | 1 | 0 | TRUE
7486 | ST-2025-027 | 2023-10-01 | 1 | 1 | FALSE
7487 | ST-2025-027 | 2023-11-01 | 2 | 2 | FALSE
7488 | ST-2025-027 | 2023-12-01 | 1 | 2 | FALSE
7489 | ST-2025-027 | 2024-01-01 | 2 | 2 | FALSE
7490 | ST-2025-027 | 2024-02-01 | 2 | 1 | TRUE
7491 | ST-2025-027 | 2024-03-01 | 2 | 2 | FALSE
7492 | ST-2025-027 | 2024-04-01 | 3 | 2 | TRUE
7493 | ST-2025-027 | 2024-05-01 | 3 | 4 | FALSE
7494 | ST-2025-027 | 2024-06-01 | 3 | 2 | TRUE
7495 | ST-2025-027 | 2024-07-01 | 4 | 6 | FALSE
7496 | ST-2025-027 | 2024-08-01 | 3 | 3 | FALSE
7497 | ST-2025-027 | 2024-09-01 | 4 | 3 | TRUE
7498 | ST-2025-027 | 2024-10-01 | 4 | 3 | TRUE
7499 | ST-2025-027 | 2024-11-01 | 5 | 6 | FALSE
7500 | ST-2025-027 | 2024-12-01 | 4 | 4 | FALSE
7501 | ST-2025-027 | 2025-01-01 | 4 | 0 | TRUE
7502 | ST-2025-027 | 2025-02-01 | 4 | 4 | FALSE
7503 | ST-2025-027 | 2025-03-01 | 3 | 3 | FALSE
7504 | ST-2025-027 | 2025-04-01 | 4 | 9 | FALSE
7505 | ST-2025-027 | 2025-05-01 | 3 | 0 | TRUE
7506 | ST-2025-027 | 2025-06-01 | 3 | 3 | FALSE
7507 | ST-2025-027 | 2025-07-01 | 3 | 6 | FALSE
7508 | ST-2025-027 | 2025-08-01 | 2 | 2 | FALSE
7509 | ST-2025-027 | 2025-09-01 | 2 | 0 | TRUE
7510 | ST-2025-027 | 2025-10-01 | 2 | 6 | FALSE
7511 | ST-2025-027 | 2025-11-01 | 1 | 0 | TRUE
7512 | ST-2025-027 | 2025-12-01 | 2 | 3 | FALSE
7513 | ST-2025-027 | 2026-01-01 | 1 | 0 | TRUE
7514 | ST-2025-027 | 2026-02-01 | 1 | 4 | FALSE
7515 | ST-2025-027 | 2026-03-01 | 1 | 0 | TRUE
7516 | ST-2025-027 | 2026-04-01 | 0 | 2 | FALSE
7517 | ST-2025-027 | 2026-05-01 | 1 | 6 | FALSE
7518 | ST-2025-028 | 2025-10-01 | 1520 | 1384 | TRUE
7519 | ST-2025-028 | 2025-11-01 | 368 | 489 | FALSE
7520 | ST-2025-028 | 2025-12-01 | 454 | 230 | TRUE
7521 | ST-2025-028 | 2026-01-01 | 558 | 625 | FALSE
7522 | ST-2025-028 | 2026-02-01 | 683 | 536 | TRUE
7523 | ST-2025-028 | 2026-03-01 | 834 | 998 | FALSE
7524 | ST-2025-028 | 2026-04-01 | 1012 | 730 | TRUE
7525 | ST-2025-028 | 2026-05-01 | 1219 | 1581 | FALSE
7526 | ST-2025-029 | 2024-07-01 | 4 | 2 | TRUE
7527 | ST-2025-029 | 2024-08-01 | 2 | 1 | TRUE
7528 | ST-2025-029 | 2024-09-01 | 2 | 2 | FALSE
7529 | ST-2025-029 | 2024-10-01 | 3 | 1 | TRUE
7530 | ST-2025-029 | 2024-11-01 | 4 | 3 | TRUE
7531 | ST-2025-029 | 2024-12-01 | 5 | 3 | TRUE
7532 | ST-2025-029 | 2025-01-01 | 7 | 3 | TRUE
7533 | ST-2025-029 | 2025-02-01 | 8 | 5 | TRUE
7534 | ST-2025-029 | 2025-03-01 | 10 | 8 | TRUE
7535 | ST-2025-029 | 2025-04-01 | 11 | 6 | TRUE
7536 | ST-2025-029 | 2025-05-01 | 14 | 8 | TRUE
7537 | ST-2025-029 | 2025-06-01 | 14 | 10 | TRUE
7538 | ST-2025-029 | 2025-07-01 | 16 | 5 | TRUE
7539 | ST-2025-029 | 2025-08-01 | 15 | 11 | TRUE
7540 | ST-2025-029 | 2025-09-01 | 14 | 14 | FALSE
7541 | ST-2025-029 | 2025-10-01 | 14 | 0 | TRUE
7542 | ST-2025-029 | 2025-11-01 | 11 | 10 | TRUE
7543 | ST-2025-029 | 2025-12-01 | 10 | 5 | TRUE
7544 | ST-2025-029 | 2026-01-01 | 8 | 6 | TRUE
7545 | ST-2025-029 | 2026-02-01 | 7 | 2 | TRUE
7546 | ST-2025-029 | 2026-03-01 | 5 | 10 | FALSE
7547 | ST-2025-029 | 2026-04-01 | 4 | 2 | TRUE
7548 | ST-2025-029 | 2026-05-01 | 3 | 5 | FALSE
7549 | ST-2025-030 | 2024-04-01 | 32 | 21 | TRUE
7550 | ST-2025-030 | 2024-05-01 | 11 | 10 | TRUE
7551 | ST-2025-030 | 2024-06-01 | 13 | 9 | TRUE
7552 | ST-2025-030 | 2024-07-01 | 17 | 9 | TRUE
7553 | ST-2025-030 | 2024-08-01 | 21 | 15 | TRUE
7554 | ST-2025-030 | 2024-09-01 | 28 | 21 | TRUE
7555 | ST-2025-030 | 2024-10-01 | 35 | 28 | TRUE
7556 | ST-2025-030 | 2024-11-01 | 42 | 31 | TRUE
7557 | ST-2025-030 | 2024-12-01 | 52 | 30 | TRUE
7558 | ST-2025-030 | 2025-01-01 | 62 | 39 | TRUE
7559 | ST-2025-030 | 2025-02-01 | 73 | 42 | TRUE
7560 | ST-2025-030 | 2025-03-01 | 81 | 79 | TRUE
7561 | ST-2025-030 | 2025-04-01 | 90 | 48 | TRUE
7562 | ST-2025-030 | 2025-05-01 | 94 | 52 | TRUE
7563 | ST-2025-030 | 2025-06-01 | 97 | 68 | TRUE
7564 | ST-2025-030 | 2025-07-01 | 94 | 61 | TRUE
7565 | ST-2025-030 | 2025-08-01 | 90 | 72 | TRUE
7566 | ST-2025-030 | 2025-09-01 | 81 | 37 | TRUE
7567 | ST-2025-030 | 2025-10-01 | 73 | 63 | TRUE
7568 | ST-2025-030 | 2025-11-01 | 62 | 15 | TRUE
7569 | ST-2025-030 | 2025-12-01 | 52 | 97 | FALSE
7570 | ST-2025-030 | 2026-01-01 | 42 | 32 | TRUE
7571 | ST-2025-030 | 2026-02-01 | 35 | 0 | TRUE
7572 | ST-2025-030 | 2026-03-01 | 28 | 55 | FALSE
7573 | ST-2025-030 | 2026-04-01 | 21 | 0 | TRUE
7574 | ST-2025-030 | 2026-05-01 | 17 | 2 | TRUE
7575 | ST-2025-032 | 2025-05-01 | 6 | 5 | TRUE
7576 | ST-2025-032 | 2025-06-01 | 1 | 1 | FALSE
7577 | ST-2025-032 | 2025-07-01 | 1 | 1 | FALSE
7578 | ST-2025-032 | 2025-08-01 | 1 | 1 | FALSE
7579 | ST-2025-032 | 2025-09-01 | 1 | 1 | FALSE
7580 | ST-2025-032 | 2025-10-01 | 2 | 1 | TRUE
7581 | ST-2025-032 | 2025-11-01 | 2 | 3 | FALSE
7582 | ST-2025-032 | 2025-12-01 | 2 | 0 | TRUE
7583 | ST-2025-032 | 2026-01-01 | 2 | 3 | FALSE
7584 | ST-2025-032 | 2026-02-01 | 3 | 4 | FALSE
7585 | ST-2025-032 | 2026-03-01 | 3 | 2 | TRUE
7586 | ST-2025-032 | 2026-04-01 | 3 | 3 | FALSE
7587 | ST-2025-032 | 2026-05-01 | 4 | 3 | TRUE
7588 | ST-2025-033 | 2022-04-01 | 0 | 0 | FALSE
7589 | ST-2025-033 | 2022-05-01 | 0 | 0 | FALSE
7590 | ST-2025-033 | 2022-06-01 | 0 | 0 | FALSE
7591 | ST-2025-033 | 2022-07-01 | 0 | 0 | FALSE
7592 | ST-2025-033 | 2022-08-01 | 0 | 0 | FALSE
7593 | ST-2025-033 | 2022-09-01 | 0 | 0 | FALSE
7594 | ST-2025-033 | 2022-10-01 | 1 | 0 | TRUE
7595 | ST-2025-033 | 2022-11-01 | 0 | 0 | FALSE
7596 | ST-2025-033 | 2022-12-01 | 0 | 0 | FALSE
7597 | ST-2025-033 | 2023-01-01 | 0 | 0 | FALSE
7598 | ST-2025-033 | 2023-02-01 | 0 | 0 | FALSE
7599 | ST-2025-033 | 2023-03-01 | 1 | 1 | FALSE
7600 | ST-2025-033 | 2023-04-01 | 0 | 0 | FALSE
7601 | ST-2025-033 | 2023-05-01 | 1 | 1 | FALSE
7602 | ST-2025-033 | 2023-06-01 | 0 | 0 | FALSE
7603 | ST-2025-033 | 2023-07-01 | 1 | 1 | FALSE
7604 | ST-2025-033 | 2023-08-01 | 0 | 0 | FALSE
7605 | ST-2025-033 | 2023-09-01 | 1 | 1 | FALSE
7606 | ST-2025-033 | 2023-10-01 | 1 | 1 | FALSE
7607 | ST-2025-033 | 2023-11-01 | 0 | 0 | FALSE
7608 | ST-2025-033 | 2023-12-01 | 1 | 0 | TRUE
7609 | ST-2025-033 | 2024-01-01 | 1 | 2 | FALSE
7610 | ST-2025-033 | 2024-02-01 | 1 | 0 | TRUE
7611 | ST-2025-033 | 2024-03-01 | 0 | 0 | FALSE
7612 | ST-2025-033 | 2024-04-01 | 1 | 2 | FALSE
7613 | ST-2025-033 | 2024-05-01 | 1 | 0 | TRUE
7614 | ST-2025-033 | 2024-06-01 | 0 | 1 | FALSE
7615 | ST-2025-033 | 2024-07-01 | 1 | 0 | TRUE
7616 | ST-2025-033 | 2024-08-01 | 0 | 0 | FALSE
7617 | ST-2025-033 | 2024-09-01 | 1 | 1 | FALSE
7618 | ST-2025-033 | 2024-10-01 | 0 | 0 | FALSE
7619 | ST-2025-033 | 2024-11-01 | 1 | 2 | FALSE
7620 | ST-2025-033 | 2024-12-01 | 0 | 0 | FALSE
7621 | ST-2025-033 | 2025-01-01 | 0 | 0 | FALSE
7622 | ST-2025-033 | 2025-02-01 | 0 | 0 | FALSE
7623 | ST-2025-033 | 2025-03-01 | 0 | 1 | FALSE
7624 | ST-2025-033 | 2025-04-01 | 1 | 1 | FALSE
7625 | ST-2025-033 | 2025-05-01 | 0 | 0 | FALSE
7626 | ST-2025-033 | 2025-06-01 | 0 | 0 | FALSE
7627 | ST-2025-033 | 2025-07-01 | 0 | 0 | FALSE
7628 | ST-2025-033 | 2025-08-01 | 0 | 1 | FALSE
7629 | ST-2025-033 | 2025-09-01 | 0 | 0 | FALSE
7630 | ST-2025-033 | 2025-10-01 | 0 | 0 | FALSE
7631 | ST-2025-033 | 2025-11-01 | 0 | 0 | FALSE
7632 | ST-2025-033 | 2025-12-01 | 0 | 1 | FALSE
7633 | ST-2025-033 | 2026-01-01 | 0 | 0 | FALSE
7634 | ST-2025-034 | 2023-06-01 | 0 | 0 | FALSE
7635 | ST-2025-034 | 2023-07-01 | 0 | 0 | FALSE
7636 | ST-2025-034 | 2023-08-01 | 0 | 0 | FALSE
7637 | ST-2025-034 | 2023-09-01 | 0 | 0 | FALSE
7638 | ST-2025-034 | 2023-10-01 | 0 | 0 | FALSE
7639 | ST-2025-034 | 2023-11-01 | 1 | 0 | TRUE
7640 | ST-2025-034 | 2023-12-01 | 0 | 0 | FALSE
7641 | ST-2025-034 | 2024-01-01 | 0 | 0 | FALSE
7642 | ST-2025-034 | 2024-02-01 | 0 | 0 | FALSE
7643 | ST-2025-034 | 2024-03-01 | 1 | 1 | FALSE
7644 | ST-2025-034 | 2024-04-01 | 0 | 1 | FALSE
7645 | ST-2025-034 | 2024-05-01 | 1 | 0 | TRUE
7646 | ST-2025-034 | 2024-06-01 | 0 | 1 | FALSE
7647 | ST-2025-034 | 2024-07-01 | 1 | 0 | TRUE
7648 | ST-2025-034 | 2024-08-01 | 0 | 0 | FALSE
7649 | ST-2025-034 | 2024-09-01 | 1 | 2 | FALSE
7650 | ST-2025-034 | 2024-10-01 | 1 | 0 | TRUE
7651 | ST-2025-034 | 2024-11-01 | 1 | 1 | FALSE
7652 | ST-2025-034 | 2024-12-01 | 1 | 1 | FALSE
7653 | ST-2025-034 | 2025-01-01 | 1 | 2 | FALSE
7654 | ST-2025-034 | 2025-02-01 | 1 | 0 | TRUE
7655 | ST-2025-034 | 2025-03-01 | 0 | 0 | FALSE
7656 | ST-2025-034 | 2025-04-01 | 1 | 1 | FALSE
7657 | ST-2025-034 | 2025-05-01 | 1 | 1 | FALSE
7658 | ST-2025-034 | 2025-06-01 | 1 | 1 | FALSE
7659 | ST-2025-034 | 2025-07-01 | 1 | 2 | FALSE
7660 | ST-2025-034 | 2025-08-01 | 1 | 0 | TRUE
7661 | ST-2025-034 | 2025-09-01 | 0 | 1 | FALSE
7662 | ST-2025-034 | 2025-10-01 | 1 | 0 | TRUE
7663 | ST-2025-034 | 2025-11-01 | 0 | 0 | FALSE
7664 | ST-2025-034 | 2025-12-01 | 1 | 1 | FALSE
7665 | ST-2025-034 | 2026-01-01 | 0 | 0 | FALSE
7666 | ST-2025-034 | 2026-02-01 | 1 | 1 | FALSE
7667 | ST-2025-034 | 2026-03-01 | 0 | 1 | FALSE
7668 | ST-2025-034 | 2026-04-01 | 0 | 0 | FALSE
7669 | ST-2025-034 | 2026-05-01 | 0 | 0 | FALSE
7670 | ST-2025-035 | 2025-06-01 | 0 | 0 | FALSE
7671 | ST-2025-035 | 2025-07-01 | 0 | 0 | FALSE
7672 | ST-2025-035 | 2025-08-01 | 0 | 0 | FALSE
7673 | ST-2025-035 | 2025-09-01 | 1 | 1 | FALSE
7674 | ST-2025-035 | 2025-10-01 | 0 | 0 | FALSE
7675 | ST-2025-035 | 2025-11-01 | 1 | 1 | FALSE
7676 | ST-2025-035 | 2025-12-01 | 1 | 1 | FALSE
7677 | ST-2025-035 | 2026-01-01 | 1 | 1 | FALSE
7678 | ST-2025-035 | 2026-02-01 | 1 | 1 | FALSE
7679 | ST-2025-035 | 2026-03-01 | 1 | 1 | FALSE
7680 | ST-2025-035 | 2026-04-01 | 2 | 2 | FALSE
7681 | ST-2025-035 | 2026-05-01 | 1 | 1 | FALSE
7682 | ST-2025-036 | 2021-11-01 | 9 | 8 | TRUE
7683 | ST-2025-036 | 2021-12-01 | 2 | 2 | FALSE
7684 | ST-2025-036 | 2022-01-01 | 1 | 0 | TRUE
7685 | ST-2025-036 | 2022-02-01 | 1 | 1 | FALSE
7686 | ST-2025-036 | 2022-03-01 | 2 | 3 | FALSE
7687 | ST-2025-036 | 2022-04-01 | 1 | 0 | TRUE
7688 | ST-2025-036 | 2022-05-01 | 2 | 3 | FALSE
7689 | ST-2025-036 | 2022-06-01 | 2 | 1 | TRUE
7690 | ST-2025-036 | 2022-07-01 | 2 | 1 | TRUE
7691 | ST-2025-036 | 2022-08-01 | 3 | 3 | FALSE
7692 | ST-2025-036 | 2022-09-01 | 2 | 2 | FALSE
7693 | ST-2025-036 | 2022-10-01 | 3 | 3 | FALSE
7694 | ST-2025-036 | 2022-11-01 | 4 | 3 | TRUE
7695 | ST-2025-036 | 2022-12-01 | 3 | 3 | FALSE
7696 | ST-2025-036 | 2023-01-01 | 4 | 5 | FALSE
7697 | ST-2025-036 | 2023-02-01 | 4 | 5 | FALSE
7698 | ST-2025-036 | 2023-03-01 | 5 | 2 | TRUE
7699 | ST-2025-036 | 2023-04-01 | 5 | 6 | FALSE
7700 | ST-2025-036 | 2023-05-01 | 6 | 4 | TRUE
7701 | ST-2025-036 | 2023-06-01 | 5 | 3 | TRUE
7702 | ST-2025-036 | 2023-07-01 | 7 | 12 | FALSE
7703 | ST-2025-036 | 2023-08-01 | 7 | 1 | TRUE
7704 | ST-2025-036 | 2023-09-01 | 7 | 13 | FALSE
7705 | ST-2025-036 | 2023-10-01 | 8 | 7 | TRUE
7706 | ST-2025-036 | 2023-11-01 | 9 | 4 | TRUE
7707 | ST-2025-036 | 2023-12-01 | 9 | 15 | FALSE
7708 | ST-2025-036 | 2024-01-01 | 10 | 10 | FALSE
7709 | ST-2025-036 | 2024-02-01 | 10 | 4 | TRUE
7710 | ST-2025-036 | 2024-03-01 | 10 | 16 | FALSE
7711 | ST-2025-036 | 2024-04-01 | 12 | 0 | TRUE
7712 | ST-2025-036 | 2024-05-01 | 11 | 15 | FALSE
7713 | ST-2025-036 | 2024-06-01 | 12 | 11 | TRUE
7714 | ST-2025-036 | 2024-07-01 | 13 | 10 | TRUE
7715 | ST-2025-036 | 2024-08-01 | 12 | 18 | FALSE
7716 | ST-2025-036 | 2024-09-01 | 13 | 13 | FALSE
7717 | ST-2025-036 | 2024-10-01 | 14 | 3 | TRUE
7718 | ST-2025-036 | 2024-11-01 | 13 | 24 | FALSE
7719 | ST-2025-036 | 2024-12-01 | 13 | 0 | TRUE
7720 | ST-2025-036 | 2025-01-01 | 13 | 15 | FALSE
7721 | ST-2025-036 | 2025-02-01 | 14 | 21 | FALSE
7722 | ST-2025-036 | 2025-03-01 | 13 | 11 | TRUE
7723 | ST-2025-036 | 2025-04-01 | 12 | 14 | FALSE
7724 | ST-2025-036 | 2025-05-01 | 13 | 0 | TRUE
7725 | ST-2025-036 | 2025-06-01 | 12 | 27 | FALSE
7726 | ST-2025-036 | 2025-07-01 | 11 | 25 | FALSE
7727 | ST-2025-036 | 2025-08-01 | 12 | 0 | TRUE
7728 | ST-2025-036 | 2025-09-01 | 10 | 0 | TRUE
7729 | ST-2025-036 | 2025-10-01 | 10 | 25 | FALSE
7730 | ST-2025-036 | 2025-11-01 | 10 | 0 | TRUE
7731 | ST-2025-036 | 2025-12-01 | 9 | 28 | FALSE
7732 | ST-2025-036 | 2026-01-01 | 9 | 21 | FALSE
7733 | ST-2025-036 | 2026-02-01 | 8 | 7 | TRUE
7734 | ST-2025-036 | 2026-03-01 | 7 | 0 | TRUE
7735 | ST-2025-036 | 2026-04-01 | 7 | 10 | FALSE
7736 | ST-2025-036 | 2026-05-01 | 7 | 9 | FALSE

## KPI Snapshot
id | study_id | enrollment_vs_plan_percent | current_rate_per_week | planned_rate_per_week | screen_failure_rate | dropout_rate | sites_activated | sites_planned | countries_activated | countries_planned | snapshot_date
639 | ST-2024-002 | 78.38 | 0.7 | 0.9 | 24.8 | 11.1 | 19 | 19 | 5 | 5 | 2026-05-18
640 | ST-2024-003 | 106.52 | 0.5 | 0.4 | 17.3 | 3.6 | 24 | 24 | 6 | 6 | 2026-05-18
641 | ST-2024-004 | 76.47 | 0.4 | 0.5 | 16 | 9.7 | 23 | 23 | 7 | 7 | 2026-05-18
642 | ST-2024-005 | 75.53 | 0.4 | 0.5 | 23.6 | 8.5 | 22 | 22 | 6 | 6 | 2026-05-18
643 | ST-2024-006 | 77.94 | 0.5 | 0.7 | 26.1 | 3.7 | 11 | 11 | 4 | 4 | 2026-05-18
644 | ST-2024-008 | 83.67 | 0.2 | 0.2 | 24.9 | 3.6 | 11 | 11 | 3 | 3 | 2026-05-18
645 | ST-2024-009 | 77.78 | 0.5 | 0.6 | 23.6 | 3.8 | 24 | 24 | 5 | 5 | 2026-05-18
646 | ST-2024-010 | 85.91 | 9.5 | 11.1 | 16.8 | 6.4 | 11 | 11 | 3 | 3 | 2026-05-18
647 | ST-2024-011 | 71.43 | 0.2 | 0.3 | 17.5 | 6.8 | 15 | 15 | 4 | 4 | 2026-05-18
648 | ST-2024-012 | 73.91 | 0.4 | 0.5 | 18 | 3.8 | 23 | 23 | 6 | 6 | 2026-05-18
649 | ST-2024-014 | 90.91 | 0.2 | 0.2 | 21.8 | 4.1 | 34 | 34 | 8 | 8 | 2026-05-18
650 | ST-2024-015 | 88.24 | 0.5 | 0.6 | 29.6 | 5.5 | 19 | 19 | 6 | 6 | 2026-05-18
651 | ST-2024-016 | 88.24 | 0.8 | 0.8 | 28.7 | 6.2 | 22 | 22 | 6 | 6 | 2026-05-18
652 | ST-2024-017 | 64.29 | 0.2 | 0.3 | 20.5 | 3.1 | 17 | 17 | 3 | 3 | 2026-05-18
653 | ST-2024-018 | 104.35 | 0.2 | 0.2 | 17.7 | 5.5 | 10 | 10 | 3 | 3 | 2026-05-18
654 | ST-2024-020 | 85.71 | 0.1 | 0.1 | 15.1 | 9.6 | 16 | 16 | 4 | 4 | 2026-05-18
655 | ST-2025-021 | 102.21 | 1.2 | 1.2 | 22.1 | 9 | 14 | 14 | 5 | 5 | 2026-05-18
656 | ST-2025-022 | 96.55 | 0.3 | 0.3 | 19.5 | 4.8 | 21 | 21 | 6 | 6 | 2026-05-18
657 | ST-2025-023 | 87.86 | 6.1 | 7 | 21.8 | 6.6 | 25 | 25 | 6 | 6 | 2026-05-18
658 | ST-2025-024 | 72.97 | 2 | 2.7 | 15 | 6.8 | 22 | 22 | 5 | 5 | 2026-05-18
659 | ST-2025-026 | 69.48 | 0.6 | 0.8 | 32.1 | 11.6 | 23 | 23 | 6 | 6 | 2026-05-18
660 | ST-2025-027 | 101.18 | 0.6 | 0.5 | 20 | 7.4 | 32 | 32 | 8 | 8 | 2026-05-18
661 | ST-2025-028 | 98.87 | 205.4 | 207.8 | 17.9 | 10.7 | 9 | 9 | 3 | 3 | 2026-05-18
662 | ST-2025-029 | 63.87 | 1.3 | 2.1 | 19.2 | 10 | 26 | 26 | 6 | 6 | 2026-05-18
663 | ST-2025-030 | 67.01 | 8.7 | 12.9 | 15.3 | 3.4 | 35 | 35 | 8 | 8 | 2026-05-18
664 | ST-2025-032 | 90.32 | 0.5 | 0.6 | 30.6 | 6 | 14 | 14 | 4 | 4 | 2026-05-18
665 | ST-2025-033 | 86.67 | 0.1 | 0.1 | 22.2 | 4.8 | 12 | 12 | 4 | 4 | 2026-05-18
666 | ST-2025-034 | 94.44 | 0.1 | 0.1 | 21.4 | 11.4 | 9 | 9 | 3 | 3 | 2026-05-18
667 | ST-2025-035 | 100 | 0.2 | 0.2 | 24.5 | 11.1 | 33 | 33 | 8 | 8 | 2026-05-18
668 | ST-2025-036 | 95.15 | 1.9 | 2 | 33.5 | 6 | 27 | 27 | 6 | 6 | 2026-05-18

## Country Breakdown
id | study_id | country | target_enrollment | actual_enrollment | enrollment_percent | sites_active | avg_enrollment_rate | performance_status | country_lead | country_selected | ccpc_planned | ccpc_actual | reg_submission_planned | reg_submission_actual | reg_approval_planned | reg_approval_actual | ethics_submission_planned | ethics_submission_actual | ethics_approval_planned | ethics_approval_actual | country_fsa_planned | country_fsa_actual | country_fsi_planned | country_fsi_actual | country_lsi_planned | country_lsi_actual | country_lsld_planned | country_lsld_actual | country_end_planned | country_end_actual | country_lsc_planned | country_lsc_actual
1510 | ST-2024-002 | United States | 18 | 13 | 72.2 | 5 | 1.9 | OFF_TRACK | Dr. Michelle Jones | 2022-12-07 | 2023-03-20 | 2023-03-19 | 2023-06-18 | 2023-06-05 | 2023-12-13 | 2023-11-29 | 2023-08-15 | 2023-08-03 | 2024-01-12 | 2024-01-04 | 2024-06-24 | 2024-06-17 | 2024-09-21 | 2024-09-23 | 2028-02-24 |  | 2028-05-19 |  | 2028-08-08 |  | 2028-09-13
1511 | ST-2024-002 | Mexico | 44 | 41 | 93.2 | 3 | 2.6 | AT_RISK | Dr. Nicole Moore | 2022-12-24 | 2023-03-18 | 2023-03-04 | 2023-07-01 | 2023-07-11 | 2023-12-28 | 2024-01-08 | 2023-08-28 | 2023-08-19 | 2024-01-22 | 2024-01-30 | 2024-06-25 | 2024-06-24 | 2024-09-25 | 2024-09-21 | 2028-02-27 |  | 2028-05-18 |  | 2028-08-19 |  | 2028-09-17
1512 | ST-2024-002 | Poland | 43 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Daniel White | 2022-12-13 | 2023-03-22 | 2023-03-09 | 2023-06-14 | 2023-06-23 | 2023-12-08 | 2023-12-08 | 2023-08-23 | 2023-08-26 | 2024-01-12 | 2024-01-01 | 2024-06-30 | 2024-06-28 | 2024-10-04 | 2024-09-22 | 2028-02-26 |  | 2028-05-22 |  | 2028-08-11 |  | 2028-09-16
1513 | ST-2024-002 | Netherlands | 41 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. David Anderson | 2023-01-02 | 2023-04-01 | 2023-04-11 | 2023-06-30 | 2023-06-25 | 2024-01-03 | 2023-12-22 | 2023-08-22 | 2023-09-04 | 2024-01-27 | 2024-01-20 | 2024-07-09 | 2024-07-22 | 2024-10-13 | 2024-10-02 | 2028-03-04 |  | 2028-05-20 |  | 2028-08-17 |  | 2028-09-07
1514 | ST-2024-002 | New Zealand | 25 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Amanda Harris | 2022-12-21 | 2023-04-01 | 2023-04-07 | 2023-06-22 | 2023-06-10 | 2023-12-11 | 2023-12-16 | 2023-08-22 | 2023-08-28 | 2024-01-20 | 2024-01-11 | 2024-07-12 | 2024-07-15 | 2024-10-15 | 2024-10-24 | 2028-03-10 |  | 2028-06-06 |  | 2028-08-21 |  | 2028-09-14
1515 | ST-2024-003 | Canada | 31 | 27 | 87.1 | 2 | 3.4 | AT_RISK | Dr. Robert Davis | 2022-07-01 | 2022-10-02 | 2022-09-25 | 2022-12-28 | 2023-01-09 | 2023-07-06 | 2023-06-23 | 2023-03-08 | 2023-03-19 | 2023-07-27 | 2023-07-23 | 2024-01-03 | 2024-01-01 | 2024-03-26 | 2024-03-20 | 2029-07-08 |  | 2029-10-05 |  | 2030-01-02 |  | 2030-01-18
1516 | ST-2024-003 | Mexico | 31 | 16 | 51.6 | 5 | 0.9 | OFF_TRACK | Dr. Robert Miller | 2022-07-05 | 2022-09-30 | 2022-10-09 | 2022-12-26 | 2022-12-29 | 2023-07-06 | 2023-07-09 | 2023-03-06 | 2023-02-28 | 2023-08-01 | 2023-08-10 | 2024-01-07 | 2024-01-11 | 2024-04-01 | 2024-03-31 | 2029-07-01 |  | 2029-09-20 |  | 2029-12-23 |  | 2030-01-21
1517 | ST-2024-003 | France | 18 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Stephanie Taylor | 2022-06-29 | 2022-10-01 | 2022-10-07 | 2022-12-27 | 2022-12-18 | 2023-06-20 | 2023-07-01 | 2023-03-07 | 2023-03-14 | 2023-08-04 | 2023-08-03 | 2024-01-14 | 2024-01-19 | 2024-04-22 | 2024-04-10 | 2029-07-15 |  | 2029-10-13 |  | 2029-12-22 |  | 2030-01-20
1518 | ST-2024-003 | Sweden | 29 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Stephanie Johnson | 2022-07-06 | 2022-10-04 | 2022-10-14 | 2023-01-05 | 2022-12-30 | 2023-06-24 | 2023-07-04 | 2023-03-08 | 2023-03-14 | 2023-07-20 | 2023-07-16 | 2024-01-22 | 2024-01-11 | 2024-04-20 | 2024-04-15 | 2029-07-15 |  | 2029-10-10 |  | 2030-01-04 |  | 2030-01-26
1519 | ST-2024-003 | New Zealand | 22 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Charles Smith | 2022-07-01 | 2022-09-20 | 2022-09-22 | 2022-12-28 | 2023-01-02 | 2023-07-02 | 2023-06-24 | 2023-02-24 | 2023-02-14 | 2023-08-05 | 2023-08-02 | 2024-01-20 | 2024-01-30 | 2024-04-29 | 2024-04-20 | 2029-07-31 |  | 2029-10-20 |  | 2030-01-03 |  | 2030-01-28
1520 | ST-2024-003 | South Korea | 17 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Nicole Smith | 2022-07-11 | 2022-10-06 | 2022-10-17 | 2022-12-20 | 2022-12-15 | 2023-07-05 | 2023-06-28 | 2023-03-01 | 2023-02-16 | 2023-08-04 | 2023-07-28 | 2024-01-29 | 2024-02-12 | 2024-04-27 | 2024-05-01 | 2029-08-14 |  | 2029-11-04 |  | 2030-01-04 |  | 2030-01-31
1521 | ST-2024-004 | Canada | 33 | 23 | 69.7 | 4 | 2.1 | OFF_TRACK | Dr. Charles Williams | 2023-04-16 | 2023-08-02 | 2023-08-04 | 2023-10-19 | 2023-11-01 | 2024-05-06 | 2024-05-11 | 2024-01-03 | 2024-01-02 | 2024-05-20 | 2024-05-12 | 2024-10-22 | 2024-10-25 | 2025-01-26 | 2025-02-05 | 2028-10-02 |  | 2028-12-26 |  | 2029-03-23 |  | 2029-04-22
1522 | ST-2024-004 | Mexico | 13 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Michelle Jackson | 2023-04-20 | 2023-07-27 | 2023-07-20 | 2023-10-29 | 2023-10-17 | 2024-05-03 | 2024-04-29 | 2024-01-06 | 2023-12-23 | 2024-05-27 | 2024-05-31 | 2024-11-05 | 2024-11-08 | 2025-02-08 | 2025-02-01 | 2028-10-12 |  | 2029-01-04 |  | 2029-03-22 |  | 2029-04-21
1523 | ST-2024-004 | Norway | 30 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Nicole Moore | 2023-04-14 | 2023-07-20 | 2023-07-14 | 2023-11-06 | 2023-11-13 | 2024-04-13 | 2024-04-14 | 2023-12-24 | 2023-12-16 | 2024-05-18 | 2024-05-21 | 2024-11-04 | 2024-10-25 | 2025-02-13 | 2025-02-22 | 2028-10-15 |  | 2029-01-01 |  | 2029-03-29 |  | 2029-04-21
1524 | ST-2024-004 | Belgium | 17 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Michael Davis | 2023-05-02 | 2023-08-05 | 2023-08-04 | 2023-11-01 | 2023-10-31 | 2024-04-19 | 2024-04-19 | 2024-01-01 | 2024-01-14 | 2024-05-29 | 2024-06-07 | 2024-11-22 | 2024-11-09 | 2025-02-16 | 2025-02-23 | 2028-10-26 |  | 2029-01-21 |  | 2029-03-27 |  | 2029-04-23
1525 | ST-2024-004 | Denmark | 12 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Michael White | 2023-05-04 | 2023-07-21 | 2023-07-20 | 2023-10-18 | 2023-10-09 | 2024-04-24 | 2024-04-18 | 2023-12-27 | 2023-12-27 | 2024-05-19 | 2024-05-12 | 2024-11-24 | 2024-12-07 | 2025-02-20 | 2025-02-08 | 2028-10-30 |  | 2029-01-23 |  | 2029-03-28 |  | 2029-04-20
1526 | ST-2024-004 | South Korea | 28 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Emily Harris | 2023-05-11 | 2023-08-04 | 2023-07-26 | 2023-10-20 | 2023-10-19 | 2024-04-13 | 2024-04-14 | 2024-01-06 | 2024-01-07 | 2024-06-02 | 2024-05-25 | 2024-11-22 | 2024-12-05 | 2025-02-19 | 2025-02-17 | 2028-11-11 |  | 2029-02-08 |  | 2029-04-03 |  | 2029-04-21
1527 | ST-2024-004 | China | 12 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Jessica Smith | 2023-04-19 | 2023-07-30 | 2023-08-06 | 2023-10-17 | 2023-10-25 | 2024-04-24 | 2024-04-25 | 2023-12-25 | 2023-12-15 | 2024-05-30 | 2024-05-22 | 2024-12-22 | 2024-12-17 | 2025-03-22 | 2025-03-14 | 2028-12-04 |  | 2029-03-02 |  | 2029-04-02 |  | 2029-04-26
1528 | ST-2024-005 | Mexico | 19 | 18 | 94.7 | 5 | 1.1 | AT_RISK | Dr. Jessica Wilson | 2020-11-18 | 2021-02-20 | 2021-02-22 | 2021-05-06 | 2021-04-27 | 2021-11-22 | 2021-11-09 | 2021-07-15 | 2021-07-17 | 2021-12-04 | 2021-11-22 | 2022-05-09 | 2022-05-22 | 2022-08-14 | 2022-08-05 | 2026-10-01 |  | 2026-12-25 |  | 2027-04-04 |  | 2027-05-01
1529 | ST-2024-005 | United States | 17 | 17 | 100 | 6 | 2.8 | ON_TRACK | Dr. Amanda Thompson | 2020-11-02 | 2021-02-10 | 2021-02-17 | 2021-05-17 | 2021-05-21 | 2021-11-02 | 2021-11-06 | 2021-07-23 | 2021-07-25 | 2021-12-10 | 2021-12-06 | 2022-05-22 | 2022-05-16 | 2022-08-18 | 2022-08-10 | 2026-09-28 |  | 2026-12-23 |  | 2027-03-22 |  | 2027-04-24
1530 | ST-2024-005 | France | 13 | 12 | 92.3 | 2 | 1.2 | AT_RISK | Dr. Christopher Harris | 2020-11-10 | 2021-02-10 | 2021-01-29 | 2021-05-13 | 2021-04-29 | 2021-11-11 | 2021-11-11 | 2021-07-09 | 2021-07-14 | 2021-12-23 | 2021-12-27 | 2022-05-29 | 2022-05-18 | 2022-08-28 | 2022-08-16 | 2026-10-15 |  | 2027-01-14 |  | 2027-04-02 |  | 2027-05-02
1531 | ST-2024-005 | Denmark | 20 | 15 | 75 | 2 | 2.5 | OFF_TRACK | Dr. Amanda Anderson | 2020-11-16 | 2021-02-11 | 2021-02-19 | 2021-05-09 | 2021-05-04 | 2021-11-10 | 2021-11-15 | 2021-07-07 | 2021-07-18 | 2021-12-10 | 2021-12-16 | 2022-06-05 | 2022-06-07 | 2022-08-31 | 2022-08-17 | 2026-10-18 |  | 2027-01-10 |  | 2027-04-03 |  | 2027-04-26
1532 | ST-2024-005 | New Zealand | 15 | 8 | 53.3 | 2 | 0.5 | OFF_TRACK | Dr. Michael Thompson | 2020-11-17 | 2021-02-12 | 2021-02-06 | 2021-05-08 | 2021-05-03 | 2021-11-27 | 2021-12-02 | 2021-07-09 | 2021-07-01 | 2021-12-11 | 2021-12-19 | 2022-06-12 | 2022-06-08 | 2022-09-21 | 2022-09-13 | 2026-10-28 |  | 2027-01-24 |  | 2027-03-29 |  | 2027-04-20
1533 | ST-2024-005 | China | 16 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Michelle Johnson | 2020-11-27 | 2021-02-11 | 2021-01-28 | 2021-05-21 | 2021-05-17 | 2021-11-14 | 2021-11-24 | 2021-07-13 | 2021-07-03 | 2021-12-04 | 2021-12-10 | 2022-06-21 | 2022-06-15 | 2022-09-26 | 2022-09-17 | 2026-11-11 |  | 2027-02-09 |  | 2027-03-25 |  | 2027-04-18
1534 | ST-2024-006 | United States | 17 | 17 | 100 | 2 | 1.7 | ON_TRACK | Dr. David Moore | 2022-05-14 | 2022-08-13 | 2022-08-16 | 2022-11-16 | 2022-11-06 | 2023-04-26 | 2023-04-25 | 2023-01-02 | 2022-12-23 | 2023-06-01 | 2023-05-19 | 2023-11-05 | 2023-10-31 | 2024-02-07 | 2024-02-04 | 2025-08-01 | 2025-08-15 | 2025-10-30 | 2025-11-10 | 2026-02-01 | 2026-02-14 | 2026-03-05 | 2026-02-20
1535 | ST-2024-006 | United Kingdom | 12 | 10 | 83.3 | 4 | 1.2 | AT_RISK | Dr. Jessica Moore | 2022-05-03 | 2022-08-07 | 2022-08-20 | 2022-11-02 | 2022-10-24 | 2023-05-07 | 2023-05-18 | 2023-01-16 | 2023-01-27 | 2023-06-12 | 2023-06-03 | 2023-11-22 | 2023-12-06 | 2024-02-20 | 2024-02-19 | 2025-08-13 | 2025-07-30 | 2025-11-12 | 2025-11-03 | 2026-02-10 | 2026-02-19 | 2026-02-27 | 2026-02-23
1536 | ST-2024-006 | Switzerland | 27 | 21 | 77.8 | 2 | 1.5 | OFF_TRACK | Dr. Jennifer Jones | 2022-05-10 | 2022-08-07 | 2022-08-07 | 2022-11-07 | 2022-11-04 | 2023-05-01 | 2023-04-26 | 2023-01-02 | 2023-01-14 | 2023-06-11 | 2023-06-22 | 2023-11-21 | 2023-12-04 | 2024-03-01 | 2024-02-23 | 2025-08-26 | 2025-08-19 | 2025-11-14 | 2025-10-31 | 2026-01-30 | 2026-02-06 | 2026-03-09 | 2026-03-01
1537 | ST-2024-006 | South Korea | 14 | 7 | 50 | 3 | 0.4 | OFF_TRACK | Dr. Thomas Johnson | 2022-05-05 | 2022-08-02 | 2022-07-22 | 2022-11-07 | 2022-11-21 | 2023-05-07 | 2023-05-01 | 2023-01-19 | 2023-01-10 | 2023-06-15 | 2023-06-19 | 2023-11-28 | 2023-11-22 | 2024-02-28 | 2024-02-15 | 2025-09-02 | 2025-08-22 | 2025-11-26 | 2025-12-01 | 2026-02-01 | 2026-01-31 | 2026-02-24 | 2026-02-21
1538 | ST-2024-007 | Canada | 8 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Robert Anderson | 2025-04-18 | 2025-07-25 | 2025-07-11 | 2025-10-30 | 2025-11-01 | 2026-04-23 | 2026-05-04 | 2025-12-14 | 2025-12-17 | 2026-05-23 |  | 2026-10-24 |  | 2027-01-14 |  | 2029-04-16 |  | 2029-07-02 |  | 2029-10-20 |  | 2029-11-12
1539 | ST-2024-007 | Mexico | 9 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Michael Thomas | 2025-05-01 | 2025-07-18 | 2025-08-01 | 2025-10-22 | 2025-10-17 | 2026-04-20 | 2026-04-22 | 2025-12-13 | 2025-12-08 | 2026-05-21 |  | 2026-11-01 |  | 2027-01-24 |  | 2029-04-30 |  | 2029-07-29 |  | 2029-10-10 |  | 2029-11-17
1540 | ST-2024-007 | Spain | 6 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. William Martin | 2025-04-18 | 2025-07-24 | 2025-07-15 | 2025-10-20 | 2025-10-25 | 2026-04-24 | 2026-04-28 | 2025-12-15 | 2025-12-10 | 2026-05-17 | 2026-05-15 | 2026-11-06 |  | 2027-02-06 |  | 2029-05-04 |  | 2029-07-30 |  | 2029-10-20 |  | 2029-11-20
1541 | ST-2024-007 | Italy | 6 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Michelle Wilson | 2025-04-08 | 2025-07-21 | 2025-07-28 | 2025-10-20 | 2025-10-12 | 2026-04-13 | 2026-04-15 | 2025-12-24 | 2025-12-25 | 2026-05-29 |  | 2026-11-15 |  | 2027-02-12 |  | 2029-05-09 |  | 2029-08-01 |  | 2029-10-16 |  | 2029-11-13
1542 | ST-2024-007 | India | 11 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. William Jones | 2025-05-03 | 2025-07-17 | 2025-07-24 | 2025-10-13 | 2025-10-08 | 2026-04-16 | 2026-04-09 | 2025-12-27 | 2026-01-07 | 2026-05-31 |  | 2026-11-29 |  | 2027-02-21 |  | 2029-05-19 |  | 2029-08-17 |  | 2029-10-21 |  | 2029-11-09
1543 | ST-2024-007 | Singapore | 10 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Lisa Davis | 2025-04-08 | 2025-07-13 | 2025-07-21 | 2025-10-18 | 2025-10-26 | 2026-04-22 | 2026-04-20 | 2025-12-30 | 2025-12-31 | 2026-05-13 | 2026-05-11 | 2026-11-15 |  | 2027-02-10 |  | 2029-05-20 |  | 2029-08-15 |  | 2029-10-18 |  | 2029-11-09
1544 | ST-2024-008 | United States | 19 | 17 | 89.5 | 3 | 1 | AT_RISK | Dr. Nicole Wilson | 2020-01-08 | 2020-03-23 | 2020-03-26 | 2020-06-25 | 2020-06-18 | 2021-01-10 | 2021-01-23 | 2020-09-04 | 2020-08-24 | 2021-01-27 | 2021-01-27 | 2021-06-28 | 2021-06-18 | 2021-10-04 | 2021-10-15 | 2025-07-06 | 2025-07-06 | 2025-09-29 | 2025-10-06 | 2025-12-28 | 2025-12-30 | 2026-01-18 | 2026-01-21
1545 | ST-2024-008 | Sweden | 22 | 15 | 68.2 | 2 | 2.1 | OFF_TRACK | Dr. William Moore | 2020-01-12 | 2020-04-06 | 2020-04-07 | 2020-07-11 | 2020-07-11 | 2021-01-12 | 2021-01-06 | 2020-09-07 | 2020-09-17 | 2021-02-02 | 2021-01-26 | 2021-07-12 | 2021-07-24 | 2021-10-07 | 2021-10-13 | 2025-07-17 | 2025-07-11 | 2025-10-04 | 2025-10-14 | 2026-01-01 | 2026-01-11 | 2026-01-31 | 2026-02-02
1546 | ST-2024-008 | Taiwan | 9 | 9 | 100 | 6 | 0.6 | ON_TRACK | Dr. Sarah Garcia | 2019-12-26 | 2020-03-31 | 2020-03-21 | 2020-07-06 | 2020-06-26 | 2020-12-19 | 2020-12-12 | 2020-08-31 | 2020-08-29 | 2021-01-27 | 2021-02-04 | 2021-07-14 | 2021-07-04 | 2021-10-11 | 2021-10-19 | 2025-07-14 | 2025-07-06 | 2025-10-13 | 2025-10-01 | 2025-12-29 | 2025-12-28 | 2026-01-19 | 2026-01-18
1547 | ST-2024-009 | Canada | 48 | 12 | 25 | 3 | 0.9 | OFF_TRACK | Dr. Jennifer Taylor | 2024-02-16 | 2024-05-20 | 2024-05-24 | 2024-08-07 | 2024-08-05 | 2025-02-06 | 2025-02-07 | 2024-10-19 | 2024-10-05 | 2025-03-18 | 2025-03-15 | 2025-08-19 | 2025-08-14 | 2025-11-17 | 2025-11-27 | 2029-03-08 |  | 2029-06-06 |  | 2029-09-17 |  | 2029-10-13
1548 | ST-2024-009 | United States | 75 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Christopher Davis | 2024-03-01 | 2024-05-20 | 2024-05-06 | 2024-08-23 | 2024-08-21 | 2025-02-23 | 2025-02-19 | 2024-10-23 | 2024-10-30 | 2025-03-25 | 2025-04-01 | 2025-08-19 | 2025-08-30 | 2025-11-19 | 2025-11-17 | 2029-03-17 |  | 2029-06-06 |  | 2029-09-09 |  | 2029-10-08
1549 | ST-2024-009 | Sweden | 35 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Jennifer Garcia | 2024-02-28 | 2024-05-21 | 2024-05-27 | 2024-08-10 | 2024-08-09 | 2025-02-19 | 2025-02-09 | 2024-10-23 | 2024-11-05 | 2025-03-06 | 2025-03-06 | 2025-09-02 | 2025-08-24 | 2025-12-02 | 2025-11-19 | 2029-04-03 |  | 2029-06-29 |  | 2029-09-03 |  | 2029-10-02
1550 | ST-2024-009 | Norway | 77 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. James Miller | 2024-02-12 | 2024-05-13 | 2024-05-01 | 2024-08-20 | 2024-08-21 | 2025-02-10 | 2025-01-27 | 2024-10-16 | 2024-10-25 | 2025-03-18 | 2025-03-21 | 2025-08-30 | 2025-08-17 | 2025-12-04 | 2025-12-01 | 2029-04-06 |  | 2029-06-28 |  | 2029-09-07 |  | 2029-10-14
1551 | ST-2024-009 | Singapore | 65 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Stephanie Jackson | 2024-02-04 | 2024-05-27 | 2024-05-17 | 2024-08-07 | 2024-08-08 | 2025-02-24 | 2025-03-03 | 2024-10-06 | 2024-09-25 | 2025-03-13 | 2025-03-17 | 2025-09-02 | 2025-08-25 | 2025-12-09 | 2025-12-09 | 2029-03-28 |  | 2029-06-22 |  | 2029-09-05 |  | 2029-10-04
1552 | ST-2024-010 | Mexico | 1254 | 1162 | 92.7 | 3 | 129.1 | AT_RISK | Dr. Jessica Wilson | 2019-06-02 | 2019-08-23 | 2019-08-18 | 2019-11-16 | 2019-11-20 | 2020-05-26 | 2020-06-02 | 2020-01-30 | 2020-01-28 | 2020-06-13 | 2020-06-11 | 2020-11-16 | 2020-11-24 | 2021-02-14 | 2021-02-06 | 2030-09-26 |  | 2030-12-21 |  | 2031-03-21 |  | 2031-05-02
1553 | ST-2024-010 | United Kingdom | 2610 | 1318 | 50.5 | 4 | 73.2 | OFF_TRACK | Dr. Charles Taylor | 2019-05-31 | 2019-09-01 | 2019-09-04 | 2019-11-18 | 2019-11-17 | 2020-05-10 | 2020-05-17 | 2020-01-20 | 2020-01-17 | 2020-06-29 | 2020-06-17 | 2020-11-19 | 2020-11-21 | 2021-02-26 | 2021-03-04 | 2030-10-08 |  | 2031-01-05 |  | 2031-03-21 |  | 2031-04-23
1554 | ST-2024-010 | Australia | 1136 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. William Davis | 2019-06-05 | 2019-08-25 | 2019-08-24 | 2019-11-26 | 2019-11-17 | 2020-05-10 | 2020-05-19 | 2020-01-24 | 2020-01-26 | 2020-06-21 | 2020-06-27 | 2020-12-06 | 2020-11-30 | 2021-03-08 | 2021-03-13 | 2030-10-20 |  | 2031-01-12 |  | 2031-04-01 |  | 2031-04-20
1555 | ST-2024-011 | United States | 27 | 5 | 18.5 | 3 | 0.3 | OFF_TRACK | Dr. Michael Taylor | 2024-04-08 | 2024-07-10 | 2024-07-04 | 2024-10-08 | 2024-10-22 | 2025-04-03 | 2025-04-03 | 2024-12-12 | 2024-12-05 | 2025-05-02 | 2025-05-12 | 2025-10-03 | 2025-10-03 | 2026-01-07 | 2026-01-11 | 2028-09-27 |  | 2028-12-26 |  | 2029-04-04 |  | 2029-04-19
1556 | ST-2024-011 | France | 38 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. William Miller | 2024-04-03 | 2024-07-05 | 2024-06-29 | 2024-09-24 | 2024-10-08 | 2025-04-05 | 2025-04-10 | 2024-12-04 | 2024-12-12 | 2025-04-29 | 2025-05-13 | 2025-10-13 | 2025-10-07 | 2026-01-05 | 2026-01-08 | 2028-10-07 |  | 2029-01-04 |  | 2029-03-25 |  | 2029-04-23
1557 | ST-2024-011 | Singapore | 52 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Michael Thomas | 2024-03-28 | 2024-06-27 | 2024-07-05 | 2024-10-01 | 2024-10-02 | 2025-04-13 | 2025-04-13 | 2024-12-07 | 2024-12-18 | 2025-05-09 | 2025-04-25 | 2025-10-13 | 2025-10-01 | 2026-01-13 | 2026-01-08 | 2028-10-04 |  | 2028-12-31 |  | 2029-03-28 |  | 2029-04-28
1558 | ST-2024-011 | Mexico | 23 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Emily Smith | 2024-04-13 | 2024-07-02 | 2024-07-05 | 2024-10-03 | 2024-09-29 | 2025-04-11 | 2025-04-08 | 2024-12-12 | 2024-12-20 | 2025-05-05 | 2025-05-05 | 2025-10-20 | 2025-10-14 | 2026-01-17 | 2026-01-12 | 2028-10-17 |  | 2029-01-07 |  | 2029-03-27 |  | 2029-04-29
1559 | ST-2024-012 | Mexico | 3 | 2 | 66.7 | 6 | 0.2 | OFF_TRACK | Dr. Jessica Brown | 2023-09-09 | 2023-12-16 | 2023-12-20 | 2024-03-20 | 2024-03-30 | 2024-09-07 | 2024-09-09 | 2024-05-27 | 2024-06-01 | 2024-10-13 | 2024-10-08 | 2025-03-17 | 2025-03-06 | 2025-06-13 | 2025-06-25 | 2026-09-22 |  | 2026-12-15 |  | 2027-03-14 |  | 2027-04-18
1560 | ST-2024-012 | Canada | 5 | 4 | 80 | 5 | 0.6 | AT_RISK | Dr. Thomas Wilson | 2023-09-13 | 2023-12-21 | 2023-12-29 | 2024-03-15 | 2024-03-05 | 2024-09-13 | 2024-09-19 | 2024-05-10 | 2024-05-23 | 2024-10-25 | 2024-11-04 | 2025-03-21 | 2025-03-22 | 2025-06-19 | 2025-06-08 | 2026-09-16 |  | 2026-12-02 |  | 2027-03-18 |  | 2027-04-11
1561 | ST-2024-012 | Belgium | 6 | 6 | 100 | 4 | 0.6 | ON_TRACK | Dr. William Anderson | 2023-09-24 | 2023-12-19 | 2023-12-31 | 2024-03-25 | 2024-03-13 | 2024-09-19 | 2024-09-17 | 2024-05-24 | 2024-05-25 | 2024-10-18 | 2024-10-06 | 2025-04-04 | 2025-04-08 | 2025-06-29 | 2025-07-05 | 2026-10-04 |  | 2027-01-02 |  | 2027-03-17 |  | 2027-04-08
1562 | ST-2024-012 | Norway | 6 | 3 | 50 | 3 | 0.4 | OFF_TRACK | Dr. Daniel Davis | 2023-09-10 | 2023-12-14 | 2023-12-25 | 2024-03-28 | 2024-04-02 | 2024-09-13 | 2024-09-06 | 2024-05-12 | 2024-05-22 | 2024-10-15 | 2024-10-17 | 2025-04-09 | 2025-04-07 | 2025-07-13 | 2025-07-13 | 2026-10-18 |  | 2027-01-09 |  | 2027-03-19 |  | 2027-04-16
1563 | ST-2024-012 | Singapore | 5 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Charles Taylor | 2023-09-15 | 2023-12-28 | 2024-01-03 | 2024-03-23 | 2024-03-15 | 2024-09-13 | 2024-09-07 | 2024-05-28 | 2024-06-04 | 2024-10-27 | 2024-10-15 | 2025-04-22 | 2025-04-13 | 2025-07-28 | 2025-07-21 | 2026-10-31 |  | 2027-01-17 |  | 2027-03-22 |  | 2027-04-10
1564 | ST-2024-012 | Chile | 5 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. James Martin | 2023-09-08 | 2023-12-15 | 2023-12-10 | 2024-03-10 | 2024-03-18 | 2024-09-17 | 2024-09-30 | 2024-05-24 | 2024-05-24 | 2024-10-27 | 2024-10-15 | 2025-04-14 | 2025-04-21 | 2025-07-08 | 2025-07-01 | 2026-10-05 |  | 2026-12-24 |  | 2027-03-14 |  | 2027-04-18
1565 | ST-2024-013 | Mexico | -6 | -6 | 100 | 3 | -0.4 | ON_TRACK | Dr. Jennifer Jones | 2025-04-02 | 2025-07-01 | 2025-06-25 | 2025-09-28 | 2025-10-10 | 2026-03-28 | 2026-03-18 | 2025-11-16 | 2025-11-04 | 2026-04-23 | 2026-04-10 | 2026-09-15 |  | 2026-12-19 |  | 2029-06-16 |  | 2029-09-11 |  | 2029-12-11 |  | 2030-01-20
1566 | ST-2024-013 | Poland | 5 | 5 | 100 | 2 | 0.4 | ON_TRACK | Dr. Thomas Thompson | 2025-03-17 | 2025-06-30 | 2025-07-02 | 2025-09-28 | 2025-10-01 | 2026-03-16 | 2026-03-17 | 2025-11-24 | 2025-11-24 | 2026-04-13 | 2026-04-01 | 2026-09-26 |  | 2026-12-27 |  | 2029-06-22 |  | 2029-09-18 |  | 2029-12-15 |  | 2030-01-10
1567 | ST-2024-013 | South Korea | 5 | 1 | 20 | 5 | 0.1 | OFF_TRACK | Dr. Lisa Wilson | 2025-04-05 | 2025-06-24 | 2025-06-28 | 2025-09-20 | 2025-09-06 | 2026-03-26 | 2026-04-05 | 2025-11-18 | 2025-11-25 | 2026-04-10 | 2026-04-22 | 2026-09-30 |  | 2026-12-29 |  | 2029-07-08 |  | 2029-10-06 |  | 2029-12-22 |  | 2030-01-15
1568 | ST-2024-013 | Chile | 5 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Jessica Harris | 2025-03-09 | 2025-06-16 | 2025-06-17 | 2025-09-25 | 2025-09-13 | 2026-03-23 | 2026-03-24 | 2025-11-30 | 2025-11-27 | 2026-04-24 | 2026-04-23 | 2026-10-04 |  | 2026-12-29 |  | 2029-07-08 |  | 2029-09-29 |  | 2029-12-19 |  | 2030-01-19
1569 | ST-2024-014 | Mexico | -5 | -5 | 100 | 4 | -0.6 | ON_TRACK | Dr. Michelle Miller | 2023-06-24 | 2023-09-09 | 2023-08-27 | 2023-12-11 | 2023-12-11 | 2024-06-11 | 2024-05-30 | 2024-02-18 | 2024-02-14 | 2024-07-20 | 2024-07-14 | 2024-12-13 | 2024-12-09 | 2025-03-17 | 2025-03-06 | 2027-10-01 |  | 2027-12-30 |  | 2028-04-01 |  | 2028-04-25
1570 | ST-2024-014 | Canada | 5 | 4 | 80 | 4 | 0.2 | AT_RISK | Dr. Michael Williams | 2023-06-15 | 2023-09-22 | 2023-10-02 | 2023-12-06 | 2023-12-07 | 2024-06-22 | 2024-06-28 | 2024-02-22 | 2024-02-22 | 2024-07-19 | 2024-07-29 | 2024-12-25 | 2024-12-12 | 2025-03-17 | 2025-03-09 | 2027-10-08 |  | 2028-01-01 |  | 2028-03-25 |  | 2028-04-26
1571 | ST-2024-014 | United States | 5 | 4 | 80 | 2 | 0.3 | AT_RISK | Dr. James Jackson | 2023-06-07 | 2023-09-15 | 2023-09-06 | 2023-12-20 | 2023-12-15 | 2024-06-29 | 2024-07-02 | 2024-02-20 | 2024-02-06 | 2024-07-08 | 2024-07-11 | 2024-12-20 | 2024-12-19 | 2025-03-28 | 2025-03-16 | 2027-10-15 |  | 2028-01-12 |  | 2028-03-23 |  | 2028-04-28
1572 | ST-2024-014 | Poland | 5 | 4 | 80 | 6 | 0.4 | AT_RISK | Dr. Sarah Moore | 2023-06-29 | 2023-09-09 | 2023-09-03 | 2023-12-20 | 2023-12-19 | 2024-06-04 | 2024-06-16 | 2024-02-25 | 2024-02-26 | 2024-07-09 | 2024-07-10 | 2024-12-31 | 2024-12-24 | 2025-04-05 | 2025-04-05 | 2027-10-21 |  | 2028-01-10 |  | 2028-03-28 |  | 2028-04-28
1573 | ST-2024-014 | Norway | 5 | 1 | 20 | 4 | 0.1 | OFF_TRACK | Dr. Michelle Martin | 2023-06-15 | 2023-09-12 | 2023-09-23 | 2023-12-25 | 2023-12-27 | 2024-06-17 | 2024-06-11 | 2024-02-09 | 2024-02-21 | 2024-07-07 | 2024-06-23 | 2025-01-11 | 2025-01-06 | 2025-04-17 | 2025-04-26 | 2027-11-05 |  | 2028-02-03 |  | 2028-03-26 |  | 2028-04-22
1574 | ST-2024-014 | Netherlands | 5 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Charles Davis | 2023-06-21 | 2023-09-24 | 2023-09-27 | 2023-12-21 | 2023-12-19 | 2024-06-28 | 2024-06-28 | 2024-02-09 | 2024-02-05 | 2024-07-19 | 2024-08-01 | 2025-01-14 | 2025-01-06 | 2025-04-11 | 2025-04-19 | 2027-10-28 |  | 2028-01-18 |  | 2028-03-28 |  | 2028-04-29
1575 | ST-2024-014 | Denmark | 5 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Jessica Jones | 2023-06-15 | 2023-09-13 | 2023-09-03 | 2023-12-19 | 2023-12-20 | 2024-06-02 | 2024-05-20 | 2024-02-15 | 2024-02-05 | 2024-07-20 | 2024-07-22 | 2025-01-15 | 2025-01-19 | 2025-04-13 | 2025-04-09 | 2027-11-05 |  | 2028-02-02 |  | 2028-04-02 |  | 2028-04-27
1576 | ST-2024-014 | Taiwan | 5 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Daniel Williams | 2023-06-30 | 2023-09-20 | 2023-09-21 | 2023-12-09 | 2023-12-20 | 2024-06-17 | 2024-06-11 | 2024-02-19 | 2024-02-15 | 2024-07-05 | 2024-07-10 | 2025-02-16 | 2025-02-24 | 2025-05-19 | 2025-05-17 | 2027-12-14 |  | 2028-03-10 |  | 2028-03-22 |  | 2028-04-18
1577 | ST-2024-015 | Canada | 27 | 12 | 44.4 | 4 | 0.9 | OFF_TRACK | Dr. Michelle Davis | 2024-03-07 | 2024-05-24 | 2024-05-17 | 2024-08-30 | 2024-09-05 | 2025-02-19 | 2025-02-26 | 2024-10-23 | 2024-10-18 | 2025-04-02 | 2025-03-26 | 2025-08-24 | 2025-09-02 | 2025-11-26 | 2025-11-14 | 2027-11-23 |  | 2028-02-08 |  | 2028-05-20 |  | 2028-06-09
1578 | ST-2024-015 | Mexico | 13 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Jessica Thomas | 2024-02-12 | 2024-06-03 | 2024-05-31 | 2024-08-16 | 2024-08-13 | 2025-02-21 | 2025-02-20 | 2024-10-18 | 2024-10-08 | 2025-03-22 | 2025-03-15 | 2025-08-24 | 2025-08-26 | 2025-11-20 | 2025-11-19 | 2027-11-27 |  | 2028-02-24 |  | 2028-05-11 |  | 2028-06-12
1579 | ST-2024-015 | Sweden | 31 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Robert Anderson | 2024-03-05 | 2024-05-19 | 2024-05-23 | 2024-08-18 | 2024-08-08 | 2025-02-12 | 2025-02-05 | 2024-10-15 | 2024-10-15 | 2025-04-01 | 2025-04-07 | 2025-09-07 | 2025-09-01 | 2025-12-07 | 2025-12-07 | 2027-12-10 |  | 2028-02-28 |  | 2028-05-18 |  | 2028-06-22
1580 | ST-2024-015 | Norway | 22 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Daniel Jones | 2024-02-09 | 2024-05-28 | 2024-05-27 | 2024-08-22 | 2024-08-30 | 2025-02-28 | 2025-02-22 | 2024-10-30 | 2024-10-30 | 2025-03-18 | 2025-03-31 | 2025-09-03 | 2025-08-29 | 2025-12-06 | 2025-11-28 | 2027-12-06 |  | 2028-03-01 |  | 2028-05-15 |  | 2028-06-18
1581 | ST-2024-015 | Switzerland | 23 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Nicole Moore | 2024-03-07 | 2024-05-29 | 2024-06-10 | 2024-08-16 | 2024-08-23 | 2025-02-14 | 2025-02-12 | 2024-10-25 | 2024-10-19 | 2025-03-31 | 2025-03-17 | 2025-10-03 | 2025-10-07 | 2026-01-03 | 2026-01-16 | 2027-12-31 |  | 2028-03-28 |  | 2028-05-15 |  | 2028-06-08
1582 | ST-2024-015 | India | 20 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Nicole Martin | 2024-03-03 | 2024-05-15 | 2024-05-07 | 2024-09-01 | 2024-09-06 | 2025-03-02 | 2025-02-24 | 2024-10-28 | 2024-11-04 | 2025-03-22 | 2025-04-01 | 2025-10-01 | 2025-10-10 | 2026-01-03 | 2026-01-13 | 2028-01-08 |  | 2028-03-30 |  | 2028-05-14 |  | 2028-06-18
1583 | ST-2024-016 | United States | 18 | 13 | 72.2 | 5 | 2.2 | OFF_TRACK | Dr. Jessica Thompson | 2023-06-18 | 2023-08-30 | 2023-08-27 | 2023-12-15 | 2023-12-24 | 2024-05-24 | 2024-05-14 | 2024-02-14 | 2024-02-02 | 2024-07-14 | 2024-07-09 | 2024-11-28 | 2024-11-24 | 2025-02-28 | 2025-03-09 | 2027-04-09 |  | 2027-07-02 |  | 2027-09-24 |  | 2027-10-31
1584 | ST-2024-016 | Canada | 17 | 17 | 100 | 2 | 1.5 | ON_TRACK | Dr. Michelle Jones | 2023-05-29 | 2023-08-30 | 2023-09-11 | 2023-12-12 | 2023-12-13 | 2024-06-18 | 2024-06-29 | 2024-02-05 | 2024-01-31 | 2024-07-10 | 2024-07-19 | 2024-12-12 | 2024-12-25 | 2025-03-16 | 2025-03-12 | 2027-04-07 |  | 2027-07-06 |  | 2027-09-26 |  | 2027-10-26
1585 | ST-2024-016 | Germany | 10 | 9 | 90 | 4 | 0.6 | AT_RISK | Dr. Lisa Jones | 2023-06-06 | 2023-08-28 | 2023-08-22 | 2023-11-29 | 2023-12-02 | 2024-06-14 | 2024-06-03 | 2024-02-01 | 2024-02-01 | 2024-07-06 | 2024-07-03 | 2024-12-24 | 2024-12-31 | 2025-03-19 | 2025-03-28 | 2027-04-16 |  | 2027-07-14 |  | 2027-09-30 |  | 2027-10-22
1586 | ST-2024-016 | Poland | 17 | 6 | 35.3 | 2 | 0.4 | OFF_TRACK | Dr. Charles Harris | 2023-06-10 | 2023-09-07 | 2023-09-12 | 2023-12-15 | 2023-12-08 | 2024-06-01 | 2024-06-07 | 2024-01-28 | 2024-01-16 | 2024-07-01 | 2024-07-07 | 2024-12-30 | 2025-01-11 | 2025-03-21 | 2025-03-21 | 2027-05-01 |  | 2027-07-31 |  | 2027-10-02 |  | 2027-10-27
1587 | ST-2024-016 | Belgium | 11 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Daniel Williams | 2023-06-01 | 2023-09-15 | 2023-09-29 | 2023-12-08 | 2023-12-11 | 2024-05-24 | 2024-05-14 | 2024-01-29 | 2024-01-27 | 2024-06-25 | 2024-06-25 | 2025-01-06 | 2025-01-03 | 2025-04-08 | 2025-04-15 | 2027-05-13 |  | 2027-07-30 |  | 2027-09-25 |  | 2027-10-25
1588 | ST-2024-016 | Australia | 17 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Jessica Jackson | 2023-06-14 | 2023-09-12 | 2023-09-06 | 2023-12-08 | 2023-11-25 | 2024-06-08 | 2024-06-16 | 2024-01-29 | 2024-01-26 | 2024-07-07 | 2024-06-29 | 2025-01-28 | 2025-01-28 | 2025-04-17 | 2025-04-17 | 2027-05-31 |  | 2027-08-23 |  | 2027-10-03 |  | 2027-10-28
1589 | ST-2024-017 | Mexico | 23 | 8 | 34.8 | 5 | 0.5 | OFF_TRACK | Dr. Jessica White | 2023-09-07 | 2023-11-25 | 2023-11-14 | 2024-02-16 | 2024-02-29 | 2024-08-30 | 2024-09-11 | 2024-04-25 | 2024-04-25 | 2024-09-29 | 2024-09-17 | 2025-02-26 | 2025-03-05 | 2025-05-20 | 2025-05-12 | 2028-01-16 |  | 2028-04-08 |  | 2028-07-17 |  | 2028-08-13
1590 | ST-2024-017 | Spain | 12 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. William Thompson | 2023-08-30 | 2023-11-14 | 2023-11-24 | 2024-02-14 | 2024-02-17 | 2024-09-03 | 2024-08-26 | 2024-04-24 | 2024-04-28 | 2024-09-19 | 2024-09-11 | 2025-02-26 | 2025-03-10 | 2025-06-04 | 2025-06-17 | 2028-02-02 |  | 2028-04-22 |  | 2028-07-14 |  | 2028-08-23
1591 | ST-2024-017 | China | 25 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Amanda Jones | 2023-09-04 | 2023-11-18 | 2023-11-25 | 2024-03-03 | 2024-03-16 | 2024-08-09 | 2024-07-26 | 2024-04-22 | 2024-04-12 | 2024-09-16 | 2024-09-02 | 2025-02-28 | 2025-02-25 | 2025-06-02 | 2025-06-13 | 2028-01-30 |  | 2028-04-28 |  | 2028-07-15 |  | 2028-08-11
1592 | ST-2024-018 | United States | 10 | 10 | 100 | 3 | 1 | ON_TRACK | Dr. Robert Jones | 2020-09-29 | 2020-12-25 | 2020-12-13 | 2021-03-16 | 2021-03-17 | 2021-09-15 | 2021-09-15 | 2021-05-24 | 2021-06-03 | 2021-10-15 | 2021-10-12 | 2022-03-22 | 2022-03-24 | 2022-06-27 | 2022-07-01 | 2024-07-31 | 2024-07-20 | 2024-10-24 | 2024-10-24 | 2025-01-21 | 2025-01-23 | 2025-02-28 | 2025-02-21
1593 | ST-2024-018 | Denmark | 6 | 6 | 100 | 2 | 0.9 | ON_TRACK | Dr. James Jones | 2020-09-12 | 2020-12-31 | 2020-12-20 | 2021-03-25 | 2021-03-26 | 2021-09-24 | 2021-10-02 | 2021-06-05 | 2021-06-05 | 2021-10-14 | 2021-10-02 | 2022-03-30 | 2022-04-13 | 2022-07-03 | 2022-06-21 | 2024-08-17 | 2024-08-13 | 2024-11-08 | 2024-11-13 | 2025-01-26 | 2025-01-16 | 2025-02-27 | 2025-02-15
1594 | ST-2024-018 | South Korea | 8 | 8 | 100 | 5 | 0.5 | ON_TRACK | Dr. Stephanie Jones | 2020-09-30 | 2021-01-04 | 2021-01-03 | 2021-04-03 | 2021-03-23 | 2021-09-27 | 2021-10-08 | 2021-05-26 | 2021-06-03 | 2021-10-26 | 2021-10-15 | 2022-04-07 | 2022-04-20 | 2022-07-03 | 2022-07-09 | 2024-08-07 | 2024-08-13 | 2024-10-30 | 2024-11-13 | 2025-01-28 | 2025-02-07 | 2025-02-26 | 2025-03-01
1595 | ST-2024-019 | Mexico | 39 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Christopher Wilson | 2025-04-14 | 2025-07-25 | 2025-07-14 | 2025-10-25 | 2025-10-21 | 2026-05-05 | 2026-05-04 | 2025-12-18 | 2025-12-14 | 2026-05-24 |  | 2026-10-20 |  | 2027-01-24 |  | 2028-12-18 |  | 2029-03-11 |  | 2029-06-14 |  | 2029-07-17
1596 | ST-2024-019 | United States | 69 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Thomas Wilson | 2025-04-19 | 2025-07-16 | 2025-07-27 | 2025-10-26 | 2025-10-16 | 2026-04-09 | 2026-04-12 | 2025-12-13 | 2025-11-30 | 2026-05-13 | 2026-05-17 | 2026-10-24 |  | 2027-01-25 |  | 2028-12-20 |  | 2029-03-18 |  | 2029-06-19 |  | 2029-07-11
1597 | ST-2024-019 | Poland | 55 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Michael Wilson | 2025-04-25 | 2025-07-22 | 2025-07-26 | 2025-10-14 | 2025-10-16 | 2026-04-20 | 2026-04-12 | 2025-12-22 | 2025-12-12 | 2026-05-24 |  | 2026-11-04 |  | 2027-02-04 |  | 2029-01-09 |  | 2029-03-31 |  | 2029-06-13 |  | 2029-07-07
1598 | ST-2024-019 | Denmark | 79 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Charles Taylor | 2025-04-15 | 2025-07-15 | 2025-07-14 | 2025-10-22 | 2025-11-04 | 2026-05-04 | 2026-05-07 | 2025-12-28 | 2026-01-07 | 2026-05-22 |  | 2026-11-09 |  | 2027-02-16 |  | 2029-01-08 |  | 2029-04-04 |  | 2029-06-11 |  | 2029-07-18
1599 | ST-2024-019 | United Kingdom | 72 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. William Garcia | 2025-04-27 | 2025-08-01 | 2025-07-28 | 2025-10-28 | 2025-10-25 | 2026-04-07 | 2026-03-24 | 2025-12-30 | 2025-12-21 | 2026-05-19 | 2026-06-01 | 2026-11-21 |  | 2027-02-19 |  | 2029-01-21 |  | 2029-04-19 |  | 2029-06-20 |  | 2029-07-10
1600 | ST-2024-019 | Australia | 82 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Nicole Miller | 2025-04-29 | 2025-07-24 | 2025-07-24 | 2025-10-13 | 2025-10-09 | 2026-04-11 | 2026-04-02 | 2025-12-31 | 2025-12-28 | 2026-05-11 | 2026-05-06 | 2026-11-08 |  | 2027-02-14 |  | 2029-01-11 |  | 2029-04-01 |  | 2029-06-14 |  | 2029-07-12
1601 | ST-2024-020 | Canada | 0 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Sarah Thompson | 2022-04-26 | 2022-07-24 | 2022-07-18 | 2022-10-24 | 2022-10-24 | 2023-04-03 | 2023-04-10 | 2022-12-06 | 2022-12-05 | 2023-05-09 | 2023-05-10 | 2023-10-11 | 2023-10-16 | 2024-01-17 | 2024-01-17 | 2026-06-16 |  | 2026-09-01 |  | 2026-12-13 |  | 2027-01-01
1602 | ST-2024-020 | Norway | 5 | 5 | 100 | 4 | 0.8 | ON_TRACK | Dr. Emily Jackson | 2022-04-08 | 2022-07-22 | 2022-07-29 | 2022-10-08 | 2022-10-03 | 2023-04-12 | 2023-03-30 | 2022-12-18 | 2022-12-11 | 2023-05-08 | 2023-05-06 | 2023-10-19 | 2023-10-24 | 2024-01-21 | 2024-01-08 | 2026-06-23 |  | 2026-09-17 |  | 2026-12-10 |  | 2027-01-08
1603 | ST-2024-020 | Netherlands | 5 | 3 | 60 | 4 | 0.2 | OFF_TRACK | Dr. Sarah Thomas | 2022-04-11 | 2022-07-12 | 2022-07-03 | 2022-10-09 | 2022-09-29 | 2023-04-25 | 2023-04-23 | 2022-12-13 | 2022-12-16 | 2023-05-14 | 2023-05-22 | 2023-10-21 | 2023-10-14 | 2024-01-13 | 2024-01-15 | 2026-06-14 |  | 2026-09-06 |  | 2026-12-14 |  | 2027-01-06
1604 | ST-2024-020 | Japan | 5 | 4 | 80 | 4 | 0.5 | AT_RISK | Dr. Michelle Williams | 2022-04-23 | 2022-07-17 | 2022-07-21 | 2022-10-07 | 2022-10-06 | 2023-04-13 | 2023-04-17 | 2022-12-06 | 2022-12-04 | 2023-05-18 | 2023-05-26 | 2023-10-31 | 2023-11-06 | 2024-02-03 | 2024-02-02 | 2026-07-13 |  | 2026-09-29 |  | 2026-12-16 |  | 2027-01-05
1605 | ST-2025-021 | Mexico | 48 | 48 | 100 | 4 | 6 | ON_TRACK | Dr. Jessica Smith | 2016-06-27 | 2016-09-18 | 2016-09-17 | 2016-12-28 | 2017-01-01 | 2017-06-19 | 2017-06-17 | 2017-03-08 | 2017-03-10 | 2017-08-01 | 2017-07-20 | 2017-12-27 | 2017-12-25 | 2018-03-21 | 2018-04-03 | 2020-09-27 | 2020-09-22 | 2020-12-26 | 2021-01-04 | 2021-03-21 | 2021-03-17 | 2021-04-20 | 2021-04-13
1606 | ST-2025-021 | United States | 48 | 48 | 100 | 2 | 5.3 | ON_TRACK | Dr. Robert Jones | 2016-06-20 | 2016-09-20 | 2016-09-29 | 2017-01-03 | 2017-01-15 | 2017-07-04 | 2017-07-10 | 2017-02-20 | 2017-03-04 | 2017-08-03 | 2017-07-24 | 2018-01-05 | 2017-12-29 | 2018-03-29 | 2018-03-18 | 2020-10-11 | 2020-10-01 | 2021-01-08 | 2021-01-02 | 2021-03-25 | 2021-03-17 | 2021-04-22 | 2021-04-13
1607 | ST-2025-021 | Belgium | 33 | 30 | 90.9 | 3 | 3 | AT_RISK | Dr. Robert Miller | 2016-07-09 | 2016-10-08 | 2016-10-15 | 2016-12-20 | 2017-01-03 | 2017-06-19 | 2017-06-23 | 2017-03-09 | 2017-03-15 | 2017-08-02 | 2017-08-08 | 2018-01-13 | 2018-01-18 | 2018-04-16 | 2018-04-12 | 2020-10-15 | 2020-10-28 | 2021-01-12 | 2021-01-18 | 2021-03-29 | 2021-03-25 | 2021-04-24 | 2021-04-14
1608 | ST-2025-021 | Sweden | 27 | 27 | 100 | 3 | 3.9 | ON_TRACK | Dr. Stephanie Brown | 2016-06-30 | 2016-10-02 | 2016-10-02 | 2017-01-07 | 2016-12-25 | 2017-06-23 | 2017-06-10 | 2017-02-25 | 2017-02-22 | 2017-08-05 | 2017-08-17 | 2018-01-11 | 2018-01-06 | 2018-04-14 | 2018-04-02 | 2020-10-19 | 2020-10-25 | 2021-01-05 | 2021-01-18 | 2021-03-24 | 2021-04-06 | 2021-04-24 | 2021-04-12
1609 | ST-2025-021 | Australia | 29 | 32 | 110.3 | 2 | 5.3 | ON_TRACK | Dr. Nicole White | 2016-07-01 | 2016-09-30 | 2016-09-26 | 2017-01-01 | 2017-01-06 | 2017-07-02 | 2017-07-03 | 2017-03-06 | 2017-03-08 | 2017-07-19 | 2017-07-09 | 2018-01-29 | 2018-01-16 | 2018-05-04 | 2018-05-04 | 2020-11-03 | 2020-10-23 | 2021-01-28 | 2021-02-08 | 2021-03-30 | 2021-04-13 | 2021-04-20 | 2021-05-02
1610 | ST-2025-022 | United States | 9 | 8 | 88.9 | 4 | 0.7 | AT_RISK | Dr. Stephanie Taylor | 2020-11-25 | 2021-02-08 | 2021-02-13 | 2021-05-24 | 2021-05-15 | 2021-11-22 | 2021-11-19 | 2021-07-13 | 2021-07-10 | 2021-12-07 | 2021-12-02 | 2022-05-15 | 2022-05-13 | 2022-08-19 | 2022-08-18 | 2025-09-02 | 2025-09-12 | 2025-11-25 | 2025-11-21 | 2026-03-02 | 2026-03-09 | 2026-03-30 | 2026-04-04
1611 | ST-2025-022 | Mexico | 9 | 6 | 66.7 | 2 | 0.4 | OFF_TRACK | Dr. David White | 2020-11-23 | 2021-02-26 | 2021-03-11 | 2021-05-18 | 2021-05-25 | 2021-11-04 | 2021-11-09 | 2021-07-18 | 2021-07-31 | 2021-12-09 | 2021-11-29 | 2022-05-24 | 2022-05-20 | 2022-08-22 | 2022-08-10 | 2025-09-05 | 2025-09-09 | 2025-11-25 | 2025-12-02 | 2026-02-26 | 2026-02-16 | 2026-04-02 | 2026-03-30
1612 | ST-2025-022 | Poland | 10 | 7 | 70 | 4 | 0.7 | OFF_TRACK | Dr. Jennifer Wilson | 2020-11-23 | 2021-02-18 | 2021-02-08 | 2021-05-12 | 2021-05-19 | 2021-11-21 | 2021-11-29 | 2021-07-10 | 2021-07-22 | 2021-12-15 | 2021-12-24 | 2022-05-31 | 2022-06-07 | 2022-08-25 | 2022-08-27 | 2025-09-16 | 2025-09-04 | 2025-12-14 | 2025-12-20 | 2026-02-27 | 2026-03-06 | 2026-04-04 | 2026-04-03
1613 | ST-2025-022 | Sweden | 10 | 8 | 80 | 6 | 0.9 | AT_RISK | Dr. Charles Davis | 2020-11-03 | 2021-02-17 | 2021-02-12 | 2021-05-17 | 2021-05-30 | 2021-11-07 | 2021-11-18 | 2021-07-14 | 2021-07-03 | 2021-12-16 | 2021-12-18 | 2022-06-09 | 2022-06-19 | 2022-09-01 | 2022-09-04 | 2025-09-19 | 2025-10-01 | 2025-12-07 | 2025-12-16 | 2026-02-24 | 2026-03-10 | 2026-03-23 | 2026-03-25
1614 | ST-2025-022 | China | 11 | 8 | 72.7 | 2 | 1 | OFF_TRACK | Dr. David Smith | 2020-11-13 | 2021-02-25 | 2021-03-08 | 2021-05-12 | 2021-05-26 | 2021-11-21 | 2021-11-12 | 2021-07-20 | 2021-07-29 | 2021-12-10 | 2021-12-10 | 2022-05-29 | 2022-05-16 | 2022-08-25 | 2022-08-24 | 2025-09-23 | 2025-09-20 | 2025-12-20 | 2025-12-27 | 2026-03-06 | 2026-03-15 | 2026-03-31 | 2026-03-24
1615 | ST-2025-022 | Chile | 11 | 23 | 209.1 | 3 | 1.3 | ON_TRACK | Dr. Jessica Harris | 2020-11-22 | 2021-02-15 | 2021-02-07 | 2021-05-22 | 2021-05-19 | 2021-11-09 | 2021-11-16 | 2021-07-25 | 2021-07-29 | 2021-12-13 | 2021-12-13 | 2022-07-06 | 2022-07-06 | 2022-10-10 | 2022-10-20 | 2025-10-28 | 2025-10-23 | 2026-01-20 | 2026-01-30 | 2026-03-08 | 2026-03-06 | 2026-04-04 | 2026-04-06
1616 | ST-2025-023 | United States | 199 | 184 | 92.5 | 2 | 10.8 | AT_RISK | Dr. Christopher Garcia | 2020-06-25 | 2020-09-29 | 2020-09-18 | 2021-01-11 | 2021-01-19 | 2021-06-23 | 2021-07-06 | 2021-03-02 | 2021-03-04 | 2021-07-24 | 2021-08-06 | 2022-01-06 | 2021-12-26 | 2022-04-01 | 2022-03-27 | 2027-01-07 |  | 2027-03-30 |  | 2027-06-30 |  | 2027-08-03
1617 | ST-2025-023 | Canada | 185 | 148 | 80 | 3 | 12.3 | AT_RISK | Dr. Sarah Williams | 2020-06-25 | 2020-10-01 | 2020-10-15 | 2021-01-06 | 2021-01-03 | 2021-07-17 | 2021-07-03 | 2021-03-10 | 2021-03-09 | 2021-07-27 | 2021-07-14 | 2022-01-06 | 2022-01-04 | 2022-03-30 | 2022-04-01 | 2027-01-12 |  | 2027-04-02 |  | 2027-07-05 |  | 2027-07-27
1618 | ST-2025-023 | Italy | 206 | 165 | 80.1 | 5 | 9.7 | AT_RISK | Dr. Jessica Taylor | 2020-07-02 | 2020-09-25 | 2020-09-15 | 2021-01-03 | 2020-12-24 | 2021-06-26 | 2021-06-13 | 2021-02-22 | 2021-02-17 | 2021-08-02 | 2021-08-14 | 2022-01-09 | 2022-01-10 | 2022-04-19 | 2022-04-27 | 2027-01-17 |  | 2027-04-14 |  | 2027-06-27 |  | 2027-08-01
1619 | ST-2025-023 | Poland | 314 | 230 | 73.2 | 6 | 13.5 | OFF_TRACK | Dr. Christopher Harris | 2020-07-14 | 2020-10-08 | 2020-10-17 | 2021-01-06 | 2021-01-11 | 2021-07-08 | 2021-07-10 | 2021-02-22 | 2021-02-21 | 2021-07-25 | 2021-07-14 | 2022-01-24 | 2022-02-03 | 2022-04-26 | 2022-04-21 | 2027-01-25 |  | 2027-04-25 |  | 2027-06-24 |  | 2027-07-28
1620 | ST-2025-023 | Japan | 202 | 182 | 90.1 | 6 | 10.1 | AT_RISK | Dr. William Taylor | 2020-06-23 | 2020-09-24 | 2020-09-29 | 2020-12-30 | 2021-01-02 | 2021-07-02 | 2021-06-18 | 2021-03-14 | 2021-03-20 | 2021-08-11 | 2021-08-13 | 2022-01-24 | 2022-01-28 | 2022-04-16 | 2022-04-09 | 2027-01-16 |  | 2027-04-16 |  | 2027-07-06 |  | 2027-07-27
1621 | ST-2025-023 | Mexico | 394 | 361 | 91.6 | 3 | 40.1 | AT_RISK | Dr. Jennifer Williams | 2020-06-29 | 2020-10-06 | 2020-10-08 | 2020-12-23 | 2020-12-20 | 2021-07-08 | 2021-06-26 | 2021-03-05 | 2021-03-07 | 2021-07-30 | 2021-08-02 | 2022-02-17 | 2022-02-19 | 2022-05-13 | 2022-05-24 | 2027-02-08 |  | 2027-05-06 |  | 2027-07-02 |  | 2027-07-21
1622 | ST-2025-024 | United States | 51 | 51 | 100 | 6 | 3.4 | ON_TRACK | Dr. Thomas Jackson | 2023-04-24 | 2023-07-11 | 2023-07-08 | 2023-10-22 | 2023-11-02 | 2024-05-02 | 2024-04-20 | 2023-12-25 | 2023-12-22 | 2024-05-10 | 2024-05-03 | 2024-10-23 | 2024-11-01 | 2025-01-15 | 2025-01-22 | 2026-09-30 |  | 2026-12-20 |  | 2027-04-01 |  | 2027-04-18
1623 | ST-2025-024 | Mexico | 44 | 44 | 100 | 6 | 7.3 | ON_TRACK | Dr. Nicole Smith | 2023-05-01 | 2023-07-29 | 2023-08-08 | 2023-10-20 | 2023-10-27 | 2024-04-09 | 2024-04-09 | 2023-12-11 | 2023-12-19 | 2024-05-20 | 2024-05-21 | 2024-10-29 | 2024-11-04 | 2025-01-22 | 2025-01-13 | 2026-10-16 |  | 2027-01-11 |  | 2027-03-23 |  | 2027-05-01
1624 | ST-2025-024 | Sweden | 62 | 33 | 53.2 | 4 | 2.8 | OFF_TRACK | Dr. Jennifer White | 2023-04-09 | 2023-07-25 | 2023-07-27 | 2023-10-11 | 2023-10-09 | 2024-04-14 | 2024-04-26 | 2023-12-16 | 2023-12-19 | 2024-05-10 | 2024-05-11 | 2024-11-03 | 2024-10-28 | 2025-02-10 | 2025-01-28 | 2026-10-13 |  | 2027-01-03 |  | 2027-04-04 |  | 2027-04-22
1625 | ST-2025-024 | Switzerland | 33 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Thomas Jackson | 2023-04-13 | 2023-07-20 | 2023-08-03 | 2023-10-21 | 2023-10-19 | 2024-05-02 | 2024-05-11 | 2023-12-11 | 2023-12-11 | 2024-05-29 | 2024-06-12 | 2024-11-13 | 2024-11-11 | 2025-02-08 | 2025-02-04 | 2026-10-22 |  | 2027-01-19 |  | 2027-03-26 |  | 2027-04-24
1626 | ST-2025-024 | Japan | 30 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Emily Brown | 2023-04-22 | 2023-07-26 | 2023-08-07 | 2023-10-21 | 2023-10-12 | 2024-04-30 | 2024-05-03 | 2023-12-26 | 2023-12-21 | 2024-05-17 | 2024-05-13 | 2024-11-24 | 2024-11-13 | 2025-03-02 | 2025-02-18 | 2026-11-11 |  | 2027-01-28 |  | 2027-03-27 |  | 2027-04-27
1627 | ST-2025-025 | Canada | -29 | -29 | 100 | 3 | -2.6 | ON_TRACK | Dr. Michelle Davis | 2024-12-16 | 2025-03-21 | 2025-03-18 | 2025-06-25 | 2025-06-30 | 2025-12-25 | 2025-12-24 | 2025-08-24 | 2025-08-18 | 2026-01-14 | 2026-01-20 | 2026-06-22 |  | 2026-09-16 |  | 2029-03-20 |  | 2029-06-05 |  | 2029-09-19 |  | 2029-10-19
1628 | ST-2025-025 | United States | 5 | 5 | 100 | 3 | 0.6 | ON_TRACK | Dr. James Garcia | 2024-12-08 | 2025-03-14 | 2025-03-21 | 2025-07-01 | 2025-07-12 | 2025-12-18 | 2025-12-18 | 2025-08-22 | 2025-08-09 | 2026-01-25 | 2026-01-15 | 2026-07-05 |  | 2026-09-23 |  | 2029-03-23 |  | 2029-06-10 |  | 2029-09-21 |  | 2029-10-15
1629 | ST-2025-025 | Spain | 5 | 3 | 60 | 4 | 0.4 | OFF_TRACK | Dr. James Jones | 2024-12-31 | 2025-04-01 | 2025-03-29 | 2025-06-22 | 2025-06-22 | 2025-12-17 | 2025-12-27 | 2025-08-23 | 2025-08-11 | 2026-01-27 | 2026-01-31 | 2026-06-23 |  | 2026-09-28 |  | 2029-03-23 |  | 2029-06-18 |  | 2029-09-15 |  | 2029-10-11
1630 | ST-2025-025 | Sweden | 5 | 3 | 60 | 5 | 0.2 | OFF_TRACK | Dr. Emily Taylor | 2024-12-18 | 2025-03-24 | 2025-03-22 | 2025-06-21 | 2025-06-24 | 2025-12-26 | 2025-12-15 | 2025-08-19 | 2025-08-13 | 2026-01-16 | 2026-01-26 | 2026-06-29 |  | 2026-09-24 |  | 2029-04-06 |  | 2029-06-24 |  | 2029-09-15 |  | 2029-10-14
1631 | ST-2025-025 | Netherlands | 5 | 3 | 60 | 3 | 0.3 | OFF_TRACK | Dr. Christopher Davis | 2024-12-21 | 2025-03-18 | 2025-04-01 | 2025-06-30 | 2025-07-08 | 2025-12-15 | 2025-12-15 | 2025-08-26 | 2025-08-14 | 2026-01-15 | 2026-01-26 | 2026-07-07 |  | 2026-10-04 |  | 2029-04-16 |  | 2029-07-03 |  | 2029-09-15 |  | 2029-10-08
1632 | ST-2025-025 | Taiwan | 5 | 3 | 60 | 4 | 0.2 | OFF_TRACK | Dr. Amanda Garcia | 2025-01-03 | 2025-03-22 | 2025-03-30 | 2025-06-22 | 2025-06-30 | 2025-12-28 | 2026-01-05 | 2025-08-13 | 2025-08-19 | 2026-01-26 | 2026-01-17 | 2026-08-03 |  | 2026-10-26 |  | 2029-05-07 |  | 2029-07-27 |  | 2029-09-21 |  | 2029-10-08
1633 | ST-2025-025 | Australia | 5 | 5 | 100 | 6 | 0.3 | ON_TRACK | Dr. Stephanie Williams | 2024-12-23 | 2025-03-19 | 2025-03-19 | 2025-06-14 | 2025-06-25 | 2025-12-12 | 2025-12-15 | 2025-08-15 | 2025-08-05 | 2026-01-16 | 2026-01-21 | 2026-08-15 |  | 2026-11-04 |  | 2029-05-11 |  | 2029-08-04 |  | 2029-09-17 |  | 2029-10-11
1634 | ST-2025-025 | Chile | 5 | 7 | 140 | 2 | 0.9 | ON_TRACK | Dr. Robert Miller | 2024-12-09 | 2025-03-21 | 2025-03-11 | 2025-06-23 | 2025-06-19 | 2025-12-28 | 2026-01-03 | 2025-08-26 | 2025-08-14 | 2026-01-25 | 2026-01-25 | 2026-08-28 |  | 2026-11-30 |  | 2029-05-26 |  | 2029-08-24 |  | 2029-09-17 |  | 2029-10-07
1635 | ST-2025-026 | Mexico | 28 | 23 | 82.1 | 6 | 1.8 | AT_RISK | Dr. Robert Wilson | 2019-02-07 | 2019-05-08 | 2019-05-21 | 2019-07-31 | 2019-07-18 | 2020-02-18 | 2020-03-01 | 2019-10-13 | 2019-10-02 | 2020-03-15 | 2020-03-17 | 2020-08-08 | 2020-07-29 | 2020-10-28 | 2020-10-23 | 2028-08-02 |  | 2028-10-20 |  | 2029-01-22 |  | 2029-02-21
1636 | ST-2025-026 | Canada | 41 | 40 | 97.6 | 3 | 2.7 | ON_TRACK | Dr. Jennifer Smith | 2019-02-01 | 2019-05-04 | 2019-05-10 | 2019-08-07 | 2019-08-02 | 2020-02-06 | 2020-02-11 | 2019-10-05 | 2019-10-08 | 2020-02-26 | 2020-02-14 | 2020-08-08 | 2020-08-10 | 2020-11-03 | 2020-11-09 | 2028-08-05 |  | 2028-10-29 |  | 2029-01-20 |  | 2029-02-15
1637 | ST-2025-026 | Switzerland | 43 | 30 | 69.8 | 2 | 1.7 | OFF_TRACK | Dr. Michael Jackson | 2019-02-09 | 2019-05-01 | 2019-05-14 | 2019-08-01 | 2019-07-18 | 2020-02-11 | 2020-01-30 | 2019-10-15 | 2019-10-02 | 2020-03-14 | 2020-03-20 | 2020-08-13 | 2020-08-23 | 2020-11-17 | 2020-11-21 | 2028-08-13 |  | 2028-11-07 |  | 2029-01-16 |  | 2029-02-26
1638 | ST-2025-026 | Sweden | 35 | 33 | 94.3 | 5 | 1.9 | AT_RISK | Dr. Michael Thompson | 2019-01-28 | 2019-05-15 | 2019-05-10 | 2019-08-09 | 2019-08-10 | 2020-02-09 | 2020-02-02 | 2019-10-16 | 2019-10-27 | 2020-02-24 | 2020-03-06 | 2020-08-22 | 2020-08-29 | 2020-11-25 | 2020-11-23 | 2028-08-16 |  | 2028-11-09 |  | 2029-01-20 |  | 2029-02-23
1639 | ST-2025-026 | Singapore | 46 | 17 | 37 | 3 | 1.4 | OFF_TRACK | Dr. Jennifer White | 2019-01-24 | 2019-04-28 | 2019-05-11 | 2019-08-01 | 2019-08-09 | 2020-02-04 | 2020-01-31 | 2019-10-09 | 2019-10-18 | 2020-03-10 | 2020-03-23 | 2020-08-28 | 2020-08-25 | 2020-11-20 | 2020-11-18 | 2028-08-17 |  | 2028-11-11 |  | 2029-01-18 |  | 2029-02-18
1640 | ST-2025-026 | New Zealand | 67 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Jessica Thompson | 2019-02-02 | 2019-05-13 | 2019-05-02 | 2019-08-13 | 2019-07-31 | 2020-01-24 | 2020-01-19 | 2019-10-06 | 2019-10-04 | 2020-03-02 | 2020-03-15 | 2020-08-28 | 2020-09-02 | 2020-11-18 | 2020-11-17 | 2028-08-16 |  | 2028-11-08 |  | 2029-01-19 |  | 2029-02-15
1641 | ST-2025-027 | Mexico | 17 | 17 | 100 | 6 | 1.4 | ON_TRACK | Dr. Michael Taylor | 2021-07-14 | 2021-09-25 | 2021-09-20 | 2021-12-30 | 2021-12-31 | 2022-07-04 | 2022-06-20 | 2022-03-01 | 2022-02-17 | 2022-07-26 | 2022-07-24 | 2022-12-26 | 2022-12-28 | 2023-03-29 | 2023-03-29 | 2026-06-01 |  | 2026-08-24 |  | 2026-11-26 |  | 2026-12-31
1642 | ST-2025-027 | Canada | 7 | 6 | 85.7 | 2 | 0.5 | AT_RISK | Dr. Thomas Wilson | 2021-06-23 | 2021-10-08 | 2021-10-09 | 2021-12-31 | 2021-12-26 | 2022-06-17 | 2022-06-20 | 2022-02-20 | 2022-02-06 | 2022-07-29 | 2022-08-11 | 2023-01-10 | 2022-12-30 | 2023-04-10 | 2023-04-09 | 2026-06-17 |  | 2026-09-15 |  | 2026-11-29 |  | 2026-12-27
1643 | ST-2025-027 | United States | 9 | 6 | 66.7 | 3 | 0.3 | OFF_TRACK | Dr. Lisa Wilson | 2021-06-25 | 2021-10-01 | 2021-09-26 | 2022-01-01 | 2021-12-20 | 2022-06-27 | 2022-06-25 | 2022-02-20 | 2022-02-22 | 2022-08-01 | 2022-08-01 | 2023-01-02 | 2023-01-12 | 2023-04-09 | 2023-04-12 | 2026-06-10 |  | 2026-08-29 |  | 2026-11-24 |  | 2026-12-25
1644 | ST-2025-027 | Switzerland | 12 | 11 | 91.7 | 2 | 1.6 | AT_RISK | Dr. Charles Davis | 2021-07-06 | 2021-10-09 | 2021-09-29 | 2021-12-23 | 2021-12-15 | 2022-06-20 | 2022-06-25 | 2022-02-22 | 2022-02-24 | 2022-08-01 | 2022-07-30 | 2023-01-14 | 2023-01-16 | 2023-04-19 | 2023-04-06 | 2026-06-14 |  | 2026-09-07 |  | 2026-11-24 |  | 2026-12-29
1645 | ST-2025-027 | Spain | 14 | 10 | 71.4 | 5 | 1.4 | OFF_TRACK | Dr. Emily Garcia | 2021-06-21 | 2021-09-30 | 2021-10-05 | 2022-01-04 | 2021-12-31 | 2022-07-02 | 2022-06-23 | 2022-03-05 | 2022-03-03 | 2022-07-24 | 2022-07-29 | 2023-01-17 | 2023-01-26 | 2023-04-20 | 2023-05-02 | 2026-06-16 |  | 2026-09-03 |  | 2026-11-24 |  | 2026-12-31
1646 | ST-2025-027 | United Kingdom | 12 | 8 | 66.7 | 6 | 0.5 | OFF_TRACK | Dr. Jessica Martin | 2021-06-27 | 2021-10-06 | 2021-10-13 | 2022-01-05 | 2021-12-25 | 2022-07-03 | 2022-07-02 | 2022-03-06 | 2022-03-10 | 2022-08-07 | 2022-08-02 | 2023-01-25 | 2023-02-05 | 2023-04-26 | 2023-05-10 | 2026-07-04 |  | 2026-09-19 |  | 2026-11-24 |  | 2026-12-22
1647 | ST-2025-027 | India | 10 | 7 | 70 | 2 | 0.5 | OFF_TRACK | Dr. Amanda Anderson | 2021-07-09 | 2021-10-10 | 2021-10-19 | 2021-12-20 | 2021-12-07 | 2022-07-05 | 2022-07-09 | 2022-03-06 | 2022-03-07 | 2022-07-28 | 2022-07-19 | 2023-02-23 | 2023-02-25 | 2023-05-24 | 2023-05-30 | 2026-07-26 |  | 2026-10-20 |  | 2026-11-28 |  | 2026-12-20
1648 | ST-2025-027 | Singapore | 7 | 17 | 242.9 | 6 | 1.7 | ON_TRACK | Dr. Emily Johnson | 2021-07-11 | 2021-10-02 | 2021-09-28 | 2021-12-24 | 2021-12-23 | 2022-07-12 | 2022-07-02 | 2022-02-26 | 2022-02-25 | 2022-07-21 | 2022-07-29 | 2023-03-03 | 2023-02-23 | 2023-06-01 | 2023-05-31 | 2026-07-24 |  | 2026-10-12 |  | 2026-11-19 |  | 2026-12-24
1649 | ST-2025-028 | Canada | 21031 | 5228 | 24.9 | 2 | 348.5 | OFF_TRACK | Dr. Thomas Brown | 2024-01-16 | 2024-04-16 | 2024-04-14 | 2024-07-02 | 2024-06-28 | 2025-01-17 | 2025-01-08 | 2024-09-04 | 2024-09-04 | 2025-02-14 | 2025-02-17 | 2025-07-08 | 2025-07-04 | 2025-10-09 | 2025-10-12 | 2028-06-30 |  | 2028-09-25 |  | 2028-12-28 |  | 2029-01-26
1650 | ST-2025-028 | Denmark | 31608 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Sarah Jones | 2024-01-21 | 2024-04-21 | 2024-05-01 | 2024-07-09 | 2024-07-04 | 2025-01-14 | 2025-01-22 | 2024-09-15 | 2024-09-07 | 2025-02-04 | 2025-02-12 | 2025-07-14 | 2025-07-22 | 2025-10-11 | 2025-10-12 | 2028-07-09 |  | 2028-09-28 |  | 2028-12-24 |  | 2029-01-22
1651 | ST-2025-028 | Australia | 15361 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Daniel Taylor | 2024-01-08 | 2024-04-18 | 2024-04-15 | 2024-07-09 | 2024-07-19 | 2025-01-04 | 2025-01-15 | 2024-09-03 | 2024-08-24 | 2025-02-16 | 2025-02-11 | 2025-07-26 | 2025-07-13 | 2025-10-20 | 2025-10-15 | 2028-07-12 |  | 2028-10-11 |  | 2028-12-27 |  | 2029-01-31
1652 | ST-2025-029 | Mexico | 43 | 35 | 81.4 | 3 | 3.9 | AT_RISK | Dr. Robert Garcia | 2022-10-10 | 2023-01-22 | 2023-01-25 | 2023-04-26 | 2023-05-04 | 2023-10-27 | 2023-10-21 | 2023-06-20 | 2023-06-10 | 2023-11-25 | 2023-11-14 | 2024-04-18 | 2024-04-23 | 2024-07-15 | 2024-07-24 | 2026-06-27 |  | 2026-09-20 |  | 2026-12-14 |  | 2027-01-21
1653 | ST-2025-029 | United States | 20 | 15 | 75 | 6 | 1.1 | OFF_TRACK | Dr. Daniel Taylor | 2022-10-15 | 2023-01-12 | 2023-01-01 | 2023-04-28 | 2023-05-05 | 2023-10-14 | 2023-10-24 | 2023-07-02 | 2023-06-22 | 2023-11-17 | 2023-11-03 | 2024-04-23 | 2024-04-26 | 2024-07-21 | 2024-07-12 | 2026-06-28 |  | 2026-09-18 |  | 2026-12-21 |  | 2027-01-14
1654 | ST-2025-029 | Netherlands | 34 | 30 | 88.2 | 5 | 1.7 | AT_RISK | Dr. Robert Taylor | 2022-11-05 | 2023-01-26 | 2023-01-14 | 2023-04-27 | 2023-05-03 | 2023-10-27 | 2023-10-31 | 2023-06-18 | 2023-06-11 | 2023-11-19 | 2023-11-22 | 2024-05-03 | 2024-05-12 | 2024-07-29 | 2024-08-07 | 2026-07-07 |  | 2026-09-22 |  | 2026-12-24 |  | 2027-01-19
1655 | ST-2025-029 | Belgium | 27 | 27 | 100 | 4 | 2.5 | ON_TRACK | Dr. Stephanie Johnson | 2022-10-09 | 2023-01-16 | 2023-01-29 | 2023-04-25 | 2023-04-20 | 2023-11-04 | 2023-11-18 | 2023-06-17 | 2023-06-04 | 2023-11-11 | 2023-10-28 | 2024-05-19 | 2024-05-14 | 2024-08-21 | 2024-08-25 | 2026-07-19 |  | 2026-10-06 |  | 2026-12-24 |  | 2027-01-18
1656 | ST-2025-029 | Australia | 34 | 9 | 26.5 | 5 | 1 | OFF_TRACK | Dr. David Williams | 2022-10-18 | 2023-01-20 | 2023-01-14 | 2023-04-26 | 2023-04-18 | 2023-10-27 | 2023-11-07 | 2023-06-29 | 2023-06-18 | 2023-11-26 | 2023-11-22 | 2024-05-23 | 2024-05-14 | 2024-08-26 | 2024-09-04 | 2026-07-17 |  | 2026-10-15 |  | 2026-12-18 |  | 2027-01-14
1657 | ST-2025-029 | India | 42 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Nicole Brown | 2022-10-16 | 2023-01-16 | 2023-01-29 | 2023-04-12 | 2023-04-18 | 2023-10-30 | 2023-11-13 | 2023-06-22 | 2023-06-20 | 2023-11-19 | 2023-12-01 | 2024-05-28 | 2024-05-27 | 2024-08-25 | 2024-08-27 | 2026-07-30 |  | 2026-10-18 |  | 2026-12-12 |  | 2027-01-16
1658 | ST-2025-030 | United States | 158 | 138 | 87.3 | 2 | 19.7 | AT_RISK | Dr. Christopher Garcia | 2022-07-10 | 2022-10-04 | 2022-10-14 | 2023-01-05 | 2022-12-30 | 2023-07-01 | 2023-06-27 | 2023-03-17 | 2023-03-12 | 2023-08-10 | 2023-08-14 | 2024-01-07 | 2024-01-16 | 2024-04-01 | 2024-04-05 | 2026-05-29 |  | 2026-08-20 |  | 2026-11-23 |  | 2026-12-25
1659 | ST-2025-030 | Canada | 177 | 177 | 100 | 6 | 16.1 | ON_TRACK | Dr. Charles Davis | 2022-07-18 | 2022-10-12 | 2022-10-26 | 2023-01-07 | 2023-01-21 | 2023-06-28 | 2023-07-06 | 2023-03-05 | 2023-03-15 | 2023-08-14 | 2023-08-09 | 2024-01-12 | 2024-01-20 | 2024-04-07 | 2024-03-27 | 2026-06-04 |  | 2026-08-30 |  | 2026-11-28 |  | 2027-01-01
1660 | ST-2025-030 | Mexico | 210 | 163 | 77.6 | 6 | 27.2 | OFF_TRACK | Dr. Jessica Smith | 2022-07-07 | 2022-10-12 | 2022-10-11 | 2023-01-19 | 2023-01-27 | 2023-07-04 | 2023-07-07 | 2023-03-09 | 2023-03-10 | 2023-08-04 | 2023-08-14 | 2024-01-27 | 2024-01-30 | 2024-04-19 | 2024-04-30 | 2026-06-17 |  | 2026-09-13 |  | 2026-11-29 |  | 2026-12-23
1661 | ST-2025-030 | Poland | 190 | 136 | 71.6 | 6 | 22.7 | OFF_TRACK | Dr. Christopher Anderson | 2022-07-04 | 2022-10-08 | 2022-10-12 | 2023-01-19 | 2023-01-08 | 2023-07-24 | 2023-07-11 | 2023-03-04 | 2023-03-16 | 2023-08-16 | 2023-08-19 | 2024-02-04 | 2024-02-18 | 2024-05-03 | 2024-05-05 | 2026-06-29 |  | 2026-09-19 |  | 2026-11-21 |  | 2027-01-01
1662 | ST-2025-030 | Spain | 170 | 152 | 89.4 | 3 | 12.7 | AT_RISK | Dr. Sarah Moore | 2022-07-15 | 2022-10-05 | 2022-09-23 | 2023-01-05 | 2023-01-19 | 2023-07-07 | 2023-07-09 | 2023-03-18 | 2023-03-18 | 2023-08-14 | 2023-08-25 | 2024-01-25 | 2024-01-12 | 2024-05-01 | 2024-05-01 | 2026-06-17 |  | 2026-09-13 |  | 2026-11-29 |  | 2026-12-25
1663 | ST-2025-030 | Switzerland | 156 | 112 | 71.8 | 6 | 18.7 | OFF_TRACK | Dr. Thomas Smith | 2022-07-11 | 2022-10-15 | 2022-10-09 | 2023-01-18 | 2023-01-30 | 2023-06-28 | 2023-06-14 | 2023-03-19 | 2023-03-28 | 2023-08-14 | 2023-08-06 | 2024-02-05 | 2024-02-09 | 2024-05-05 | 2024-04-23 | 2026-06-20 |  | 2026-09-16 |  | 2026-11-20 |  | 2026-12-24
1664 | ST-2025-030 | China | 167 | 64 | 38.3 | 2 | 4.9 | OFF_TRACK | Dr. Emily White | 2022-07-09 | 2022-10-03 | 2022-10-13 | 2023-01-17 | 2023-01-23 | 2023-06-28 | 2023-07-07 | 2023-03-04 | 2023-03-10 | 2023-08-15 | 2023-08-14 | 2024-01-27 | 2024-01-24 | 2024-04-28 | 2024-05-12 | 2026-06-23 |  | 2026-09-10 |  | 2026-12-02 |  | 2026-12-20
1665 | ST-2025-030 | Japan | 172 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Thomas Thomas | 2022-07-25 | 2022-10-13 | 2022-10-11 | 2023-01-12 | 2023-01-14 | 2023-06-29 | 2023-06-19 | 2023-03-19 | 2023-03-28 | 2023-08-04 | 2023-07-28 | 2024-02-26 | 2024-03-09 | 2024-05-27 | 2024-05-13 | 2026-07-12 |  | 2026-09-28 |  | 2026-11-22 |  | 2026-12-26
1666 | ST-2025-031 | Canada | 10 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. Jessica Davis | 2025-04-17 | 2025-07-26 | 2025-07-18 | 2025-10-28 | 2025-11-11 | 2026-04-20 | 2026-04-29 | 2025-12-28 | 2026-01-07 | 2026-05-23 |  | 2026-10-18 |  | 2027-01-14 |  | 2029-08-20 |  | 2029-11-10 |  | 2030-02-10 |  | 2030-03-12
1667 | ST-2025-031 | United States | 7 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Jennifer White | 2025-05-03 | 2025-07-25 | 2025-07-30 | 2025-10-30 | 2025-11-06 | 2026-05-01 | 2026-05-09 | 2025-12-11 | 2025-12-24 | 2026-05-18 | 2026-05-05 | 2026-10-22 |  | 2027-01-16 |  | 2029-08-18 |  | 2029-11-12 |  | 2030-02-08 |  | 2030-03-15
1668 | ST-2025-031 | Mexico | 5 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. David Williams | 2025-04-09 | 2025-07-24 | 2025-08-02 | 2025-10-25 | 2025-10-29 | 2026-04-14 | 2026-04-10 | 2025-12-28 | 2026-01-01 | 2026-05-17 | 2026-05-22 | 2026-10-25 |  | 2027-01-23 |  | 2029-08-31 |  | 2029-11-20 |  | 2030-02-11 |  | 2030-03-21
1669 | ST-2025-031 | United Kingdom | 12 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Emily Miller | 2025-05-04 | 2025-07-22 | 2025-07-26 | 2025-10-18 | 2025-11-01 | 2026-04-16 | 2026-04-25 | 2025-12-15 | 2025-12-06 | 2026-05-27 |  | 2026-11-14 |  | 2027-02-13 |  | 2029-09-13 |  | 2029-12-03 |  | 2030-02-08 |  | 2030-03-16
1670 | ST-2025-031 | France | 9 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Robert Smith | 2025-04-21 | 2025-07-29 | 2025-07-28 | 2025-10-26 | 2025-10-25 | 2026-04-08 | 2026-03-29 | 2025-12-22 | 2025-12-17 | 2026-05-31 |  | 2026-11-26 |  | 2027-02-18 |  | 2029-09-26 |  | 2029-12-20 |  | 2030-02-13 |  | 2030-03-19
1671 | ST-2025-031 | Belgium | 9 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Stephanie Moore | 2025-05-02 | 2025-07-29 | 2025-07-28 | 2025-10-26 | 2025-10-25 | 2026-04-14 | 2026-04-17 | 2025-12-18 | 2025-12-20 | 2026-05-20 |  | 2026-11-17 |  | 2027-02-23 |  | 2029-09-20 |  | 2029-12-20 |  | 2030-02-08 |  | 2030-03-16
1672 | ST-2025-031 | Taiwan | 11 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Jennifer Thompson | 2025-04-15 | 2025-07-20 | 2025-08-01 | 2025-10-17 | 2025-10-09 | 2026-04-17 | 2026-04-04 | 2025-12-31 | 2025-12-25 | 2026-05-13 | 2026-05-11 | 2026-11-18 |  | 2027-02-20 |  | 2029-09-14 |  | 2029-12-01 |  | 2030-02-16 |  | 2030-03-19
1673 | ST-2025-031 | Japan | 5 | 0 | 0 | 5 | 0 | OFF_TRACK | Dr. David Martin | 2025-04-27 | 2025-07-13 | 2025-07-08 | 2025-10-13 | 2025-09-29 | 2026-04-13 | 2026-04-05 | 2025-12-29 | 2025-12-21 | 2026-05-28 |  | 2026-12-15 |  | 2027-03-17 |  | 2029-10-13 |  | 2030-01-11 |  | 2030-02-22 |  | 2030-03-13
1674 | ST-2025-032 | Canada | 118 | 25 | 21.2 | 2 | 1.5 | OFF_TRACK | Dr. Lisa Williams | 2023-08-08 | 2023-11-23 | 2023-11-18 | 2024-02-14 | 2024-02-12 | 2024-08-25 | 2024-08-25 | 2024-04-27 | 2024-04-30 | 2024-09-12 | 2024-09-18 | 2025-02-16 | 2025-02-13 | 2025-05-23 | 2025-05-18 | 2029-09-28 |  | 2029-12-22 |  | 2030-03-26 |  | 2030-04-30
1675 | ST-2025-032 | Mexico | 82 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Daniel Taylor | 2023-08-21 | 2023-11-23 | 2023-12-06 | 2024-02-21 | 2024-02-14 | 2024-08-06 | 2024-08-15 | 2024-04-23 | 2024-04-13 | 2024-09-16 | 2024-09-02 | 2025-02-18 | 2025-02-12 | 2025-05-19 | 2025-05-22 | 2029-10-05 |  | 2029-12-27 |  | 2030-03-21 |  | 2030-04-27
1676 | ST-2025-032 | United Kingdom | 48 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Daniel Williams | 2023-08-23 | 2023-11-21 | 2023-11-24 | 2024-02-16 | 2024-02-22 | 2024-08-07 | 2024-08-14 | 2024-04-14 | 2024-04-10 | 2024-09-16 | 2024-09-10 | 2025-03-05 | 2025-03-15 | 2025-06-04 | 2025-06-16 | 2029-10-24 |  | 2030-01-22 |  | 2030-03-24 |  | 2030-04-25
1677 | ST-2025-032 | Norway | 52 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Stephanie Brown | 2023-08-28 | 2023-11-28 | 2023-12-12 | 2024-02-22 | 2024-02-25 | 2024-08-17 | 2024-08-23 | 2024-04-13 | 2024-03-31 | 2024-09-17 | 2024-09-19 | 2025-03-05 | 2025-02-20 | 2025-06-01 | 2025-06-13 | 2029-10-27 |  | 2030-01-20 |  | 2030-03-28 |  | 2030-04-20
1678 | ST-2025-033 | Mexico | 1 | 1 | 100 | 5 | 0.2 | ON_TRACK | Dr. Thomas White | 2020-08-06 | 2020-10-15 | 2020-10-17 | 2021-01-13 | 2021-01-13 | 2021-07-23 | 2021-07-20 | 2021-03-19 | 2021-03-06 | 2021-09-02 | 2021-09-07 | 2022-01-20 | 2022-01-26 | 2022-04-16 | 2022-04-23 | 2025-07-28 | 2025-08-02 | 2025-10-15 | 2025-10-16 | 2026-01-12 | 2026-01-19 | 2026-02-12 | 2026-02-13
1679 | ST-2025-033 | Canada | 5 | 5 | 100 | 3 | 0.6 | ON_TRACK | Dr. Nicole Williams | 2020-07-28 | 2020-10-31 | 2020-11-08 | 2021-01-26 | 2021-02-02 | 2021-07-10 | 2021-07-09 | 2021-03-15 | 2021-03-26 | 2021-08-29 | 2021-08-20 | 2022-01-25 | 2022-01-14 | 2022-04-27 | 2022-04-16 | 2025-07-25 | 2025-07-27 | 2025-10-10 | 2025-09-30 | 2026-01-20 | 2026-01-13 | 2026-02-22 | 2026-02-14
1680 | ST-2025-033 | Switzerland | 5 | 3 | 60 | 2 | 0.3 | OFF_TRACK | Dr. David Miller | 2020-07-19 | 2020-10-25 | 2020-10-18 | 2021-01-21 | 2021-01-16 | 2021-08-04 | 2021-08-11 | 2021-03-27 | 2021-04-08 | 2021-08-15 | 2021-08-28 | 2022-02-07 | 2022-01-26 | 2022-05-07 | 2022-05-13 | 2025-08-09 | 2025-08-22 | 2025-11-03 | 2025-11-09 | 2026-01-15 | 2026-01-25 | 2026-02-20 | 2026-02-07
1681 | ST-2025-033 | Poland | 5 | 4 | 80 | 2 | 0.3 | AT_RISK | Dr. Christopher Taylor | 2020-07-23 | 2020-10-26 | 2020-10-25 | 2021-01-30 | 2021-02-05 | 2021-07-25 | 2021-08-05 | 2021-03-16 | 2021-03-12 | 2021-09-02 | 2021-09-06 | 2022-01-29 | 2022-02-11 | 2022-05-08 | 2022-04-27 | 2025-07-31 | 2025-08-14 | 2025-10-17 | 2025-10-19 | 2026-01-19 | 2026-01-06 | 2026-02-22 | 2026-02-15
1682 | ST-2025-034 | Canada | 8 | 7 | 87.5 | 2 | 0.4 | AT_RISK | Dr. Amanda Smith | 2021-10-15 | 2022-01-09 | 2022-01-16 | 2022-04-07 | 2022-03-25 | 2022-09-25 | 2022-09-16 | 2022-05-24 | 2022-06-06 | 2022-10-23 | 2022-10-19 | 2023-04-06 | 2023-03-23 | 2023-07-07 | 2023-06-29 | 2026-08-29 |  | 2026-11-28 |  | 2027-02-28 |  | 2027-03-29
1683 | ST-2025-034 | France | 6 | 4 | 66.7 | 3 | 0.3 | OFF_TRACK | Dr. Nicole Taylor | 2021-10-12 | 2022-01-03 | 2022-01-17 | 2022-03-25 | 2022-03-28 | 2022-09-26 | 2022-09-22 | 2022-05-28 | 2022-05-26 | 2022-11-08 | 2022-11-18 | 2023-04-07 | 2023-04-16 | 2023-07-10 | 2023-06-30 | 2026-09-15 |  | 2026-12-14 |  | 2027-02-26 |  | 2027-03-30
1684 | ST-2025-034 | New Zealand | 6 | 6 | 100 | 4 | 0.4 | ON_TRACK | Dr. Emily Garcia | 2021-10-10 | 2021-12-24 | 2021-12-29 | 2022-04-08 | 2022-04-18 | 2022-10-10 | 2022-10-15 | 2022-06-03 | 2022-06-08 | 2022-10-22 | 2022-10-20 | 2023-04-15 | 2023-04-25 | 2023-07-17 | 2023-07-13 | 2026-09-15 |  | 2026-12-14 |  | 2027-02-21 |  | 2027-03-25
1685 | ST-2025-035 | Canada | -20 | -20 | 100 | 6 | -1.3 | ON_TRACK | Dr. Christopher Johnson | 2023-09-23 | 2024-01-02 | 2023-12-31 | 2024-04-03 | 2024-03-22 | 2024-09-20 | 2024-09-30 | 2024-05-30 | 2024-06-04 | 2024-11-03 | 2024-10-29 | 2025-03-29 | 2025-04-09 | 2025-06-25 | 2025-06-18 | 2026-12-21 |  | 2027-03-18 |  | 2027-06-25 |  | 2027-07-24
1686 | ST-2025-035 | Mexico | 5 | 4 | 80 | 2 | 0.4 | AT_RISK | Dr. Amanda Johnson | 2023-09-17 | 2023-12-27 | 2023-12-22 | 2024-03-23 | 2024-03-23 | 2024-09-25 | 2024-09-22 | 2024-06-08 | 2024-06-18 | 2024-10-21 | 2024-10-15 | 2025-04-06 | 2025-03-26 | 2025-07-02 | 2025-06-22 | 2027-01-01 |  | 2027-03-20 |  | 2027-06-17 |  | 2027-07-14
1687 | ST-2025-035 | United States | 5 | 5 | 100 | 3 | 0.3 | ON_TRACK | Dr. Emily Jackson | 2023-09-28 | 2024-01-02 | 2024-01-07 | 2024-04-05 | 2024-04-10 | 2024-09-30 | 2024-10-11 | 2024-06-04 | 2024-05-31 | 2024-10-30 | 2024-11-12 | 2025-04-01 | 2025-03-30 | 2025-06-27 | 2025-06-13 | 2026-12-28 |  | 2027-03-20 |  | 2027-06-24 |  | 2027-07-15
1688 | ST-2025-035 | Sweden | 5 | 4 | 80 | 6 | 0.2 | AT_RISK | Dr. Michael Taylor | 2023-09-27 | 2023-12-21 | 2023-12-15 | 2024-04-05 | 2024-03-31 | 2024-10-11 | 2024-10-05 | 2024-05-26 | 2024-05-27 | 2024-11-04 | 2024-10-25 | 2025-04-17 | 2025-04-05 | 2025-07-08 | 2025-06-29 | 2027-01-15 |  | 2027-04-08 |  | 2027-06-18 |  | 2027-07-16
1689 | ST-2025-035 | Netherlands | 5 | 3 | 60 | 4 | 0.2 | OFF_TRACK | Dr. Charles Smith | 2023-09-28 | 2023-12-28 | 2024-01-02 | 2024-04-03 | 2024-03-26 | 2024-10-08 | 2024-10-08 | 2024-05-21 | 2024-05-10 | 2024-10-28 | 2024-10-18 | 2025-04-22 | 2025-04-17 | 2025-07-18 | 2025-07-04 | 2027-01-25 |  | 2027-04-22 |  | 2027-06-23 |  | 2027-07-23
1690 | ST-2025-035 | Italy | 5 | 5 | 100 | 3 | 0.3 | ON_TRACK | Dr. William Williams | 2023-09-25 | 2024-01-07 | 2024-01-12 | 2024-03-31 | 2024-03-21 | 2024-10-08 | 2024-10-03 | 2024-05-29 | 2024-05-25 | 2024-10-31 | 2024-11-05 | 2025-05-18 | 2025-05-26 | 2025-08-15 | 2025-08-07 | 2027-02-21 |  | 2027-05-22 |  | 2027-06-29 |  | 2027-07-24
1691 | ST-2025-035 | Germany | 5 | 5 | 100 | 5 | 0.7 | ON_TRACK | Dr. David Wilson | 2023-09-20 | 2023-12-31 | 2024-01-12 | 2024-03-29 | 2024-04-09 | 2024-09-22 | 2024-09-20 | 2024-06-08 | 2024-06-05 | 2024-11-01 | 2024-10-21 | 2025-05-12 | 2025-05-16 | 2025-08-11 | 2025-08-03 | 2027-02-01 |  | 2027-04-24 |  | 2027-06-22 |  | 2027-07-18
1692 | ST-2025-035 | Australia | 5 | 2 | 40 | 4 | 0.1 | OFF_TRACK | Dr. Daniel Moore | 2023-10-02 | 2023-12-24 | 2024-01-05 | 2024-04-05 | 2024-04-18 | 2024-09-13 | 2024-09-24 | 2024-06-02 | 2024-06-13 | 2024-10-23 | 2024-10-22 | 2025-05-23 | 2025-05-30 | 2025-08-24 | 2025-08-25 | 2027-02-15 |  | 2027-05-16 |  | 2027-06-27 |  | 2027-07-15
1693 | ST-2025-036 | Mexico | 78 | 78 | 100 | 5 | 4.6 | ON_TRACK | Dr. Robert Taylor | 2020-01-30 | 2020-05-02 | 2020-04-30 | 2020-08-02 | 2020-08-05 | 2021-02-09 | 2021-02-11 | 2020-09-28 | 2020-10-11 | 2021-03-07 | 2021-03-15 | 2021-08-04 | 2021-08-03 | 2021-10-26 | 2021-10-29 | 2027-10-02 |  | 2027-12-27 |  | 2028-03-27 |  | 2028-04-26
1694 | ST-2025-036 | United States | 95 | 95 | 100 | 2 | 11.9 | ON_TRACK | Dr. Thomas Harris | 2020-02-01 | 2020-05-12 | 2020-05-17 | 2020-08-13 | 2020-07-31 | 2021-02-08 | 2021-02-12 | 2020-09-26 | 2020-10-02 | 2021-02-25 | 2021-03-04 | 2021-08-05 | 2021-08-11 | 2021-11-08 | 2021-11-06 | 2027-10-09 |  | 2027-12-30 |  | 2028-03-22 |  | 2028-04-27
1695 | ST-2025-036 | Poland | 99 | 99 | 100 | 6 | 5.5 | ON_TRACK | Dr. Stephanie Smith | 2020-01-31 | 2020-05-08 | 2020-05-16 | 2020-07-28 | 2020-08-01 | 2021-01-19 | 2021-01-12 | 2020-09-27 | 2020-09-27 | 2021-03-02 | 2021-02-27 | 2021-08-22 | 2021-08-20 | 2021-11-23 | 2021-11-23 | 2027-10-27 |  | 2028-01-20 |  | 2028-03-28 |  | 2028-04-26
1696 | ST-2025-036 | United Kingdom | 43 | 37 | 86 | 5 | 2.5 | AT_RISK | Dr. Jessica Smith | 2020-02-08 | 2020-05-11 | 2020-05-23 | 2020-07-29 | 2020-08-07 | 2021-01-30 | 2021-01-20 | 2020-09-24 | 2020-09-21 | 2021-03-09 | 2021-03-04 | 2021-08-26 | 2021-08-22 | 2021-11-25 | 2021-11-25 | 2027-10-28 |  | 2028-01-27 |  | 2028-03-21 |  | 2028-04-18
1697 | ST-2025-036 | Switzerland | 104 | 84 | 80.8 | 6 | 7 | AT_RISK | Dr. James Smith | 2020-02-06 | 2020-05-10 | 2020-05-18 | 2020-08-05 | 2020-07-25 | 2021-02-03 | 2021-01-20 | 2020-09-27 | 2020-10-10 | 2021-03-08 | 2021-03-04 | 2021-09-10 | 2021-09-16 | 2021-12-05 | 2021-11-24 | 2027-11-01 |  | 2028-01-21 |  | 2028-03-20 |  | 2028-04-29
1698 | ST-2025-036 | Australia | 81 | 20 | 24.7 | 3 | 1.8 | OFF_TRACK | Dr. Stephanie Jones | 2020-01-26 | 2020-05-02 | 2020-04-30 | 2020-08-10 | 2020-08-16 | 2021-01-24 | 2021-01-15 | 2020-10-11 | 2020-10-02 | 2021-02-27 | 2021-03-05 | 2021-09-13 | 2021-09-20 | 2021-12-13 | 2021-12-12 | 2027-11-11 |  | 2028-02-03 |  | 2028-03-23 |  | 2028-04-29
1699 | ST-2025-037 | Mexico | 1448 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Thomas Jackson | 2024-11-29 | 2025-02-28 | 2025-03-10 | 2025-05-17 | 2025-05-25 | 2025-11-19 | 2025-11-30 | 2025-07-29 | 2025-08-09 | 2025-12-22 | 2025-12-10 | 2026-05-21 |  | 2026-08-11 |  | 2027-11-24 |  | 2028-02-12 |  | 2028-05-12 |  | 2028-06-10
1700 | ST-2025-037 | United States | 1362 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Jennifer Martin | 2024-12-01 | 2025-02-26 | 2025-02-28 | 2025-05-16 | 2025-05-22 | 2025-11-16 | 2025-11-12 | 2025-07-21 | 2025-07-26 | 2025-12-15 | 2025-12-13 | 2026-05-30 |  | 2026-08-20 |  | 2027-11-25 |  | 2028-02-20 |  | 2028-05-22 |  | 2028-06-13
1701 | ST-2025-037 | Canada | 1496 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Amanda Moore | 2024-11-24 | 2025-02-12 | 2025-02-17 | 2025-05-22 | 2025-05-26 | 2025-11-16 | 2025-11-04 | 2025-07-25 | 2025-08-01 | 2025-12-28 | 2025-12-18 | 2026-06-02 |  | 2026-09-09 |  | 2027-12-09 |  | 2028-03-06 |  | 2028-05-21 |  | 2028-06-10
1702 | ST-2025-037 | Denmark | 835 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Jessica Brown | 2024-11-13 | 2025-02-18 | 2025-02-16 | 2025-05-14 | 2025-05-13 | 2025-11-10 | 2025-11-01 | 2025-07-22 | 2025-07-23 | 2025-12-13 | 2025-12-19 | 2026-06-09 |  | 2026-09-03 |  | 2027-12-06 |  | 2028-03-01 |  | 2028-05-11 |  | 2028-06-15
1703 | ST-2025-037 | Netherlands | 1461 | 0 | 0 | 2 | 0 | OFF_TRACK | Dr. Charles Taylor | 2024-11-26 | 2025-02-14 | 2025-02-01 | 2025-05-28 | 2025-06-10 | 2025-11-10 | 2025-11-07 | 2025-07-26 | 2025-07-12 | 2025-12-18 | 2025-12-19 | 2026-06-15 |  | 2026-09-11 |  | 2027-12-17 |  | 2028-03-16 |  | 2028-05-16 |  | 2028-06-15
1704 | ST-2025-037 | United Kingdom | 935 | 0 | 0 | 6 | 0 | OFF_TRACK | Dr. Jennifer Jackson | 2024-12-02 | 2025-02-21 | 2025-02-21 | 2025-05-28 | 2025-05-29 | 2025-11-21 | 2025-11-12 | 2025-07-31 | 2025-07-19 | 2025-12-24 | 2025-12-28 | 2026-06-12 |  | 2026-09-12 |  | 2027-12-12 |  | 2028-03-04 |  | 2028-05-20 |  | 2028-06-19
1705 | ST-2025-037 | Italy | 1633 | 0 | 0 | 3 | 0 | OFF_TRACK | Dr. Nicole Thomas | 2024-11-30 | 2025-02-16 | 2025-02-25 | 2025-05-20 | 2025-05-30 | 2025-11-06 | 2025-11-16 | 2025-07-19 | 2025-07-20 | 2025-12-16 | 2025-12-19 | 2026-06-14 |  | 2026-09-06 |  | 2027-12-07 |  | 2028-03-05 |  | 2028-05-16 |  | 2028-06-15
1706 | ST-2025-037 | Taiwan | 830 | 0 | 0 | 4 | 0 | OFF_TRACK | Dr. Christopher Thomas | 2024-11-24 | 2025-02-12 | 2025-02-12 | 2025-05-19 | 2025-05-22 | 2025-11-29 | 2025-11-21 | 2025-07-28 | 2025-07-27 | 2025-12-20 | 2025-12-09 | 2026-07-12 |  | 2026-10-13 |  | 2028-01-14 |  | 2028-03-31 |  | 2028-05-21 |  | 2028-06-17

## Site Breakdown
id | study_id | country | site_id | site_name | target_enrollment | actual_enrollment | enrollment_percent | enrollment_rate | site_status | principal_investigator | site_coordinator | site_selected | site_contract_signed_planned | site_contract_signed_actual | greenlight_planned | greenlight_actual | siv_planned | siv_actual | site_initiated_planned | site_initiated_actual | site_activation_planned | site_activation_actual | site_fsi_planned | site_fsi_actual | site_monitoring_visit_planned | site_monitoring_visit_actual | site_lsi_planned | site_lsi_actual | site_lsdl_planned | site_lsdl_actual | site_study_end_planned | site_study_end_actual | site_closeout_visit_planned | site_closeout_visit_actual | site_closed_planned | site_closed_actual
5855 | ST-2024-002 | United States | S0001 | UNIT-Medical Center | 5 | 4 | 80 | 0.4 | SCREENING | Dr. Sarah Taylor | Dr. Michael Thompson | 2024-03-21 | 2024-04-16 | 2024-04-27 | 2024-05-13 | 2024-05-06 | 2024-05-29 | 2024-05-21 | 2024-06-12 | 2024-06-23 | 2024-06-25 | 2024-07-04 | 2024-09-19 | 2024-09-23 | 2024-11-20 | 2024-11-28 | 2028-03-01 |  | 2028-04-22 |  | 2028-08-10 |  | 2028-09-17 |  | 2028-10-11
5856 | ST-2024-002 | United States | S0002 | UNIT-University Hospital | 4 | 3 | 75 | 0.3 | CLOSED | Dr. Nicole Miller | Dr. Michelle Jones | 2024-03-22 | 2024-04-23 | 2024-04-26 | 2024-05-26 | 2024-05-20 | 2024-06-17 | 2024-06-22 | 2024-06-29 | 2024-07-02 | 2024-07-14 | 2024-07-05 | 2024-09-20 | 2024-09-16 | 2024-11-20 | 2024-11-28 | 2028-02-24 |  | 2028-04-18 |  | 2028-08-07 |  | 2028-09-22 |  | 2028-10-12
5857 | ST-2024-002 | United States | S0003 | UNIT-General Hospital | 3 | 1 | 33.3 | 0.1 | CLOSED | Dr. Nicole Davis | Dr. Nicole White | 2024-03-20 | 2024-04-16 | 2024-04-22 | 2024-05-17 | 2024-05-07 | 2024-06-12 | 2024-06-20 | 2024-06-29 | 2024-07-12 | 2024-07-10 | 2024-06-30 | 2024-09-23 | 2024-09-16 | 2024-11-23 | 2024-11-13 | 2028-03-07 |  | 2028-05-03 |  | 2028-08-10 |  | 2028-09-20 |  | 2028-10-14
5858 | ST-2024-002 | United States | S0004 | UNIT-University Hospital | 3 | 3 | 100 | 0.4 | SCREENING | Dr. Stephanie Thomas | Dr. Stephanie White | 2024-03-24 | 2024-04-19 | 2024-04-07 | 2024-05-22 | 2024-05-28 | 2024-06-13 | 2024-06-24 | 2024-06-27 | 2024-07-11 | 2024-07-09 | 2024-07-19 | 2024-10-10 | 2024-09-28 | 2024-12-08 | 2024-12-06 | 2028-03-09 |  | 2028-05-09 |  | 2028-08-26 |  | 2028-10-08 |  | 2028-10-29
5859 | ST-2024-002 | United States | S0005 | UNIT-Clinical Center | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Emily Johnson | Dr. Charles Taylor | 2024-03-15 | 2024-04-12 | 2024-04-20 | 2024-05-12 | 2024-05-09 | 2024-06-04 | 2024-06-17 | 2024-06-17 | 2024-06-05 | 2024-07-02 | 2024-07-13 | 2024-10-03 | 2024-10-06 | 2024-12-04 | 2024-12-02 | 2028-03-19 |  | 2028-05-10 |  | 2028-08-29 |  | 2028-10-15 |  | 2028-11-07
5860 | ST-2024-002 | Mexico | S0006 | MEXI-University Hospital | 23 | 21 | 91.3 | 2.1 | SCREENING | Dr. Lisa Williams | Dr. Christopher Moore | 2024-03-18 | 2024-04-13 | 2024-04-14 | 2024-05-13 | 2024-05-24 | 2024-06-02 | 2024-05-29 | 2024-06-15 | 2024-06-29 | 2024-07-02 | 2024-07-09 | 2024-09-22 | 2024-10-02 | 2024-11-15 | 2024-11-02 | 2028-02-28 |  | 2028-04-28 |  | 2028-08-16 |  | 2028-10-01 |  | 2028-10-25
5861 | ST-2024-002 | Mexico | S0007 | MEXI-Medical Center | 10 | 6 | 60 | 1 | ON_HOLD | Dr. Michelle Smith | Dr. Michael Davis | 2024-03-22 | 2024-04-21 | 2024-04-16 | 2024-05-14 | 2024-05-05 | 2024-05-31 | 2024-06-13 | 2024-06-17 | 2024-07-01 | 2024-06-29 | 2024-06-23 | 2024-09-27 | 2024-09-15 | 2024-11-22 | 2024-11-28 | 2028-02-22 |  | 2028-04-19 |  | 2028-08-19 |  | 2028-09-27 |  | 2028-10-20
5862 | ST-2024-002 | Mexico | S0008 | MEXI-University Hospital | 11 | 14 | 127.3 | 1.2 | SCREENING | Dr. Nicole Miller | Dr. Charles Johnson | 2024-03-13 | 2024-04-10 | 2024-04-18 | 2024-05-13 | 2024-05-02 | 2024-06-08 | 2024-05-25 | 2024-06-20 | 2024-06-12 | 2024-07-01 | 2024-07-02 | 2024-10-02 | 2024-09-20 | 2024-11-30 | 2024-11-20 | 2028-03-03 |  | 2028-04-26 |  | 2028-08-28 |  | 2028-10-14 |  | 2028-11-01
5863 | ST-2024-002 | Poland | S0009 | POLA-Research Institute | 15 | 0 | 0 | 0 | CLOSED | Dr. Michelle Martin | Dr. Robert Miller | 2024-03-25 | 2024-04-27 | 2024-04-20 | 2024-05-27 | 2024-05-25 | 2024-06-12 | 2024-05-31 | 2024-06-23 | 2024-07-02 | 2024-07-09 | 2024-07-20 | 2024-10-02 | 2024-09-21 | 2024-12-03 | 2024-11-22 | 2028-02-20 |  | 2028-04-17 |  | 2028-08-08 |  | 2028-09-21 |  | 2028-10-09
5864 | ST-2024-002 | Poland | S0010 | POLA-Research Institute | 10 | 0 | 0 | 0 | SCREENING | Dr. Michelle Johnson | Dr. Thomas Johnson | 2024-03-31 | 2024-04-27 | 2024-04-29 | 2024-05-22 | 2024-05-26 | 2024-06-13 | 2024-05-30 | 2024-06-30 | 2024-07-05 | 2024-07-17 | 2024-07-23 | 2024-10-13 | 2024-10-04 | 2024-12-14 | 2024-12-14 | 2028-02-25 |  | 2028-04-26 |  | 2028-08-20 |  | 2028-09-28 |  | 2028-10-16
5865 | ST-2024-002 | Poland | S0011 | POLA-Medical Center | 18 | 0 | 0 | 0 | ON_HOLD | Dr. Daniel Thompson | Dr. Jennifer Johnson | 2024-03-20 | 2024-04-22 | 2024-04-11 | 2024-05-17 | 2024-05-21 | 2024-06-08 | 2024-06-17 | 2024-06-23 | 2024-06-21 | 2024-07-09 | 2024-07-06 | 2024-10-12 | 2024-10-11 | 2024-12-13 | 2024-12-09 | 2028-03-01 |  | 2028-04-22 |  | 2028-08-15 |  | 2028-09-23 |  | 2028-10-17
5866 | ST-2024-002 | Netherlands | S0012 | NETH-University Hospital | 23 | 0 | 0 | 0 | SCREENING | Dr. Lisa Johnson | Dr. Michael White | 2024-03-29 | 2024-04-25 | 2024-05-08 | 2024-05-28 | 2024-06-04 | 2024-06-14 | 2024-06-28 | 2024-06-26 | 2024-06-21 | 2024-07-11 | 2024-07-03 | 2024-10-15 | 2024-10-17 | 2024-12-12 | 2024-12-17 | 2028-03-08 |  | 2028-05-07 |  | 2028-08-16 |  | 2028-09-22 |  | 2028-10-16
5867 | ST-2024-002 | Netherlands | S0013 | NETH-General Hospital | 8 | 0 | 0 | 0 | CLOSED | Dr. Daniel Taylor | Dr. William Miller | 2024-04-06 | 2024-05-05 | 2024-05-06 | 2024-06-01 | 2024-06-07 | 2024-06-27 | 2024-07-02 | 2024-07-08 | 2024-06-26 | 2024-07-25 | 2024-07-27 | 2024-10-25 | 2024-11-08 | 2024-12-25 | 2024-12-11 | 2028-03-05 |  | 2028-05-02 |  | 2028-08-23 |  | 2028-09-30 |  | 2028-10-19
5868 | ST-2024-002 | Netherlands | S0014 | NETH-General Hospital | 10 | 0 | 0 | 0 | ON_HOLD | Dr. Lisa Wilson | Dr. Charles Jones | 2024-04-09 | 2024-05-07 | 2024-05-08 | 2024-06-01 | 2024-06-11 | 2024-06-23 | 2024-06-11 | 2024-07-10 | 2024-06-26 | 2024-07-27 | 2024-07-31 | 2024-10-29 | 2024-10-17 | 2024-12-23 | 2024-12-09 | 2028-03-16 |  | 2028-05-14 |  | 2028-09-05 |  | 2028-10-14 |  | 2028-11-07
5869 | ST-2024-002 | New Zealand | S0015 | NEW-University Hospital | 8 | 0 | 0 | 0 | ON_HOLD | Dr. Robert Thomas | Dr. Michael Davis | 2024-03-29 | 2024-04-21 | 2024-04-27 | 2024-05-20 | 2024-05-23 | 2024-06-13 | 2024-06-16 | 2024-06-26 | 2024-07-01 | 2024-07-12 | 2024-07-02 | 2024-10-19 | 2024-10-13 | 2024-12-15 | 2024-12-03 | 2028-03-15 |  | 2028-05-11 |  | 2028-08-22 |  | 2028-10-04 |  | 2028-10-22
5870 | ST-2024-002 | New Zealand | S0016 | NEW-Research Institute | 4 | 0 | 0 | 0 | SCREENING | Dr. Christopher Moore | Dr. Jessica Thompson | 2024-04-06 | 2024-05-02 | 2024-04-27 | 2024-05-27 | 2024-06-04 | 2024-06-20 | 2024-06-19 | 2024-07-03 | 2024-07-12 | 2024-07-17 | 2024-07-30 | 2024-10-21 | 2024-10-14 | 2024-12-19 | 2024-12-06 | 2028-03-19 |  | 2028-05-19 |  | 2028-08-30 |  | 2028-10-16 |  | 2028-11-03
5871 | ST-2024-002 | New Zealand | S0017 | NEW-Medical Center | 4 | 0 | 0 | 0 | CLOSED | Dr. Jessica Brown | Dr. Robert Wilson | 2024-04-12 | 2024-05-11 | 2024-05-19 | 2024-06-04 | 2024-05-25 | 2024-06-27 | 2024-07-05 | 2024-07-12 | 2024-06-28 | 2024-07-27 | 2024-07-18 | 2024-10-15 | 2024-10-16 | 2024-12-07 | 2024-12-04 | 2028-03-20 |  | 2028-05-20 |  | 2028-08-25 |  | 2028-10-02 |  | 2028-10-20
5872 | ST-2024-002 | New Zealand | S0018 | NEW-Medical Center | 6 | 0 | 0 | 0 | CLOSED | Dr. Michelle Jones | Dr. William Anderson | 2024-04-10 | 2024-05-07 | 2024-05-06 | 2024-06-01 | 2024-05-26 | 2024-06-22 | 2024-06-24 | 2024-07-04 | 2024-06-22 | 2024-07-20 | 2024-07-14 | 2024-11-03 | 2024-11-11 | 2025-01-04 | 2025-01-08 | 2028-03-21 |  | 2028-05-12 |  | 2028-08-30 |  | 2028-10-11 |  | 2028-11-04
5873 | ST-2024-002 | New Zealand | S0019 | NEW-Health System | 3 | 0 | 0 | 0 | CLOSED | Dr. Thomas Miller | Dr. William Thompson | 2024-04-05 | 2024-05-05 | 2024-04-24 | 2024-06-05 | 2024-06-19 | 2024-06-26 | 2024-06-30 | 2024-07-07 | 2024-07-14 | 2024-07-21 | 2024-07-30 | 2024-11-11 | 2024-10-31 | 2025-01-08 | 2025-01-01 | 2028-03-26 |  | 2028-05-21 |  | 2028-09-08 |  | 2028-10-19 |  | 2028-11-12
5874 | ST-2024-003 | Canada | S0001 | CANA-Cancer Center | 20 | 16 | 80 | 1.3 | ON_HOLD | Dr. Michelle Davis | Dr. Nicole Davis | 2023-09-20 | 2023-10-13 | 2023-10-24 | 2023-11-05 | 2023-11-13 | 2023-11-24 | 2023-12-03 | 2023-12-05 | 2023-12-11 | 2023-12-19 | 2023-12-18 | 2024-03-24 | 2024-03-17 | 2024-05-18 | 2024-05-14 | 2029-07-15 |  | 2029-09-06 |  | 2029-12-30 |  | 2030-02-05 |  | 2030-02-27
5875 | ST-2024-003 | Canada | S0002 | CANA-Research Institute | 11 | 11 | 100 | 0.9 | SCREENING | Dr. James Jackson | Dr. Thomas Jackson | 2023-10-04 | 2023-11-01 | 2023-11-03 | 2023-11-28 | 2023-11-15 | 2023-12-15 | 2023-12-13 | 2023-12-30 | 2023-12-18 | 2024-01-12 | 2024-01-26 | 2024-03-23 | 2024-03-23 | 2024-05-19 | 2024-06-01 | 2029-07-14 |  | 2029-09-03 |  | 2030-01-02 |  | 2030-02-11 |  | 2030-03-07
5876 | ST-2024-003 | Mexico | S0003 | MEXI-Clinical Center | 8 | 8 | 100 | 1 | ON_HOLD | Dr. Jennifer Johnson | Dr. William Jackson | 2023-10-07 | 2023-11-03 | 2023-11-08 | 2023-12-01 | 2023-11-24 | 2023-12-18 | 2023-12-18 | 2024-01-02 | 2023-12-30 | 2024-01-16 | 2024-01-20 | 2024-03-25 | 2024-03-26 | 2024-05-18 | 2024-05-28 | 2029-06-27 |  | 2029-08-21 |  | 2029-12-27 |  | 2030-02-06 |  | 2030-03-01
5877 | ST-2024-003 | Mexico | S0004 | MEXI-Research Institute | 6 | 5 | 83.3 | 0.6 | ON_HOLD | Dr. Thomas Taylor | Dr. Charles Wilson | 2023-10-05 | 2023-11-05 | 2023-10-22 | 2023-12-01 | 2023-12-11 | 2023-12-19 | 2023-12-26 | 2023-12-30 | 2023-12-28 | 2024-01-13 | 2024-01-26 | 2024-03-31 | 2024-04-09 | 2024-05-22 | 2024-05-31 | 2029-07-08 |  | 2029-09-02 |  | 2030-01-03 |  | 2030-02-09 |  | 2030-03-01
5878 | ST-2024-003 | Mexico | S0005 | MEXI-Cancer Center | 6 | 3 | 50 | 0.2 | ON_HOLD | Dr. Michael Martin | Dr. James Moore | 2023-09-27 | 2023-10-28 | 2023-10-30 | 2023-11-23 | 2023-11-22 | 2023-12-15 | 2023-12-23 | 2023-12-29 | 2024-01-12 | 2024-01-09 | 2024-01-06 | 2024-04-03 | 2024-04-03 | 2024-06-02 | 2024-06-11 | 2029-07-05 |  | 2029-08-26 |  | 2029-12-25 |  | 2030-02-03 |  | 2030-02-27
5879 | ST-2024-003 | Mexico | S0006 | MEXI-Medical Center | 7 | 0 | 0 | 0 | SCREENING | Dr. Michael Johnson | Dr. James Davis | 2023-09-25 | 2023-10-26 | 2023-10-19 | 2023-11-20 | 2023-11-15 | 2023-12-16 | 2023-12-10 | 2024-01-02 | 2024-01-15 | 2024-01-16 | 2024-01-12 | 2024-04-03 | 2024-04-14 | 2024-05-31 | 2024-05-29 | 2029-07-11 |  | 2029-08-31 |  | 2030-01-01 |  | 2030-02-17 |  | 2030-03-08
5880 | ST-2024-003 | Mexico | S0007 | MEXI-University Hospital | 4 | 0 | 0 | 0 | CLOSED | Dr. Robert Davis | Dr. Robert Martin | 2023-10-05 | 2023-11-02 | 2023-10-24 | 2023-11-30 | 2023-11-30 | 2023-12-23 | 2023-12-23 | 2024-01-05 | 2024-01-01 | 2024-01-17 | 2024-01-16 | 2024-04-17 | 2024-04-06 | 2024-06-08 | 2024-06-11 | 2029-07-18 |  | 2029-09-16 |  | 2030-01-10 |  | 2030-02-18 |  | 2030-03-08
5881 | ST-2024-003 | France | S0008 | FRAN-General Hospital | 10 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Brown | Dr. Jennifer Anderson | 2023-10-13 | 2023-11-08 | 2023-11-16 | 2023-12-08 | 2023-12-16 | 2023-12-28 | 2024-01-02 | 2024-01-11 | 2023-12-29 | 2024-01-24 | 2024-01-16 | 2024-04-28 | 2024-05-10 | 2024-06-17 | 2024-06-30 | 2029-07-09 |  | 2029-08-31 |  | 2029-12-27 |  | 2030-02-06 |  | 2030-03-02
5882 | ST-2024-003 | France | S0009 | FRAN-Medical Center | 8 | 0 | 0 | 0 | SCREENING | Dr. Jessica Jackson | Dr. Charles Miller | 2023-10-02 | 2023-10-28 | 2023-10-28 | 2023-11-25 | 2023-11-28 | 2023-12-17 | 2023-12-26 | 2024-01-01 | 2024-01-04 | 2024-01-12 | 2024-01-05 | 2024-04-29 | 2024-04-18 | 2024-06-21 | 2024-06-21 | 2029-07-16 |  | 2029-09-07 |  | 2029-12-21 |  | 2030-02-02 |  | 2030-02-26
5883 | ST-2024-003 | Sweden | S0010 | SWED-Clinical Center | 4 | 0 | 0 | 0 | ON_HOLD | Dr. Michael Thompson | Dr. Thomas Smith | 2023-10-21 | 2023-11-15 | 2023-11-21 | 2023-12-09 | 2023-12-15 | 2023-12-25 | 2023-12-13 | 2024-01-05 | 2024-01-09 | 2024-01-22 | 2024-01-26 | 2024-04-25 | 2024-04-19 | 2024-06-16 | 2024-06-28 | 2029-07-10 |  | 2029-09-02 |  | 2030-01-05 |  | 2030-02-16 |  | 2030-03-11
5884 | ST-2024-003 | Sweden | S0011 | SWED-Cancer Center | 5 | 0 | 0 | 0 | ON_HOLD | Dr. Emily White | Dr. Amanda Harris | 2023-10-10 | 2023-11-05 | 2023-10-23 | 2023-12-08 | 2023-11-29 | 2023-12-31 | 2024-01-04 | 2024-01-17 | 2024-01-16 | 2024-01-29 | 2024-02-10 | 2024-04-16 | 2024-04-25 | 2024-06-18 | 2024-06-16 | 2029-07-23 |  | 2029-09-17 |  | 2030-01-02 |  | 2030-02-08 |  | 2030-03-01
5885 | ST-2024-003 | Sweden | S0012 | SWED-General Hospital | 5 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Thompson | Dr. William Moore | 2023-10-15 | 2023-11-17 | 2023-11-22 | 2023-12-16 | 2023-12-21 | 2024-01-03 | 2024-01-08 | 2024-01-16 | 2024-01-09 | 2024-01-28 | 2024-02-03 | 2024-05-06 | 2024-05-01 | 2024-06-26 | 2024-06-27 | 2029-07-21 |  | 2029-09-14 |  | 2030-01-15 |  | 2030-02-23 |  | 2030-03-13
5886 | ST-2024-003 | Sweden | S0013 | SWED-Cancer Center | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Wilson | Dr. Thomas Davis | 2023-10-17 | 2023-11-16 | 2023-11-27 | 2023-12-09 | 2023-12-12 | 2023-12-26 | 2024-01-06 | 2024-01-08 | 2023-12-25 | 2024-01-22 | 2024-01-20 | 2024-04-27 | 2024-05-08 | 2024-06-21 | 2024-06-29 | 2029-07-23 |  | 2029-09-22 |  | 2030-01-19 |  | 2030-02-28 |  | 2030-03-23
5887 | ST-2024-003 | Sweden | S0014 | SWED-Cancer Center | 6 | 0 | 0 | 0 | ON_HOLD | Dr. Christopher Davis | Dr. Christopher Jackson | 2023-10-17 | 2023-11-16 | 2023-11-02 | 2023-12-14 | 2023-12-28 | 2024-01-08 | 2024-01-19 | 2024-01-23 | 2024-02-02 | 2024-02-05 | 2024-01-30 | 2024-05-04 | 2024-04-21 | 2024-06-26 | 2024-07-07 | 2029-07-25 |  | 2029-09-14 |  | 2030-01-19 |  | 2030-03-06 |  | 2030-03-25
5888 | ST-2024-003 | Sweden | S0015 | SWED-Research Institute | 6 | 0 | 0 | 0 | ON_HOLD | Dr. Thomas Garcia | Dr. Nicole Miller | 2023-10-17 | 2023-11-14 | 2023-11-07 | 2023-12-16 | 2023-12-20 | 2024-01-04 | 2024-01-17 | 2024-01-16 | 2024-01-27 | 2024-01-27 | 2024-01-25 | 2024-05-21 | 2024-05-18 | 2024-07-19 | 2024-07-31 | 2029-08-15 |  | 2029-10-09 |  | 2030-02-11 |  | 2030-03-20 |  | 2030-04-13
5889 | ST-2024-003 | New Zealand | S0016 | NEW-Health System | 9 | 0 | 0 | 0 | CLOSED | Dr. David Williams | Dr. Lisa White | 2023-10-09 | 2023-11-03 | 2023-11-07 | 2023-11-29 | 2023-11-19 | 2023-12-24 | 2023-12-28 | 2024-01-06 | 2023-12-29 | 2024-01-23 | 2024-02-04 | 2024-05-03 | 2024-05-14 | 2024-07-02 | 2024-07-16 | 2029-07-29 |  | 2029-09-27 |  | 2029-12-29 |  | 2030-02-09 |  | 2030-03-03
5890 | ST-2024-003 | New Zealand | S0017 | NEW-Clinical Center | 6 | 0 | 0 | 0 | SCREENING | Dr. Nicole Martin | Dr. Christopher Smith | 2023-10-15 | 2023-11-11 | 2023-10-28 | 2023-12-06 | 2023-12-02 | 2023-12-29 | 2024-01-03 | 2024-01-09 | 2024-01-01 | 2024-01-20 | 2024-01-31 | 2024-04-29 | 2024-04-19 | 2024-06-20 | 2024-06-16 | 2029-08-09 |  | 2029-10-02 |  | 2030-01-05 |  | 2030-02-19 |  | 2030-03-12
5891 | ST-2024-003 | New Zealand | S0018 | NEW-Medical Center | 7 | 0 | 0 | 0 | SCREENING | Dr. Charles Davis | Dr. Jessica Thomas | 2023-10-21 | 2023-11-18 | 2023-11-15 | 2023-12-11 | 2023-12-19 | 2023-12-27 | 2024-01-03 | 2024-01-08 | 2024-01-06 | 2024-01-23 | 2024-01-27 | 2024-05-14 | 2024-05-03 | 2024-07-16 | 2024-07-12 | 2029-08-06 |  | 2029-09-27 |  | 2030-01-17 |  | 2030-02-28 |  | 2030-03-18
5892 | ST-2024-003 | South Korea | S0019 | SOUT-Health System | 2 | 0 | 0 | 0 | CLOSED | Dr. Jennifer Miller | Dr. David Martin | 2023-10-18 | 2023-11-12 | 2023-11-19 | 2023-12-11 | 2023-12-15 | 2024-01-06 | 2024-01-18 | 2024-01-20 | 2024-01-11 | 2024-02-05 | 2024-02-03 | 2024-04-25 | 2024-04-20 | 2024-06-15 | 2024-06-24 | 2029-08-18 |  | 2029-10-16 |  | 2030-01-08 |  | 2030-02-19 |  | 2030-03-10
5893 | ST-2024-003 | South Korea | S0020 | SOUT-Research Institute | 3 | 0 | 0 | 0 | CLOSED | Dr. Daniel Anderson | Dr. Emily Miller | 2023-10-18 | 2023-11-12 | 2023-11-17 | 2023-12-05 | 2023-11-28 | 2023-12-30 | 2024-01-05 | 2024-01-13 | 2024-01-17 | 2024-01-30 | 2024-01-19 | 2024-05-07 | 2024-05-08 | 2024-07-04 | 2024-06-24 | 2029-08-12 |  | 2029-10-04 |  | 2030-01-13 |  | 2030-02-24 |  | 2030-03-20
5894 | ST-2024-003 | South Korea | S0021 | SOUT-Research Institute | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Anderson | Dr. James Moore | 2023-10-17 | 2023-11-12 | 2023-10-29 | 2023-12-10 | 2023-12-04 | 2023-12-31 | 2023-12-23 | 2024-01-12 | 2024-01-05 | 2024-01-28 | 2024-02-05 | 2024-05-11 | 2024-04-29 | 2024-06-30 | 2024-06-27 | 2029-08-27 |  | 2029-10-27 |  | 2030-01-16 |  | 2030-02-27 |  | 2030-03-20
5895 | ST-2024-003 | South Korea | S0022 | SOUT-University Hospital | 3 | 0 | 0 | 0 | SCREENING | Dr. Sarah Moore | Dr. Jessica Jones | 2023-10-17 | 2023-11-09 | 2023-11-12 | 2023-12-02 | 2023-11-30 | 2023-12-24 | 2023-12-13 | 2024-01-07 | 2024-01-19 | 2024-01-23 | 2024-01-24 | 2024-05-06 | 2024-05-17 | 2024-06-26 | 2024-07-09 | 2029-08-31 |  | 2029-10-27 |  | 2030-01-16 |  | 2030-02-28 |  | 2030-03-20
5896 | ST-2024-003 | South Korea | S0023 | SOUT-General Hospital | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Emily Smith | Dr. Jessica Martin | 2023-10-28 | 2023-11-30 | 2023-11-19 | 2023-12-26 | 2023-12-14 | 2024-01-13 | 2024-01-09 | 2024-01-27 | 2024-01-18 | 2024-02-07 | 2024-02-21 | 2024-05-22 | 2024-05-20 | 2024-07-23 | 2024-07-14 | 2029-08-27 |  | 2029-10-21 |  | 2030-01-19 |  | 2030-03-02 |  | 2030-03-22
5897 | ST-2024-003 | South Korea | S0024 | SOUT-Clinical Center | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Johnson | Dr. William Martin | 2023-10-24 | 2023-11-17 | 2023-11-08 | 2023-12-15 | 2023-12-02 | 2024-01-09 | 2023-12-29 | 2024-01-24 | 2024-01-20 | 2024-02-07 | 2024-01-30 | 2024-05-29 | 2024-05-21 | 2024-07-17 | 2024-07-16 | 2029-09-10 |  | 2029-11-10 |  | 2030-01-29 |  | 2030-03-16 |  | 2030-04-06
5898 | ST-2024-004 | Canada | S0001 | CANA-Cancer Center | 6 | 4 | 66.7 | 0.5 | SCREENING | Dr. Jennifer Williams | Dr. Charles Davis | 2024-07-20 | 2024-08-20 | 2024-08-21 | 2024-09-16 | 2024-09-06 | 2024-10-12 | 2024-09-29 | 2024-10-25 | 2024-10-22 | 2024-11-07 | 2024-10-24 | 2025-01-22 | 2025-01-21 | 2025-03-13 | 2025-03-01 | 2028-09-25 |  | 2028-11-21 |  | 2029-03-27 |  | 2029-05-11 |  | 2029-06-04
5899 | ST-2024-004 | Canada | S0002 | CANA-Clinical Center | 12 | 11 | 91.7 | 0.7 | SCREENING | Dr. Lisa Harris | Dr. William Harris | 2024-07-19 | 2024-08-21 | 2024-09-03 | 2024-09-22 | 2024-09-11 | 2024-10-15 | 2024-10-10 | 2024-10-27 | 2024-11-07 | 2024-11-07 | 2024-11-05 | 2025-01-23 | 2025-01-24 | 2025-03-16 | 2025-03-17 | 2028-10-01 |  | 2028-12-01 |  | 2029-03-26 |  | 2029-05-03 |  | 2029-05-24
5900 | ST-2024-004 | Canada | S0003 | CANA-Research Institute | 7 | 6 | 85.7 | 0.4 | SCREENING | Dr. Christopher Anderson | Dr. Michelle Garcia | 2024-07-13 | 2024-08-06 | 2024-07-31 | 2024-09-08 | 2024-09-08 | 2024-10-02 | 2024-10-02 | 2024-10-16 | 2024-10-10 | 2024-10-28 | 2024-10-21 | 2025-02-06 | 2025-02-18 | 2025-04-10 | 2025-04-04 | 2028-10-14 |  | 2028-12-09 |  | 2029-04-02 |  | 2029-05-16 |  | 2029-06-03
5901 | ST-2024-004 | Canada | S0004 | CANA-Medical Center | 8 | 2 | 25 | 0.2 | ON_HOLD | Dr. Jessica White | Dr. William Harris | 2024-07-11 | 2024-08-13 | 2024-08-25 | 2024-09-06 | 2024-09-04 | 2024-09-23 | 2024-10-05 | 2024-10-09 | 2024-10-11 | 2024-10-22 | 2024-10-21 | 2025-02-15 | 2025-02-18 | 2025-04-13 | 2025-04-20 | 2028-10-16 |  | 2028-12-15 |  | 2029-04-05 |  | 2029-05-20 |  | 2029-06-07
5902 | ST-2024-004 | Mexico | S0005 | MEXI-General Hospital | 4 | 0 | 0 | 0 | SCREENING | Dr. Charles Wilson | Dr. James Johnson | 2024-07-30 | 2024-08-31 | 2024-09-11 | 2024-09-26 | 2024-09-30 | 2024-10-19 | 2024-10-26 | 2024-11-01 | 2024-11-06 | 2024-11-12 | 2024-11-02 | 2025-02-07 | 2025-01-27 | 2025-04-11 | 2025-04-21 | 2028-10-18 |  | 2028-12-08 |  | 2029-03-25 |  | 2029-05-10 |  | 2029-06-01
5903 | ST-2024-004 | Mexico | S0006 | MEXI-Health System | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Jessica Davis | Dr. Amanda Davis | 2024-07-25 | 2024-08-20 | 2024-08-25 | 2024-09-15 | 2024-09-09 | 2024-10-03 | 2024-09-29 | 2024-10-14 | 2024-10-23 | 2024-10-28 | 2024-11-08 | 2025-02-06 | 2025-01-25 | 2025-04-06 | 2025-03-25 | 2028-10-15 |  | 2028-12-08 |  | 2029-03-31 |  | 2029-05-09 |  | 2029-06-02
5904 | ST-2024-004 | Mexico | S0007 | MEXI-General Hospital | 3 | 0 | 0 | 0 | CLOSED | Dr. William Jones | Dr. Emily Johnson | 2024-07-29 | 2024-08-29 | 2024-08-28 | 2024-09-26 | 2024-09-15 | 2024-10-16 | 2024-10-15 | 2024-10-31 | 2024-10-21 | 2024-11-14 | 2024-11-04 | 2025-02-23 | 2025-02-27 | 2025-04-26 | 2025-04-30 | 2028-10-13 |  | 2028-12-12 |  | 2029-04-03 |  | 2029-05-18 |  | 2029-06-11
5905 | ST-2024-004 | Mexico | S0008 | MEXI-Research Institute | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Sarah Thomas | Dr. Robert Williams | 2024-07-24 | 2024-08-17 | 2024-08-23 | 2024-09-18 | 2024-09-19 | 2024-10-05 | 2024-10-09 | 2024-10-22 | 2024-10-27 | 2024-11-04 | 2024-11-05 | 2025-03-01 | 2025-02-16 | 2025-04-27 | 2025-04-18 | 2028-11-03 |  | 2028-12-29 |  | 2029-04-07 |  | 2029-05-18 |  | 2029-06-08
5906 | ST-2024-004 | Norway | S0009 | NORW-Health System | 12 | 0 | 0 | 0 | SCREENING | Dr. William Martin | Dr. Jessica Taylor | 2024-07-24 | 2024-08-25 | 2024-08-26 | 2024-09-26 | 2024-09-20 | 2024-10-22 | 2024-11-05 | 2024-11-07 | 2024-11-04 | 2024-11-21 | 2024-11-07 | 2025-02-06 | 2025-02-02 | 2025-04-02 | 2025-04-14 | 2028-10-22 |  | 2028-12-17 |  | 2029-03-27 |  | 2029-05-03 |  | 2029-05-26
5907 | ST-2024-004 | Norway | S0010 | NORW-Cancer Center | 6 | 0 | 0 | 0 | ON_HOLD | Dr. Michael Jones | Dr. Lisa Jackson | 2024-07-26 | 2024-08-22 | 2024-08-21 | 2024-09-21 | 2024-09-26 | 2024-10-17 | 2024-10-23 | 2024-10-28 | 2024-10-16 | 2024-11-14 | 2024-11-06 | 2025-02-15 | 2025-02-15 | 2025-04-07 | 2025-03-30 | 2028-10-18 |  | 2028-12-15 |  | 2029-04-04 |  | 2029-05-15 |  | 2029-06-07
5908 | ST-2024-004 | Norway | S0011 | NORW-Cancer Center | 7 | 0 | 0 | 0 | CLOSED | Dr. Amanda Williams | Dr. Charles Smith | 2024-07-28 | 2024-08-27 | 2024-08-17 | 2024-09-27 | 2024-10-07 | 2024-10-18 | 2024-10-31 | 2024-11-04 | 2024-11-06 | 2024-11-15 | 2024-11-29 | 2025-02-27 | 2025-03-03 | 2025-04-29 | 2025-04-15 | 2028-10-23 |  | 2028-12-14 |  | 2029-04-10 |  | 2029-05-25 |  | 2029-06-15
5909 | ST-2024-004 | Norway | S0012 | NORW-Research Institute | 5 | 0 | 0 | 0 | SCREENING | Dr. Christopher Thomas | Dr. William Jackson | 2024-08-05 | 2024-08-31 | 2024-08-31 | 2024-09-23 | 2024-09-25 | 2024-10-12 | 2024-10-10 | 2024-10-23 | 2024-10-29 | 2024-11-06 | 2024-10-26 | 2025-02-15 | 2025-02-22 | 2025-04-19 | 2025-04-05 | 2028-10-22 |  | 2028-12-15 |  | 2029-04-06 |  | 2029-05-18 |  | 2029-06-11
5910 | ST-2024-004 | Belgium | S0013 | BELG-University Hospital | 9 | 0 | 0 | 0 | SCREENING | Dr. Michelle Taylor | Dr. Lisa Williams | 2024-08-16 | 2024-09-17 | 2024-09-29 | 2024-10-17 | 2024-10-25 | 2024-11-04 | 2024-10-23 | 2024-11-21 | 2024-11-16 | 2024-12-05 | 2024-11-21 | 2025-02-18 | 2025-02-16 | 2025-04-16 | 2025-04-03 | 2028-10-24 |  | 2028-12-19 |  | 2029-03-24 |  | 2029-05-04 |  | 2029-05-27
5911 | ST-2024-004 | Belgium | S0014 | BELG-General Hospital | 8 | 0 | 0 | 0 | CLOSED | Dr. Jessica White | Dr. Emily Jones | 2024-08-18 | 2024-09-13 | 2024-09-23 | 2024-10-09 | 2024-10-19 | 2024-11-04 | 2024-11-11 | 2024-11-16 | 2024-11-02 | 2024-12-02 | 2024-12-03 | 2025-02-15 | 2025-02-05 | 2025-04-09 | 2025-04-15 | 2028-11-01 |  | 2028-12-28 |  | 2029-04-02 |  | 2029-05-09 |  | 2029-06-02
5912 | ST-2024-004 | Denmark | S0015 | DENM-Research Institute | 1 | 0 | 0 | 0 | CLOSED | Dr. Michelle White | Dr. Robert White | 2024-08-23 | 2024-09-15 | 2024-09-28 | 2024-10-11 | 2024-10-08 | 2024-10-31 | 2024-10-31 | 2024-11-15 | 2024-11-09 | 2024-12-02 | 2024-11-24 | 2025-02-17 | 2025-02-17 | 2025-04-18 | 2025-04-13 | 2028-11-03 |  | 2029-01-03 |  | 2029-03-27 |  | 2029-05-09 |  | 2029-05-30
5913 | ST-2024-004 | Denmark | S0016 | DENM-General Hospital | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Wilson | Dr. Sarah Thomas | 2024-08-24 | 2024-09-25 | 2024-09-30 | 2024-10-24 | 2024-10-19 | 2024-11-18 | 2024-11-13 | 2024-11-29 | 2024-12-06 | 2024-12-10 | 2024-11-29 | 2025-02-26 | 2025-02-27 | 2025-04-26 | 2025-04-14 | 2028-11-10 |  | 2029-01-05 |  | 2029-04-05 |  | 2029-05-22 |  | 2029-06-13
5914 | ST-2024-004 | Denmark | S0017 | DENM-University Hospital | 5 | 0 | 0 | 0 | ON_HOLD | Dr. Lisa Thomas | Dr. Emily Thomas | 2024-08-15 | 2024-09-17 | 2024-09-27 | 2024-10-15 | 2024-10-08 | 2024-11-04 | 2024-11-18 | 2024-11-17 | 2024-11-04 | 2024-12-03 | 2024-12-14 | 2025-03-03 | 2025-03-16 | 2025-05-05 | 2025-05-16 | 2028-11-09 |  | 2029-01-03 |  | 2029-04-02 |  | 2029-05-11 |  | 2029-06-02
5915 | ST-2024-004 | Denmark | S0018 | DENM-Health System | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Sarah Jackson | Dr. William Miller | 2024-08-17 | 2024-09-19 | 2024-09-17 | 2024-10-17 | 2024-10-26 | 2024-11-12 | 2024-10-30 | 2024-11-24 | 2024-11-28 | 2024-12-10 | 2024-12-18 | 2025-03-03 | 2025-03-07 | 2025-05-01 | 2025-05-13 | 2028-11-17 |  | 2029-01-11 |  | 2029-04-14 |  | 2029-05-27 |  | 2029-06-17
5916 | ST-2024-004 | South Korea | S0019 | SOUT-Medical Center | 15 | 0 | 0 | 0 | SCREENING | Dr. James Johnson | Dr. Thomas Davis | 2024-08-20 | 2024-09-15 | 2024-09-06 | 2024-10-18 | 2024-10-30 | 2024-11-11 | 2024-11-18 | 2024-11-27 | 2024-12-11 | 2024-12-14 | 2024-12-17 | 2025-02-19 | 2025-02-10 | 2025-04-23 | 2025-04-18 | 2028-11-14 |  | 2029-01-09 |  | 2029-04-06 |  | 2029-05-17 |  | 2029-06-10
5917 | ST-2024-004 | South Korea | S0020 | SOUT-University Hospital | 13 | 0 | 0 | 0 | CLOSED | Dr. David Williams | Dr. Michelle Miller | 2024-08-11 | 2024-09-07 | 2024-09-18 | 2024-10-08 | 2024-10-22 | 2024-10-26 | 2024-10-22 | 2024-11-11 | 2024-11-08 | 2024-11-24 | 2024-11-18 | 2025-02-25 | 2025-03-01 | 2025-04-16 | 2025-04-11 | 2028-11-10 |  | 2029-01-05 |  | 2029-04-04 |  | 2029-05-15 |  | 2029-06-05
5918 | ST-2024-004 | China | S0021 | CHIN-Health System | 4 | 0 | 0 | 0 | ON_HOLD | Dr. Robert Jones | Dr. Michelle Wilson | 2024-09-09 | 2024-10-09 | 2024-10-16 | 2024-11-01 | 2024-10-30 | 2024-11-27 | 2024-11-29 | 2024-12-12 | 2024-12-07 | 2024-12-27 | 2024-12-26 | 2025-03-24 | 2025-03-11 | 2025-05-13 | 2025-05-26 | 2028-12-04 |  | 2029-01-27 |  | 2029-04-05 |  | 2029-05-13 |  | 2029-06-06
5919 | ST-2024-004 | China | S0022 | CHIN-Cancer Center | 5 | 0 | 0 | 0 | SCREENING | Dr. James Jones | Dr. James Thomas | 2024-09-10 | 2024-10-06 | 2024-10-12 | 2024-11-03 | 2024-10-25 | 2024-11-25 | 2024-11-21 | 2024-12-10 | 2024-12-16 | 2024-12-24 | 2024-12-11 | 2025-03-23 | 2025-03-09 | 2025-05-16 | 2025-05-16 | 2028-12-16 |  | 2029-02-07 |  | 2029-04-04 |  | 2029-05-18 |  | 2029-06-07
5920 | ST-2024-004 | China | S0023 | CHIN-Cancer Center | 3 | 0 | 0 | 0 | SCREENING | Dr. Thomas Smith | Dr. Jennifer Wilson | 2024-09-20 | 2024-10-15 | 2024-10-14 | 2024-11-16 | 2024-11-14 | 2024-12-04 | 2024-12-03 | 2024-12-18 | 2024-12-19 | 2025-01-04 | 2025-01-02 | 2025-04-03 | 2025-03-20 | 2025-06-03 | 2025-05-21 | 2028-12-05 |  | 2029-01-27 |  | 2029-04-13 |  | 2029-05-26 |  | 2029-06-18
5921 | ST-2024-005 | Mexico | S0001 | MEXI-Research Institute | 5 | 3 | 60 | 0.2 | ENROLLING | Dr. Daniel Garcia | Dr. Sarah Davis | 2022-02-04 | 2022-03-04 | 2022-02-25 | 2022-03-27 | 2022-03-20 | 2022-04-17 | 2022-04-25 | 2022-05-04 | 2022-05-18 | 2022-05-21 | 2022-05-18 | 2022-08-15 | 2022-08-10 | 2022-10-06 | 2022-09-26 | 2026-09-24 |  | 2026-11-24 |  | 2027-03-30 |  | 2027-05-16 |  | 2027-06-08
5922 | ST-2024-005 | Mexico | S0002 | MEXI-General Hospital | 4 | 2 | 50 | 0.2 | SCREENING | Dr. Daniel Thompson | Dr. Jennifer Thomas | 2022-02-01 | 2022-03-05 | 2022-03-01 | 2022-04-01 | 2022-03-31 | 2022-04-19 | 2022-05-03 | 2022-04-30 | 2022-05-07 | 2022-05-17 | 2022-05-07 | 2022-08-10 | 2022-08-06 | 2022-10-02 | 2022-10-16 | 2026-10-01 |  | 2026-11-28 |  | 2027-04-10 |  | 2027-05-26 |  | 2027-06-17
5923 | ST-2024-005 | Mexico | S0003 | MEXI-Research Institute | 4 | 2 | 50 | 0.2 | SCREENING | Dr. Stephanie Taylor | Dr. Sarah Taylor | 2022-02-05 | 2022-03-03 | 2022-02-22 | 2022-03-28 | 2022-03-17 | 2022-04-19 | 2022-04-16 | 2022-04-30 | 2022-05-08 | 2022-05-12 | 2022-05-18 | 2022-08-19 | 2022-08-30 | 2022-10-18 | 2022-10-05 | 2026-10-05 |  | 2026-11-28 |  | 2027-04-08 |  | 2027-05-24 |  | 2027-06-15
5924 | ST-2024-005 | Mexico | S0004 | MEXI-Medical Center | 3 | 3 | 100 | 0.3 | ENROLLING | Dr. Michelle Jackson | Dr. Jessica Wilson | 2022-02-03 | 2022-03-02 | 2022-02-19 | 2022-04-02 | 2022-04-01 | 2022-04-27 | 2022-04-27 | 2022-05-08 | 2022-05-06 | 2022-05-23 | 2022-05-12 | 2022-08-19 | 2022-08-22 | 2022-10-17 | 2022-10-11 | 2026-10-07 |  | 2026-12-07 |  | 2027-04-11 |  | 2027-05-18 |  | 2027-06-10
5925 | ST-2024-005 | Mexico | S0005 | MEXI-General Hospital | 3 | 8 | 266.7 | 0.5 | ON_HOLD | Dr. Robert Taylor | Dr. Michael Jones | 2022-01-26 | 2022-02-21 | 2022-02-26 | 2022-03-26 | 2022-04-03 | 2022-04-21 | 2022-04-11 | 2022-05-02 | 2022-05-01 | 2022-05-15 | 2022-05-27 | 2022-08-31 | 2022-09-14 | 2022-10-29 | 2022-10-18 | 2026-10-13 |  | 2026-12-13 |  | 2027-04-25 |  | 2027-06-05 |  | 2027-06-27
5926 | ST-2024-005 | United States | S0006 | UNIT-General Hospital | 2 | 1 | 50 | 0.1 | SCREENING | Dr. Daniel Williams | Dr. Stephanie Thompson | 2022-02-15 | 2022-03-11 | 2022-03-08 | 2022-04-07 | 2022-04-15 | 2022-04-24 | 2022-04-23 | 2022-05-11 | 2022-05-06 | 2022-05-22 | 2022-05-13 | 2022-08-18 | 2022-08-05 | 2022-10-09 | 2022-10-12 | 2026-09-30 |  | 2026-11-23 |  | 2027-03-21 |  | 2027-05-05 |  | 2027-05-24
5927 | ST-2024-005 | United States | S0007 | UNIT-Research Institute | 3 | 2 | 66.7 | 0.3 | ENROLLING | Dr. Jessica Garcia | Dr. David Taylor | 2022-02-09 | 2022-03-11 | 2022-03-01 | 2022-04-08 | 2022-03-27 | 2022-04-27 | 2022-05-07 | 2022-05-08 | 2022-05-10 | 2022-05-19 | 2022-05-07 | 2022-08-26 | 2022-09-04 | 2022-10-15 | 2022-10-24 | 2026-10-10 |  | 2026-12-01 |  | 2027-03-31 |  | 2027-05-17 |  | 2027-06-07
5928 | ST-2024-005 | United States | S0008 | UNIT-Cancer Center | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Lisa Jones | Dr. Robert Williams | 2022-02-10 | 2022-03-15 | 2022-03-26 | 2022-04-10 | 2022-04-17 | 2022-05-03 | 2022-04-29 | 2022-05-16 | 2022-05-15 | 2022-05-29 | 2022-06-07 | 2022-08-23 | 2022-08-12 | 2022-10-11 | 2022-09-30 | 2026-09-27 |  | 2026-11-19 |  | 2027-03-22 |  | 2027-05-02 |  | 2027-05-22
5929 | ST-2024-005 | United States | S0009 | UNIT-Research Institute | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Daniel Moore | Dr. Daniel Johnson | 2022-02-20 | 2022-03-15 | 2022-03-03 | 2022-04-07 | 2022-04-04 | 2022-04-25 | 2022-05-07 | 2022-05-11 | 2022-05-07 | 2022-05-27 | 2022-05-18 | 2022-09-01 | 2022-08-21 | 2022-10-25 | 2022-10-23 | 2026-10-15 |  | 2026-12-12 |  | 2027-04-14 |  | 2027-05-25 |  | 2027-06-17
5930 | ST-2024-005 | United States | S0010 | UNIT-General Hospital | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Robert Jackson | Dr. Robert Garcia | 2022-02-13 | 2022-03-12 | 2022-03-21 | 2022-04-10 | 2022-03-28 | 2022-05-03 | 2022-05-16 | 2022-05-20 | 2022-05-11 | 2022-06-03 | 2022-05-23 | 2022-09-06 | 2022-09-05 | 2022-11-08 | 2022-11-12 | 2026-10-19 |  | 2026-12-11 |  | 2027-04-03 |  | 2027-05-12 |  | 2027-06-04
5931 | ST-2024-005 | United States | S0011 | UNIT-University Hospital | 3 | 8 | 266.7 | 0.5 | SCREENING | Dr. Jennifer Harris | Dr. Sarah White | 2022-02-15 | 2022-03-20 | 2022-03-21 | 2022-04-19 | 2022-04-08 | 2022-05-07 | 2022-05-21 | 2022-05-22 | 2022-05-21 | 2022-06-05 | 2022-06-05 | 2022-09-14 | 2022-09-01 | 2022-11-07 | 2022-10-26 | 2026-10-22 |  | 2026-12-12 |  | 2027-04-18 |  | 2027-05-27 |  | 2027-06-17
5932 | ST-2024-005 | France | S0012 | FRAN-Health System | 6 | 6 | 100 | 0.6 | ON_HOLD | Dr. Christopher Davis | Dr. Michelle Davis | 2022-02-18 | 2022-03-13 | 2022-03-15 | 2022-04-15 | 2022-04-23 | 2022-05-09 | 2022-05-17 | 2022-05-26 | 2022-05-31 | 2022-06-11 | 2022-05-31 | 2022-08-30 | 2022-08-29 | 2022-10-29 | 2022-11-05 | 2026-10-17 |  | 2026-12-10 |  | 2027-04-07 |  | 2027-05-19 |  | 2027-06-10
5933 | ST-2024-005 | France | S0013 | FRAN-Research Institute | 7 | 6 | 85.7 | 0.3 | SCREENING | Dr. David Thomas | Dr. Christopher Harris | 2022-02-20 | 2022-03-20 | 2022-03-26 | 2022-04-22 | 2022-04-13 | 2022-05-18 | 2022-05-20 | 2022-06-03 | 2022-06-16 | 2022-06-17 | 2022-06-18 | 2022-08-29 | 2022-09-11 | 2022-10-30 | 2022-10-31 | 2026-10-27 |  | 2026-12-25 |  | 2027-04-12 |  | 2027-05-19 |  | 2027-06-06
5934 | ST-2024-005 | Denmark | S0014 | DENM-Clinical Center | 10 | 9 | 90 | 1.1 | SCREENING | Dr. Robert Wilson | Dr. Sarah Martin | 2022-02-21 | 2022-03-23 | 2022-04-04 | 2022-04-20 | 2022-04-13 | 2022-05-09 | 2022-04-27 | 2022-05-22 | 2022-05-22 | 2022-06-04 | 2022-06-04 | 2022-08-24 | 2022-09-04 | 2022-10-20 | 2022-10-24 | 2026-10-14 |  | 2026-12-12 |  | 2027-04-08 |  | 2027-05-21 |  | 2027-06-11
5935 | ST-2024-005 | Denmark | S0015 | DENM-Cancer Center | 10 | 6 | 60 | 0.5 | CLOSED | Dr. Emily Thompson | Dr. Emily Anderson | 2022-03-05 | 2022-04-04 | 2022-04-07 | 2022-05-04 | 2022-05-07 | 2022-05-25 | 2022-05-11 | 2022-06-05 | 2022-06-17 | 2022-06-19 | 2022-06-07 | 2022-09-08 | 2022-09-19 | 2022-11-06 | 2022-11-11 | 2026-10-15 |  | 2026-12-06 |  | 2027-04-08 |  | 2027-05-21 |  | 2027-06-08
5936 | ST-2024-005 | New Zealand | S0016 | NEW-Health System | 8 | 6 | 75 | 0.8 | ON_HOLD | Dr. Michael Davis | Dr. Christopher Thomas | 2022-03-09 | 2022-04-05 | 2022-04-05 | 2022-05-06 | 2022-05-02 | 2022-05-30 | 2022-06-02 | 2022-06-11 | 2022-06-21 | 2022-06-27 | 2022-07-02 | 2022-09-24 | 2022-09-29 | 2022-11-19 | 2022-11-20 | 2026-10-26 |  | 2026-12-21 |  | 2027-03-24 |  | 2027-05-03 |  | 2027-05-27
5937 | ST-2024-005 | New Zealand | S0017 | NEW-Medical Center | 7 | 2 | 28.6 | 0.2 | SCREENING | Dr. Charles Thompson | Dr. Amanda Davis | 2022-03-04 | 2022-04-03 | 2022-04-05 | 2022-04-27 | 2022-04-24 | 2022-05-14 | 2022-05-22 | 2022-05-31 | 2022-05-20 | 2022-06-16 | 2022-06-03 | 2022-09-23 | 2022-10-07 | 2022-11-11 | 2022-11-02 | 2026-11-01 |  | 2026-12-27 |  | 2027-04-09 |  | 2027-05-20 |  | 2027-06-11
5938 | ST-2024-005 | China | S0018 | CHIN-Cancer Center | 4 | 0 | 0 | 0 | CLOSED | Dr. Robert Martin | Dr. Christopher Smith | 2022-03-21 | 2022-04-19 | 2022-04-30 | 2022-05-13 | 2022-05-05 | 2022-06-02 | 2022-06-10 | 2022-06-17 | 2022-06-13 | 2022-06-29 | 2022-06-18 | 2022-09-22 | 2022-10-02 | 2022-11-11 | 2022-11-10 | 2026-11-18 |  | 2027-01-14 |  | 2027-03-23 |  | 2027-05-06 |  | 2027-05-30
5939 | ST-2024-005 | China | S0019 | CHIN-Medical Center | 3 | 0 | 0 | 0 | ON_HOLD | Dr. David Jones | Dr. Michelle Thompson | 2022-03-18 | 2022-04-20 | 2022-04-22 | 2022-05-22 | 2022-05-31 | 2022-06-08 | 2022-05-26 | 2022-06-25 | 2022-06-28 | 2022-07-09 | 2022-07-08 | 2022-09-28 | 2022-10-10 | 2022-11-26 | 2022-11-30 | 2026-11-15 |  | 2027-01-13 |  | 2027-03-24 |  | 2027-05-07 |  | 2027-05-25
5940 | ST-2024-005 | China | S0020 | CHIN-Clinical Center | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Lisa Anderson | Dr. Emily Johnson | 2022-03-16 | 2022-04-10 | 2022-04-12 | 2022-05-12 | 2022-05-26 | 2022-05-30 | 2022-05-28 | 2022-06-15 | 2022-06-14 | 2022-07-02 | 2022-07-07 | 2022-09-30 | 2022-10-08 | 2022-11-19 | 2022-11-29 | 2026-11-19 |  | 2027-01-19 |  | 2027-04-07 |  | 2027-05-23 |  | 2027-06-12
5941 | ST-2024-005 | China | S0021 | CHIN-University Hospital | 3 | 0 | 0 | 0 | CLOSED | Dr. Christopher Williams | Dr. Emily Martin | 2022-03-14 | 2022-04-11 | 2022-04-07 | 2022-05-08 | 2022-05-16 | 2022-05-31 | 2022-06-09 | 2022-06-17 | 2022-06-20 | 2022-06-29 | 2022-07-05 | 2022-10-01 | 2022-09-23 | 2022-11-25 | 2022-11-17 | 2026-11-23 |  | 2027-01-21 |  | 2027-04-03 |  | 2027-05-18 |  | 2027-06-11
5942 | ST-2024-005 | China | S0022 | CHIN-Health System | 3 | 0 | 0 | 0 | SCREENING | Dr. Daniel Davis | Dr. Robert Anderson | 2022-03-19 | 2022-04-15 | 2022-04-23 | 2022-05-18 | 2022-05-07 | 2022-06-08 | 2022-06-18 | 2022-06-24 | 2022-06-21 | 2022-07-06 | 2022-07-09 | 2022-10-13 | 2022-10-14 | 2022-12-11 | 2022-12-15 | 2026-11-19 |  | 2027-01-17 |  | 2027-04-10 |  | 2027-05-27 |  | 2027-06-16
5943 | ST-2024-006 | United States | S0001 | UNIT-General Hospital | 13 | 8 | 61.5 | 0.4 | SCREENING | Dr. William Miller | Dr. Stephanie Smith | 2023-08-02 | 2023-08-31 | 2023-08-21 | 2023-10-03 | 2023-09-20 | 2023-10-27 | 2023-11-03 | 2023-11-09 | 2023-10-27 | 2023-11-26 | 2023-11-18 | 2024-02-06 | 2024-01-31 | 2024-04-07 | 2024-04-17 | 2025-07-25 | 2025-08-05 | 2025-09-22 | 2025-09-13 | 2026-01-28 | 2026-01-23 | 2026-03-06 | 2026-03-13 | 2026-03-27 | 2026-03-21
5944 | ST-2024-006 | United States | S0002 | UNIT-Clinical Center | 4 | 9 | 225 | 0.6 | SCREENING | Dr. Jessica Anderson | Dr. Nicole Davis | 2023-07-23 | 2023-08-19 | 2023-08-12 | 2023-09-14 | 2023-09-23 | 2023-10-08 | 2023-10-14 | 2023-10-19 | 2023-10-22 | 2023-11-01 | 2023-10-30 | 2024-02-16 | 2024-02-09 | 2024-04-12 | 2024-04-14 | 2025-07-29 | 2025-08-09 | 2025-09-27 | 2025-10-08 | 2026-02-09 | 2026-02-20 | 2026-03-26 | 2026-04-03 | 2026-04-19 | 2026-04-14
5945 | ST-2024-006 | United Kingdom | S0003 | UNIT-University Hospital | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. Robert Taylor | Dr. Thomas Thomas | 2023-08-09 | 2023-09-07 | 2023-09-20 | 2023-10-06 | 2023-10-16 | 2023-10-28 | 2023-11-10 | 2023-11-14 | 2023-11-27 | 2023-11-30 | 2023-11-30 | 2024-02-18 | 2024-03-01 | 2024-04-15 | 2024-04-08 | 2025-08-06 | 2025-08-12 | 2025-09-26 | 2025-10-04 | 2026-02-09 | 2026-02-17 | 2026-03-21 | 2026-03-27 | 2026-04-12 | 2026-04-09
5946 | ST-2024-006 | United Kingdom | S0004 | UNIT-Clinical Center | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Daniel Moore | Dr. Emily Taylor | 2023-08-17 | 2023-09-18 | 2023-09-16 | 2023-10-14 | 2023-10-01 | 2023-11-02 | 2023-11-01 | 2023-11-15 | 2023-11-09 | 2023-11-29 | 2023-12-02 | 2024-02-21 | 2024-02-15 | 2024-04-20 | 2024-04-10 | 2025-08-13 | 2025-08-04 | 2025-10-05 | 2025-10-09 | 2026-02-13 | 2026-02-26 | 2026-03-30 | 2026-03-24 | 2026-04-17 | 2026-04-03
5947 | ST-2024-006 | United Kingdom | S0005 | UNIT-University Hospital | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. William Harris | Dr. Lisa Jones | 2023-08-20 | 2023-09-14 | 2023-09-15 | 2023-10-07 | 2023-10-18 | 2023-10-25 | 2023-10-29 | 2023-11-07 | 2023-11-10 | 2023-11-22 | 2023-11-19 | 2024-02-20 | 2024-02-08 | 2024-04-21 | 2024-05-02 | 2025-08-27 | 2025-09-04 | 2025-10-27 | 2025-10-23 | 2026-02-21 | 2026-02-23 | 2026-04-09 | 2026-04-02 | 2026-04-29 | 2026-04-20
5948 | ST-2024-006 | United Kingdom | S0006 | UNIT-Medical Center | 3 | 5 | 166.7 | 0.8 | SCREENING | Dr. Charles White | Dr. Lisa Garcia | 2023-08-21 | 2023-09-21 | 2023-09-17 | 2023-10-16 | 2023-10-13 | 2023-11-07 | 2023-11-02 | 2023-11-22 | 2023-11-14 | 2023-12-07 | 2023-12-17 | 2024-03-04 | 2024-03-09 | 2024-04-23 | 2024-04-25 | 2025-08-25 | 2025-08-26 | 2025-10-18 | 2025-10-21 | 2026-02-22 | 2026-03-06 | 2026-04-10 | 2026-04-20 | 2026-04-30 | 2026-05-06
5949 | ST-2024-006 | Switzerland | S0007 | SWIT-University Hospital | 13 | 13 | 100 | 0.7 | SCREENING | Dr. Nicole Thompson | Dr. Christopher Martin | 2023-08-18 | 2023-09-15 | 2023-09-26 | 2023-10-15 | 2023-10-04 | 2023-11-03 | 2023-11-01 | 2023-11-19 | 2023-11-13 | 2023-12-04 | 2023-12-07 | 2024-03-08 | 2024-03-17 | 2024-05-05 | 2024-04-30 | 2025-08-22 | 2025-08-08 | 2025-10-12 | 2025-10-14 | 2026-02-04 | 2026-02-16 | 2026-03-18 | 2026-03-28 | 2026-04-08 | 2026-04-05
5950 | ST-2024-006 | Switzerland | S0008 | SWIT-Research Institute | 14 | 8 | 57.1 | 0.6 | SCREENING | Dr. Michael Jackson | Dr. Daniel Harris | 2023-08-16 | 2023-09-15 | 2023-09-18 | 2023-10-15 | 2023-10-18 | 2023-10-31 | 2023-10-17 | 2023-11-13 | 2023-11-19 | 2023-11-29 | 2023-11-17 | 2024-03-02 | 2024-02-23 | 2024-04-25 | 2024-05-02 | 2025-09-01 | 2025-09-07 | 2025-10-23 | 2025-11-02 | 2026-01-31 | 2026-01-23 | 2026-03-11 | 2026-03-24 | 2026-04-04 | 2026-04-11
5951 | ST-2024-006 | South Korea | S0009 | SOUT-Cancer Center | 8 | 5 | 62.5 | 0.3 | CLOSED | Dr. Nicole Anderson | Dr. Michelle Smith | 2023-08-16 | 2023-09-11 | 2023-09-07 | 2023-10-12 | 2023-09-29 | 2023-11-03 | 2023-10-22 | 2023-11-19 | 2023-11-07 | 2023-12-06 | 2023-11-23 | 2024-02-22 | 2024-02-13 | 2024-04-22 | 2024-05-03 | 2025-09-05 | 2025-08-30 | 2025-10-28 | 2025-10-31 | 2026-01-27 | 2026-01-15 | 2026-03-12 | 2026-03-16 | 2026-04-04 | 2026-04-16
5952 | ST-2024-006 | South Korea | S0010 | SOUT-Cancer Center | 3 | 2 | 66.7 | 0.3 | ON_HOLD | Dr. Robert Wilson | Dr. Amanda Jackson | 2023-08-19 | 2023-09-17 | 2023-09-03 | 2023-10-16 | 2023-10-22 | 2023-11-08 | 2023-11-17 | 2023-11-24 | 2023-11-29 | 2023-12-08 | 2023-11-26 | 2024-03-01 | 2024-03-11 | 2024-04-24 | 2024-05-03 | 2025-08-29 | 2025-09-02 | 2025-10-25 | 2025-10-12 | 2026-02-09 | 2026-02-17 | 2026-03-19 | 2026-04-01 | 2026-04-10 | 2026-03-29
5953 | ST-2024-006 | South Korea | S0011 | SOUT-Research Institute | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Sarah Moore | Dr. David Thomas | 2023-08-23 | 2023-09-16 | 2023-09-23 | 2023-10-13 | 2023-09-29 | 2023-11-08 | 2023-11-09 | 2023-11-21 | 2023-11-12 | 2023-12-06 | 2023-12-09 | 2024-03-01 | 2024-02-23 | 2024-04-23 | 2024-04-13 | 2025-09-15 | 2025-09-24 | 2025-11-12 | 2025-11-10 | 2026-02-10 | 2026-02-21 | 2026-03-25 | 2026-04-05 | 2026-04-18 | 2026-05-01
5954 | ST-2024-007 | Canada | S0001 | CANA-General Hospital | -1 | -1 | 100 | -0.1 | SCREENING | Dr. James Moore | Dr. Jennifer White | 2026-07-21 | 2026-08-15 |  | 2026-09-11 |  | 2026-10-07 |  | 2026-10-24 |  | 2026-11-10 |  | 2027-01-18 |  | 2027-03-18 |  | 2029-04-14 |  | 2029-06-04 |  | 2029-10-23 |  | 2029-12-07 |  | 2029-12-26
5955 | ST-2024-007 | Canada | S0002 | CANA-General Hospital | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. David Anderson | Dr. Thomas Anderson | 2026-07-11 | 2026-08-12 |  | 2026-09-13 |  | 2026-10-05 |  | 2026-10-20 |  | 2026-11-04 |  | 2027-01-11 |  | 2027-03-05 |  | 2029-04-15 |  | 2029-06-10 |  | 2029-10-21 |  | 2029-12-03 |  | 2029-12-26
5956 | ST-2024-007 | Canada | S0003 | CANA-General Hospital | 3 | 0 | 0 | 0 | SCREENING | Dr. Lisa Moore | Dr. Sarah Garcia | 2026-07-13 | 2026-08-07 |  | 2026-09-01 |  | 2026-09-20 |  | 2026-10-05 |  | 2026-10-22 |  | 2027-01-24 |  | 2027-03-17 |  | 2029-04-23 |  | 2029-06-15 |  | 2029-11-07 |  | 2029-12-23 |  | 2030-01-16
5957 | ST-2024-007 | Canada | S0004 | CANA-Clinical Center | 3 | 0 | 0 | 0 | SCREENING | Dr. Charles Martin | Dr. Jennifer Anderson | 2026-07-23 | 2026-08-23 |  | 2026-09-22 |  | 2026-10-18 |  | 2026-11-02 |  | 2026-11-13 |  | 2027-01-18 |  | 2027-03-18 |  | 2029-04-17 |  | 2029-06-11 |  | 2029-10-23 |  | 2029-12-02 |  | 2029-12-25
5958 | ST-2024-007 | Mexico | S0005 | MEXI-Medical Center | 6 | 0 | 0 | 0 | ON_HOLD | Dr. Christopher Moore | Dr. Daniel Martin | 2026-07-24 | 2026-08-21 |  | 2026-09-15 |  | 2026-10-11 |  | 2026-10-27 |  | 2026-11-08 |  | 2027-01-18 |  | 2027-03-12 |  | 2029-05-02 |  | 2029-06-23 |  | 2029-10-08 |  | 2029-11-19 |  | 2029-12-10
5959 | ST-2024-007 | Mexico | S0006 | MEXI-University Hospital | 3 | 0 | 0 | 0 | ON_HOLD | Dr. William Miller | Dr. Emily Taylor | 2026-07-28 | 2026-08-30 |  | 2026-09-26 |  | 2026-10-21 |  | 2026-11-02 |  | 2026-11-17 |  | 2027-01-30 |  | 2027-03-25 |  | 2029-05-09 |  | 2029-07-04 |  | 2029-10-15 |  | 2029-11-23 |  | 2029-12-11
5960 | ST-2024-007 | Spain | S0007 | SPAI-Cancer Center | -6 | -6 | 100 | -0.4 | ON_HOLD | Dr. Stephanie Thompson | Dr. Thomas Williams | 2026-08-05 | 2026-08-31 |  | 2026-10-03 |  | 2026-10-25 |  | 2026-11-07 |  | 2026-11-24 |  | 2027-02-04 |  | 2027-03-27 |  | 2029-05-07 |  | 2029-07-02 |  | 2029-10-22 |  | 2029-12-05 |  | 2029-12-26
5961 | ST-2024-007 | Spain | S0008 | SPAI-Clinical Center | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Jennifer Jones | Dr. Nicole Taylor | 2026-07-28 | 2026-08-27 |  | 2026-09-27 |  | 2026-10-14 |  | 2026-10-26 |  | 2026-11-11 |  | 2027-02-12 |  | 2027-04-03 |  | 2029-05-14 |  | 2029-07-08 |  | 2029-10-21 |  | 2029-12-05 |  | 2029-12-24
5962 | ST-2024-007 | Spain | S0009 | SPAI-University Hospital | 3 | 3 | 100 | 0.5 | ON_HOLD | Dr. Charles Davis | Dr. Christopher Wilson | 2026-08-07 | 2026-09-09 |  | 2026-10-03 |  | 2026-10-20 |  | 2026-10-31 |  | 2026-11-17 |  | 2027-02-14 |  | 2027-04-14 |  | 2029-05-04 |  | 2029-07-03 |  | 2029-10-31 |  | 2029-12-13 |  | 2030-01-06
5963 | ST-2024-007 | Spain | S0010 | SPAI-Research Institute | 3 | 1 | 33.3 | 0.1 | CLOSED | Dr. James Wilson | Dr. Amanda Davis | 2026-08-07 | 2026-08-30 |  | 2026-09-30 |  | 2026-10-20 |  | 2026-11-04 |  | 2026-11-19 |  | 2027-02-21 |  | 2027-04-21 |  | 2029-05-24 |  | 2029-07-16 |  | 2029-11-04 |  | 2029-12-17 |  | 2030-01-05
5964 | ST-2024-007 | Spain | S0011 | SPAI-Medical Center | 3 | 0 | 0 | 0 | SCREENING | Dr. Christopher Anderson | Dr. Jennifer Jackson | 2026-08-02 | 2026-08-29 |  | 2026-09-23 |  | 2026-10-16 |  | 2026-10-31 |  | 2026-11-15 |  | 2027-02-26 |  | 2027-04-22 |  | 2029-05-28 |  | 2029-07-26 |  | 2029-11-10 |  | 2029-12-27 |  | 2030-01-15
5965 | ST-2024-007 | Italy | S0012 | ITAL-General Hospital | 0 | 0 | 0 | 0 | ON_HOLD | Dr. Lisa Davis | Dr. Robert Martin | 2026-08-14 | 2026-09-15 |  | 2026-10-18 |  | 2026-11-05 |  | 2026-11-22 |  | 2026-12-07 |  | 2027-02-07 |  | 2027-04-04 |  | 2029-05-04 |  | 2029-06-26 |  | 2029-10-20 |  | 2029-12-05 |  | 2029-12-28
5966 | ST-2024-007 | Italy | S0013 | ITAL-University Hospital | 3 | 0 | 0 | 0 | CLOSED | Dr. Amanda White | Dr. Michelle Martin | 2026-08-04 | 2026-09-03 |  | 2026-10-01 |  | 2026-10-17 |  | 2026-10-29 |  | 2026-11-15 |  | 2027-02-18 |  | 2027-04-11 |  | 2029-05-09 |  | 2029-07-03 |  | 2029-10-22 |  | 2029-12-01 |  | 2029-12-19
5967 | ST-2024-007 | Italy | S0014 | ITAL-Cancer Center | 3 | 0 | 0 | 0 | CLOSED | Dr. David Davis | Dr. Michael Thompson | 2026-08-10 | 2026-09-07 |  | 2026-10-06 |  | 2026-10-29 |  | 2026-11-12 |  | 2026-11-23 |  | 2027-02-16 |  | 2027-04-16 |  | 2029-05-18 |  | 2029-07-09 |  | 2029-10-30 |  | 2029-12-16 |  | 2030-01-09
5968 | ST-2024-007 | India | S0015 | INDI-Medical Center | -4 | -4 | 100 | -0.2 | SCREENING | Dr. Nicole Williams | Dr. Daniel Harris | 2026-08-27 | 2026-09-23 |  | 2026-10-25 |  | 2026-11-18 |  | 2026-12-03 |  | 2026-12-15 |  | 2027-02-20 |  | 2027-04-20 |  | 2029-05-18 |  | 2029-07-13 |  | 2029-10-25 |  | 2029-12-11 |  | 2030-01-04
5969 | ST-2024-007 | India | S0016 | INDI-Cancer Center | 3 | 2 | 66.7 | 0.3 | ON_HOLD | Dr. Robert Thompson | Dr. Stephanie Harris | 2026-08-20 | 2026-09-18 |  | 2026-10-14 |  | 2026-11-07 |  | 2026-11-21 |  | 2026-12-04 |  | 2027-03-01 |  | 2027-05-02 |  | 2029-05-19 |  | 2029-07-16 |  | 2029-10-25 |  | 2029-12-10 |  | 2029-12-28
5970 | ST-2024-007 | India | S0017 | INDI-Health System | 3 | 2 | 66.7 | 0.3 | CLOSED | Dr. Christopher Anderson | Dr. James Jackson | 2026-08-18 | 2026-09-17 |  | 2026-10-12 |  | 2026-10-31 |  | 2026-11-11 |  | 2026-11-26 |  | 2027-03-05 |  | 2027-04-27 |  | 2029-05-24 |  | 2029-07-16 |  | 2029-10-27 |  | 2029-12-05 |  | 2029-12-25
5971 | ST-2024-007 | India | S0018 | INDI-Research Institute | 3 | 0 | 0 | 0 | CLOSED | Dr. David Williams | Dr. Sarah White | 2026-08-29 | 2026-09-22 |  | 2026-10-25 |  | 2026-11-13 |  | 2026-11-27 |  | 2026-12-14 |  | 2027-03-06 |  | 2027-05-05 |  | 2029-05-28 |  | 2029-07-25 |  | 2029-11-10 |  | 2029-12-24 |  | 2030-01-14
5972 | ST-2024-007 | India | S0019 | INDI-Research Institute | 3 | 0 | 0 | 0 | SCREENING | Dr. Michelle Johnson | Dr. Michael Martin | 2026-08-18 | 2026-09-20 |  | 2026-10-19 |  | 2026-11-04 |  | 2026-11-16 |  | 2026-11-27 |  | 2027-03-01 |  | 2027-04-28 |  | 2029-06-03 |  | 2029-07-26 |  | 2029-10-31 |  | 2029-12-17 |  | 2030-01-08
5973 | ST-2024-007 | India | S0020 | INDI-Medical Center | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Jones | Dr. Stephanie Thomas | 2026-08-25 | 2026-09-19 |  | 2026-10-12 |  | 2026-10-30 |  | 2026-11-12 |  | 2026-11-24 |  | 2027-03-05 |  | 2027-04-29 |  | 2029-06-01 |  | 2029-07-31 |  | 2029-11-06 |  | 2029-12-13 |  | 2030-01-05
5974 | ST-2024-007 | Singapore | S0021 | SING-Clinical Center | 7 | 0 | 0 | 0 | SCREENING | Dr. Michelle Jones | Dr. Amanda Brown | 2026-08-15 | 2026-09-11 |  | 2026-10-05 |  | 2026-10-24 |  | 2026-11-07 |  | 2026-11-22 |  | 2027-02-10 |  | 2027-04-13 |  | 2029-05-20 |  | 2029-07-12 |  | 2029-10-16 |  | 2029-11-28 |  | 2029-12-20
5975 | ST-2024-007 | Singapore | S0022 | SING-University Hospital | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Daniel Jones | Dr. Lisa Smith | 2026-08-11 | 2026-09-05 |  | 2026-10-07 |  | 2026-11-02 |  | 2026-11-17 |  | 2026-11-30 |  | 2027-02-08 |  | 2027-04-09 |  | 2029-05-26 |  | 2029-07-21 |  | 2029-10-23 |  | 2029-12-08 |  | 2029-12-30
5976 | ST-2024-008 | United States | S0001 | UNIT-General Hospital | 8 | 7 | 87.5 | 0.6 | ENROLLING | Dr. Jessica Garcia | Dr. Lisa Jackson | 2021-03-21 | 2021-04-19 | 2021-04-09 | 2021-05-14 | 2021-05-19 | 2021-05-31 | 2021-05-20 | 2021-06-11 | 2021-06-02 | 2021-06-23 | 2021-06-24 | 2021-10-05 | 2021-10-19 | 2021-12-06 | 2021-12-11 | 2025-07-13 | 2025-07-18 | 2025-09-10 | 2025-08-28 | 2026-01-02 | 2026-01-16 | 2026-02-14 | 2026-02-25 | 2026-03-10 | 2026-03-13
5977 | ST-2024-008 | United States | S0002 | UNIT-General Hospital | 4 | 4 | 100 | 0.3 | SCREENING | Dr. Charles Jones | Dr. Michael Thompson | 2021-03-16 | 2021-04-09 | 2021-04-08 | 2021-05-09 | 2021-05-06 | 2021-06-04 | 2021-06-17 | 2021-06-16 | 2021-06-03 | 2021-07-01 | 2021-07-09 | 2021-10-10 | 2021-10-12 | 2021-12-11 | 2021-12-10 | 2025-07-04 | 2025-06-27 | 2025-09-03 | 2025-09-14 | 2026-01-07 | 2026-01-08 | 2026-02-19 | 2026-03-02 | 2026-03-13 | 2026-03-23
5978 | ST-2024-008 | United States | S0003 | UNIT-General Hospital | 7 | 6 | 85.7 | 0.5 | ENROLLING | Dr. Emily White | Dr. Lisa Williams | 2021-03-24 | 2021-04-25 | 2021-04-24 | 2021-05-19 | 2021-05-13 | 2021-06-10 | 2021-06-02 | 2021-06-22 | 2021-06-08 | 2021-07-05 | 2021-07-13 | 2021-10-12 | 2021-10-21 | 2021-12-12 | 2021-12-23 | 2025-07-10 | 2025-06-26 | 2025-08-31 | 2025-09-04 | 2026-01-04 | 2026-01-06 | 2026-02-19 | 2026-02-08 | 2026-03-13 | 2026-03-15
5979 | ST-2024-008 | Sweden | S0004 | SWED-Clinical Center | 9 | 9 | 100 | 0.5 | ON_HOLD | Dr. James Wilson | Dr. Christopher Martin | 2021-04-08 | 2021-05-04 | 2021-05-07 | 2021-06-01 | 2021-05-31 | 2021-06-23 | 2021-06-27 | 2021-07-06 | 2021-07-03 | 2021-07-17 | 2021-07-22 | 2021-10-02 | 2021-09-26 | 2021-11-26 | 2021-12-03 | 2025-07-20 | 2025-07-18 | 2025-09-18 | 2025-09-28 | 2025-12-31 | 2025-12-23 | 2026-02-10 | 2026-02-09 | 2026-03-06 | 2026-03-09
5980 | ST-2024-008 | Sweden | S0005 | SWED-University Hospital | 13 | 6 | 46.2 | 0.5 | CLOSED | Dr. Charles White | Dr. Jennifer Jackson | 2021-04-05 | 2021-04-30 | 2021-05-13 | 2021-05-28 | 2021-06-04 | 2021-06-21 | 2021-06-10 | 2021-07-06 | 2021-07-15 | 2021-07-20 | 2021-07-13 | 2021-10-10 | 2021-10-10 | 2021-12-02 | 2021-12-13 | 2025-07-25 | 2025-08-02 | 2025-09-19 | 2025-09-10 | 2026-01-08 | 2025-12-28 | 2026-02-16 | 2026-02-08 | 2026-03-12 | 2026-03-14
5981 | ST-2024-008 | Taiwan | S0006 | TAIW-Medical Center | -6 | -6 | 100 | -0.6 | ENROLLING | Dr. Amanda Wilson | Dr. Emily Jones | 2021-04-05 | 2021-05-06 | 2021-05-11 | 2021-06-07 | 2021-06-06 | 2021-07-03 | 2021-06-21 | 2021-07-19 | 2021-07-07 | 2021-07-30 | 2021-07-24 | 2021-10-06 | 2021-09-29 | 2021-11-30 | 2021-11-27 | 2025-07-17 | 2025-07-05 | 2025-09-06 | 2025-09-11 | 2025-12-25 | 2025-12-12 | 2026-02-02 | 2026-02-11 | 2026-02-23 | 2026-02-21
5982 | ST-2024-008 | Taiwan | S0007 | TAIW-Medical Center | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Christopher Moore | Dr. Michelle Thompson | 2021-04-06 | 2021-05-08 | 2021-04-24 | 2021-06-10 | 2021-06-02 | 2021-07-04 | 2021-07-17 | 2021-07-17 | 2021-07-24 | 2021-08-02 | 2021-08-13 | 2021-10-20 | 2021-10-22 | 2021-12-08 | 2021-12-03 | 2025-07-26 | 2025-07-18 | 2025-09-17 | 2025-09-04 | 2026-01-10 | 2026-01-21 | 2026-02-23 | 2026-02-28 | 2026-03-16 | 2026-03-18
5983 | ST-2024-008 | Taiwan | S0008 | TAIW-Clinical Center | 3 | 3 | 100 | 0.4 | ENROLLING | Dr. Michael Thomas | Dr. Michelle Williams | 2021-04-03 | 2021-05-05 | 2021-05-03 | 2021-05-30 | 2021-05-27 | 2021-06-25 | 2021-07-02 | 2021-07-06 | 2021-07-04 | 2021-07-19 | 2021-07-17 | 2021-10-16 | 2021-10-20 | 2021-12-14 | 2021-12-06 | 2025-07-16 | 2025-07-18 | 2025-09-07 | 2025-08-24 | 2026-01-03 | 2026-01-12 | 2026-02-13 | 2026-02-21 | 2026-03-09 | 2026-02-25
5984 | ST-2024-008 | Taiwan | S0009 | TAIW-Health System | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Charles Smith | Dr. Jessica White | 2021-04-08 | 2021-05-05 | 2021-05-09 | 2021-06-05 | 2021-05-22 | 2021-06-30 | 2021-06-24 | 2021-07-13 | 2021-07-04 | 2021-07-26 | 2021-07-25 | 2021-11-06 | 2021-11-08 | 2021-12-29 | 2021-12-18 | 2025-07-30 | 2025-08-02 | 2025-09-28 | 2025-09-16 | 2026-01-16 | 2026-01-18 | 2026-03-01 | 2026-02-24 | 2026-03-22 | 2026-03-18
5985 | ST-2024-008 | Taiwan | S0010 | TAIW-Clinical Center | 3 | 1 | 33.3 | 0.1 | ENROLLING | Dr. Michelle Davis | Dr. Daniel Garcia | 2021-04-12 | 2021-05-13 | 2021-05-23 | 2021-06-09 | 2021-06-02 | 2021-07-03 | 2021-07-13 | 2021-07-20 | 2021-07-16 | 2021-08-06 | 2021-08-16 | 2021-11-09 | 2021-11-09 | 2022-01-01 | 2022-01-08 | 2025-08-14 | 2025-08-14 | 2025-10-11 | 2025-10-25 | 2026-01-26 | 2026-01-30 | 2026-03-13 | 2026-03-26 | 2026-04-03 | 2026-03-20
5986 | ST-2024-008 | Taiwan | S0011 | TAIW-General Hospital | 3 | 7 | 233.3 | 0.6 | ENROLLING | Dr. Robert Wilson | Dr. Jessica Wilson | 2021-04-04 | 2021-04-28 | 2021-05-01 | 2021-05-27 | 2021-05-13 | 2021-06-22 | 2021-06-30 | 2021-07-09 | 2021-07-21 | 2021-07-21 | 2021-07-15 | 2021-11-05 | 2021-10-29 | 2022-01-04 | 2021-12-30 | 2025-08-01 | 2025-07-20 | 2025-09-26 | 2025-09-24 | 2026-01-21 | 2026-01-28 | 2026-03-04 | 2026-03-13 | 2026-03-26 | 2026-04-07
5987 | ST-2024-009 | Canada | S0001 | CANA-Health System | 13 | 12 | 92.3 | 1.7 | CLOSED | Dr. Jennifer Thomas | Dr. Thomas Miller | 2025-05-14 | 2025-06-08 | 2025-06-17 | 2025-07-08 | 2025-06-30 | 2025-07-29 | 2025-07-22 | 2025-08-11 | 2025-08-20 | 2025-08-23 | 2025-08-16 | 2025-11-24 | 2025-12-07 | 2026-01-21 | 2026-01-15 | 2029-03-05 |  | 2029-04-27 |  | 2029-09-22 |  | 2029-11-01 |  | 2029-11-22
5988 | ST-2024-009 | Canada | S0002 | CANA-Clinical Center | 17 | 0 | 0 | 0 | ON_HOLD | Dr. Nicole Thompson | Dr. Thomas Jackson | 2025-05-09 | 2025-06-04 | 2025-06-09 | 2025-07-06 | 2025-06-22 | 2025-07-27 | 2025-08-06 | 2025-08-08 | 2025-08-21 | 2025-08-25 | 2025-08-28 | 2025-11-14 | 2025-11-01 | 2026-01-03 | 2026-01-16 | 2029-03-18 |  | 2029-05-09 |  | 2029-09-25 |  | 2029-11-11 |  | 2029-12-02
5989 | ST-2024-009 | Canada | S0003 | CANA-Health System | 18 | 0 | 0 | 0 | CLOSED | Dr. Emily Thomas | Dr. Amanda Harris | 2025-05-15 | 2025-06-12 | 2025-06-22 | 2025-07-12 | 2025-07-16 | 2025-08-06 | 2025-07-27 | 2025-08-23 | 2025-08-10 | 2025-09-05 | 2025-09-07 | 2025-11-26 | 2025-12-07 | 2026-01-16 | 2026-01-15 | 2029-03-22 |  | 2029-05-20 |  | 2029-09-25 |  | 2029-11-07 |  | 2029-11-26
5990 | ST-2024-009 | United States | S0004 | UNIT-Health System | 16 | 0 | 0 | 0 | ON_HOLD | Dr. Robert Jackson | Dr. Stephanie Garcia | 2025-05-14 | 2025-06-06 | 2025-06-02 | 2025-07-07 | 2025-07-15 | 2025-07-28 | 2025-07-14 | 2025-08-11 | 2025-07-28 | 2025-08-28 | 2025-09-04 | 2025-11-22 | 2025-11-14 | 2026-01-22 | 2026-01-20 | 2029-03-12 |  | 2029-05-09 |  | 2029-09-05 |  | 2029-10-20 |  | 2029-11-10
5991 | ST-2024-009 | United States | S0005 | UNIT-Clinical Center | 16 | 0 | 0 | 0 | CLOSED | Dr. Jennifer Moore | Dr. Jennifer Martin | 2025-05-11 | 2025-06-08 | 2025-05-30 | 2025-07-10 | 2025-07-11 | 2025-07-30 | 2025-07-29 | 2025-08-11 | 2025-08-03 | 2025-08-26 | 2025-08-25 | 2025-11-21 | 2025-11-29 | 2026-01-12 | 2026-01-22 | 2029-03-19 |  | 2029-05-16 |  | 2029-09-18 |  | 2029-10-30 |  | 2029-11-19
5992 | ST-2024-009 | United States | S0006 | UNIT-Research Institute | 14 | 0 | 0 | 0 | SCREENING | Dr. Thomas Harris | Dr. Sarah Thomas | 2025-05-19 | 2025-06-17 | 2025-06-10 | 2025-07-14 | 2025-07-17 | 2025-08-06 | 2025-08-05 | 2025-08-18 | 2025-08-31 | 2025-09-02 | 2025-08-31 | 2025-11-22 | 2025-11-14 | 2026-01-19 | 2026-01-09 | 2029-03-28 |  | 2029-05-21 |  | 2029-09-13 |  | 2029-10-24 |  | 2029-11-17
5993 | ST-2024-009 | United States | S0007 | UNIT-Medical Center | 9 | 0 | 0 | 0 | SCREENING | Dr. David Jackson | Dr. Michelle Thompson | 2025-05-17 | 2025-06-11 | 2025-06-07 | 2025-07-11 | 2025-07-22 | 2025-07-27 | 2025-07-28 | 2025-08-08 | 2025-08-03 | 2025-08-22 | 2025-08-16 | 2025-12-07 | 2025-12-10 | 2026-01-27 | 2026-02-09 | 2029-04-11 |  | 2029-06-11 |  | 2029-09-30 |  | 2029-11-14 |  | 2029-12-07
5994 | ST-2024-009 | United States | S0008 | UNIT-General Hospital | 13 | 0 | 0 | 0 | ON_HOLD | Dr. Nicole White | Dr. Christopher Martin | 2025-05-12 | 2025-06-05 | 2025-06-01 | 2025-06-30 | 2025-06-24 | 2025-07-16 | 2025-07-13 | 2025-07-28 | 2025-07-25 | 2025-08-14 | 2025-08-17 | 2025-12-06 | 2025-12-09 | 2026-01-31 | 2026-02-11 | 2029-04-12 |  | 2029-06-12 |  | 2029-09-25 |  | 2029-11-08 |  | 2029-12-01
5995 | ST-2024-009 | United States | S0009 | UNIT-University Hospital | 7 | 0 | 0 | 0 | CLOSED | Dr. James Davis | Dr. Jessica Johnson | 2025-05-06 | 2025-06-04 | 2025-05-26 | 2025-06-28 | 2025-07-08 | 2025-07-19 | 2025-07-14 | 2025-08-05 | 2025-08-02 | 2025-08-21 | 2025-08-17 | 2025-12-08 | 2025-12-15 | 2026-01-29 | 2026-01-31 | 2029-04-05 |  | 2029-06-04 |  | 2029-10-01 |  | 2029-11-17 |  | 2029-12-09
5996 | ST-2024-009 | Sweden | S0010 | SWED-Cancer Center | 8 | 0 | 0 | 0 | ON_HOLD | Dr. Michelle Johnson | Dr. Christopher Moore | 2025-05-31 | 2025-06-30 | 2025-07-06 | 2025-07-24 | 2025-07-29 | 2025-08-15 | 2025-08-19 | 2025-08-30 | 2025-08-28 | 2025-09-12 | 2025-09-25 | 2025-12-02 | 2025-11-20 | 2026-01-30 | 2026-01-18 | 2029-03-29 |  | 2029-05-21 |  | 2029-09-08 |  | 2029-10-20 |  | 2029-11-10
5997 | ST-2024-009 | Sweden | S0011 | SWED-University Hospital | 7 | 0 | 0 | 0 | SCREENING | Dr. Lisa Anderson | Dr. Sarah Harris | 2025-05-23 | 2025-06-20 | 2025-07-03 | 2025-07-18 | 2025-07-15 | 2025-08-13 | 2025-08-22 | 2025-08-26 | 2025-08-30 | 2025-09-11 | 2025-09-13 | 2025-12-02 | 2025-12-02 | 2026-01-29 | 2026-01-28 | 2029-04-09 |  | 2029-06-05 |  | 2029-09-05 |  | 2029-10-19 |  | 2029-11-12
5998 | ST-2024-009 | Sweden | S0012 | SWED-Research Institute | 4 | 0 | 0 | 0 | SCREENING | Dr. Christopher Brown | Dr. Lisa Miller | 2025-06-02 | 2025-06-25 | 2025-06-14 | 2025-07-20 | 2025-07-09 | 2025-08-08 | 2025-07-27 | 2025-08-24 | 2025-09-07 | 2025-09-06 | 2025-09-07 | 2025-12-12 | 2025-12-15 | 2026-02-10 | 2026-01-28 | 2029-04-13 |  | 2029-06-04 |  | 2029-09-07 |  | 2029-10-16 |  | 2029-11-06
5999 | ST-2024-009 | Sweden | S0013 | SWED-Cancer Center | 7 | 0 | 0 | 0 | CLOSED | Dr. Amanda White | Dr. Jennifer Jones | 2025-05-26 | 2025-06-26 | 2025-07-05 | 2025-07-20 | 2025-07-15 | 2025-08-06 | 2025-08-06 | 2025-08-19 | 2025-08-25 | 2025-09-03 | 2025-08-24 | 2025-12-04 | 2025-11-24 | 2026-01-23 | 2026-01-25 | 2029-04-13 |  | 2029-06-09 |  | 2029-09-09 |  | 2029-10-19 |  | 2029-11-07
6000 | ST-2024-009 | Sweden | S0014 | SWED-Cancer Center | 9 | 0 | 0 | 0 | SCREENING | Dr. Sarah Thomas | Dr. Michelle Wilson | 2025-05-20 | 2025-06-12 | 2025-06-02 | 2025-07-15 | 2025-07-23 | 2025-08-05 | 2025-08-08 | 2025-08-22 | 2025-08-13 | 2025-09-04 | 2025-09-08 | 2026-01-02 | 2026-01-07 | 2026-02-27 | 2026-02-27 | 2029-04-28 |  | 2029-06-26 |  | 2029-09-27 |  | 2029-11-11 |  | 2029-12-02
6001 | ST-2024-009 | Norway | S0015 | NORW-University Hospital | 18 | 0 | 0 | 0 | ON_HOLD | Dr. Sarah Wilson | Dr. Robert Jones | 2025-05-27 | 2025-06-28 | 2025-07-09 | 2025-07-27 | 2025-07-15 | 2025-08-20 | 2025-08-20 | 2025-09-05 | 2025-08-31 | 2025-09-21 | 2025-09-18 | 2025-12-05 | 2025-12-04 | 2026-01-27 | 2026-01-21 | 2029-04-13 |  | 2029-06-08 |  | 2029-09-09 |  | 2029-10-24 |  | 2029-11-12
6002 | ST-2024-009 | Norway | S0016 | NORW-University Hospital | 10 | 0 | 0 | 0 | CLOSED | Dr. Thomas Davis | Dr. Charles Martin | 2025-05-17 | 2025-06-09 | 2025-06-19 | 2025-07-10 | 2025-07-09 | 2025-07-28 | 2025-08-08 | 2025-08-10 | 2025-08-05 | 2025-08-23 | 2025-08-28 | 2025-12-07 | 2025-11-30 | 2026-02-02 | 2026-02-13 | 2029-04-02 |  | 2029-05-30 |  | 2029-09-12 |  | 2029-10-23 |  | 2029-11-10
6003 | ST-2024-009 | Norway | S0017 | NORW-University Hospital | 22 | 0 | 0 | 0 | CLOSED | Dr. William White | Dr. Charles Harris | 2025-05-22 | 2025-06-17 | 2025-06-11 | 2025-07-16 | 2025-07-04 | 2025-08-09 | 2025-08-08 | 2025-08-23 | 2025-08-29 | 2025-09-06 | 2025-08-30 | 2025-12-04 | 2025-12-06 | 2026-01-24 | 2026-02-03 | 2029-04-14 |  | 2029-06-14 |  | 2029-09-12 |  | 2029-10-25 |  | 2029-11-13
6004 | ST-2024-009 | Norway | S0018 | NORW-Medical Center | 11 | 0 | 0 | 0 | SCREENING | Dr. Charles Thompson | Dr. William Thomas | 2025-05-26 | 2025-06-28 | 2025-06-18 | 2025-07-25 | 2025-07-20 | 2025-08-14 | 2025-08-03 | 2025-08-30 | 2025-09-05 | 2025-09-15 | 2025-09-15 | 2025-12-23 | 2025-12-28 | 2026-02-22 | 2026-02-22 | 2029-04-21 |  | 2029-06-17 |  | 2029-09-23 |  | 2029-10-31 |  | 2029-11-19
6005 | ST-2024-009 | Norway | S0019 | NORW-Clinical Center | 16 | 0 | 0 | 0 | ON_HOLD | Dr. James Williams | Dr. Christopher Thomas | 2025-05-26 | 2025-06-25 | 2025-06-15 | 2025-07-21 | 2025-07-29 | 2025-08-11 | 2025-08-11 | 2025-08-22 | 2025-08-31 | 2025-09-03 | 2025-08-20 | 2025-12-11 | 2025-12-04 | 2026-02-06 | 2026-01-25 | 2029-04-13 |  | 2029-06-05 |  | 2029-09-17 |  | 2029-10-28 |  | 2029-11-17
6006 | ST-2024-009 | Singapore | S0020 | SING-University Hospital | 15 | 0 | 0 | 0 | ON_HOLD | Dr. Thomas Johnson | Dr. Sarah Brown | 2025-05-27 | 2025-06-22 | 2025-07-04 | 2025-07-20 | 2025-07-30 | 2025-08-11 | 2025-08-01 | 2025-08-24 | 2025-08-11 | 2025-09-10 | 2025-09-04 | 2025-12-14 | 2025-12-24 | 2026-02-08 | 2026-02-06 | 2029-03-26 |  | 2029-05-23 |  | 2029-08-31 |  | 2029-10-12 |  | 2029-10-30
6007 | ST-2024-009 | Singapore | S0021 | SING-General Hospital | 13 | 0 | 0 | 0 | ON_HOLD | Dr. James Brown | Dr. Jennifer Harris | 2025-05-27 | 2025-06-21 | 2025-06-30 | 2025-07-17 | 2025-07-04 | 2025-08-06 | 2025-07-29 | 2025-08-23 | 2025-08-23 | 2025-09-06 | 2025-09-15 | 2025-12-17 | 2025-12-27 | 2026-02-04 | 2026-01-24 | 2029-03-24 |  | 2029-05-17 |  | 2029-09-08 |  | 2029-10-22 |  | 2029-11-10
6008 | ST-2024-009 | Singapore | S0022 | SING-Clinical Center | 9 | 0 | 0 | 0 | ON_HOLD | Dr. David Jones | Dr. Jessica Garcia | 2025-05-23 | 2025-06-22 | 2025-06-16 | 2025-07-21 | 2025-07-22 | 2025-08-16 | 2025-08-22 | 2025-08-29 | 2025-08-24 | 2025-09-11 | 2025-09-03 | 2025-12-13 | 2025-12-10 | 2026-02-10 | 2026-02-24 | 2029-04-10 |  | 2029-05-31 |  | 2029-09-17 |  | 2029-11-01 |  | 2029-11-19
6009 | ST-2024-009 | Singapore | S0023 | SING-Cancer Center | 15 | 0 | 0 | 0 | SCREENING | Dr. Amanda Wilson | Dr. Michael Thomas | 2025-05-30 | 2025-06-25 | 2025-07-06 | 2025-07-19 | 2025-07-12 | 2025-08-07 | 2025-07-24 | 2025-08-23 | 2025-08-10 | 2025-09-06 | 2025-09-10 | 2025-12-14 | 2025-12-25 | 2026-02-01 | 2026-02-09 | 2029-03-30 |  | 2029-05-24 |  | 2029-09-16 |  | 2029-10-24 |  | 2029-11-14
6010 | ST-2024-009 | Singapore | S0024 | SING-General Hospital | 13 | 0 | 0 | 0 | SCREENING | Dr. Sarah Jackson | Dr. Jessica Davis | 2025-05-29 | 2025-06-23 | 2025-06-10 | 2025-07-21 | 2025-07-18 | 2025-08-07 | 2025-08-13 | 2025-08-19 | 2025-08-09 | 2025-08-31 | 2025-09-08 | 2025-12-27 | 2025-12-30 | 2026-02-15 | 2026-02-26 | 2029-04-18 |  | 2029-06-17 |  | 2029-09-23 |  | 2029-11-09 |  | 2029-11-27
6011 | ST-2024-010 | Mexico | S0001 | MEXI-University Hospital | 283 | 269 | 95.1 | 20.7 | SCREENING | Dr. Thomas White | Dr. Emily Moore | 2020-08-10 | 2020-09-05 | 2020-09-03 | 2020-10-03 | 2020-09-30 | 2020-10-27 | 2020-11-05 | 2020-11-13 | 2020-11-03 | 2020-11-29 | 2020-11-23 | 2021-02-19 | 2021-03-05 | 2021-04-14 | 2021-04-01 | 2030-10-01 |  | 2030-11-28 |  | 2031-03-19 |  | 2031-04-25 |  | 2031-05-18
6012 | ST-2024-010 | Mexico | S0002 | MEXI-Research Institute | 344 | 238 | 69.2 | 13.2 | ENROLLING | Dr. Christopher Anderson | Dr. Christopher Wilson | 2020-08-10 | 2020-09-10 | 2020-09-10 | 2020-10-07 | 2020-10-01 | 2020-10-31 | 2020-11-13 | 2020-11-16 | 2020-11-28 | 2020-11-30 | 2020-12-05 | 2021-02-14 | 2021-02-27 | 2021-04-13 | 2021-04-16 | 2030-09-25 |  | 2030-11-23 |  | 2031-03-25 |  | 2031-05-06 |  | 2031-05-29
6013 | ST-2024-010 | Mexico | S0003 | MEXI-Cancer Center | 627 | 655 | 104.5 | 93.6 | ENROLLING | Dr. Jennifer Anderson | Dr. Sarah Miller | 2020-08-11 | 2020-09-05 | 2020-09-14 | 2020-10-05 | 2020-09-26 | 2020-10-25 | 2020-11-08 | 2020-11-11 | 2020-10-28 | 2020-11-24 | 2020-11-29 | 2021-02-21 | 2021-03-06 | 2021-04-16 | 2021-04-13 | 2030-10-02 |  | 2030-11-22 |  | 2031-04-01 |  | 2031-05-16 |  | 2031-06-06
6014 | ST-2024-010 | United Kingdom | S0004 | UNIT-Research Institute | 997 | 811 | 81.3 | 101.4 | SCREENING | Dr. Charles Harris | Dr. Michelle Moore | 2020-08-09 | 2020-09-06 | 2020-09-11 | 2020-09-30 | 2020-09-25 | 2020-10-26 | 2020-10-22 | 2020-11-10 | 2020-11-09 | 2020-11-27 | 2020-12-03 | 2021-02-25 | 2021-02-21 | 2021-04-18 | 2021-04-07 | 2030-10-09 |  | 2030-12-09 |  | 2031-03-23 |  | 2031-05-07 |  | 2031-05-26
6015 | ST-2024-010 | United Kingdom | S0005 | UNIT-University Hospital | 616 | 507 | 82.3 | 72.4 | ON_HOLD | Dr. Emily Jones | Dr. Emily Smith | 2020-08-16 | 2020-09-09 | 2020-09-13 | 2020-10-02 | 2020-10-08 | 2020-10-20 | 2020-11-01 | 2020-11-01 | 2020-10-30 | 2020-11-18 | 2020-11-25 | 2021-02-22 | 2021-02-23 | 2021-04-15 | 2021-04-17 | 2030-10-05 |  | 2030-12-02 |  | 2031-03-22 |  | 2031-04-29 |  | 2031-05-17
6016 | ST-2024-010 | United Kingdom | S0006 | UNIT-Medical Center | 440 | 0 | 0 | 0 | SCREENING | Dr. Robert Miller | Dr. Charles Thomas | 2020-08-15 | 2020-09-11 | 2020-08-30 | 2020-10-04 | 2020-10-04 | 2020-10-25 | 2020-11-05 | 2020-11-06 | 2020-11-12 | 2020-11-21 | 2020-11-08 | 2021-03-12 | 2021-03-09 | 2021-05-01 | 2021-05-04 | 2030-10-11 |  | 2030-12-04 |  | 2031-04-05 |  | 2031-05-19 |  | 2031-06-12
6017 | ST-2024-010 | United Kingdom | S0007 | UNIT-General Hospital | 557 | 0 | 0 | 0 | CLOSED | Dr. Michael Wilson | Dr. Michael Smith | 2020-08-20 | 2020-09-18 | 2020-09-20 | 2020-10-16 | 2020-10-05 | 2020-11-01 | 2020-10-21 | 2020-11-18 | 2020-11-27 | 2020-12-03 | 2020-11-26 | 2021-03-12 | 2021-03-15 | 2021-05-08 | 2021-05-06 | 2030-10-18 |  | 2030-12-09 |  | 2031-04-06 |  | 2031-05-14 |  | 2031-06-02
6018 | ST-2024-010 | Australia | S0008 | AUST-Medical Center | 368 | 0 | 0 | 0 | ON_HOLD | Dr. Sarah Garcia | Dr. Stephanie Jackson | 2020-08-31 | 2020-10-03 | 2020-09-30 | 2020-10-29 | 2020-11-05 | 2020-11-23 | 2020-11-23 | 2020-12-09 | 2020-12-17 | 2020-12-21 | 2020-12-28 | 2021-03-09 | 2021-03-08 | 2021-05-08 | 2021-05-22 | 2030-10-21 |  | 2030-12-17 |  | 2031-03-28 |  | 2031-05-14 |  | 2031-06-05
6019 | ST-2024-010 | Australia | S0009 | AUST-Clinical Center | 170 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Garcia | Dr. Amanda Miller | 2020-09-04 | 2020-09-29 | 2020-10-02 | 2020-10-30 | 2020-10-26 | 2020-11-21 | 2020-12-04 | 2020-12-06 | 2020-12-03 | 2020-12-19 | 2020-12-18 | 2021-03-14 | 2021-03-24 | 2021-05-04 | 2021-05-10 | 2030-10-24 |  | 2030-12-23 |  | 2031-04-06 |  | 2031-05-18 |  | 2031-06-07
6020 | ST-2024-010 | Australia | S0010 | AUST-University Hospital | 279 | 0 | 0 | 0 | ON_HOLD | Dr. Christopher Jones | Dr. Sarah Davis | 2020-09-03 | 2020-10-01 | 2020-10-01 | 2020-11-02 | 2020-10-31 | 2020-11-21 | 2020-11-07 | 2020-12-06 | 2020-12-15 | 2020-12-21 | 2020-12-08 | 2021-03-12 | 2021-03-07 | 2021-05-06 | 2021-05-11 | 2030-11-02 |  | 2030-12-31 |  | 2031-04-08 |  | 2031-05-20 |  | 2031-06-10
6021 | ST-2024-010 | Australia | S0011 | AUST-General Hospital | 319 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Moore | Dr. Nicole Johnson | 2020-08-25 | 2020-09-21 | 2020-09-25 | 2020-10-14 | 2020-10-18 | 2020-11-03 | 2020-10-24 | 2020-11-15 | 2020-11-04 | 2020-11-27 | 2020-11-14 | 2021-03-21 | 2021-03-21 | 2021-05-14 | 2021-05-11 | 2030-10-20 |  | 2030-12-14 |  | 2031-04-11 |  | 2031-05-26 |  | 2031-06-17
6022 | ST-2024-011 | United States | S0001 | UNIT-Clinical Center | 7 | 4 | 57.1 | 0.4 | CLOSED | Dr. Charles Brown | Dr. Nicole Davis | 2025-06-24 | 2025-07-22 | 2025-07-31 | 2025-08-23 | 2025-08-11 | 2025-09-11 | 2025-09-20 | 2025-09-23 | 2025-09-19 | 2025-10-06 | 2025-10-17 | 2026-01-12 | 2026-01-13 | 2026-03-06 | 2026-02-25 | 2028-09-21 |  | 2028-11-20 |  | 2029-04-05 |  | 2029-05-21 |  | 2029-06-09
6023 | ST-2024-011 | United States | S0002 | UNIT-University Hospital | 10 | 1 | 10 | 0.1 | SCREENING | Dr. Sarah Anderson | Dr. James Taylor | 2025-07-04 | 2025-08-05 | 2025-07-23 | 2025-08-29 | 2025-09-08 | 2025-09-23 | 2025-09-19 | 2025-10-09 | 2025-10-06 | 2025-10-22 | 2025-11-05 | 2026-01-04 | 2026-01-16 | 2026-03-05 | 2026-03-04 | 2028-10-06 |  | 2028-12-05 |  | 2029-04-09 |  | 2029-05-17 |  | 2029-06-10
6024 | ST-2024-011 | United States | S0003 | UNIT-Research Institute | 10 | 0 | 0 | 0 | SCREENING | Dr. Thomas Garcia | Dr. Charles Garcia | 2025-07-03 | 2025-07-27 | 2025-07-29 | 2025-08-22 | 2025-08-09 | 2025-09-17 | 2025-09-13 | 2025-10-04 | 2025-10-07 | 2025-10-19 | 2025-10-23 | 2026-01-22 | 2026-01-12 | 2026-03-12 | 2026-03-08 | 2028-10-08 |  | 2028-12-08 |  | 2029-04-13 |  | 2029-05-20 |  | 2029-06-09
6025 | ST-2024-011 | France | S0004 | FRAN-University Hospital | 11 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Johnson | Dr. Emily Taylor | 2025-07-03 | 2025-07-28 | 2025-07-27 | 2025-08-20 | 2025-08-15 | 2025-09-15 | 2025-09-26 | 2025-10-01 | 2025-09-29 | 2025-10-15 | 2025-10-05 | 2026-01-05 | 2025-12-26 | 2026-03-07 | 2026-03-03 | 2028-10-09 |  | 2028-12-08 |  | 2029-03-28 |  | 2029-05-05 |  | 2029-05-24
6026 | ST-2024-011 | France | S0005 | FRAN-University Hospital | 7 | 0 | 0 | 0 | ON_HOLD | Dr. Michelle Moore | Dr. William Anderson | 2025-07-09 | 2025-08-01 | 2025-07-24 | 2025-09-01 | 2025-09-02 | 2025-09-23 | 2025-09-21 | 2025-10-06 | 2025-10-12 | 2025-10-17 | 2025-10-21 | 2026-01-07 | 2025-12-30 | 2026-03-05 | 2026-03-08 | 2028-10-09 |  | 2028-12-01 |  | 2029-03-25 |  | 2029-05-08 |  | 2029-05-30
6027 | ST-2024-011 | France | S0006 | FRAN-Research Institute | 9 | 0 | 0 | 0 | SCREENING | Dr. Sarah Jackson | Dr. Michelle Martin | 2025-07-11 | 2025-08-11 | 2025-08-18 | 2025-09-06 | 2025-09-05 | 2025-09-25 | 2025-09-24 | 2025-10-06 | 2025-10-03 | 2025-10-19 | 2025-10-16 | 2026-01-20 | 2026-01-12 | 2026-03-16 | 2026-03-12 | 2028-10-15 |  | 2028-12-15 |  | 2029-04-08 |  | 2029-05-16 |  | 2029-06-03
6028 | ST-2024-011 | France | S0007 | FRAN-University Hospital | 4 | 0 | 0 | 0 | ON_HOLD | Dr. James White | Dr. Michael Anderson | 2025-07-10 | 2025-08-02 | 2025-08-14 | 2025-08-29 | 2025-08-22 | 2025-09-16 | 2025-09-08 | 2025-09-29 | 2025-10-06 | 2025-10-14 | 2025-10-11 | 2026-01-22 | 2026-01-12 | 2026-03-24 | 2026-04-03 | 2028-10-18 |  | 2028-12-17 |  | 2029-04-02 |  | 2029-05-16 |  | 2029-06-03
6029 | ST-2024-011 | France | S0008 | FRAN-Cancer Center | 7 | 0 | 0 | 0 | CLOSED | Dr. Nicole Miller | Dr. Emily Smith | 2025-07-01 | 2025-07-25 | 2025-08-05 | 2025-08-17 | 2025-08-06 | 2025-09-05 | 2025-08-31 | 2025-09-20 | 2025-09-20 | 2025-10-02 | 2025-10-03 | 2026-02-03 | 2026-01-20 | 2026-04-06 | 2026-04-02 | 2028-11-05 |  | 2028-12-30 |  | 2029-04-12 |  | 2029-05-24 |  | 2029-06-16
6030 | ST-2024-011 | Singapore | S0009 | SING-Cancer Center | 12 | 0 | 0 | 0 | ON_HOLD | Dr. Nicole Wilson | Dr. Michael Moore | 2025-07-08 | 2025-08-03 | 2025-08-01 | 2025-08-29 | 2025-09-02 | 2025-09-22 | 2025-10-06 | 2025-10-07 | 2025-10-14 | 2025-10-24 | 2025-10-26 | 2026-01-10 | 2025-12-28 | 2026-03-08 | 2026-03-02 | 2028-10-04 |  | 2028-12-03 |  | 2029-03-25 |  | 2029-05-11 |  | 2029-05-29
6031 | ST-2024-011 | Singapore | S0010 | SING-Clinical Center | 17 | 0 | 0 | 0 | ON_HOLD | Dr. Charles Thomas | Dr. Jennifer Harris | 2025-07-04 | 2025-07-30 | 2025-08-12 | 2025-08-31 | 2025-09-07 | 2025-09-20 | 2025-09-17 | 2025-10-01 | 2025-10-14 | 2025-10-15 | 2025-10-04 | 2026-01-19 | 2026-01-05 | 2026-03-09 | 2026-03-04 | 2028-10-01 |  | 2028-11-27 |  | 2029-04-05 |  | 2029-05-16 |  | 2029-06-08
6032 | ST-2024-011 | Singapore | S0011 | SING-Medical Center | 23 | 0 | 0 | 0 | ON_HOLD | Dr. Christopher Wilson | Dr. Lisa Wilson | 2025-07-10 | 2025-08-08 | 2025-07-30 | 2025-09-03 | 2025-08-26 | 2025-09-25 | 2025-09-27 | 2025-10-10 | 2025-10-10 | 2025-10-26 | 2025-10-29 | 2026-01-20 | 2026-01-28 | 2026-03-24 | 2026-03-10 | 2028-10-15 |  | 2028-12-12 |  | 2029-04-14 |  | 2029-05-29 |  | 2029-06-16
6033 | ST-2024-011 | Mexico | S0012 | MEXI-Cancer Center | 9 | 0 | 0 | 0 | SCREENING | Dr. Michelle Johnson | Dr. Charles Thompson | 2025-07-21 | 2025-08-21 | 2025-08-27 | 2025-09-17 | 2025-09-12 | 2025-10-08 | 2025-10-01 | 2025-10-22 | 2025-10-24 | 2025-11-05 | 2025-10-30 | 2026-01-21 | 2026-02-01 | 2026-03-13 | 2026-02-28 | 2028-10-10 |  | 2028-12-05 |  | 2029-04-01 |  | 2029-05-13 |  | 2029-06-02
6034 | ST-2024-011 | Mexico | S0013 | MEXI-Clinical Center | 4 | 0 | 0 | 0 | CLOSED | Dr. Nicole Davis | Dr. Nicole Anderson | 2025-07-21 | 2025-08-19 | 2025-08-28 | 2025-09-11 | 2025-09-09 | 2025-10-05 | 2025-10-07 | 2025-10-18 | 2025-10-25 | 2025-10-30 | 2025-11-04 | 2026-01-17 | 2026-01-30 | 2026-03-12 | 2026-03-18 | 2028-10-29 |  | 2028-12-25 |  | 2029-04-06 |  | 2029-05-15 |  | 2029-06-02
6035 | ST-2024-011 | Mexico | S0014 | MEXI-Medical Center | 7 | 0 | 0 | 0 | CLOSED | Dr. Sarah Thompson | Dr. Daniel Jones | 2025-07-13 | 2025-08-08 | 2025-08-14 | 2025-09-09 | 2025-08-30 | 2025-09-27 | 2025-10-01 | 2025-10-11 | 2025-10-14 | 2025-10-24 | 2025-10-31 | 2026-02-04 | 2026-02-15 | 2026-04-03 | 2026-03-26 | 2028-10-26 |  | 2028-12-23 |  | 2029-04-10 |  | 2029-05-19 |  | 2029-06-07
6036 | ST-2024-011 | Mexico | S0015 | MEXI-Medical Center | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Garcia | Dr. David Miller | 2025-07-11 | 2025-08-11 | 2025-08-14 | 2025-09-05 | 2025-09-14 | 2025-09-27 | 2025-09-16 | 2025-10-14 | 2025-10-05 | 2025-10-26 | 2025-10-22 | 2026-02-08 | 2026-02-20 | 2026-04-12 | 2026-04-26 | 2028-11-07 |  | 2028-12-30 |  | 2029-04-15 |  | 2029-05-23 |  | 2029-06-14
6037 | ST-2024-012 | Mexico | S0001 | MEXI-Cancer Center | -12 | -12 | 100 | -0.9 | CLOSED | Dr. Amanda Thompson | Dr. Jessica Garcia | 2024-12-02 | 2024-12-30 | 2024-12-22 | 2025-01-28 | 2025-01-17 | 2025-02-19 | 2025-02-09 | 2025-03-04 | 2025-02-23 | 2025-03-18 | 2025-03-04 | 2025-06-17 | 2025-06-27 | 2025-08-19 | 2025-08-24 | 2026-09-28 |  | 2026-11-28 |  | 2027-03-13 |  | 2027-04-21 |  | 2027-05-15
6038 | ST-2024-012 | Mexico | S0002 | MEXI-Cancer Center | 3 | 2 | 66.7 | 0.1 | CLOSED | Dr. Jennifer Anderson | Dr. Emily Martin | 2024-12-11 | 2025-01-12 | 2025-01-14 | 2025-02-13 | 2025-02-26 | 2025-03-04 | 2025-03-09 | 2025-03-19 | 2025-03-20 | 2025-03-31 | 2025-04-08 | 2025-06-14 | 2025-06-20 | 2025-08-12 | 2025-08-09 | 2026-09-20 |  | 2026-11-15 |  | 2027-03-15 |  | 2027-04-28 |  | 2027-05-17
6039 | ST-2024-012 | Mexico | S0003 | MEXI-University Hospital | 3 | 3 | 100 | 0.2 | ON_HOLD | Dr. Michelle Garcia | Dr. Thomas Williams | 2024-12-08 | 2025-01-07 | 2025-01-16 | 2025-02-06 | 2025-02-13 | 2025-02-24 | 2025-02-16 | 2025-03-08 | 2025-03-18 | 2025-03-20 | 2025-03-12 | 2025-06-15 | 2025-06-03 | 2025-08-03 | 2025-07-25 | 2026-09-27 |  | 2026-11-17 |  | 2027-03-19 |  | 2027-05-01 |  | 2027-05-20
6040 | ST-2024-012 | Mexico | S0004 | MEXI-University Hospital | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Jessica White | Dr. Thomas Thomas | 2024-12-09 | 2025-01-10 | 2025-01-22 | 2025-02-09 | 2025-02-07 | 2025-03-02 | 2025-03-11 | 2025-03-19 | 2025-03-15 | 2025-04-02 | 2025-03-31 | 2025-07-10 | 2025-07-15 | 2025-08-31 | 2025-09-09 | 2026-10-11 |  | 2026-12-07 |  | 2027-03-29 |  | 2027-05-14 |  | 2027-06-06
6041 | ST-2024-012 | Mexico | S0005 | MEXI-Research Institute | 3 | 2 | 66.7 | 0.1 | ON_HOLD | Dr. Christopher Brown | Dr. Nicole Johnson | 2024-12-10 | 2025-01-10 | 2025-01-08 | 2025-02-12 | 2025-02-21 | 2025-02-28 | 2025-02-15 | 2025-03-15 | 2025-03-18 | 2025-03-26 | 2025-03-24 | 2025-07-03 | 2025-07-05 | 2025-08-28 | 2025-09-07 | 2026-10-18 |  | 2026-12-08 |  | 2027-04-01 |  | 2027-05-16 |  | 2027-06-07
6042 | ST-2024-012 | Mexico | S0006 | MEXI-Cancer Center | 3 | 5 | 166.7 | 0.3 | CLOSED | Dr. Michael Martin | Dr. David Thompson | 2024-12-02 | 2024-12-28 | 2025-01-02 | 2025-01-24 | 2025-01-11 | 2025-02-16 | 2025-02-24 | 2025-03-02 | 2025-03-04 | 2025-03-15 | 2025-03-29 | 2025-07-14 | 2025-07-04 | 2025-09-14 | 2025-09-14 | 2026-10-15 |  | 2026-12-12 |  | 2027-04-06 |  | 2027-05-19 |  | 2027-06-08
6043 | ST-2024-012 | Canada | S0007 | CANA-Clinical Center | -7 | -7 | 100 | -0.9 | SCREENING | Dr. Jennifer Williams | Dr. Nicole Taylor | 2024-12-13 | 2025-01-06 | 2025-01-02 | 2025-02-06 | 2025-02-06 | 2025-02-23 | 2025-02-09 | 2025-03-07 | 2025-02-26 | 2025-03-24 | 2025-03-24 | 2025-06-21 | 2025-06-25 | 2025-08-23 | 2025-09-06 | 2026-09-20 |  | 2026-11-18 |  | 2027-03-15 |  | 2027-04-27 |  | 2027-05-18
6044 | ST-2024-012 | Canada | S0008 | CANA-General Hospital | 3 | 3 | 100 | 0.4 | SCREENING | Dr. Sarah Smith | Dr. Christopher Wilson | 2024-12-09 | 2025-01-08 | 2025-01-16 | 2025-02-01 | 2025-02-01 | 2025-02-21 | 2025-02-27 | 2025-03-06 | 2025-03-03 | 2025-03-22 | 2025-03-10 | 2025-06-28 | 2025-06-30 | 2025-08-30 | 2025-09-07 | 2026-09-26 |  | 2026-11-18 |  | 2027-03-20 |  | 2027-04-27 |  | 2027-05-15
6045 | ST-2024-012 | Canada | S0009 | CANA-University Hospital | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Jennifer Martin | Dr. Michael Jones | 2024-12-18 | 2025-01-18 | 2025-01-25 | 2025-02-19 | 2025-03-04 | 2025-03-09 | 2025-02-27 | 2025-03-23 | 2025-03-14 | 2025-04-07 | 2025-04-20 | 2025-06-26 | 2025-06-16 | 2025-08-14 | 2025-08-05 | 2026-09-29 |  | 2026-11-21 |  | 2027-03-26 |  | 2027-05-11 |  | 2027-06-04
6046 | ST-2024-012 | Canada | S0010 | CANA-Health System | 3 | 3 | 100 | 0.2 | ON_HOLD | Dr. Stephanie Jackson | Dr. Stephanie Martin | 2024-12-06 | 2025-01-04 | 2024-12-21 | 2025-01-31 | 2025-02-05 | 2025-02-20 | 2025-03-02 | 2025-03-08 | 2025-03-02 | 2025-03-25 | 2025-03-11 | 2025-07-07 | 2025-07-07 | 2025-08-29 | 2025-08-30 | 2026-10-07 |  | 2026-11-29 |  | 2027-04-01 |  | 2027-05-10 |  | 2027-05-29
6047 | ST-2024-012 | Canada | S0011 | CANA-Clinical Center | 3 | 3 | 100 | 0.5 | ENROLLING | Dr. Michelle Miller | Dr. Amanda Smith | 2024-12-14 | 2025-01-06 | 2025-01-11 | 2025-02-07 | 2025-02-12 | 2025-03-02 | 2025-02-16 | 2025-03-14 | 2025-03-07 | 2025-03-26 | 2025-04-09 | 2025-07-16 | 2025-07-19 | 2025-09-13 | 2025-09-07 | 2026-10-11 |  | 2026-12-08 |  | 2027-04-13 |  | 2027-05-27 |  | 2027-06-14
6048 | ST-2024-012 | Belgium | S0012 | BELG-Research Institute | -3 | -3 | 100 | -0.3 | ENROLLING | Dr. Emily Jackson | Dr. Daniel Anderson | 2024-12-28 | 2025-01-23 | 2025-02-04 | 2025-02-15 | 2025-02-20 | 2025-03-05 | 2025-02-28 | 2025-03-17 | 2025-03-13 | 2025-03-28 | 2025-03-16 | 2025-07-02 | 2025-06-19 | 2025-08-25 | 2025-08-14 | 2026-09-27 |  | 2026-11-19 |  | 2027-03-12 |  | 2027-04-28 |  | 2027-05-20
6049 | ST-2024-012 | Belgium | S0013 | BELG-University Hospital | 3 | 3 | 100 | 0.4 | ENROLLING | Dr. Jessica Anderson | Dr. Christopher Thompson | 2024-12-22 | 2025-01-16 | 2025-01-25 | 2025-02-18 | 2025-02-22 | 2025-03-10 | 2025-03-07 | 2025-03-25 | 2025-03-12 | 2025-04-10 | 2025-03-29 | 2025-07-07 | 2025-07-17 | 2025-09-05 | 2025-08-31 | 2026-10-10 |  | 2026-12-09 |  | 2027-03-24 |  | 2027-05-02 |  | 2027-05-23
6050 | ST-2024-012 | Belgium | S0014 | BELG-Health System | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Stephanie Jones | Dr. Thomas Martin | 2025-01-03 | 2025-02-01 | 2025-02-03 | 2025-02-25 | 2025-02-24 | 2025-03-19 | 2025-03-21 | 2025-04-05 | 2025-03-28 | 2025-04-20 | 2025-04-28 | 2025-06-30 | 2025-06-22 | 2025-08-22 | 2025-08-27 | 2026-10-11 |  | 2026-12-03 |  | 2027-03-20 |  | 2027-04-30 |  | 2027-05-20
6051 | ST-2024-012 | Belgium | S0015 | BELG-Research Institute | 3 | 4 | 133.3 | 0.2 | ENROLLING | Dr. Jennifer Jackson | Dr. James Davis | 2024-12-29 | 2025-01-31 | 2025-01-27 | 2025-03-03 | 2025-02-25 | 2025-03-20 | 2025-03-22 | 2025-04-03 | 2025-04-07 | 2025-04-19 | 2025-04-24 | 2025-07-10 | 2025-07-07 | 2025-09-06 | 2025-08-27 | 2026-10-18 |  | 2026-12-12 |  | 2027-03-25 |  | 2027-05-10 |  | 2027-06-03
6052 | ST-2024-012 | Norway | S0016 | NORW-Medical Center | 0 | 0 | 0 | 0 | CLOSED | Dr. Sarah Jackson | Dr. William Moore | 2025-01-01 | 2025-02-01 | 2025-01-21 | 2025-03-06 | 2025-02-20 | 2025-03-29 | 2025-03-29 | 2025-04-12 | 2025-04-18 | 2025-04-29 | 2025-05-10 | 2025-07-08 | 2025-06-27 | 2025-09-09 | 2025-09-18 | 2026-10-20 |  | 2026-12-13 |  | 2027-03-18 |  | 2027-04-27 |  | 2027-05-15
6053 | ST-2024-012 | Norway | S0017 | NORW-Health System | 3 | 2 | 66.7 | 0.3 | CLOSED | Dr. Sarah Brown | Dr. James Johnson | 2025-01-06 | 2025-02-07 | 2025-01-30 | 2025-03-08 | 2025-03-16 | 2025-03-30 | 2025-03-25 | 2025-04-10 | 2025-04-04 | 2025-04-23 | 2025-05-04 | 2025-07-17 | 2025-07-05 | 2025-09-12 | 2025-09-07 | 2026-10-29 |  | 2026-12-29 |  | 2027-03-23 |  | 2027-04-29 |  | 2027-05-22
6054 | ST-2024-012 | Norway | S0018 | NORW-General Hospital | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. Christopher Jackson | Dr. Emily Moore | 2025-01-02 | 2025-01-30 | 2025-01-21 | 2025-02-22 | 2025-02-14 | 2025-03-11 | 2025-03-07 | 2025-03-27 | 2025-04-08 | 2025-04-09 | 2025-04-05 | 2025-07-18 | 2025-07-25 | 2025-09-11 | 2025-09-12 | 2026-10-29 |  | 2026-12-28 |  | 2027-03-30 |  | 2027-05-06 |  | 2027-05-30
6055 | ST-2024-012 | Singapore | S0019 | SING-General Hospital | 2 | 0 | 0 | 0 | SCREENING | Dr. Jessica White | Dr. Emily Thompson | 2025-01-19 | 2025-02-11 | 2025-02-23 | 2025-03-16 | 2025-03-15 | 2025-04-03 | 2025-04-12 | 2025-04-17 | 2025-04-04 | 2025-04-29 | 2025-05-11 | 2025-07-31 | 2025-08-02 | 2025-09-25 | 2025-09-20 | 2026-11-07 |  | 2027-01-05 |  | 2027-03-22 |  | 2027-05-05 |  | 2027-05-29
6056 | ST-2024-012 | Singapore | S0020 | SING-Research Institute | 3 | 0 | 0 | 0 | CLOSED | Dr. Robert White | Dr. Emily Thompson | 2025-01-17 | 2025-02-14 | 2025-02-26 | 2025-03-17 | 2025-03-03 | 2025-04-10 | 2025-04-06 | 2025-04-21 | 2025-04-19 | 2025-05-03 | 2025-05-09 | 2025-08-04 | 2025-08-07 | 2025-10-02 | 2025-10-14 | 2026-11-03 |  | 2026-12-29 |  | 2027-03-23 |  | 2027-05-01 |  | 2027-05-21
6057 | ST-2024-012 | Chile | S0021 | CHIL-University Hospital | -1 | -1 | 100 | -0.1 | ON_HOLD | Dr. Daniel Miller | Dr. Amanda White | 2025-01-08 | 2025-02-06 | 2025-01-25 | 2025-03-03 | 2025-03-04 | 2025-03-28 | 2025-04-11 | 2025-04-08 | 2025-04-01 | 2025-04-25 | 2025-04-22 | 2025-07-13 | 2025-07-13 | 2025-09-12 | 2025-09-24 | 2026-10-02 |  | 2026-11-27 |  | 2027-03-09 |  | 2027-04-19 |  | 2027-05-10
6058 | ST-2024-012 | Chile | S0022 | CHIL-Research Institute | 3 | 1 | 33.3 | 0.1 | SCREENING | Dr. Michelle Martin | Dr. David Martin | 2025-01-02 | 2025-02-02 | 2025-01-19 | 2025-03-01 | 2025-03-12 | 2025-03-19 | 2025-03-20 | 2025-03-30 | 2025-04-13 | 2025-04-12 | 2025-04-14 | 2025-07-20 | 2025-07-10 | 2025-09-07 | 2025-08-30 | 2026-10-17 |  | 2026-12-10 |  | 2027-03-17 |  | 2027-04-30 |  | 2027-05-22
6059 | ST-2024-012 | Chile | S0023 | CHIL-Research Institute | 3 | 0 | 0 | 0 | SCREENING | Dr. James Williams | Dr. Emily Martin | 2025-01-06 | 2025-02-06 | 2025-02-15 | 2025-03-05 | 2025-02-20 | 2025-03-26 | 2025-03-26 | 2025-04-07 | 2025-04-05 | 2025-04-24 | 2025-05-02 | 2025-07-22 | 2025-08-04 | 2025-09-10 | 2025-09-12 | 2026-10-19 |  | 2026-12-17 |  | 2027-03-27 |  | 2027-05-05 |  | 2027-05-24
6060 | ST-2024-013 | Mexico | S0001 | MEXI-Cancer Center | -12 | -12 | 100 | -0.7 | SCREENING | Dr. Thomas Moore | Dr. David Miller | 2026-06-06 | 2026-06-29 |  | 2026-08-01 |  | 2026-08-26 |  | 2026-09-12 |  | 2026-09-23 |  | 2026-12-17 |  | 2027-02-11 |  | 2029-06-23 |  | 2029-08-13 |  | 2029-12-07 |  | 2030-01-21 |  | 2030-02-14
6061 | ST-2024-013 | Mexico | S0002 | MEXI-University Hospital | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Jessica Thomas | Dr. Robert Garcia | 2026-06-06 | 2026-06-29 |  | 2026-07-31 |  | 2026-08-20 |  | 2026-09-05 |  | 2026-09-17 |  | 2026-12-22 |  | 2027-02-12 |  | 2029-06-17 |  | 2029-08-11 |  | 2029-12-15 |  | 2030-01-29 |  | 2030-02-18
6062 | ST-2024-013 | Mexico | S0003 | MEXI-Health System | 3 | 4 | 133.3 | 0.3 | SCREENING | Dr. Thomas Brown | Dr. Amanda Moore | 2026-06-12 | 2026-07-06 |  | 2026-08-02 |  | 2026-08-20 |  | 2026-09-01 |  | 2026-09-14 |  | 2026-12-25 |  | 2027-02-12 |  | 2029-06-30 |  | 2029-08-28 |  | 2029-12-26 |  | 2030-02-02 |  | 2030-02-21
6063 | ST-2024-013 | Poland | S0004 | POLA-Clinical Center | 2 | 2 | 100 | 0.1 | SCREENING | Dr. Michelle Anderson | Dr. Stephanie Smith | 2026-06-21 | 2026-07-19 |  | 2026-08-15 |  | 2026-09-02 |  | 2026-09-18 |  | 2026-10-05 |  | 2026-12-24 |  | 2027-02-20 |  | 2029-06-18 |  | 2029-08-10 |  | 2029-12-11 |  | 2030-01-21 |  | 2030-02-12
6064 | ST-2024-013 | Poland | S0005 | POLA-Health System | 3 | 3 | 100 | 0.4 | ENROLLING | Dr. Charles Jones | Dr. Sarah Johnson | 2026-06-21 | 2026-07-21 |  | 2026-08-13 |  | 2026-08-31 |  | 2026-09-11 |  | 2026-09-25 |  | 2027-01-09 |  | 2027-03-09 |  | 2029-06-21 |  | 2029-08-12 |  | 2029-12-22 |  | 2030-01-28 |  | 2030-02-15
6065 | ST-2024-013 | South Korea | S0006 | SOUT-Medical Center | -7 | -7 | 100 | -0.6 | ON_HOLD | Dr. Emily Moore | Dr. Lisa Moore | 2026-06-19 | 2026-07-21 |  | 2026-08-22 |  | 2026-09-17 |  | 2026-10-04 |  | 2026-10-20 |  | 2027-01-02 |  | 2027-02-27 |  | 2029-07-10 |  | 2029-09-04 |  | 2029-12-21 |  | 2030-02-01 |  | 2030-02-25
6066 | ST-2024-013 | South Korea | S0007 | SOUT-Clinical Center | 3 | 3 | 100 | 0.3 | CLOSED | Dr. Jessica Johnson | Dr. Charles Jackson | 2026-06-29 | 2026-08-01 |  | 2026-09-01 |  | 2026-09-18 |  | 2026-10-05 |  | 2026-10-22 |  | 2027-01-01 |  | 2027-02-28 |  | 2029-07-06 |  | 2029-08-27 |  | 2029-12-27 |  | 2030-02-03 |  | 2030-02-24
6067 | ST-2024-013 | South Korea | S0008 | SOUT-Clinical Center | 3 | 2 | 66.7 | 0.1 | CLOSED | Dr. Thomas Moore | Dr. Sarah Smith | 2026-06-27 | 2026-07-27 |  | 2026-08-26 |  | 2026-09-14 |  | 2026-09-26 |  | 2026-10-08 |  | 2027-01-11 |  | 2027-03-15 |  | 2029-07-17 |  | 2029-09-10 |  | 2029-12-29 |  | 2030-02-10 |  | 2030-03-01
6068 | ST-2024-013 | South Korea | S0009 | SOUT-General Hospital | 3 | 3 | 100 | 0.3 | SCREENING | Dr. Christopher Davis | Dr. Amanda Moore | 2026-06-27 | 2026-07-25 |  | 2026-08-22 |  | 2026-09-14 |  | 2026-09-28 |  | 2026-10-09 |  | 2027-01-09 |  | 2027-03-06 |  | 2029-07-19 |  | 2029-09-13 |  | 2030-01-10 |  | 2030-02-23 |  | 2030-03-19
6069 | ST-2024-013 | South Korea | S0010 | SOUT-General Hospital | 3 | 0 | 0 | 0 | SCREENING | Dr. David Anderson | Dr. Christopher Garcia | 2026-06-29 | 2026-07-27 |  | 2026-08-28 |  | 2026-09-22 |  | 2026-10-04 |  | 2026-10-19 |  | 2027-01-04 |  | 2027-02-28 |  | 2029-07-26 |  | 2029-09-16 |  | 2030-01-03 |  | 2030-02-17 |  | 2030-03-12
6070 | ST-2024-013 | Chile | S0011 | CHIL-Cancer Center | -7 | -7 | 100 | -0.7 | SCREENING | Dr. Thomas Harris | Dr. Robert Johnson | 2026-06-25 | 2026-07-26 |  | 2026-08-25 |  | 2026-09-16 |  | 2026-10-01 |  | 2026-10-15 |  | 2026-12-25 |  | 2027-02-21 |  | 2029-07-04 |  | 2029-09-01 |  | 2029-12-16 |  | 2030-01-29 |  | 2030-02-19
6071 | ST-2024-013 | Chile | S0012 | CHIL-University Hospital | 3 | 2 | 66.7 | 0.2 | CLOSED | Dr. Sarah Anderson | Dr. Nicole Moore | 2026-06-24 | 2026-07-26 |  | 2026-08-24 |  | 2026-09-15 |  | 2026-09-30 |  | 2026-10-17 |  | 2026-12-29 |  | 2027-02-24 |  | 2029-07-14 |  | 2029-09-06 |  | 2029-12-18 |  | 2030-02-03 |  | 2030-02-26
6072 | ST-2024-013 | Chile | S0013 | CHIL-Research Institute | 3 | 2 | 66.7 | 0.3 | CLOSED | Dr. Thomas Thompson | Dr. Lisa Garcia | 2026-07-05 | 2026-08-06 |  | 2026-09-05 |  | 2026-09-22 |  | 2026-10-07 |  | 2026-10-22 |  | 2027-01-03 |  | 2027-02-26 |  | 2029-07-14 |  | 2029-09-04 |  | 2029-12-26 |  | 2030-02-03 |  | 2030-02-23
6073 | ST-2024-013 | Chile | S0014 | CHIL-Health System | 3 | 2 | 66.7 | 0.3 | CLOSED | Dr. Jennifer White | Dr. Michelle Moore | 2026-06-22 | 2026-07-24 |  | 2026-08-17 |  | 2026-09-12 |  | 2026-09-29 |  | 2026-10-14 |  | 2027-01-23 |  | 2027-03-26 |  | 2029-07-27 |  | 2029-09-21 |  | 2030-01-10 |  | 2030-02-26 |  | 2030-03-21
6074 | ST-2024-013 | Chile | S0015 | CHIL-Clinical Center | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. Lisa Miller | Dr. Thomas Taylor | 2026-06-24 | 2026-07-19 |  | 2026-08-20 |  | 2026-09-15 |  | 2026-10-02 |  | 2026-10-13 |  | 2027-01-13 |  | 2027-03-05 |  | 2029-07-21 |  | 2029-09-12 |  | 2029-12-31 |  | 2030-02-14 |  | 2030-03-06
6075 | ST-2024-014 | Mexico | S0001 | MEXI-Health System | -14 | -14 | 100 | -1.8 | ENROLLING | Dr. Jennifer Garcia | Dr. Robert Martin | 2024-09-08 | 2024-10-08 | 2024-10-05 | 2024-11-03 | 2024-10-22 | 2024-11-22 | 2024-11-26 | 2024-12-08 | 2024-11-24 | 2024-12-21 | 2024-12-26 | 2025-03-14 | 2025-03-16 | 2025-05-11 | 2025-05-09 | 2027-10-06 |  | 2027-12-06 |  | 2028-03-31 |  | 2028-05-13 |  | 2028-06-05
6076 | ST-2024-014 | Mexico | S0002 | MEXI-Research Institute | 3 | 2 | 66.7 | 0.3 | ENROLLING | Dr. Nicole Davis | Dr. Michael Wilson | 2024-09-12 | 2024-10-09 | 2024-09-25 | 2024-11-01 | 2024-10-25 | 2024-11-22 | 2024-11-21 | 2024-12-07 | 2024-12-15 | 2024-12-18 | 2024-12-22 | 2025-03-16 | 2025-03-14 | 2025-05-15 | 2025-05-21 | 2027-10-08 |  | 2027-12-03 |  | 2028-04-03 |  | 2028-05-14 |  | 2028-06-07
6077 | ST-2024-014 | Mexico | S0003 | MEXI-Research Institute | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. David Thompson | Dr. Amanda Jackson | 2024-09-05 | 2024-10-04 | 2024-10-16 | 2024-11-02 | 2024-10-30 | 2024-11-24 | 2024-12-06 | 2024-12-09 | 2024-12-08 | 2024-12-21 | 2024-12-11 | 2025-03-27 | 2025-03-22 | 2025-05-17 | 2025-05-30 | 2027-10-08 |  | 2027-11-30 |  | 2028-04-06 |  | 2028-05-21 |  | 2028-06-11
6078 | ST-2024-014 | Mexico | S0004 | MEXI-Clinical Center | 3 | 5 | 166.7 | 0.4 | ENROLLING | Dr. Sarah Taylor | Dr. Emily Thompson | 2024-09-01 | 2024-09-24 | 2024-09-14 | 2024-10-18 | 2024-10-24 | 2024-11-13 | 2024-11-24 | 2024-11-24 | 2024-11-23 | 2024-12-06 | 2024-12-19 | 2025-04-06 | 2025-04-06 | 2025-06-08 | 2025-06-22 | 2027-10-17 |  | 2027-12-17 |  | 2028-04-18 |  | 2028-05-27 |  | 2028-06-14
6079 | ST-2024-014 | Canada | S0005 | CANA-Health System | -4 | -4 | 100 | -0.2 | ENROLLING | Dr. Daniel Wilson | Dr. Charles Davis | 2024-09-20 | 2024-10-19 | 2024-10-10 | 2024-11-20 | 2024-11-19 | 2024-12-08 | 2024-12-13 | 2024-12-22 | 2024-12-08 | 2025-01-06 | 2025-01-10 | 2025-03-16 | 2025-03-17 | 2025-05-12 | 2025-05-25 | 2027-10-14 |  | 2027-12-11 |  | 2028-03-26 |  | 2028-05-07 |  | 2028-05-26
6080 | ST-2024-014 | Canada | S0006 | CANA-Health System | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Amanda Martin | Dr. Nicole Smith | 2024-09-22 | 2024-10-23 | 2024-10-27 | 2024-11-19 | 2024-11-20 | 2024-12-11 | 2024-12-19 | 2024-12-26 | 2024-12-14 | 2025-01-10 | 2024-12-31 | 2025-03-21 | 2025-03-30 | 2025-05-09 | 2025-05-18 | 2027-10-07 |  | 2027-12-06 |  | 2028-04-02 |  | 2028-05-14 |  | 2028-06-01
6081 | ST-2024-014 | Canada | S0007 | CANA-Health System | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Jennifer Davis | Dr. Michael Thompson | 2024-09-24 | 2024-10-21 | 2024-10-28 | 2024-11-20 | 2024-11-27 | 2024-12-14 | 2024-12-02 | 2024-12-25 | 2025-01-01 | 2025-01-09 | 2025-01-15 | 2025-04-02 | 2025-04-05 | 2025-05-30 | 2025-06-10 | 2027-10-11 |  | 2027-12-04 |  | 2028-04-05 |  | 2028-05-22 |  | 2028-06-14
6082 | ST-2024-014 | Canada | S0008 | CANA-General Hospital | 3 | 4 | 133.3 | 0.4 | ENROLLING | Dr. Robert Garcia | Dr. Jennifer Thomas | 2024-09-20 | 2024-10-13 | 2024-10-10 | 2024-11-10 | 2024-11-21 | 2024-12-04 | 2024-11-29 | 2024-12-21 | 2024-12-16 | 2025-01-01 | 2024-12-23 | 2025-04-01 | 2025-03-19 | 2025-05-27 | 2025-06-04 | 2027-10-24 |  | 2027-12-21 |  | 2028-04-13 |  | 2028-05-25 |  | 2028-06-15
6083 | ST-2024-014 | United States | S0009 | UNIT-Clinical Center | 2 | 1 | 50 | 0.1 | SCREENING | Dr. Emily Martin | Dr. Nicole Martin | 2024-09-17 | 2024-10-14 | 2024-10-25 | 2024-11-15 | 2024-11-24 | 2024-12-05 | 2024-12-10 | 2024-12-16 | 2024-12-02 | 2025-01-01 | 2024-12-27 | 2025-03-28 | 2025-03-29 | 2025-05-25 | 2025-05-13 | 2027-10-10 |  | 2027-12-09 |  | 2028-03-18 |  | 2028-05-04 |  | 2028-05-24
6084 | ST-2024-014 | United States | S0010 | UNIT-University Hospital | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. Stephanie Smith | Dr. Lisa Johnson | 2024-09-07 | 2024-10-04 | 2024-10-08 | 2024-10-31 | 2024-11-09 | 2024-11-18 | 2024-11-08 | 2024-12-03 | 2024-12-10 | 2024-12-16 | 2024-12-16 | 2025-03-28 | 2025-03-25 | 2025-05-29 | 2025-06-09 | 2027-10-15 |  | 2027-12-05 |  | 2028-03-22 |  | 2028-05-07 |  | 2028-05-26
6085 | ST-2024-014 | Poland | S0011 | POLA-General Hospital | -10 | -10 | 100 | -1.7 | ON_HOLD | Dr. Jessica Williams | Dr. David Harris | 2024-09-29 | 2024-10-25 | 2024-10-15 | 2024-11-24 | 2024-12-06 | 2024-12-12 | 2024-12-13 | 2024-12-29 | 2025-01-08 | 2025-01-13 | 2025-01-12 | 2025-04-11 | 2025-04-21 | 2025-05-30 | 2025-05-28 | 2027-10-19 |  | 2027-12-10 |  | 2028-03-25 |  | 2028-05-10 |  | 2028-06-03
6086 | ST-2024-014 | Poland | S0012 | POLA-Health System | 3 | 3 | 100 | 0.2 | SCREENING | Dr. Jennifer Davis | Dr. Stephanie Jones | 2024-09-24 | 2024-10-27 | 2024-10-18 | 2024-11-21 | 2024-11-21 | 2024-12-10 | 2024-12-08 | 2024-12-25 | 2024-12-26 | 2025-01-10 | 2025-01-05 | 2025-04-14 | 2025-04-15 | 2025-06-07 | 2025-06-16 | 2027-10-17 |  | 2027-12-17 |  | 2028-03-30 |  | 2028-05-07 |  | 2028-05-25
6087 | ST-2024-014 | Poland | S0013 | POLA-Cancer Center | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Daniel Wilson | Dr. Jennifer Taylor | 2024-10-01 | 2024-11-01 | 2024-10-27 | 2024-11-27 | 2024-12-08 | 2024-12-19 | 2024-12-19 | 2025-01-04 | 2025-01-02 | 2025-01-20 | 2025-01-27 | 2025-04-17 | 2025-04-13 | 2025-06-12 | 2025-06-14 | 2027-10-31 |  | 2027-12-23 |  | 2028-04-13 |  | 2028-05-26 |  | 2028-06-13
6088 | ST-2024-014 | Poland | S0014 | POLA-Clinical Center | 3 | 2 | 66.7 | 0.1 | ON_HOLD | Dr. Michael Davis | Dr. Charles Jackson | 2024-09-17 | 2024-10-11 | 2024-10-05 | 2024-11-11 | 2024-11-22 | 2024-12-07 | 2024-11-26 | 2024-12-20 | 2024-12-14 | 2025-01-06 | 2025-01-12 | 2025-04-20 | 2025-04-24 | 2025-06-17 | 2025-06-15 | 2027-11-13 |  | 2028-01-13 |  | 2028-04-12 |  | 2028-05-24 |  | 2028-06-13
6089 | ST-2024-014 | Poland | S0015 | POLA-University Hospital | 3 | 3 | 100 | 0.4 | ENROLLING | Dr. David Thompson | Dr. Daniel White | 2024-09-27 | 2024-10-23 | 2024-10-30 | 2024-11-25 | 2024-11-11 | 2024-12-20 | 2025-01-01 | 2025-01-06 | 2024-12-25 | 2025-01-18 | 2025-01-04 | 2025-04-23 | 2025-04-22 | 2025-06-16 | 2025-06-05 | 2027-11-10 |  | 2028-01-02 |  | 2028-04-14 |  | 2028-05-29 |  | 2028-06-16
6090 | ST-2024-014 | Poland | S0016 | POLA-Cancer Center | 3 | 4 | 133.3 | 0.5 | ON_HOLD | Dr. Emily Garcia | Dr. Nicole Johnson | 2024-09-27 | 2024-10-27 | 2024-11-01 | 2024-11-24 | 2024-12-01 | 2024-12-13 | 2024-12-27 | 2024-12-29 | 2025-01-10 | 2025-01-11 | 2025-01-03 | 2025-04-25 | 2025-04-30 | 2025-06-16 | 2025-06-22 | 2027-11-06 |  | 2027-12-27 |  | 2028-04-24 |  | 2028-06-01 |  | 2028-06-19
6091 | ST-2024-014 | Norway | S0017 | NORW-Medical Center | -4 | -4 | 100 | -0.2 | CLOSED | Dr. Stephanie Thompson | Dr. Stephanie Thomas | 2024-09-29 | 2024-10-23 | 2024-10-14 | 2024-11-24 | 2024-11-18 | 2024-12-12 | 2024-12-07 | 2024-12-26 | 2024-12-26 | 2025-01-11 | 2025-01-18 | 2025-04-22 | 2025-04-10 | 2025-06-24 | 2025-06-30 | 2027-11-08 |  | 2028-01-07 |  | 2028-03-23 |  | 2028-04-30 |  | 2028-05-23
6092 | ST-2024-014 | Norway | S0018 | NORW-Cancer Center | 3 | 3 | 100 | 0.5 | CLOSED | Dr. Daniel White | Dr. Lisa Martin | 2024-10-02 | 2024-10-31 | 2024-10-18 | 2024-12-03 | 2024-11-27 | 2024-12-24 | 2025-01-05 | 2025-01-06 | 2024-12-31 | 2025-01-18 | 2025-01-09 | 2025-04-26 | 2025-04-26 | 2025-06-15 | 2025-06-03 | 2027-11-06 |  | 2027-12-27 |  | 2028-03-31 |  | 2028-05-13 |  | 2028-06-02
6093 | ST-2024-014 | Norway | S0019 | NORW-Cancer Center | 3 | 2 | 66.7 | 0.1 | ON_HOLD | Dr. Amanda Brown | Dr. Stephanie Jones | 2024-10-12 | 2024-11-07 | 2024-11-13 | 2024-12-09 | 2024-11-28 | 2024-12-31 | 2024-12-31 | 2025-01-12 | 2025-01-20 | 2025-01-28 | 2025-01-22 | 2025-04-26 | 2025-04-15 | 2025-06-15 | 2025-06-02 | 2027-11-09 |  | 2028-01-07 |  | 2028-04-05 |  | 2028-05-15 |  | 2028-06-06
6094 | ST-2024-014 | Norway | S0020 | NORW-Research Institute | 3 | 0 | 0 | 0 | SCREENING | Dr. Michael Anderson | Dr. Michelle White | 2024-10-07 | 2024-11-03 | 2024-10-24 | 2024-12-03 | 2024-12-11 | 2024-12-19 | 2024-12-15 | 2025-01-02 | 2025-01-16 | 2025-01-14 | 2025-01-12 | 2025-04-27 | 2025-05-01 | 2025-06-25 | 2025-06-11 | 2027-11-05 |  | 2027-12-26 |  | 2028-04-07 |  | 2028-05-20 |  | 2028-06-09
6095 | ST-2024-014 | Netherlands | S0021 | NETH-Health System | -1 | -1 | 100 | -0.2 | ON_HOLD | Dr. David Taylor | Dr. Stephanie Thomas | 2024-10-13 | 2024-11-12 | 2024-11-10 | 2024-12-12 | 2024-12-20 | 2025-01-03 | 2025-01-15 | 2025-01-17 | 2025-01-27 | 2025-02-03 | 2025-02-04 | 2025-04-15 | 2025-04-04 | 2025-06-15 | 2025-06-19 | 2027-11-02 |  | 2027-12-24 |  | 2028-03-31 |  | 2028-05-10 |  | 2028-05-28
6096 | ST-2024-014 | Netherlands | S0022 | NETH-Medical Center | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. William Wilson | Dr. Michelle White | 2024-10-06 | 2024-11-03 | 2024-11-15 | 2024-12-06 | 2024-12-06 | 2024-12-26 | 2025-01-05 | 2025-01-09 | 2025-01-19 | 2025-01-20 | 2025-01-15 | 2025-04-19 | 2025-04-25 | 2025-06-17 | 2025-06-09 | 2027-10-27 |  | 2027-12-22 |  | 2028-04-05 |  | 2028-05-17 |  | 2028-06-04
6097 | ST-2024-014 | Netherlands | S0023 | NETH-Health System | 3 | 0 | 0 | 0 | CLOSED | Dr. William Jackson | Dr. David White | 2024-10-01 | 2024-10-30 | 2024-11-13 | 2024-12-02 | 2024-12-08 | 2024-12-21 | 2024-12-21 | 2025-01-03 | 2025-01-12 | 2025-01-19 | 2025-01-11 | 2025-04-16 | 2025-04-06 | 2025-06-18 | 2025-06-05 | 2027-10-28 |  | 2027-12-28 |  | 2028-04-03 |  | 2028-05-17 |  | 2028-06-04
6098 | ST-2024-014 | Denmark | S0024 | DENM-Medical Center | -10 | -10 | 100 | -0.6 | SCREENING | Dr. Christopher Garcia | Dr. Emily Miller | 2024-10-13 | 2024-11-14 | 2024-11-25 | 2024-12-10 | 2024-12-10 | 2025-01-02 | 2024-12-19 | 2025-01-16 | 2025-01-03 | 2025-01-27 | 2025-01-23 | 2025-04-18 | 2025-04-05 | 2025-06-14 | 2025-06-10 | 2027-11-08 |  | 2028-01-02 |  | 2028-04-04 |  | 2028-05-19 |  | 2028-06-12
6099 | ST-2024-014 | Denmark | S0025 | DENM-Health System | 3 | 3 | 100 | 0.2 | ON_HOLD | Dr. Michelle Johnson | Dr. Jennifer Jackson | 2024-10-02 | 2024-10-31 | 2024-11-04 | 2024-11-24 | 2024-11-17 | 2024-12-13 | 2024-12-01 | 2024-12-30 | 2024-12-17 | 2025-01-15 | 2025-01-24 | 2025-04-22 | 2025-04-12 | 2025-06-18 | 2025-06-19 | 2027-11-11 |  | 2028-01-11 |  | 2028-04-11 |  | 2028-05-20 |  | 2028-06-12
6100 | ST-2024-014 | Denmark | S0026 | DENM-General Hospital | 3 | 2 | 66.7 | 0.3 | SCREENING | Dr. Robert Martin | Dr. Stephanie Williams | 2024-10-09 | 2024-11-10 | 2024-11-21 | 2024-12-03 | 2024-11-22 | 2024-12-22 | 2024-12-22 | 2025-01-07 | 2025-01-12 | 2025-01-23 | 2025-01-14 | 2025-04-19 | 2025-05-01 | 2025-06-07 | 2025-06-11 | 2027-11-11 |  | 2028-01-11 |  | 2028-04-08 |  | 2028-05-19 |  | 2028-06-12
6101 | ST-2024-014 | Denmark | S0027 | DENM-Medical Center | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Amanda Williams | Dr. Sarah Jackson | 2024-10-15 | 2024-11-08 | 2024-11-20 | 2024-12-02 | 2024-12-11 | 2024-12-25 | 2025-01-01 | 2025-01-09 | 2025-01-07 | 2025-01-26 | 2025-01-22 | 2025-04-22 | 2025-04-11 | 2025-06-13 | 2025-06-20 | 2027-11-06 |  | 2027-12-30 |  | 2028-04-10 |  | 2028-05-22 |  | 2028-06-15
6102 | ST-2024-014 | Denmark | S0028 | DENM-Clinical Center | 3 | 3 | 100 | 0.2 | CLOSED | Dr. Daniel Anderson | Dr. Sarah Garcia | 2024-10-04 | 2024-11-01 | 2024-11-09 | 2024-11-27 | 2024-11-24 | 2024-12-13 | 2024-12-16 | 2024-12-28 | 2024-12-19 | 2025-01-09 | 2025-01-09 | 2025-05-01 | 2025-04-24 | 2025-06-20 | 2025-06-24 | 2027-11-19 |  | 2028-01-13 |  | 2028-04-19 |  | 2028-06-01 |  | 2028-06-20
6103 | ST-2024-014 | Denmark | S0029 | DENM-General Hospital | 3 | 0 | 0 | 0 | ON_HOLD | Dr. James Miller | Dr. Daniel Anderson | 2024-10-03 | 2024-11-05 | 2024-10-24 | 2024-12-07 | 2024-12-15 | 2024-12-29 | 2025-01-04 | 2025-01-15 | 2025-01-19 | 2025-01-27 | 2025-02-10 | 2025-04-17 | 2025-04-12 | 2025-06-19 | 2025-06-18 | 2027-11-16 |  | 2028-01-07 |  | 2028-04-08 |  | 2028-05-15 |  | 2028-06-03
6104 | ST-2024-014 | Taiwan | S0030 | TAIW-Medical Center | -7 | -7 | 100 | -0.7 | ON_HOLD | Dr. Amanda Jackson | Dr. Charles Miller | 2024-11-15 | 2024-12-15 | 2024-12-23 | 2025-01-09 | 2024-12-27 | 2025-01-28 | 2025-02-02 | 2025-02-09 | 2025-01-31 | 2025-02-25 | 2025-03-05 | 2025-05-16 | 2025-05-17 | 2025-07-12 | 2025-07-17 | 2027-12-14 |  | 2028-02-09 |  | 2028-03-20 |  | 2028-04-28 |  | 2028-05-20
6105 | ST-2024-014 | Taiwan | S0031 | TAIW-Health System | 3 | 2 | 66.7 | 0.3 | CLOSED | Dr. Michael Williams | Dr. Michelle Anderson | 2024-11-13 | 2024-12-10 | 2024-12-23 | 2025-01-07 | 2025-01-17 | 2025-01-29 | 2025-02-01 | 2025-02-09 | 2025-02-11 | 2025-02-24 | 2025-02-17 | 2025-05-22 | 2025-05-22 | 2025-07-13 | 2025-07-23 | 2027-12-15 |  | 2028-02-12 |  | 2028-03-25 |  | 2028-05-10 |  | 2028-05-30
6106 | ST-2024-014 | Taiwan | S0032 | TAIW-General Hospital | 3 | 2 | 66.7 | 0.1 | CLOSED | Dr. Amanda Thomas | Dr. William Davis | 2024-11-06 | 2024-12-03 | 2024-12-10 | 2024-12-26 | 2024-12-13 | 2025-01-14 | 2025-01-01 | 2025-01-25 | 2025-01-31 | 2025-02-11 | 2025-02-08 | 2025-05-24 | 2025-05-19 | 2025-07-22 | 2025-07-14 | 2027-12-30 |  | 2028-02-26 |  | 2028-04-03 |  | 2028-05-12 |  | 2028-05-31
6107 | ST-2024-014 | Taiwan | S0033 | TAIW-Health System | 3 | 3 | 100 | 0.3 | ON_HOLD | Dr. Charles Smith | Dr. William Garcia | 2024-11-08 | 2024-12-10 | 2024-12-12 | 2025-01-09 | 2024-12-29 | 2025-01-25 | 2025-01-13 | 2025-02-05 | 2025-02-19 | 2025-02-21 | 2025-02-14 | 2025-05-25 | 2025-06-03 | 2025-07-27 | 2025-07-27 | 2027-12-28 |  | 2028-02-19 |  | 2028-04-01 |  | 2028-05-08 |  | 2028-05-29
6108 | ST-2024-014 | Taiwan | S0034 | TAIW-Clinical Center | 3 | 0 | 0 | 0 | SCREENING | Dr. Michelle Williams | Dr. Daniel Anderson | 2024-11-08 | 2024-12-07 | 2024-12-06 | 2025-01-02 | 2025-01-15 | 2025-01-28 | 2025-01-20 | 2025-02-10 | 2025-02-08 | 2025-02-22 | 2025-03-08 | 2025-06-13 | 2025-06-06 | 2025-08-02 | 2025-07-21 | 2028-01-01 |  | 2028-02-24 |  | 2028-04-07 |  | 2028-05-17 |  | 2028-06-09
6109 | ST-2024-015 | Canada | S0001 | CANA-Health System | 7 | 7 | 100 | 0.6 | ON_HOLD | Dr. Lisa Garcia | Dr. Charles Jackson | 2025-05-18 | 2025-06-10 | 2025-06-02 | 2025-07-09 | 2025-07-15 | 2025-07-27 | 2025-07-24 | 2025-08-08 | 2025-08-02 | 2025-08-23 | 2025-08-15 | 2025-11-26 | 2025-11-22 | 2026-01-16 | 2026-01-06 | 2027-11-22 |  | 2028-01-17 |  | 2028-05-17 |  | 2028-06-30 |  | 2028-07-23
6110 | ST-2024-015 | Canada | S0002 | CANA-University Hospital | 7 | 5 | 71.4 | 0.5 | SCREENING | Dr. Stephanie Davis | Dr. Daniel Wilson | 2025-05-20 | 2025-06-12 | 2025-06-17 | 2025-07-09 | 2025-06-30 | 2025-07-27 | 2025-08-07 | 2025-08-07 | 2025-08-18 | 2025-08-24 | 2025-08-30 | 2025-11-28 | 2025-12-03 | 2026-01-23 | 2026-02-06 | 2027-11-24 |  | 2028-01-16 |  | 2028-05-22 |  | 2028-07-01 |  | 2028-07-21
6111 | ST-2024-015 | Canada | S0003 | CANA-Research Institute | 7 | 0 | 0 | 0 | CLOSED | Dr. Michelle Wilson | Dr. Stephanie Miller | 2025-05-19 | 2025-06-14 | 2025-05-31 | 2025-07-08 | 2025-07-17 | 2025-07-30 | 2025-07-29 | 2025-08-16 | 2025-08-25 | 2025-08-31 | 2025-09-13 | 2025-12-02 | 2025-11-25 | 2026-02-02 | 2026-01-26 | 2027-11-25 |  | 2028-01-24 |  | 2028-05-28 |  | 2028-07-11 |  | 2028-07-31
6112 | ST-2024-015 | Canada | S0004 | CANA-Cancer Center | 6 | 0 | 0 | 0 | SCREENING | Dr. Robert Anderson | Dr. Emily Harris | 2025-05-20 | 2025-06-15 | 2025-06-17 | 2025-07-17 | 2025-07-15 | 2025-08-04 | 2025-08-05 | 2025-08-19 | 2025-08-30 | 2025-08-30 | 2025-09-10 | 2025-12-06 | 2025-12-14 | 2026-01-24 | 2026-02-05 | 2027-11-27 |  | 2028-01-24 |  | 2028-06-03 |  | 2028-07-10 |  | 2028-07-31
6113 | ST-2024-015 | Mexico | S0005 | MEXI-University Hospital | 8 | 0 | 0 | 0 | SCREENING | Dr. Robert Johnson | Dr. Michelle Smith | 2025-05-18 | 2025-06-13 | 2025-06-06 | 2025-07-07 | 2025-07-13 | 2025-07-31 | 2025-07-19 | 2025-08-17 | 2025-08-03 | 2025-08-28 | 2025-08-29 | 2025-11-24 | 2025-12-01 | 2026-01-23 | 2026-01-18 | 2027-11-26 |  | 2028-01-19 |  | 2028-05-08 |  | 2028-06-19 |  | 2028-07-09
6114 | ST-2024-015 | Mexico | S0006 | MEXI-University Hospital | 5 | 0 | 0 | 0 | ON_HOLD | Dr. William Jones | Dr. Christopher Smith | 2025-05-18 | 2025-06-19 | 2025-06-19 | 2025-07-21 | 2025-07-29 | 2025-08-06 | 2025-08-12 | 2025-08-20 | 2025-08-06 | 2025-09-03 | 2025-09-16 | 2025-11-28 | 2025-12-04 | 2026-01-18 | 2026-01-06 | 2027-12-06 |  | 2028-02-01 |  | 2028-05-11 |  | 2028-06-22 |  | 2028-07-15
6115 | ST-2024-015 | Sweden | S0007 | SWED-Research Institute | 7 | 0 | 0 | 0 | SCREENING | Dr. Sarah Wilson | Dr. Charles Williams | 2025-06-05 | 2025-07-03 | 2025-06-25 | 2025-08-03 | 2025-08-14 | 2025-08-19 | 2025-08-26 | 2025-09-01 | 2025-08-20 | 2025-09-15 | 2025-09-20 | 2025-12-12 | 2025-12-26 | 2026-02-03 | 2026-01-30 | 2027-12-14 |  | 2028-02-12 |  | 2028-05-21 |  | 2028-07-06 |  | 2028-07-30
6116 | ST-2024-015 | Sweden | S0008 | SWED-Health System | 5 | 0 | 0 | 0 | SCREENING | Dr. David Wilson | Dr. Charles Smith | 2025-05-25 | 2025-06-25 | 2025-06-16 | 2025-07-28 | 2025-08-03 | 2025-08-18 | 2025-08-21 | 2025-08-29 | 2025-09-06 | 2025-09-09 | 2025-08-28 | 2025-12-12 | 2025-12-15 | 2026-02-04 | 2026-02-12 | 2027-12-16 |  | 2028-02-14 |  | 2028-05-19 |  | 2028-06-30 |  | 2028-07-20
6117 | ST-2024-015 | Sweden | S0009 | SWED-Medical Center | 7 | 0 | 0 | 0 | CLOSED | Dr. Lisa Jackson | Dr. Christopher Davis | 2025-05-27 | 2025-06-24 | 2025-06-21 | 2025-07-20 | 2025-08-03 | 2025-08-13 | 2025-08-07 | 2025-08-24 | 2025-08-26 | 2025-09-09 | 2025-09-16 | 2025-12-19 | 2025-12-18 | 2026-02-17 | 2026-02-11 | 2027-12-27 |  | 2028-02-25 |  | 2028-05-28 |  | 2028-07-07 |  | 2028-07-27
6118 | ST-2024-015 | Sweden | S0010 | SWED-General Hospital | 6 | 0 | 0 | 0 | SCREENING | Dr. Christopher Brown | Dr. Daniel Miller | 2025-05-30 | 2025-06-27 | 2025-06-27 | 2025-07-27 | 2025-08-01 | 2025-08-19 | 2025-08-16 | 2025-09-03 | 2025-09-14 | 2025-09-18 | 2025-09-25 | 2025-12-20 | 2025-12-28 | 2026-02-08 | 2026-02-19 | 2027-12-17 |  | 2028-02-14 |  | 2028-05-30 |  | 2028-07-14 |  | 2028-08-03
6119 | ST-2024-015 | Sweden | S0011 | SWED-Clinical Center | 6 | 0 | 0 | 0 | CLOSED | Dr. Jessica Taylor | Dr. Jennifer Johnson | 2025-06-08 | 2025-07-02 | 2025-06-26 | 2025-07-28 | 2025-07-17 | 2025-08-20 | 2025-08-28 | 2025-08-31 | 2025-08-21 | 2025-09-11 | 2025-09-12 | 2026-01-03 | 2025-12-24 | 2026-03-07 | 2026-03-20 | 2028-01-02 |  | 2028-02-26 |  | 2028-06-11 |  | 2028-07-19 |  | 2028-08-07
6120 | ST-2024-015 | Norway | S0012 | NORW-Clinical Center | 12 | 0 | 0 | 0 | ON_HOLD | Dr. David Thomas | Dr. Sarah Miller | 2025-05-31 | 2025-06-23 | 2025-06-29 | 2025-07-20 | 2025-07-06 | 2025-08-11 | 2025-08-06 | 2025-08-27 | 2025-08-19 | 2025-09-11 | 2025-08-30 | 2025-12-13 | 2025-11-29 | 2026-02-02 | 2026-02-15 | 2027-12-06 |  | 2028-01-31 |  | 2028-05-16 |  | 2028-06-29 |  | 2028-07-22
6121 | ST-2024-015 | Norway | S0013 | NORW-Medical Center | 10 | 0 | 0 | 0 | CLOSED | Dr. Stephanie Taylor | Dr. James Garcia | 2025-06-03 | 2025-07-04 | 2025-07-12 | 2025-08-06 | 2025-08-08 | 2025-08-27 | 2025-09-08 | 2025-09-10 | 2025-09-13 | 2025-09-25 | 2025-09-25 | 2025-12-10 | 2025-12-10 | 2026-02-07 | 2026-02-02 | 2027-12-15 |  | 2028-02-09 |  | 2028-05-23 |  | 2028-07-08 |  | 2028-07-31
6122 | ST-2024-015 | Switzerland | S0014 | SWIT-General Hospital | 8 | 0 | 0 | 0 | SCREENING | Dr. Amanda Williams | Dr. Lisa Garcia | 2025-07-04 | 2025-07-31 | 2025-07-31 | 2025-08-25 | 2025-08-16 | 2025-09-14 | 2025-09-19 | 2025-09-26 | 2025-09-17 | 2025-10-10 | 2025-10-18 | 2026-01-01 | 2026-01-04 | 2026-02-23 | 2026-02-18 | 2028-01-05 |  | 2028-02-25 |  | 2028-05-12 |  | 2028-06-23 |  | 2028-07-13
6123 | ST-2024-015 | Switzerland | S0015 | SWIT-Clinical Center | 6 | 0 | 0 | 0 | CLOSED | Dr. Thomas Johnson | Dr. Sarah Thomas | 2025-06-22 | 2025-07-25 | 2025-07-16 | 2025-08-19 | 2025-08-11 | 2025-09-06 | 2025-09-09 | 2025-09-18 | 2025-09-26 | 2025-09-29 | 2025-09-16 | 2025-12-30 | 2026-01-06 | 2026-02-22 | 2026-02-18 | 2028-01-05 |  | 2028-02-27 |  | 2028-05-20 |  | 2028-06-30 |  | 2028-07-20
6124 | ST-2024-015 | Switzerland | S0016 | SWIT-General Hospital | 5 | 0 | 0 | 0 | CLOSED | Dr. Michelle Brown | Dr. Robert Martin | 2025-06-22 | 2025-07-20 | 2025-07-10 | 2025-08-19 | 2025-08-19 | 2025-09-12 | 2025-09-08 | 2025-09-24 | 2025-09-14 | 2025-10-09 | 2025-09-25 | 2026-01-14 | 2026-01-23 | 2026-03-05 | 2026-03-08 | 2028-01-21 |  | 2028-03-12 |  | 2028-05-30 |  | 2028-07-13 |  | 2028-08-06
6125 | ST-2024-015 | Switzerland | S0017 | SWIT-University Hospital | 4 | 0 | 0 | 0 | CLOSED | Dr. Amanda Harris | Dr. David Smith | 2025-06-25 | 2025-07-28 | 2025-07-17 | 2025-08-24 | 2025-09-02 | 2025-09-16 | 2025-09-17 | 2025-09-29 | 2025-10-13 | 2025-10-16 | 2025-10-03 | 2026-01-26 | 2026-01-16 | 2026-03-26 | 2026-04-02 | 2028-01-16 |  | 2028-03-16 |  | 2028-06-07 |  | 2028-07-19 |  | 2028-08-11
6126 | ST-2024-015 | India | S0018 | INDI-Medical Center | 12 | 0 | 0 | 0 | CLOSED | Dr. Christopher Moore | Dr. Jessica Moore | 2025-06-22 | 2025-07-15 | 2025-07-07 | 2025-08-13 | 2025-08-17 | 2025-09-07 | 2025-09-09 | 2025-09-24 | 2025-09-17 | 2025-10-06 | 2025-10-17 | 2026-01-03 | 2026-01-13 | 2026-02-26 | 2026-02-20 | 2028-01-02 |  | 2028-02-27 |  | 2028-05-09 |  | 2028-06-24 |  | 2028-07-17
6127 | ST-2024-015 | India | S0019 | INDI-General Hospital | 8 | 0 | 0 | 0 | SCREENING | Dr. Jennifer Moore | Dr. Amanda Taylor | 2025-06-19 | 2025-07-20 | 2025-07-22 | 2025-08-19 | 2025-08-06 | 2025-09-14 | 2025-09-21 | 2025-09-30 | 2025-09-27 | 2025-10-11 | 2025-10-09 | 2026-01-07 | 2025-12-28 | 2026-03-03 | 2026-03-11 | 2028-01-07 |  | 2028-03-05 |  | 2028-05-17 |  | 2028-07-02 |  | 2028-07-24
6128 | ST-2024-016 | United States | S0001 | UNIT-Cancer Center | 5 | 3 | 60 | 0.4 | ON_HOLD | Dr. Michelle Miller | Dr. Nicole Jackson | 2024-08-20 | 2024-09-18 | 2024-10-02 | 2024-10-16 | 2024-10-16 | 2024-11-01 | 2024-11-10 | 2024-11-14 | 2024-11-13 | 2024-11-27 | 2024-12-08 | 2025-02-26 | 2025-02-26 | 2025-04-20 | 2025-04-15 | 2027-04-09 |  | 2027-06-07 |  | 2027-09-20 |  | 2027-10-30 |  | 2027-11-22
6129 | ST-2024-016 | United States | S0002 | UNIT-General Hospital | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Michelle Thompson | Dr. Lisa Davis | 2024-08-26 | 2024-09-24 | 2024-09-26 | 2024-10-23 | 2024-10-19 | 2024-11-10 | 2024-10-29 | 2024-11-27 | 2024-12-01 | 2024-12-12 | 2024-12-22 | 2025-03-05 | 2025-03-03 | 2025-04-24 | 2025-04-12 | 2027-04-07 |  | 2027-05-31 |  | 2027-09-26 |  | 2027-11-09 |  | 2027-12-03
6130 | ST-2024-016 | United States | S0003 | UNIT-Medical Center | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. Thomas Williams | Dr. Emily White | 2024-08-25 | 2024-09-21 | 2024-09-19 | 2024-10-20 | 2024-10-15 | 2024-11-07 | 2024-11-10 | 2024-11-22 | 2024-11-23 | 2024-12-06 | 2024-11-23 | 2025-03-08 | 2025-03-20 | 2025-05-05 | 2025-05-17 | 2027-04-18 |  | 2027-06-10 |  | 2027-09-26 |  | 2027-11-04 |  | 2027-11-28
6131 | ST-2024-016 | United States | S0004 | UNIT-Clinical Center | 4 | 4 | 100 | 0.4 | ON_HOLD | Dr. David Taylor | Dr. Amanda Smith | 2024-08-24 | 2024-09-20 | 2024-09-26 | 2024-10-20 | 2024-11-01 | 2024-11-13 | 2024-11-19 | 2024-11-29 | 2024-11-30 | 2024-12-13 | 2024-12-02 | 2025-03-07 | 2025-03-13 | 2025-04-25 | 2025-05-02 | 2027-04-25 |  | 2027-06-15 |  | 2027-10-02 |  | 2027-11-12 |  | 2027-12-02
6132 | ST-2024-016 | United States | S0005 | UNIT-Cancer Center | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Amanda Harris | Dr. Robert Harris | 2024-08-21 | 2024-09-15 | 2024-09-12 | 2024-10-15 | 2024-10-19 | 2024-11-10 | 2024-11-11 | 2024-11-22 | 2024-11-26 | 2024-12-03 | 2024-12-02 | 2025-03-20 | 2025-04-02 | 2025-05-20 | 2025-05-14 | 2027-05-02 |  | 2027-06-29 |  | 2027-10-16 |  | 2027-12-01 |  | 2027-12-24
6133 | ST-2024-016 | Canada | S0006 | CANA-Research Institute | 5 | 3 | 60 | 0.4 | SCREENING | Dr. Michael Brown | Dr. Sarah Davis | 2024-09-05 | 2024-09-29 | 2024-09-25 | 2024-10-27 | 2024-10-27 | 2024-11-20 | 2024-12-04 | 2024-12-06 | 2024-12-14 | 2024-12-21 | 2024-12-11 | 2025-03-09 | 2025-03-06 | 2025-05-10 | 2025-05-01 | 2027-04-04 |  | 2027-05-27 |  | 2027-09-30 |  | 2027-11-06 |  | 2027-11-25
6134 | ST-2024-016 | Canada | S0007 | CANA-Health System | 12 | 14 | 116.7 | 1.8 | ENROLLING | Dr. James Taylor | Dr. Emily Anderson | 2024-09-03 | 2024-10-02 | 2024-10-08 | 2024-11-04 | 2024-10-26 | 2024-11-25 | 2024-12-05 | 2024-12-06 | 2024-11-25 | 2024-12-19 | 2024-12-24 | 2025-03-15 | 2025-03-25 | 2025-05-11 | 2025-05-02 | 2027-04-12 |  | 2027-06-03 |  | 2027-10-01 |  | 2027-11-10 |  | 2027-12-04
6135 | ST-2024-016 | Germany | S0008 | GERM-Clinical Center | 1 | 0 | 0 | 0 | ON_HOLD | Dr. Robert Smith | Dr. Charles Thompson | 2024-09-23 | 2024-10-21 | 2024-11-02 | 2024-11-23 | 2024-11-13 | 2024-12-13 | 2024-11-29 | 2024-12-26 | 2024-12-16 | 2025-01-11 | 2025-01-13 | 2025-03-23 | 2025-03-18 | 2025-05-22 | 2025-05-19 | 2027-04-14 |  | 2027-06-05 |  | 2027-10-03 |  | 2027-11-18 |  | 2027-12-08
6136 | ST-2024-016 | Germany | S0009 | GERM-Medical Center | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Sarah Anderson | Dr. David Wilson | 2024-09-16 | 2024-10-14 | 2024-10-26 | 2024-11-08 | 2024-11-10 | 2024-11-25 | 2024-12-08 | 2024-12-07 | 2024-12-10 | 2024-12-19 | 2024-12-27 | 2025-03-26 | 2025-03-29 | 2025-05-17 | 2025-05-25 | 2027-04-28 |  | 2027-06-21 |  | 2027-10-09 |  | 2027-11-24 |  | 2027-12-17
6137 | ST-2024-016 | Germany | S0010 | GERM-Medical Center | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. James Williams | Dr. Charles Wilson | 2024-09-11 | 2024-10-10 | 2024-10-07 | 2024-11-09 | 2024-10-30 | 2024-11-26 | 2024-12-08 | 2024-12-07 | 2024-12-07 | 2024-12-24 | 2025-01-07 | 2025-03-26 | 2025-03-31 | 2025-05-28 | 2025-05-30 | 2027-04-21 |  | 2027-06-18 |  | 2027-10-12 |  | 2027-11-22 |  | 2027-12-15
6138 | ST-2024-016 | Germany | S0011 | GERM-General Hospital | 3 | 5 | 166.7 | 0.3 | SCREENING | Dr. Emily Smith | Dr. Jessica Jackson | 2024-09-15 | 2024-10-10 | 2024-10-02 | 2024-11-06 | 2024-10-27 | 2024-11-22 | 2024-11-10 | 2024-12-08 | 2024-12-07 | 2024-12-25 | 2025-01-02 | 2025-03-31 | 2025-04-10 | 2025-05-22 | 2025-06-02 | 2027-04-29 |  | 2027-06-21 |  | 2027-10-16 |  | 2027-11-26 |  | 2027-12-15
6139 | ST-2024-016 | Poland | S0012 | POLA-Medical Center | 8 | 6 | 75 | 0.5 | ON_HOLD | Dr. Michelle Williams | Dr. Jennifer Miller | 2024-09-16 | 2024-10-16 | 2024-10-05 | 2024-11-14 | 2024-11-08 | 2024-11-30 | 2024-11-17 | 2024-12-12 | 2024-11-30 | 2024-12-23 | 2024-12-18 | 2025-03-14 | 2025-03-21 | 2025-05-14 | 2025-04-30 | 2027-05-04 |  | 2027-07-02 |  | 2027-10-06 |  | 2027-11-12 |  | 2027-12-03
6140 | ST-2024-016 | Poland | S0013 | POLA-Health System | 9 | 0 | 0 | 0 | CLOSED | Dr. James Johnson | Dr. Lisa Thompson | 2024-09-28 | 2024-10-22 | 2024-10-31 | 2024-11-23 | 2024-11-17 | 2024-12-12 | 2024-12-16 | 2024-12-27 | 2024-12-24 | 2025-01-08 | 2025-01-05 | 2025-03-22 | 2025-03-13 | 2025-05-20 | 2025-06-02 | 2027-05-05 |  | 2027-06-25 |  | 2027-10-04 |  | 2027-11-12 |  | 2027-12-06
6141 | ST-2024-016 | Belgium | S0014 | BELG-Research Institute | -4 | -4 | 100 | -0.3 | SCREENING | Dr. Michelle Wilson | Dr. Lisa Jones | 2024-10-04 | 2024-11-05 | 2024-10-28 | 2024-12-01 | 2024-11-26 | 2024-12-25 | 2024-12-16 | 2025-01-09 | 2025-01-23 | 2025-01-20 | 2025-01-30 | 2025-04-02 | 2025-04-05 | 2025-06-03 | 2025-05-20 | 2027-05-15 |  | 2027-07-05 |  | 2027-09-28 |  | 2027-11-07 |  | 2027-11-30
6142 | ST-2024-016 | Belgium | S0015 | BELG-Research Institute | 3 | 3 | 100 | 0.2 | CLOSED | Dr. Robert Williams | Dr. Charles Thompson | 2024-09-24 | 2024-10-20 | 2024-10-17 | 2024-11-20 | 2024-11-18 | 2024-12-13 | 2024-12-12 | 2024-12-26 | 2024-12-18 | 2025-01-11 | 2025-01-13 | 2025-04-17 | 2025-04-10 | 2025-06-07 | 2025-06-06 | 2027-05-20 |  | 2027-07-20 |  | 2027-09-28 |  | 2027-11-06 |  | 2027-11-30
6143 | ST-2024-016 | Belgium | S0016 | BELG-General Hospital | 3 | 1 | 33.3 | 0.1 | CLOSED | Dr. Lisa White | Dr. Lisa Jones | 2024-09-28 | 2024-10-22 | 2024-10-18 | 2024-11-21 | 2024-11-22 | 2024-12-08 | 2024-11-27 | 2024-12-23 | 2024-12-21 | 2025-01-04 | 2024-12-30 | 2025-04-13 | 2025-04-13 | 2025-06-13 | 2025-06-18 | 2027-05-16 |  | 2027-07-10 |  | 2027-10-03 |  | 2027-11-09 |  | 2027-11-27
6144 | ST-2024-016 | Belgium | S0017 | BELG-Clinical Center | 3 | 0 | 0 | 0 | CLOSED | Dr. Thomas Harris | Dr. Michelle Jones | 2024-10-03 | 2024-11-02 | 2024-10-24 | 2024-11-28 | 2024-11-14 | 2024-12-22 | 2024-12-29 | 2025-01-05 | 2025-01-06 | 2025-01-18 | 2025-01-25 | 2025-05-01 | 2025-04-20 | 2025-06-25 | 2025-06-23 | 2027-05-26 |  | 2027-07-17 |  | 2027-10-14 |  | 2027-11-30 |  | 2027-12-20
6145 | ST-2024-016 | Belgium | S0018 | BELG-University Hospital | 3 | 0 | 0 | 0 | SCREENING | Dr. Michelle Miller | Dr. Robert Anderson | 2024-10-03 | 2024-11-05 | 2024-10-28 | 2024-11-29 | 2024-11-25 | 2024-12-16 | 2024-12-08 | 2024-12-28 | 2025-01-02 | 2025-01-11 | 2025-01-24 | 2025-04-24 | 2025-04-22 | 2025-06-23 | 2025-06-12 | 2027-06-01 |  | 2027-07-23 |  | 2027-10-09 |  | 2027-11-16 |  | 2027-12-06
6146 | ST-2024-016 | Belgium | S0019 | BELG-General Hospital | 3 | 0 | 0 | 0 | CLOSED | Dr. Robert White | Dr. Robert Garcia | 2024-09-29 | 2024-10-29 | 2024-11-05 | 2024-11-25 | 2024-11-30 | 2024-12-20 | 2024-12-18 | 2025-01-04 | 2025-01-05 | 2025-01-17 | 2025-01-19 | 2025-04-29 | 2025-04-23 | 2025-06-29 | 2025-06-19 | 2027-06-03 |  | 2027-08-03 |  | 2027-10-12 |  | 2027-11-23 |  | 2027-12-14
6147 | ST-2024-016 | Australia | S0020 | AUST-University Hospital | 5 | 0 | 0 | 0 | SCREENING | Dr. Thomas White | Dr. Stephanie Anderson | 2024-10-16 | 2024-11-09 | 2024-11-16 | 2024-12-06 | 2024-11-22 | 2024-12-29 | 2024-12-20 | 2025-01-12 | 2025-01-10 | 2025-01-24 | 2025-01-29 | 2025-04-20 | 2025-04-27 | 2025-06-10 | 2025-06-06 | 2027-05-24 |  | 2027-07-15 |  | 2027-09-28 |  | 2027-11-05 |  | 2027-11-26
6148 | ST-2024-016 | Australia | S0021 | AUST-Clinical Center | 5 | 0 | 0 | 0 | CLOSED | Dr. William Jones | Dr. David Brown | 2024-10-24 | 2024-11-25 | 2024-11-26 | 2024-12-19 | 2024-12-20 | 2025-01-05 | 2025-01-07 | 2025-01-21 | 2025-01-15 | 2025-02-07 | 2025-02-10 | 2025-04-21 | 2025-04-17 | 2025-06-21 | 2025-07-02 | 2027-06-03 |  | 2027-07-31 |  | 2027-10-04 |  | 2027-11-14 |  | 2027-12-07
6149 | ST-2024-016 | Australia | S0022 | AUST-University Hospital | 7 | 0 | 0 | 0 | SCREENING | Dr. William Davis | Dr. Lisa Davis | 2024-10-23 | 2024-11-15 | 2024-11-02 | 2024-12-08 | 2024-11-29 | 2024-12-30 | 2025-01-02 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2025-02-06 | 2025-04-30 | 2025-05-10 | 2025-06-23 | 2025-06-18 | 2027-06-19 |  | 2027-08-15 |  | 2027-10-18 |  | 2027-12-01 |  | 2027-12-19
6150 | ST-2024-017 | Mexico | S0001 | MEXI-Medical Center | 5 | 5 | 100 | 0.8 | ON_HOLD | Dr. Emily Miller | Dr. Stephanie White | 2024-11-15 | 2024-12-15 | 2024-12-22 | 2025-01-13 | 2025-01-16 | 2025-01-31 | 2025-02-07 | 2025-02-13 | 2025-02-16 | 2025-03-01 | 2025-03-05 | 2025-05-19 | 2025-05-20 | 2025-07-14 | 2025-07-15 | 2028-01-21 |  | 2028-03-13 |  | 2028-07-21 |  | 2028-09-06 |  | 2028-09-27
6151 | ST-2024-017 | Mexico | S0002 | MEXI-Medical Center | 4 | 2 | 50 | 0.2 | ON_HOLD | Dr. Michelle Miller | Dr. James Miller | 2024-11-15 | 2024-12-16 | 2024-12-03 | 2025-01-08 | 2024-12-25 | 2025-01-30 | 2025-02-03 | 2025-02-12 | 2025-01-30 | 2025-02-26 | 2025-02-16 | 2025-05-27 | 2025-06-08 | 2025-07-21 | 2025-07-18 | 2028-01-23 |  | 2028-03-24 |  | 2028-07-22 |  | 2028-09-01 |  | 2028-09-21
6152 | ST-2024-017 | Mexico | S0003 | MEXI-General Hospital | 5 | 1 | 20 | 0.1 | ON_HOLD | Dr. Michael Anderson | Dr. Jessica Thompson | 2024-11-24 | 2024-12-26 | 2025-01-02 | 2025-01-18 | 2025-01-11 | 2025-02-13 | 2025-02-06 | 2025-02-26 | 2025-02-19 | 2025-03-12 | 2025-03-18 | 2025-05-22 | 2025-05-17 | 2025-07-16 | 2025-07-20 | 2028-01-22 |  | 2028-03-18 |  | 2028-07-26 |  | 2028-09-06 |  | 2028-09-24
6153 | ST-2024-017 | Mexico | S0004 | MEXI-Health System | 4 | 0 | 0 | 0 | SCREENING | Dr. Emily Taylor | Dr. Thomas Jackson | 2024-11-24 | 2024-12-18 | 2024-12-17 | 2025-01-14 | 2025-01-18 | 2025-01-31 | 2025-02-02 | 2025-02-13 | 2025-02-27 | 2025-02-25 | 2025-02-24 | 2025-05-21 | 2025-05-15 | 2025-07-17 | 2025-07-03 | 2028-01-22 |  | 2028-03-13 |  | 2028-07-27 |  | 2028-09-12 |  | 2028-10-06
6154 | ST-2024-017 | Mexico | S0005 | MEXI-General Hospital | 5 | 0 | 0 | 0 | CLOSED | Dr. James Garcia | Dr. David Taylor | 2024-11-22 | 2024-12-15 | 2024-12-11 | 2025-01-12 | 2025-01-13 | 2025-02-03 | 2025-02-05 | 2025-02-18 | 2025-03-01 | 2025-03-04 | 2025-03-14 | 2025-06-09 | 2025-06-16 | 2025-08-06 | 2025-08-02 | 2028-02-01 |  | 2028-03-30 |  | 2028-08-04 |  | 2028-09-20 |  | 2028-10-09
6155 | ST-2024-017 | Spain | S0006 | SPAI-Cancer Center | -3 | -3 | 100 | -0.2 | CLOSED | Dr. Sarah Thompson | Dr. Jessica Taylor | 2024-11-17 | 2024-12-15 | 2024-12-02 | 2025-01-13 | 2025-01-08 | 2025-02-01 | 2025-02-05 | 2025-02-15 | 2025-02-13 | 2025-03-03 | 2025-03-14 | 2025-06-10 | 2025-06-03 | 2025-08-10 | 2025-08-15 | 2028-01-27 |  | 2028-03-26 |  | 2028-07-12 |  | 2028-08-22 |  | 2028-09-11
6156 | ST-2024-017 | Spain | S0007 | SPAI-Health System | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. David Taylor | Dr. Amanda Williams | 2024-11-14 | 2024-12-16 | 2024-12-13 | 2025-01-09 | 2025-01-20 | 2025-02-03 | 2025-01-22 | 2025-02-16 | 2025-02-22 | 2025-03-01 | 2025-03-13 | 2025-06-04 | 2025-05-30 | 2025-08-01 | 2025-08-03 | 2028-02-13 |  | 2028-04-12 |  | 2028-07-22 |  | 2028-09-03 |  | 2028-09-22
6157 | ST-2024-017 | Spain | S0008 | SPAI-University Hospital | 3 | 1 | 33.3 | 0.1 | SCREENING | Dr. Thomas Jackson | Dr. Michelle Garcia | 2024-11-19 | 2024-12-22 | 2024-12-25 | 2025-01-22 | 2025-01-13 | 2025-02-12 | 2025-02-26 | 2025-02-24 | 2025-02-10 | 2025-03-10 | 2025-03-16 | 2025-06-15 | 2025-06-23 | 2025-08-07 | 2025-08-09 | 2028-02-16 |  | 2028-04-15 |  | 2028-07-28 |  | 2028-09-13 |  | 2028-10-07
6158 | ST-2024-017 | Spain | S0009 | SPAI-Health System | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Brown | Dr. Jessica Taylor | 2024-11-22 | 2024-12-22 | 2025-01-01 | 2025-01-17 | 2025-01-16 | 2025-02-12 | 2025-02-16 | 2025-03-01 | 2025-03-10 | 2025-03-17 | 2025-03-23 | 2025-06-23 | 2025-06-10 | 2025-08-15 | 2025-08-17 | 2028-02-28 |  | 2028-04-29 |  | 2028-08-05 |  | 2028-09-20 |  | 2028-10-14
6159 | ST-2024-017 | Spain | S0010 | SPAI-General Hospital | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Williams | Dr. Nicole Davis | 2024-11-20 | 2024-12-15 | 2024-12-27 | 2025-01-10 | 2024-12-29 | 2025-01-28 | 2025-02-03 | 2025-02-13 | 2025-02-05 | 2025-03-01 | 2025-03-14 | 2025-06-21 | 2025-06-20 | 2025-08-13 | 2025-08-07 | 2028-02-20 |  | 2028-04-17 |  | 2028-07-27 |  | 2028-09-07 |  | 2028-10-01
6160 | ST-2024-017 | Spain | S0011 | SPAI-Research Institute | 3 | 0 | 0 | 0 | ON_HOLD | Dr. David Thompson | Dr. Jessica Garcia | 2024-11-23 | 2024-12-18 | 2024-12-29 | 2025-01-14 | 2025-01-26 | 2025-02-09 | 2025-02-04 | 2025-02-24 | 2025-02-24 | 2025-03-08 | 2025-03-09 | 2025-07-04 | 2025-07-07 | 2025-08-25 | 2025-08-24 | 2028-02-27 |  | 2028-04-20 |  | 2028-08-12 |  | 2028-09-18 |  | 2028-10-07
6161 | ST-2024-017 | China | S0012 | CHIN-Health System | 4 | 0 | 0 | 0 | ON_HOLD | Dr. Robert Brown | Dr. Daniel Jones | 2024-11-29 | 2024-12-22 | 2024-12-28 | 2025-01-17 | 2025-01-30 | 2025-02-04 | 2025-01-22 | 2025-02-17 | 2025-02-26 | 2025-03-01 | 2025-03-02 | 2025-05-26 | 2025-06-06 | 2025-07-18 | 2025-07-04 | 2028-02-04 |  | 2028-03-30 |  | 2028-07-20 |  | 2028-09-03 |  | 2028-09-22
6162 | ST-2024-017 | China | S0013 | CHIN-University Hospital | 5 | 0 | 0 | 0 | SCREENING | Dr. Christopher Jackson | Dr. Daniel Brown | 2024-11-29 | 2024-12-23 | 2024-12-21 | 2025-01-20 | 2025-02-01 | 2025-02-14 | 2025-02-23 | 2025-02-27 | 2025-03-11 | 2025-03-16 | 2025-03-06 | 2025-05-29 | 2025-05-22 | 2025-07-31 | 2025-07-20 | 2028-01-31 |  | 2028-03-27 |  | 2028-07-22 |  | 2028-09-07 |  | 2028-09-25
6163 | ST-2024-017 | China | S0014 | CHIN-Medical Center | 5 | 0 | 0 | 0 | SCREENING | Dr. Michael Taylor | Dr. Christopher Johnson | 2024-11-23 | 2024-12-17 | 2024-12-22 | 2025-01-17 | 2025-01-06 | 2025-02-12 | 2025-02-22 | 2025-03-01 | 2025-03-12 | 2025-03-16 | 2025-03-12 | 2025-06-17 | 2025-06-13 | 2025-08-19 | 2025-08-31 | 2028-02-10 |  | 2028-04-05 |  | 2028-07-27 |  | 2028-09-03 |  | 2028-09-22
6164 | ST-2024-017 | China | S0015 | CHIN-Medical Center | 5 | 0 | 0 | 0 | CLOSED | Dr. Jessica Smith | Dr. Jessica Miller | 2024-11-21 | 2024-12-17 | 2024-12-21 | 2025-01-15 | 2025-01-02 | 2025-02-03 | 2025-02-04 | 2025-02-15 | 2025-02-18 | 2025-02-26 | 2025-02-23 | 2025-06-12 | 2025-06-20 | 2025-08-03 | 2025-07-23 | 2028-02-11 |  | 2028-04-09 |  | 2028-07-31 |  | 2028-09-10 |  | 2028-10-04
6165 | ST-2024-017 | China | S0016 | CHIN-Research Institute | 3 | 0 | 0 | 0 | SCREENING | Dr. Jessica Wilson | Dr. Michelle Taylor | 2024-11-21 | 2024-12-21 | 2024-12-27 | 2025-01-23 | 2025-02-06 | 2025-02-11 | 2025-02-16 | 2025-02-24 | 2025-02-11 | 2025-03-13 | 2025-03-25 | 2025-06-24 | 2025-07-03 | 2025-08-14 | 2025-08-21 | 2028-02-12 |  | 2028-04-10 |  | 2028-07-30 |  | 2028-09-09 |  | 2028-09-27
6166 | ST-2024-017 | China | S0017 | CHIN-Cancer Center | 3 | 0 | 0 | 0 | CLOSED | Dr. Emily Wilson | Dr. Robert Garcia | 2024-11-15 | 2024-12-18 | 2024-12-31 | 2025-01-13 | 2025-01-06 | 2025-02-02 | 2025-02-15 | 2025-02-17 | 2025-02-17 | 2025-03-03 | 2025-03-01 | 2025-06-29 | 2025-06-15 | 2025-08-27 | 2025-08-25 | 2028-03-04 |  | 2028-04-29 |  | 2028-08-19 |  | 2028-09-26 |  | 2028-10-18
6167 | ST-2024-018 | United States | S0001 | UNIT-Health System | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Jennifer Harris | Dr. Daniel White | 2021-12-21 | 2022-01-17 | 2022-01-31 | 2022-02-13 | 2022-02-24 | 2022-03-02 | 2022-03-12 | 2022-03-19 | 2022-03-25 | 2022-04-05 | 2022-04-04 | 2022-06-23 | 2022-07-04 | 2022-08-15 | 2022-08-02 | 2024-07-27 | 2024-07-21 | 2024-09-18 | 2024-10-01 | 2025-01-23 | 2025-01-11 | 2025-03-11 | 2025-03-23 | 2025-03-31 | 2025-04-10
6168 | ST-2024-018 | United States | S0002 | UNIT-Health System | 4 | 4 | 100 | 0.3 | ENROLLING | Dr. Amanda Davis | Dr. Jennifer White | 2021-12-14 | 2022-01-12 | 2022-01-11 | 2022-02-09 | 2022-02-14 | 2022-03-03 | 2022-03-12 | 2022-03-20 | 2022-04-01 | 2022-03-31 | 2022-04-03 | 2022-07-10 | 2022-07-19 | 2022-08-30 | 2022-08-26 | 2024-08-11 | 2024-08-11 | 2024-10-05 | 2024-10-13 | 2025-01-31 | 2025-01-17 | 2025-03-10 | 2025-03-20 | 2025-03-30 | 2025-03-17
6169 | ST-2024-018 | United States | S0003 | UNIT-Health System | 3 | 4 | 133.3 | 0.7 | SCREENING | Dr. Nicole Davis | Dr. Daniel Wilson | 2021-12-09 | 2022-01-11 | 2021-12-31 | 2022-02-10 | 2022-02-01 | 2022-03-08 | 2022-03-01 | 2022-03-20 | 2022-03-22 | 2022-03-31 | 2022-04-08 | 2022-07-06 | 2022-07-16 | 2022-08-27 | 2022-09-08 | 2024-08-13 | 2024-08-19 | 2024-10-07 | 2024-10-17 | 2025-01-31 | 2025-01-21 | 2025-03-18 | 2025-03-31 | 2025-04-05 | 2025-04-10
6170 | ST-2024-018 | Denmark | S0004 | DENM-Medical Center | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Amanda Brown | Dr. Nicole Williams | 2021-12-27 | 2022-01-24 | 2022-01-19 | 2022-02-23 | 2022-02-15 | 2022-03-18 | 2022-03-06 | 2022-04-04 | 2022-04-03 | 2022-04-20 | 2022-04-17 | 2022-06-28 | 2022-06-19 | 2022-08-20 | 2022-08-18 | 2024-08-12 | 2024-08-26 | 2024-10-12 | 2024-10-10 | 2025-01-30 | 2025-02-11 | 2025-03-13 | 2025-03-27 | 2025-04-06 | 2025-04-10
6171 | ST-2024-018 | Denmark | S0005 | DENM-University Hospital | 3 | 4 | 133.3 | 0.2 | SCREENING | Dr. Daniel Wilson | Dr. Christopher Thompson | 2021-12-15 | 2022-01-15 | 2022-01-13 | 2022-02-17 | 2022-02-22 | 2022-03-14 | 2022-03-13 | 2022-03-30 | 2022-04-04 | 2022-04-11 | 2022-04-05 | 2022-07-13 | 2022-07-03 | 2022-09-01 | 2022-08-20 | 2024-08-20 | 2024-08-17 | 2024-10-13 | 2024-10-04 | 2025-01-28 | 2025-02-01 | 2025-03-08 | 2025-02-25 | 2025-03-26 | 2025-03-12
6172 | ST-2024-018 | South Korea | S0006 | SOUT-Research Institute | -4 | -4 | 100 | -0.3 | ENROLLING | Dr. Thomas Moore | Dr. James Martin | 2021-12-29 | 2022-01-28 | 2022-01-18 | 2022-03-02 | 2022-03-01 | 2022-03-25 | 2022-04-07 | 2022-04-05 | 2022-03-28 | 2022-04-17 | 2022-04-22 | 2022-07-07 | 2022-06-29 | 2022-08-28 | 2022-09-09 | 2024-08-03 | 2024-07-29 | 2024-09-27 | 2024-10-06 | 2025-01-27 | 2025-02-03 | 2025-03-12 | 2025-03-04 | 2025-04-02 | 2025-04-01
6173 | ST-2024-018 | South Korea | S0007 | SOUT-Clinical Center | 3 | 1 | 33.3 | 0.1 | ENROLLING | Dr. Thomas White | Dr. Amanda Anderson | 2022-01-04 | 2022-01-29 | 2022-02-04 | 2022-02-21 | 2022-02-21 | 2022-03-13 | 2022-03-01 | 2022-03-26 | 2022-03-12 | 2022-04-07 | 2022-04-08 | 2022-07-08 | 2022-06-28 | 2022-09-02 | 2022-09-15 | 2024-08-17 | 2024-08-13 | 2024-10-10 | 2024-10-18 | 2025-01-31 | 2025-01-29 | 2025-03-18 | 2025-03-25 | 2025-04-10 | 2025-04-02
6174 | ST-2024-018 | South Korea | S0008 | SOUT-Research Institute | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Jessica Wilson | Dr. Sarah Martin | 2022-01-03 | 2022-02-01 | 2022-02-06 | 2022-03-05 | 2022-03-12 | 2022-03-25 | 2022-04-05 | 2022-04-05 | 2022-04-10 | 2022-04-16 | 2022-04-24 | 2022-07-15 | 2022-07-24 | 2022-09-02 | 2022-09-13 | 2024-08-11 | 2024-07-29 | 2024-10-06 | 2024-09-22 | 2025-02-06 | 2025-01-31 | 2025-03-22 | 2025-03-24 | 2025-04-11 | 2025-04-16
6175 | ST-2024-018 | South Korea | S0009 | SOUT-Health System | 3 | 3 | 100 | 0.4 | SCREENING | Dr. Sarah Anderson | Dr. James Anderson | 2021-12-29 | 2022-01-31 | 2022-02-14 | 2022-02-28 | 2022-02-28 | 2022-03-18 | 2022-03-08 | 2022-04-02 | 2022-03-21 | 2022-04-13 | 2022-04-09 | 2022-07-17 | 2022-07-25 | 2022-09-06 | 2022-09-08 | 2024-08-16 | 2024-08-15 | 2024-10-08 | 2024-09-28 | 2025-02-12 | 2025-02-06 | 2025-03-28 | 2025-03-17 | 2025-04-17 | 2025-04-13
6176 | ST-2024-018 | South Korea | S0010 | SOUT-Clinical Center | 3 | 6 | 200 | 0.9 | ENROLLING | Dr. Daniel Williams | Dr. William Wilson | 2021-12-25 | 2022-01-24 | 2022-01-23 | 2022-02-20 | 2022-03-06 | 2022-03-13 | 2022-03-04 | 2022-03-27 | 2022-03-23 | 2022-04-09 | 2022-04-18 | 2022-07-19 | 2022-07-20 | 2022-09-20 | 2022-09-30 | 2024-08-13 | 2024-08-03 | 2024-10-12 | 2024-10-15 | 2025-02-05 | 2025-02-18 | 2025-03-22 | 2025-03-29 | 2025-04-11 | 2025-04-17
6177 | ST-2024-019 | Mexico | S0001 | MEXI-University Hospital | 25 | 0 | 0 | 0 | ON_HOLD | Dr. David Brown | Dr. Christopher Wilson | 2024-11-15: 2026-07-07; 2024-12-15: 2026-08-02; 2025-01-13: 2026-08-27; 2025-01-31: 2026-09-12; 2025-02-13: 2026-09-24; 2025-03-01: 2026-10-06; 2025-05-19: 2027-01-17; 2025-07-14: 2027-03-14; 2028-01-21: 2028-12-15 |  | 2029-02-06 |  | 2029-06-16 |  | 2029-07-29 |  | 2029-08-16
6178 | ST-2024-019 | Mexico | S0002 | MEXI-Medical Center | 14 | 0 | 0 | 0 | SCREENING | Dr. Michael Wilson | Dr. Christopher Smith | 2024-11-15: 2026-07-21; 2024-12-15: 2026-08-20; 2025-01-13: 2026-09-12; 2025-01-31: 2026-10-05; 2025-02-13: 2026-10-18; 2025-03-01: 2026-11-03; 2025-05-19: 2027-02-01; 2025-07-14: 2027-03-29; 2028-01-21: 2028-12-25 |  | 2029-02-21 |  | 2029-06-17 |  | 2029-07-26 |  | 2029-08-13
6179 | ST-2024-019 | United States | S0003 | UNIT-Health System | 19 | 0 | 0 | 0 | ON_HOLD | Dr. Nicole White | Dr. Charles Williams | 2024-11-15: 2026-07-14; 2024-12-15: 2026-08-10; 2025-01-13: 2026-09-04; 2025-01-31: 2026-09-22; 2025-02-13: 2026-10-08; 2025-03-01: 2026-10-23; 2025-05-19: 2027-01-31; 2025-07-14: 2027-03-25; 2028-01-21: 2028-12-22 |  | 2029-02-21 |  | 2029-06-23 |  | 2029-08-02 |  | 2029-08-24
6180 | ST-2024-019 | United States | S0004 | UNIT-Health System | 7 | 0 | 0 | 0 | SCREENING | Dr. Charles Martin | Dr. Emily Moore | 2024-11-15: 2026-07-11; 2024-12-15: 2026-08-11; 2025-01-13: 2026-09-12; 2025-01-31: 2026-09-30; 2025-02-13: 2026-10-14; 2025-03-01: 2026-10-25; 2025-05-19: 2027-01-28; 2025-07-14: 2027-03-30; 2028-01-21: 2028-12-27 |  | 2029-02-26 |  | 2029-06-22 |  | 2029-08-03 |  | 2029-08-21
6181 | ST-2024-019 | United States | S0005 | UNIT-Research Institute | 13 | 0 | 0 | 0 | CLOSED | Dr. Jessica Jackson | Dr. Sarah Williams | 2024-11-15: 2026-07-21; 2024-12-15: 2026-08-14; 2025-01-13: 2026-09-12; 2025-01-31: 2026-10-03; 2025-02-13: 2026-10-18; 2025-03-01: 2026-10-29; 2025-05-19: 2027-02-07; 2025-07-14: 2027-04-02; 2028-01-21: 2028-12-22 |  | 2029-02-11 |  | 2029-06-22 |  | 2029-08-05 |  | 2029-08-29
6182 | ST-2024-019 | United States | S0006 | UNIT-Research Institute | 17 | 0 | 0 | 0 | ON_HOLD | Dr. Michael Harris | Dr. Jessica Miller | 2024-11-15: 2026-07-18; 2024-12-15: 2026-08-17; 2025-01-13: 2026-09-19; 2025-01-31: 2026-10-09; 2025-02-13: 2026-10-24; 2025-03-01: 2026-11-09; 2025-05-19: 2027-02-04; 2025-07-14: 2027-03-30; 2028-01-21: 2028-12-30 |  | 2029-03-01 |  | 2029-07-10 |  | 2029-08-23 |  | 2029-09-12
6183 | ST-2024-019 | United States | S0007 | UNIT-University Hospital | 13 | 0 | 0 | 0 | SCREENING | Dr. Charles Miller | Dr. Jessica Jackson | 2024-11-15: 2026-07-22; 2024-12-15: 2026-08-23; 2025-01-13: 2026-09-17; 2025-01-31: 2026-10-06; 2025-02-13: 2026-10-23; 2025-03-01: 2026-11-03; 2025-05-19: 2027-02-26; 2025-07-14: 2027-04-26; 2028-01-21: 2029-01-13 |  | 2029-03-10 |  | 2029-07-11 |  | 2029-08-18 |  | 2029-09-09
6184 | ST-2024-019 | Poland | S0008 | POLA-General Hospital | 24 | 0 | 0 | 0 | SCREENING | Dr. Sarah Miller | Dr. James Davis | 2024-11-15: 2026-07-28; 2024-12-15: 2026-08-21; 2025-01-13: 2026-09-19; 2025-01-31: 2026-10-09; 2025-02-13: 2026-10-21; 2025-03-01: 2026-11-02; 2025-05-19: 2027-02-09; 2025-07-14: 2027-04-12; 2028-01-21: 2029-01-08 |  | 2029-03-01 |  | 2029-06-08 |  | 2029-07-18 |  | 2029-08-06
6185 | ST-2024-019 | Poland | S0009 | POLA-Clinical Center | 18 | 0 | 0 | 0 | SCREENING | Dr. Michelle Anderson | Dr. Nicole Moore | 2024-11-15: 2026-07-28; 2024-12-15: 2026-08-24; 2025-01-13: 2026-09-26; 2025-01-31: 2026-10-22; 2025-02-13: 2026-11-03; 2025-03-01: 2026-11-14; 2025-05-19: 2027-02-05; 2025-07-14: 2027-04-02; 2028-01-21: 2029-01-18 |  | 2029-03-16 |  | 2029-06-16 |  | 2029-08-02 |  | 2029-08-24
6186 | ST-2024-019 | Poland | S0010 | POLA-Cancer Center | 13 | 0 | 0 | 0 | ON_HOLD | Dr. James Johnson | Dr. Thomas Johnson | 2024-11-15: 2026-08-01; 2024-12-15: 2026-08-25; 2025-01-13: 2026-09-22; 2025-01-31: 2026-10-16; 2025-02-13: 2026-10-28; 2025-03-01: 2026-11-11; 2025-05-19: 2027-02-09; 2025-07-14: 2027-04-13; 2028-01-21: 2029-01-13 |  | 2029-03-12 |  | 2029-06-17 |  | 2029-08-02 |  | 2029-08-24
6187 | ST-2024-019 | Denmark | S0011 | DENM-University Hospital | 33 | 0 | 0 | 0 | CLOSED | Dr. Daniel Harris | Dr. Michelle Jones | 2024-11-15: 2026-08-08; 2024-12-15: 2026-09-06; 2025-01-13: 2026-10-04; 2025-01-31: 2026-10-29; 2025-02-13: 2026-11-10; 2025-03-01: 2026-11-24; 2025-05-19: 2027-02-19; 2025-07-14: 2027-04-15; 2028-01-21: 2029-01-02 |  | 2029-02-22 |  | 2029-06-14 |  | 2029-07-26 |  | 2029-08-16
6188 | ST-2024-019 | Denmark | S0012 | DENM-General Hospital | 46 | 0 | 0 | 0 | SCREENING | Dr. Michael Johnson | Dr. Robert Martin | 2024-11-15: 2026-08-06; 2024-12-15: 2026-09-08; 2025-01-13: 2026-10-03; 2025-01-31: 2026-10-26; 2025-02-13: 2026-11-10; 2025-03-01: 2026-11-26; 2025-05-19: 2027-02-24; 2025-07-14: 2027-04-22; 2028-01-21: 2029-01-07 |  | 2029-03-03 |  | 2029-06-18 |  | 2029-07-31 |  | 2029-08-18
6189 | ST-2024-019 | United Kingdom | S0013 | UNIT-Medical Center | 40 | 0 | 0 | 0 | CLOSED | Dr. Robert Smith | Dr. Jennifer Johnson | 2024-11-15: 2026-08-15; 2024-12-15: 2026-09-11; 2025-01-13: 2026-10-06; 2025-01-31: 2026-10-24; 2025-02-13: 2026-11-09; 2025-03-01: 2026-11-22; 2025-05-19: 2027-02-25; 2025-07-14: 2027-04-18; 2028-01-21: 2029-01-22 |  | 2029-03-20 |  | 2029-06-19 |  | 2029-08-04 |  | 2029-08-22
6190 | ST-2024-019 | United Kingdom | S0014 | UNIT-Research Institute | 32 | 0 | 0 | 0 | SCREENING | Dr. Christopher Garcia | Dr. Michael Brown | 2024-11-15: 2026-08-22; 2024-12-15: 2026-09-14; 2025-01-13: 2026-10-15; 2025-01-31: 2026-11-01; 2025-02-13: 2026-11-16; 2025-03-01: 2026-11-30; 2025-05-19: 2027-02-23; 2025-07-14: 2027-04-14; 2028-01-21: 2029-01-26 |  | 2029-03-28 |  | 2029-06-29 |  | 2029-08-09 |  | 2029-08-29
6191 | ST-2024-019 | Australia | S0015 | AUST-Medical Center | 14 | 0 | 0 | 0 | CLOSED | Dr. Michelle Jones | Dr. Thomas Miller | 2024-11-15: 2026-07-27; 2024-12-15: 2026-08-27; 2025-01-13: 2026-09-19; 2025-01-31: 2026-10-06; 2025-02-13: 2026-10-22; 2025-03-01: 2026-11-07; 2025-05-19: 2027-02-14; 2025-07-14: 2027-04-06; 2028-01-21: 2029-01-16 |  | 2029-03-10 |  | 2029-06-15 |  | 2029-07-22 |  | 2029-08-09
6192 | ST-2024-019 | Australia | S0016 | AUST-Cancer Center | 21 | 0 | 0 | 0 | CLOSED | Dr. Jennifer Taylor | Dr. Michael Brown | 2024-11-15: 2026-08-06; 2024-12-15: 2026-09-02; 2025-01-13: 2026-09-30; 2025-01-31: 2026-10-25; 2025-02-13: 2026-11-10; 2025-03-01: 2026-11-24; 2025-05-19: 2027-02-23; 2025-07-14: 2027-04-23; 2028-01-21: 2029-01-15 |  | 2029-03-16 |  | 2029-06-17 |  | 2029-07-29 |  | 2029-08-22
6193 | ST-2024-019 | Australia | S0017 | AUST-Research Institute | 22 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Thomas | Dr. Michelle Garcia | 2024-11-15: 2026-07-29; 2024-12-15: 2026-08-23; 2025-01-13: 2026-09-16; 2025-01-31: 2026-10-11; 2025-02-13: 2026-10-24; 2025-03-01: 2026-11-10; 2025-05-19: 2027-03-01; 2025-07-14: 2027-04-20; 2028-01-21: 2029-01-22 |  | 2029-03-22 |  | 2029-06-21 |  | 2029-07-28 |  | 2029-08-18
6194 | ST-2024-019 | Australia | S0018 | AUST-Clinical Center | 11 | 0 | 0 | 0 | CLOSED | Dr. Sarah Jones | Dr. Emily Jackson | 2024-11-15: 2026-07-28; 2024-12-15: 2026-08-30; 2025-01-13: 2026-09-29; 2025-01-31: 2026-10-22; 2025-02-13: 2026-11-07; 2025-03-01: 2026-11-21; 2025-05-19: 2027-02-28; 2025-07-14: 2027-04-28; 2028-01-21: 2029-01-23 |  | 2029-03-24 |  | 2029-06-24 |  | 2029-08-04 |  | 2029-08-26
6195 | ST-2024-019 | Australia | S0019 | AUST-Cancer Center | 14 | 0 | 0 | 0 | SCREENING | Dr. Nicole Williams | Dr. James Smith | 2024-11-15: 2026-08-04; 2024-12-15: 2026-09-01; 2025-01-13: 2026-10-04; 2025-01-31: 2026-10-30; 2025-02-13: 2026-11-13; 2025-03-01: 2026-11-30; 2025-05-19: 2027-03-07; 2025-07-14: 2027-04-26; 2028-01-21: 2029-01-30 |  | 2029-03-24 |  | 2029-07-03 |  | 2029-08-12 |  | 2029-08-30
6196 | ST-2024-020 | Canada | S0001 | CANA-Cancer Center | -9 | -9 | 100 | -0.6 | CLOSED | Dr. David Davis | Dr. Thomas Thomas | 2023-07-09 | 2023-08-04 | 2023-07-23 | 2023-08-27 | 2023-08-22 | 2023-09-15 | 2023-09-25 | 2023-09-29 | 2023-09-29 | 2023-10-15 | 2023-10-05 | 2024-01-12 | 2024-01-13 | 2024-03-11 | 2024-03-10 | 2026-06-12 |  | 2026-08-08 |  | 2026-12-18 |  | 2027-02-01 |  | 2027-02-20
6197 | ST-2024-020 | Canada | S0002 | CANA-Research Institute | 3 | 2 | 66.7 | 0.1 | CLOSED | Dr. Stephanie Wilson | Dr. Sarah Williams | 2023-06-30 | 2023-07-25 | 2023-08-06 | 2023-08-24 | 2023-09-05 | 2023-09-16 | 2023-09-14 | 2023-09-30 | 2023-09-17 | 2023-10-11 | 2023-10-07 | 2024-01-25 | 2024-01-11 | 2024-03-21 | 2024-03-10 | 2026-06-20 |  | 2026-08-13 |  | 2026-12-13 |  | 2027-01-23 |  | 2027-02-14
6198 | ST-2024-020 | Canada | S0003 | CANA-Research Institute | 3 | 3 | 100 | 0.3 | ON_HOLD | Dr. Nicole Thompson | Dr. Daniel Brown | 2023-07-09 | 2023-08-07 | 2023-08-08 | 2023-09-05 | 2023-09-07 | 2023-09-28 | 2023-10-02 | 2023-10-14 | 2023-10-23 | 2023-10-29 | 2023-11-03 | 2024-01-29 | 2024-02-05 | 2024-03-29 | 2024-04-12 | 2026-06-27 |  | 2026-08-21 |  | 2026-12-18 |  | 2027-01-31 |  | 2027-02-21
6199 | ST-2024-020 | Canada | S0004 | CANA-Clinical Center | 3 | 4 | 133.3 | 0.2 | CLOSED | Dr. Michelle Anderson | Dr. Christopher Thomas | 2023-07-05 | 2023-07-31 | 2023-08-14 | 2023-08-23 | 2023-08-24 | 2023-09-16 | 2023-09-05 | 2023-09-27 | 2023-09-28 | 2023-10-11 | 2023-10-16 | 2024-02-06 | 2024-02-12 | 2024-03-31 | 2024-03-28 | 2026-07-05 |  | 2026-08-26 |  | 2026-12-30 |  | 2027-02-15 |  | 2027-03-08
6200 | ST-2024-020 | Norway | S0005 | NORW-Medical Center | -4 | -4 | 100 | -0.3 | ENROLLING | Dr. Jessica Williams | Dr. Emily Garcia | 2023-07-12 | 2023-08-04 | 2023-08-11 | 2023-08-29 | 2023-08-25 | 2023-09-18 | 2023-09-23 | 2023-10-04 | 2023-10-17 | 2023-10-16 | 2023-10-28 | 2024-01-21 | 2024-01-29 | 2024-03-15 | 2024-03-22 | 2026-06-23 |  | 2026-08-16 |  | 2026-12-13 |  | 2027-01-22 |  | 2027-02-13
6201 | ST-2024-020 | Norway | S0006 | NORW-Research Institute | 3 | 3 | 100 | 0.4 | SCREENING | Dr. Robert Martin | Dr. Robert Miller | 2023-07-20 | 2023-08-16 | 2023-08-11 | 2023-09-14 | 2023-09-22 | 2023-10-06 | 2023-10-15 | 2023-10-23 | 2023-10-11 | 2023-11-08 | 2023-11-15 | 2024-01-28 | 2024-01-29 | 2024-03-28 | 2024-03-18 | 2026-06-25 |  | 2026-08-22 |  | 2026-12-11 |  | 2027-01-26 |  | 2027-02-14
6202 | ST-2024-020 | Norway | S0007 | NORW-Health System | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Jessica White | Dr. Michelle Jones | 2023-07-08 | 2023-08-09 | 2023-08-06 | 2023-09-08 | 2023-09-22 | 2023-09-25 | 2023-09-19 | 2023-10-12 | 2023-10-09 | 2023-10-26 | 2023-11-02 | 2024-01-27 | 2024-01-18 | 2024-03-20 | 2024-03-11 | 2026-06-25 |  | 2026-08-18 |  | 2026-12-19 |  | 2027-01-25 |  | 2027-02-12
6203 | ST-2024-020 | Norway | S0008 | NORW-Clinical Center | 3 | 4 | 133.3 | 0.4 | ENROLLING | Dr. Christopher Smith | Dr. Jessica Miller | 2023-07-20 | 2023-08-20 | 2023-08-14 | 2023-09-12 | 2023-09-08 | 2023-09-29 | 2023-10-10 | 2023-10-12 | 2023-10-09 | 2023-10-26 | 2023-11-05 | 2024-02-02 | 2024-01-20 | 2024-03-31 | 2024-04-10 | 2026-07-07 |  | 2026-08-28 |  | 2026-12-31 |  | 2027-02-09 |  | 2027-03-02
6204 | ST-2024-020 | Netherlands | S0009 | NETH-General Hospital | -4 | -4 | 100 | -0.2 | ON_HOLD | Dr. Nicole Thompson | Dr. Michelle Harris | 2023-07-12 | 2023-08-06 | 2023-08-17 | 2023-09-06 | 2023-09-11 | 2023-10-01 | 2023-10-06 | 2023-10-17 | 2023-10-28 | 2023-10-28 | 2023-11-10 | 2024-01-17 | 2024-01-06 | 2024-03-06 | 2024-03-18 | 2026-06-21 |  | 2026-08-18 |  | 2026-12-16 |  | 2027-01-23 |  | 2027-02-10
6205 | ST-2024-020 | Netherlands | S0010 | NETH-Clinical Center | 3 | 2 | 66.7 | 0.2 | CLOSED | Dr. Robert Anderson | Dr. Jennifer Wilson | 2023-07-16 | 2023-08-09 | 2023-08-11 | 2023-09-03 | 2023-09-04 | 2023-09-29 | 2023-10-08 | 2023-10-10 | 2023-10-23 | 2023-10-27 | 2023-10-16 | 2024-01-14 | 2024-01-04 | 2024-03-17 | 2024-03-23 | 2026-06-17 |  | 2026-08-09 |  | 2026-12-18 |  | 2027-01-31 |  | 2027-02-24
6206 | ST-2024-020 | Netherlands | S0011 | NETH-University Hospital | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. Jessica Johnson | Dr. Robert Thomas | 2023-07-21 | 2023-08-15 | 2023-08-17 | 2023-09-08 | 2023-08-30 | 2023-09-27 | 2023-09-15 | 2023-10-11 | 2023-10-05 | 2023-10-25 | 2023-10-22 | 2024-01-26 | 2024-02-03 | 2024-03-27 | 2024-04-06 | 2026-06-15 |  | 2026-08-08 |  | 2026-12-24 |  | 2027-02-04 |  | 2027-02-24
6207 | ST-2024-020 | Netherlands | S0012 | NETH-Research Institute | 3 | 3 | 100 | 0.2 | SCREENING | Dr. Jennifer Moore | Dr. Jessica Garcia | 2023-07-18 | 2023-08-20 | 2023-08-19 | 2023-09-15 | 2023-09-29 | 2023-10-03 | 2023-10-03 | 2023-10-20 | 2023-11-02 | 2023-11-06 | 2023-11-08 | 2024-01-26 | 2024-02-06 | 2024-03-21 | 2024-03-28 | 2026-07-01 |  | 2026-08-24 |  | 2026-12-23 |  | 2027-02-04 |  | 2027-02-25
6208 | ST-2024-020 | Japan | S0013 | JAPA-Research Institute | -4 | -4 | 100 | -0.3 | ENROLLING | Dr. Christopher Wilson | Dr. Amanda Garcia | 2023-07-18 | 2023-08-17 | 2023-08-08 | 2023-09-11 | 2023-09-10 | 2023-09-27 | 2023-09-14 | 2023-10-13 | 2023-10-11 | 2023-10-30 | 2023-11-09 | 2024-02-04 | 2024-01-22 | 2024-03-25 | 2024-04-01 | 2026-07-07 |  | 2026-09-01 |  | 2026-12-16 |  | 2027-01-28 |  | 2027-02-21
6209 | ST-2024-020 | Japan | S0014 | JAPA-University Hospital | 3 | 2 | 66.7 | 0.1 | ON_HOLD | Dr. Sarah Taylor | Dr. Amanda Jones | 2023-07-20 | 2023-08-21 | 2023-08-29 | 2023-09-13 | 2023-09-16 | 2023-10-09 | 2023-10-22 | 2023-10-25 | 2023-10-20 | 2023-11-11 | 2023-11-20 | 2024-02-13 | 2024-02-22 | 2024-04-16 | 2024-04-12 | 2026-07-21 |  | 2026-09-14 |  | 2026-12-24 |  | 2027-02-05 |  | 2027-02-28
6210 | ST-2024-020 | Japan | S0015 | JAPA-Research Institute | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. Jennifer Moore | Dr. Jessica Brown | 2023-07-18 | 2023-08-14 | 2023-08-19 | 2023-09-14 | 2023-09-20 | 2023-10-09 | 2023-10-09 | 2023-10-21 | 2023-10-29 | 2023-11-06 | 2023-11-03 | 2024-02-15 | 2024-02-29 | 2024-04-11 | 2024-04-22 | 2026-07-29 |  | 2026-09-21 |  | 2027-01-01 |  | 2027-02-16 |  | 2027-03-12
6211 | ST-2024-020 | Japan | S0016 | JAPA-Medical Center | 3 | 5 | 166.7 | 0.4 | SCREENING | Dr. Robert Harris | Dr. Thomas Jones | 2023-07-24 | 2023-08-19 | 2023-08-11 | 2023-09-15 | 2023-09-03 | 2023-10-02 | 2023-10-04 | 2023-10-13 | 2023-10-16 | 2023-10-28 | 2023-10-23 | 2024-02-19 | 2024-02-21 | 2024-04-14 | 2024-04-10 | 2026-08-04 |  | 2026-09-26 |  | 2027-01-06 |  | 2027-02-20 |  | 2027-03-12
6212 | ST-2025-021 | Mexico | S0001 | MEXI-Medical Center | 9 | 5 | 55.6 | 0.5 | SCREENING | Dr. James Brown | Dr. Emily Miller | 2017-09-15 | 2017-10-08 | 2017-10-17 | 2017-10-31 | 2017-10-18 | 2017-11-24 | 2017-12-06 | 2017-12-09 | 2017-12-06 | 2017-12-22 | 2017-12-16 | 2018-03-17 | 2018-03-23 | 2018-05-18 | 2018-05-20 | 2020-10-02 | 2020-09-29 | 2020-11-26 | 2020-11-15 | 2021-03-22 | 2021-03-09 | 2021-05-06 | 2021-05-16 | 2021-05-24 | 2021-05-30
6213 | ST-2025-021 | Mexico | S0002 | MEXI-Health System | 8 | 5 | 62.5 | 0.6 | ENROLLING | Dr. Amanda Smith | Dr. Michael Jones | 2017-09-20 | 2017-10-17 | 2017-10-20 | 2017-11-18 | 2017-12-01 | 2017-12-04 | 2017-12-09 | 2017-12-18 | 2017-12-11 | 2017-12-31 | 2017-12-28 | 2018-03-24 | 2018-03-19 | 2018-05-24 | 2018-05-19 | 2020-10-08 | 2020-10-15 | 2020-12-07 | 2020-12-18 | 2021-04-01 | 2021-04-13 | 2021-05-18 | 2021-05-26 | 2021-06-10 | 2021-06-14
6214 | ST-2025-021 | Mexico | S0003 | MEXI-Cancer Center | 17 | 12 | 70.6 | 0.7 | ENROLLING | Dr. Amanda Thomas | Dr. Jennifer Thompson | 2017-09-24 | 2017-10-23 | 2017-10-31 | 2017-11-23 | 2017-11-22 | 2017-12-12 | 2017-12-24 | 2017-12-23 | 2017-12-22 | 2018-01-05 | 2017-12-24 | 2018-04-02 | 2018-03-21 | 2018-05-30 | 2018-05-17 | 2020-10-04 | 2020-10-03 | 2020-11-29 | 2020-12-13 | 2021-04-03 | 2021-03-24 | 2021-05-11 | 2021-05-12 | 2021-05-30 | 2021-05-22
6215 | ST-2025-021 | Mexico | S0004 | MEXI-Cancer Center | 14 | 26 | 185.7 | 1.5 | SCREENING | Dr. Lisa Thompson | Dr. Michael Brown | 2017-09-18 | 2017-10-21 | 2017-10-20 | 2017-11-21 | 2017-11-21 | 2017-12-13 | 2017-12-21 | 2017-12-28 | 2017-12-29 | 2018-01-12 | 2018-01-21 | 2018-04-04 | 2018-04-03 | 2018-06-04 | 2018-06-16 | 2020-10-09 | 2020-09-30 | 2020-12-03 | 2020-11-23 | 2021-04-07 | 2021-04-09 | 2021-05-21 | 2021-05-11 | 2021-06-13 | 2021-06-14
6216 | ST-2025-021 | United States | S0005 | UNIT-General Hospital | 25 | 22 | 88 | 2.4 | ENROLLING | Dr. Jennifer Moore | Dr. James Brown | 2017-09-24 | 2017-10-25 | 2017-10-30 | 2017-11-25 | 2017-12-08 | 2017-12-12 | 2017-12-11 | 2017-12-28 | 2017-12-17 | 2018-01-09 | 2017-12-29 | 2018-03-29 | 2018-03-26 | 2018-05-24 | 2018-05-28 | 2020-10-04 | 2020-09-29 | 2020-11-26 | 2020-11-13 | 2021-03-28 | 2021-03-30 | 2021-05-09 | 2021-04-29 | 2021-05-27 | 2021-05-16
6217 | ST-2025-021 | United States | S0006 | UNIT-University Hospital | 23 | 26 | 113 | 1.9 | SCREENING | Dr. Nicole Thomas | Dr. Jennifer Harris | 2017-09-27 | 2017-10-24 | 2017-11-07 | 2017-11-20 | 2017-11-15 | 2017-12-13 | 2017-12-05 | 2017-12-24 | 2017-12-15 | 2018-01-10 | 2018-01-22 | 2018-03-28 | 2018-04-06 | 2018-05-18 | 2018-05-19 | 2020-10-20 | 2020-10-06 | 2020-12-19 | 2020-12-08 | 2021-03-30 | 2021-04-02 | 2021-05-06 | 2021-05-03 | 2021-05-26 | 2021-05-14
6218 | ST-2025-021 | Belgium | S0007 | BELG-Health System | 13 | 13 | 100 | 1.4 | SCREENING | Dr. Emily Taylor | Dr. Emily Harris | 2017-10-06 | 2017-11-05 | 2017-11-15 | 2017-12-07 | 2017-11-27 | 2017-12-27 | 2017-12-29 | 2018-01-11 | 2018-01-17 | 2018-01-25 | 2018-01-25 | 2018-04-23 | 2018-05-03 | 2018-06-16 | 2018-06-16 | 2020-10-20 | 2020-10-27 | 2020-12-16 | 2020-12-16 | 2021-03-31 | 2021-03-21 | 2021-05-16 | 2021-05-29 | 2021-06-04 | 2021-06-13
6219 | ST-2025-021 | Belgium | S0008 | BELG-Medical Center | 6 | 5 | 83.3 | 0.4 | ENROLLING | Dr. Nicole Thomas | Dr. Jessica Moore | 2017-10-12 | 2017-11-13 | 2017-11-27 | 2017-12-16 | 2017-12-16 | 2018-01-10 | 2018-01-19 | 2018-01-24 | 2018-01-18 | 2018-02-07 | 2018-02-13 | 2018-04-16 | 2018-04-04 | 2018-06-18 | 2018-07-01 | 2020-10-18 | 2020-10-09 | 2020-12-13 | 2020-12-21 | 2021-04-05 | 2021-03-22 | 2021-05-12 | 2021-05-16 | 2021-06-04 | 2021-06-10
6220 | ST-2025-021 | Belgium | S0009 | BELG-General Hospital | 14 | 12 | 85.7 | 2 | ENROLLING | Dr. Thomas Martin | Dr. Emily Jackson | 2017-10-11 | 2017-11-07 | 2017-10-25 | 2017-12-08 | 2017-12-12 | 2018-01-03 | 2018-01-05 | 2018-01-14 | 2018-01-06 | 2018-01-30 | 2018-02-09 | 2018-04-29 | 2018-04-30 | 2018-06-18 | 2018-06-20 | 2020-10-23 | 2020-11-06 | 2020-12-22 | 2020-12-08 | 2021-04-13 | 2021-04-02 | 2021-05-29 | 2021-06-05 | 2021-06-22 | 2021-06-25
6221 | ST-2025-021 | Sweden | S0010 | SWED-Health System | 8 | 8 | 100 | 0.7 | ENROLLING | Dr. Stephanie Miller | Dr. Michael Martin | 2017-09-28 | 2017-10-25 | 2017-10-21 | 2017-11-20 | 2017-11-18 | 2017-12-09 | 2017-12-13 | 2017-12-26 | 2017-12-13 | 2018-01-11 | 2018-01-12 | 2018-04-20 | 2018-05-03 | 2018-06-22 | 2018-06-08 | 2020-10-21 | 2020-10-17 | 2020-12-18 | 2020-12-17 | 2021-03-20 | 2021-03-11 | 2021-05-04 | 2021-05-03 | 2021-05-26 | 2021-05-12
6222 | ST-2025-021 | Sweden | S0011 | SWED-General Hospital | 11 | 9 | 81.8 | 0.8 | ENROLLING | Dr. James Martin | Dr. Emily Jackson | 2017-10-03 | 2017-11-01 | 2017-10-20 | 2017-11-28 | 2017-11-18 | 2017-12-15 | 2017-12-10 | 2017-12-26 | 2017-12-25 | 2018-01-06 | 2018-01-13 | 2018-04-21 | 2018-04-12 | 2018-06-11 | 2018-05-29 | 2020-10-22 | 2020-10-27 | 2020-12-14 | 2020-12-10 | 2021-03-27 | 2021-03-18 | 2021-05-07 | 2021-04-23 | 2021-05-31 | 2021-06-08
6223 | ST-2025-021 | Sweden | S0012 | SWED-Clinical Center | 8 | 10 | 125 | 0.7 | SCREENING | Dr. Michael Brown | Dr. Robert Jackson | 2017-10-04 | 2017-10-28 | 2017-11-07 | 2017-11-25 | 2017-11-30 | 2017-12-13 | 2017-12-17 | 2017-12-27 | 2017-12-20 | 2018-01-09 | 2018-01-10 | 2018-04-16 | 2018-04-18 | 2018-06-10 | 2018-06-20 | 2020-10-30 | 2020-11-01 | 2020-12-21 | 2020-12-19 | 2021-03-24 | 2021-03-13 | 2021-05-03 | 2021-04-27 | 2021-05-22 | 2021-05-09
6224 | ST-2025-021 | Australia | S0013 | AUST-University Hospital | 14 | 9 | 64.3 | 1.3 | ENROLLING | Dr. David Taylor | Dr. David Jackson | 2017-10-24 | 2017-11-22 | 2017-11-29 | 2017-12-16 | 2017-12-05 | 2018-01-08 | 2018-01-01 | 2018-01-19 | 2018-01-29 | 2018-02-02 | 2018-02-05 | 2018-05-07 | 2018-05-13 | 2018-06-28 | 2018-07-09 | 2020-11-10 | 2020-10-31 | 2020-12-31 | 2020-12-26 | 2021-03-29 | 2021-04-02 | 2021-05-13 | 2021-05-12 | 2021-06-04 | 2021-06-04
6225 | ST-2025-021 | Australia | S0014 | AUST-Medical Center | 15 | 23 | 153.3 | 2.6 | ENROLLING | Dr. Nicole Wilson | Dr. William Jackson | 2017-10-26 | 2017-11-26 | 2017-11-13 | 2017-12-22 | 2017-12-08 | 2018-01-09 | 2018-01-21 | 2018-01-22 | 2018-01-22 | 2018-02-06 | 2018-02-18 | 2018-05-02 | 2018-05-07 | 2018-07-02 | 2018-06-27 | 2020-11-02 | 2020-11-08 | 2020-12-31 | 2020-12-22 | 2021-04-03 | 2021-03-20 | 2021-05-18 | 2021-05-05 | 2021-06-08 | 2021-06-09
6226 | ST-2025-022 | United States | S0001 | UNIT-Cancer Center | 0 | 0 | 0 | 0 | SCREENING | Dr. Michelle Garcia | Dr. Sarah Martin | 2022-02-03 | 2022-03-08 | 2022-03-17 | 2022-04-06 | 2022-04-09 | 2022-04-27 | 2022-05-01 | 2022-05-14 | 2022-05-02 | 2022-05-30 | 2022-05-25 | 2022-08-15 | 2022-08-03 | 2022-10-12 | 2022-10-10 | 2025-09-08 | 2025-09-16 | 2025-11-06 | 2025-10-26 | 2026-03-01 | 2026-03-13 | 2026-04-07 | 2026-03-28 | 2026-04-26 | 2026-05-05
6227 | ST-2025-022 | United States | S0002 | UNIT-Cancer Center | 3 | 2 | 66.7 | 0.3 | ENROLLING | Dr. Michael Taylor | Dr. Jessica Williams | 2022-02-03 | 2022-03-04 | 2022-03-12 | 2022-03-30 | 2022-03-30 | 2022-04-24 | 2022-04-18 | 2022-05-09 | 2022-05-02 | 2022-05-26 | 2022-06-02 | 2022-08-22 | 2022-08-18 | 2022-10-24 | 2022-10-20 | 2025-09-10 | 2025-09-02 | 2025-11-05 | 2025-11-05 | 2026-03-12 | 2026-03-17 | 2026-04-22 | 2026-04-18 | 2026-05-16 | 2026-05-02
6228 | ST-2025-022 | United States | S0003 | UNIT-Clinical Center | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. Michael Jackson | Dr. Robert Davis | 2022-02-01 | 2022-03-06 | 2022-03-14 | 2022-03-29 | 2022-03-30 | 2022-04-23 | 2022-05-03 | 2022-05-07 | 2022-05-05 | 2022-05-18 | 2022-05-21 | 2022-09-08 | 2022-08-27 | 2022-10-27 | 2022-11-07 | 2025-09-18 | 2025-10-02 | 2025-11-10 | 2025-11-16 | 2026-03-16 | 2026-03-22 | 2026-04-30 | 2026-04-18 | 2026-05-23
6229 | ST-2025-022 | United States | S0004 | UNIT-Medical Center | 3 | 5 | 166.7 | 0.3 | ON_HOLD | Dr. Daniel Brown | Dr. Daniel Thompson | 2022-02-13 | 2022-03-18 | 2022-03-30 | 2022-04-17 | 2022-04-27 | 2022-05-13 | 2022-05-24 | 2022-05-24 | 2022-06-01 | 2022-06-06 | 2022-05-23 | 2022-09-08 | 2022-08-28 | 2022-11-02 | 2022-11-02 | 2025-09-22 | 2025-09-19 | 2025-11-21 | 2025-11-13 | 2026-03-16 | 2026-03-16 | 2026-04-28 | 2026-04-14 | 2026-05-17 | 2026-05-10
6230 | ST-2025-022 | Mexico | S0005 | MEXI-Medical Center | 4 | 2 | 50 | 0.1 | ON_HOLD | Dr. Thomas Jackson | Dr. Lisa White | 2022-02-20 | 2022-03-19 | 2022-03-16 | 2022-04-21 | 2022-04-08 | 2022-05-12 | 2022-05-06 | 2022-05-24 | 2022-05-25 | 2022-06-04 | 2022-06-18 | 2022-08-28 | 2022-09-05 | 2022-10-25 | 2022-11-02 | 2025-09-08 | 2025-09-13 | 2025-11-02 | 2025-10-25 | 2026-02-24 | 2026-02-10 | 2026-04-05 | 2026-03-28 | 2026-04-26 | 2026-05-08
6231 | ST-2025-022 | Mexico | S0006 | MEXI-University Hospital | 5 | 4 | 80 | 0.5 | SCREENING | Dr. Jennifer Miller | Dr. William Harris | 2022-02-09 | 2022-03-08 | 2022-03-12 | 2022-04-09 | 2022-03-31 | 2022-05-03 | 2022-04-21 | 2022-05-17 | 2022-05-21 | 2022-05-29 | 2022-05-19 | 2022-08-28 | 2022-09-06 | 2022-10-19 | 2022-10-07 | 2025-09-13 | 2025-09-03 | 2025-11-12 | 2025-11-06 | 2026-03-08 | 2026-03-12 | 2026-04-24 | 2026-05-07 | 2026-05-16 | 2026-05-09
6232 | ST-2025-022 | Poland | S0007 | POLA-Clinical Center | 1 | 1 | 100 | 0.1 | SCREENING | Dr. William Jones | Dr. Amanda Martin | 2022-02-26 | 2022-03-25 | 2022-03-11 | 2022-04-20 | 2022-04-19 | 2022-05-16 | 2022-05-22 | 2022-05-27 | 2022-06-03 | 2022-06-12 | 2022-06-18 | 2022-08-28 | 2022-08-15 | 2022-10-24 | 2022-11-06 | 2025-09-18 | 2025-09-14 | 2025-11-12 | 2025-11-11 | 2026-03-04 | 2026-03-17 | 2026-04-18 | 2026-04-17 | 2026-05-09 | 2026-05-03
6233 | ST-2025-022 | Poland | S0008 | POLA-General Hospital | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. James Johnson | Dr. Sarah Davis | 2022-02-23 | 2022-03-25 | 2022-03-28 | 2022-04-24 | 2022-04-24 | 2022-05-15 | 2022-05-11 | 2022-05-30 | 2022-05-16 | 2022-06-16 | 2022-06-14 | 2022-08-21 | 2022-08-13 | 2022-10-23 | 2022-10-19 | 2025-09-23 | 2025-09-11 | 2025-11-16 | 2025-11-30 | 2026-02-25 | 2026-03-01 | 2026-04-07 | 2026-04-18 | 2026-04-28 | 2026-04-14
6234 | ST-2025-022 | Poland | S0009 | POLA-Research Institute | 3 | 2 | 66.7 | 0.1 | ON_HOLD | Dr. Jessica Thomas | Dr. Emily Moore | 2022-02-18 | 2022-03-19 | 2022-03-20 | 2022-04-12 | 2022-04-11 | 2022-05-01 | 2022-05-12 | 2022-05-13 | 2022-04-29 | 2022-05-25 | 2022-05-29 | 2022-09-06 | 2022-09-17 | 2022-10-29 | 2022-11-04 | 2025-09-24 | 2025-09-20 | 2025-11-24 | 2025-12-06 | 2026-03-18 | 2026-03-12 | 2026-04-25 | 2026-04-18 | 2026-05-13 | 2026-05-02
6235 | ST-2025-022 | Poland | S0010 | POLA-Cancer Center | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. Charles Smith | Dr. Charles Wilson | 2022-02-20 | 2022-03-15 | 2022-03-15 | 2022-04-12 | 2022-04-16 | 2022-05-06 | 2022-04-25 | 2022-05-23 | 2022-05-11 | 2022-06-04 | 2022-05-22 | 2022-09-01 | 2022-08-19 | 2022-11-01 | 2022-10-30 | 2025-10-01 | 2025-09-27 | 2025-11-30 | 2025-12-14 | 2026-03-14 | 2026-03-27 | 2026-04-21 | 2026-04-29 | 2026-05-14 | 2026-05-02
6236 | ST-2025-022 | Sweden | S0011 | SWED-Research Institute | -5 | -5 | 100 | -0.7 | SCREENING | Dr. Nicole White | Dr. Thomas White | 2022-02-24 | 2022-03-26 | 2022-03-21 | 2022-04-18 | 2022-05-01 | 2022-05-08 | 2022-05-06 | 2022-05-23 | 2022-05-21 | 2022-06-08 | 2022-05-28 | 2022-08-31 | 2022-09-05 | 2022-10-20 | 2022-10-30 | 2025-09-13 | 2025-09-12 | 2025-11-13 | 2025-11-06 | 2026-02-19 | 2026-03-04 | 2026-04-05 | 2026-04-10 | 2026-04-23 | 2026-05-04
6237 | ST-2025-022 | Sweden | S0012 | SWED-Cancer Center | 3 | 2 | 66.7 | 0.3 | ENROLLING | Dr. William Thompson | Dr. Michael Thomas | 2022-02-24 | 2022-03-26 | 2022-04-06 | 2022-04-24 | 2022-04-10 | 2022-05-17 | 2022-05-17 | 2022-06-03 | 2022-06-05 | 2022-06-17 | 2022-06-13 | 2022-09-13 | 2022-09-17 | 2022-11-10 | 2022-11-02 | 2025-09-26 | 2025-09-15 | 2025-11-17 | 2025-11-06 | 2026-03-01 | 2026-02-15 | 2026-04-17 | 2026-04-22 | 2026-05-10 | 2026-05-18
6238 | ST-2025-022 | Sweden | S0013 | SWED-Clinical Center | 3 | 3 | 100 | 0.2 | ON_HOLD | Dr. Michelle Taylor | Dr. Christopher Smith | 2022-03-08 | 2022-04-03 | 2022-03-27 | 2022-05-05 | 2022-04-25 | 2022-05-23 | 2022-06-03 | 2022-06-08 | 2022-05-26 | 2022-06-23 | 2022-06-10 | 2022-09-03 | 2022-08-24 | 2022-10-27 | 2022-10-22 | 2025-09-23 | 2025-09-27 | 2025-11-20 | 2025-11-19 | 2026-03-05 | 2026-03-07 | 2026-04-18 | 2026-04-24 | 2026-05-07 | 2026-05-17
6239 | ST-2025-022 | Sweden | S0014 | SWED-Cancer Center | 3 | 2 | 66.7 | 0.3 | ON_HOLD | Dr. Jennifer Harris | Dr. Robert Smith | 2022-03-05 | 2022-04-05 | 2022-04-12 | 2022-04-30 | 2022-05-07 | 2022-05-18 | 2022-05-08 | 2022-06-01 | 2022-05-19 | 2022-06-14 | 2022-06-07 | 2022-09-15 | 2022-09-17 | 2022-11-08 | 2022-11-20 | 2025-09-28 | 2025-10-10 | 2025-11-23 | 2025-11-26 | 2026-03-03 | 2026-03-16 | 2026-04-17 | 2026-04-04 | 2026-05-09 | 2026-05-08
6240 | ST-2025-022 | Sweden | S0015 | SWED-Clinical Center | 3 | 3 | 100 | 0.3 | ON_HOLD | Dr. Jessica Taylor | Dr. Michael Brown | 2022-02-27 | 2022-04-01 | 2022-04-05 | 2022-04-27 | 2022-05-01 | 2022-05-14 | 2022-05-10 | 2022-05-27 | 2022-06-01 | 2022-06-08 | 2022-06-03 | 2022-09-19 | 2022-09-18 | 2022-11-14 | 2022-11-10 | 2025-10-08 | 2025-09-29 | 2025-12-05 | 2025-11-24 | 2026-03-15 | 2026-03-15 | 2026-04-26 | 2026-05-10 | 2026-05-20
6241 | ST-2025-022 | Sweden | S0016 | SWED-University Hospital | 3 | 3 | 100 | 0.3 | ON_HOLD | Dr. Robert White | Dr. Thomas Harris | 2022-02-24 | 2022-03-26 | 2022-04-04 | 2022-04-21 | 2022-05-01 | 2022-05-07 | 2022-05-19 | 2022-05-23 | 2022-05-19 | 2022-06-04 | 2022-06-15 | 2022-10-05 | 2022-10-14 | 2022-11-26 | 2022-11-24 | 2025-10-19 | 2025-10-11 | 2025-12-18 | 2025-12-16 | 2026-03-24 | 2026-03-15 | 2026-05-03 | 2026-05-15 | 2026-05-24
6242 | ST-2025-022 | China | S0017 | CHIN-General Hospital | 5 | 3 | 60 | 0.2 | ON_HOLD | Dr. Jessica Miller | Dr. Michael White | 2022-02-18 | 2022-03-13 | 2022-03-23 | 2022-04-06 | 2022-04-03 | 2022-04-27 | 2022-04-14 | 2022-05-08 | 2022-04-24 | 2022-05-23 | 2022-05-15 | 2022-08-19 | 2022-08-11 | 2022-10-09 | 2022-10-04 | 2025-09-20 | 2025-09-11 | 2025-11-17 | 2025-11-10 | 2026-03-04 | 2026-03-18 | 2026-04-20 | 2026-04-14 | 2026-05-12 | 2026-05-21
6243 | ST-2025-022 | China | S0018 | CHIN-Research Institute | 6 | 5 | 83.3 | 0.6 | ON_HOLD | Dr. Charles Davis | Dr. James Smith | 2022-02-26 | 2022-03-29 | 2022-03-27 | 2022-04-24 | 2022-04-30 | 2022-05-12 | 2022-05-23 | 2022-05-24 | 2022-06-07 | 2022-06-04 | 2022-05-24 | 2022-08-23 | 2022-08-19 | 2022-10-24 | 2022-10-16 | 2025-09-23 | 2025-09-18 | 2025-11-14 | 2025-11-14 | 2026-03-04 | 2026-02-25 | 2026-04-20 | 2026-04-17 | 2026-05-09 | 2026-05-20
6244 | ST-2025-022 | Chile | S0019 | CHIL-University Hospital | 5 | 5 | 100 | 0.5 | SCREENING | Dr. Jennifer Johnson | Dr. Charles White | 2022-03-25 | 2022-04-25 | 2022-04-23 | 2022-05-27 | 2022-06-04 | 2022-06-18 | 2022-06-15 | 2022-07-04 | 2022-06-30 | 2022-07-15 | 2022-07-20 | 2022-10-04 | 2022-10-03 | 2022-11-24 | 2022-11-30 | 2025-11-04 | 2025-10-28 | 2025-12-27 | 2025-12-14 | 2026-03-06 | 2026-03-16 | 2026-04-15 | 2026-04-20 | 2026-05-07 | 2026-05-11
6245 | ST-2025-022 | Chile | S0020 | CHIL-Health System | 3 | 3 | 100 | 0.3 | ENROLLING | Dr. Michael Thomas | Dr. Jennifer Brown | 2022-03-31 | 2022-04-27 | 2022-04-19 | 2022-05-22 | 2022-05-31 | 2022-06-12 | 2022-05-31 | 2022-06-24 | 2022-07-05 | 2022-07-05 | 2022-07-06 | 2022-10-16 | 2022-10-27 | 2022-12-16 | 2022-12-23 | 2025-10-28 | 2025-11-02 | 2025-12-20 | 2025-12-08 | 2026-03-14 | 2026-03-05 | 2026-04-29 | 2026-05-01 | 2026-05-20
6246 | ST-2025-022 | Chile | S0021 | CHIL-Medical Center | 3 | 15 | 500 | 0.9 | SCREENING | Dr. Stephanie Harris | Dr. Nicole Brown | 2022-04-06 | 2022-05-09 | 2022-05-10 | 2022-06-09 | 2022-06-10 | 2022-06-30 | 2022-06-24 | 2022-07-14 | 2022-07-18 | 2022-07-29 | 2022-07-27 | 2022-10-18 | 2022-10-24 | 2022-12-08 | 2022-12-19 | 2025-11-03 | 2025-11-07 | 2025-12-29 | 2026-01-04 | 2026-03-19 | 2026-03-06 | 2026-05-02 | 2026-04-24 | 2026-05-25
6247 | ST-2025-023 | United States | S0001 | UNIT-Medical Center | 106 | 106 | 100 | 8.8 | ON_HOLD | Dr. James Smith | Dr. Charles Brown | 2021-09-26 | 2021-10-26 | 2021-10-29 | 2021-11-21 | 2021-11-09 | 2021-12-13 | 2021-12-03 | 2021-12-25 | 2022-01-04 | 2022-01-07 | 2021-12-26 | 2022-03-31 | 2022-03-26 | 2022-06-02 | 2022-06-02 | 2027-01-06 |  | 2027-03-07 |  | 2027-06-27 |  | 2027-08-08 |  | 2027-08-28
6248 | ST-2025-023 | United States | S0002 | UNIT-Medical Center | 93 | 78 | 83.9 | 9.8 | ON_HOLD | Dr. Nicole Harris | Dr. Charles Martin | 2021-09-26 | 2021-10-28 | 2021-11-08 | 2021-11-20 | 2021-11-21 | 2021-12-13 | 2021-12-09 | 2021-12-28 | 2021-12-22 | 2022-01-12 | 2022-01-10 | 2022-04-04 | 2022-03-21 | 2022-05-29 | 2022-05-20 | 2027-01-12 |  | 2027-03-11 |  | 2027-07-06 |  | 2027-08-18 |  | 2027-09-07
6249 | ST-2025-023 | Canada | S0003 | CANA-General Hospital | 47 | 47 | 100 | 3.9 | SCREENING | Dr. Michael Jones | Dr. Robert Smith | 2021-09-27 | 2021-10-30 | 2021-10-24 | 2021-11-23 | 2021-11-16 | 2021-12-14 | 2021-12-03 | 2021-12-25 | 2021-12-14 | 2022-01-07 | 2021-12-26 | 2022-04-05 | 2022-04-02 | 2022-06-01 | 2022-05-19 | 2027-01-13 |  | 2027-03-13 |  | 2027-07-10 |  | 2027-08-17 |  | 2027-09-10
6250 | ST-2025-023 | Canada | S0004 | CANA-University Hospital | 75 | 75 | 100 | 10.7 | ENROLLING | Dr. David Smith | Dr. David Martin | 2021-09-28 | 2021-10-24 | 2021-10-29 | 2021-11-26 | 2021-11-16 | 2021-12-17 | 2021-12-30 | 2021-12-30 | 2022-01-09 | 2022-01-12 | 2022-01-20 | 2022-04-08 | 2022-04-17 | 2022-06-09 | 2022-06-12 | 2027-01-22 |  | 2027-03-24 |  | 2027-07-09 |  | 2027-08-18 |  | 2027-09-10
6251 | ST-2025-023 | Canada | S0005 | CANA-General Hospital | 63 | 26 | 41.3 | 3.2 | ON_HOLD | Dr. Lisa White | Dr. Michelle Miller | 2021-09-23 | 2021-10-20 | 2021-10-22 | 2021-11-16 | 2021-11-26 | 2021-12-07 | 2021-11-27 | 2021-12-24 | 2022-01-06 | 2022-01-07 | 2022-01-05 | 2022-04-11 | 2022-04-04 | 2022-06-12 | 2022-06-05 | 2027-01-27 |  | 2027-03-29 |  | 2027-07-13 |  | 2027-08-26 |  | 2027-09-18
6252 | ST-2025-023 | Italy | S0006 | ITAL-Medical Center | 32 | 32 | 100 | 2.5 | ON_HOLD | Dr. Lisa Miller | Dr. Jessica Jackson | 2021-09-29 | 2021-10-29 | 2021-11-11 | 2021-11-24 | 2021-11-16 | 2021-12-18 | 2021-12-17 | 2022-01-02 | 2022-01-12 | 2022-01-19 | 2022-01-27 | 2022-04-20 | 2022-04-19 | 2022-06-20 | 2022-06-12 | 2027-01-17 |  | 2027-03-16 |  | 2027-06-27 |  | 2027-08-04 |  | 2027-08-24
6253 | ST-2025-023 | Italy | S0007 | ITAL-Medical Center | 64 | 64 | 100 | 5.8 | ENROLLING | Dr. Emily White | Dr. Stephanie Martin | 2021-10-09 | 2021-11-09 | 2021-11-06 | 2021-12-02 | 2021-11-28 | 2021-12-23 | 2021-12-16 | 2022-01-04 | 2022-01-03 | 2022-01-19 | 2022-01-18 | 2022-04-29 | 2022-05-06 | 2022-06-19 | 2022-06-29 | 2027-01-18 |  | 2027-03-10 |  | 2027-07-03 |  | 2027-08-19 |  | 2027-09-12
6254 | ST-2025-023 | Italy | S0008 | ITAL-General Hospital | 33 | 28 | 84.8 | 1.9 | ON_HOLD | Dr. Michelle Anderson | Dr. Sarah Martin | 2021-10-08 | 2021-11-08 | 2021-11-14 | 2021-12-05 | 2021-12-16 | 2021-12-26 | 2021-12-31 | 2022-01-10 | 2022-01-15 | 2022-01-21 | 2022-01-25 | 2022-04-29 | 2022-05-12 | 2022-06-29 | 2022-06-27 | 2027-01-18 |  | 2027-03-12 |  | 2027-07-02 |  | 2027-08-13 |  | 2027-09-04
6255 | ST-2025-023 | Italy | S0009 | ITAL-Clinical Center | 46 | 40 | 87 | 3.1 | ON_HOLD | Dr. Nicole Davis | Dr. Sarah Thompson | 2021-09-29 | 2021-10-28 | 2021-10-16 | 2021-11-21 | 2021-11-12 | 2021-12-15 | 2021-12-04 | 2021-12-29 | 2022-01-05 | 2022-01-10 | 2022-01-13 | 2022-05-10 | 2022-05-01 | 2022-06-29 | 2022-06-16 | 2027-02-05 |  | 2027-04-06 |  | 2027-07-20 |  | 2027-09-05 |  | 2027-09-25
6256 | ST-2025-023 | Italy | S0010 | ITAL-Medical Center | 31 | 1 | 3.2 | 0.1 | ON_HOLD | Dr. Thomas Moore | Dr. Michael Wilson | 2021-10-05 | 2021-11-04 | 2021-11-06 | 2021-11-27 | 2021-11-15 | 2021-12-15 | 2021-12-15 | 2021-12-27 | 2021-12-14 | 2022-01-07 | 2022-01-04 | 2022-05-21 | 2022-05-23 | 2022-07-15 | 2022-07-01 | 2027-02-08 |  | 2027-04-03 |  | 2027-07-20 |  | 2027-08-30 |  | 2027-09-22
6257 | ST-2025-023 | Poland | S0011 | POLA-University Hospital | 70 | 70 | 100 | 5 | SCREENING | Dr. Thomas Harris | Dr. Robert Anderson | 2021-10-24 | 2021-11-22 | 2021-12-05 | 2021-12-21 | 2021-12-13 | 2022-01-08 | 2022-01-03 | 2022-01-19 | 2022-01-18 | 2022-01-31 | 2022-02-12 | 2022-04-27 | 2022-05-05 | 2022-06-21 | 2022-06-28 | 2027-01-25 |  | 2027-03-18 |  | 2027-06-25 |  | 2027-08-04 |  | 2027-08-23
6258 | ST-2025-023 | Poland | S0012 | POLA-General Hospital | 43 | 26 | 60.5 | 1.5 | ON_HOLD | Dr. Stephanie Thomas | Dr. Nicole Garcia | 2021-10-20 | 2021-11-21 | 2021-11-21 | 2021-12-18 | 2021-12-06 | 2022-01-12 | 2022-01-24 | 2022-01-24 | 2022-01-22 | 2022-02-08 | 2022-02-13 | 2022-05-04 | 2022-05-15 | 2022-07-02 | 2022-06-25 | 2027-01-29 |  | 2027-03-25 |  | 2027-06-26 |  | 2027-08-02 |  | 2027-08-21
6259 | ST-2025-023 | Poland | S0013 | POLA-Health System | 46 | 35 | 76.1 | 3.9 | ON_HOLD | Dr. Michael Martin | Dr. Robert Garcia | 2021-10-25 | 2021-11-26 | 2021-12-04 | 2021-12-26 | 2022-01-07 | 2022-01-18 | 2022-01-26 | 2022-02-01 | 2022-02-12 | 2022-02-16 | 2022-02-11 | 2022-04-28 | 2022-04-26 | 2022-06-27 | 2022-07-02 | 2027-01-28 |  | 2027-03-24 |  | 2027-07-08 |  | 2027-08-21 |  | 2027-09-10
6260 | ST-2025-023 | Poland | S0014 | POLA-University Hospital | 47 | 33 | 70.2 | 4.1 | CLOSED | Dr. Nicole Brown | Dr. Stephanie Martin | 2021-10-24 | 2021-11-18 | 2021-11-22 | 2021-12-17 | 2021-12-06 | 2022-01-05 | 2022-01-03 | 2022-01-17 | 2022-01-25 | 2022-02-01 | 2022-01-19 | 2022-05-18 | 2022-05-11 | 2022-07-12 | 2022-07-26 | 2027-02-12 |  | 2027-04-10 |  | 2027-07-17 |  | 2027-08-25 |  | 2027-09-17
6261 | ST-2025-023 | Poland | S0015 | POLA-Research Institute | 68 | 54 | 79.4 | 6 | SCREENING | Dr. Michelle Johnson | Dr. James Thomas | 2021-10-15 | 2021-11-17 | 2021-11-20 | 2021-12-18 | 2021-12-07 | 2022-01-07 | 2022-01-04 | 2022-01-23 | 2022-01-11 | 2022-02-03 | 2022-02-13 | 2022-05-25 | 2022-05-14 | 2022-07-24 | 2022-07-26 | 2027-02-23 |  | 2027-04-18 |  | 2027-07-21 |  | 2027-09-02 |  | 2027-09-26
6262 | ST-2025-023 | Poland | S0016 | POLA-Research Institute | 40 | 12 | 30 | 1.1 | CLOSED | Dr. Jennifer Garcia | Dr. Daniel Johnson | 2021-10-16 | 2021-11-14 | 2021-11-21 | 2021-12-14 | 2021-12-23 | 2022-01-01 | 2022-01-01 | 2022-01-14 | 2022-01-12 | 2022-01-26 | 2022-01-22 | 2022-05-26 | 2022-06-04 | 2022-07-14 | 2022-07-12 | 2027-02-23 |  | 2027-04-15 |  | 2027-07-19 |  | 2027-09-04 |  | 2027-09-27
6263 | ST-2025-023 | Japan | S0017 | JAPA-University Hospital | 50 | 50 | 100 | 2.9 | ON_HOLD | Dr. Emily Johnson | Dr. Christopher Harris | 2021-10-17 | 2021-11-09 | 2021-10-28 | 2021-12-02 | 2021-11-20 | 2021-12-22 | 2021-12-25 | 2022-01-02 | 2022-01-09 | 2022-01-18 | 2022-01-11 | 2022-04-23 | 2022-05-01 | 2022-06-13 | 2022-06-13 | 2027-01-14 |  | 2027-03-16 |  | 2027-07-08 |  | 2027-08-21 |  | 2027-09-11
6264 | ST-2025-023 | Japan | S0018 | JAPA-Cancer Center | 30 | 30 | 100 | 1.7 | ENROLLING | Dr. Emily Brown | Dr. Michelle Johnson | 2021-10-24 | 2021-11-20 | 2021-11-18 | 2021-12-15 | 2021-12-06 | 2022-01-02 | 2021-12-21 | 2022-01-19 | 2022-01-26 | 2022-01-30 | 2022-02-09 | 2022-04-21 | 2022-04-07 | 2022-06-10 | 2022-06-17 | 2027-01-14 |  | 2027-03-10 |  | 2027-07-05 |  | 2027-08-19 |  | 2027-09-11
6265 | ST-2025-023 | Japan | S0019 | JAPA-Health System | 22 | 22 | 100 | 3.1 | ENROLLING | Dr. Emily Miller | Dr. Amanda Garcia | 2021-10-18 | 2021-11-15 | 2021-11-21 | 2021-12-10 | 2021-12-21 | 2021-12-29 | 2021-12-31 | 2022-01-14 | 2022-01-20 | 2022-01-25 | 2022-02-01 | 2022-04-30 | 2022-05-08 | 2022-06-28 | 2022-07-05 | 2027-01-24 |  | 2027-03-19 |  | 2027-07-15 |  | 2027-08-21 |  | 2027-09-14
6266 | ST-2025-023 | Japan | S0020 | JAPA-General Hospital | 26 | 26 | 100 | 2.6 | ON_HOLD | Dr. Christopher Thompson | Dr. Nicole Brown | 2021-10-17 | 2021-11-13 | 2021-11-05 | 2021-12-13 | 2021-12-01 | 2021-12-29 | 2021-12-15 | 2022-01-13 | 2022-01-12 | 2022-01-24 | 2022-01-10 | 2022-04-28 | 2022-04-14 | 2022-06-28 | 2022-06-24 | 2027-02-03 |  | 2027-03-29 |  | 2027-07-23 |  | 2027-09-03 |  | 2027-09-22
6267 | ST-2025-023 | Japan | S0021 | JAPA-University Hospital | 38 | 35 | 92.1 | 2.2 | SCREENING | Dr. Thomas Jones | Dr. Emily Miller | 2021-10-21 | 2021-11-23 | 2021-11-25 | 2021-12-17 | 2021-12-06 | 2022-01-05 | 2022-01-17 | 2022-01-16 | 2022-01-12 | 2022-02-02 | 2022-01-29 | 2022-05-16 | 2022-05-19 | 2022-07-17 | 2022-07-23 | 2027-02-12 |  | 2027-04-06 |  | 2027-07-27 |  | 2027-09-02 |  | 2027-09-23
6268 | ST-2025-023 | Japan | S0022 | JAPA-Clinical Center | 36 | 19 | 52.8 | 1.6 | ENROLLING | Dr. Lisa Martin | Dr. Thomas Anderson | 2021-10-14 | 2021-11-14 | 2021-11-20 | 2021-12-13 | 2021-12-09 | 2022-01-04 | 2021-12-21 | 2022-01-15 | 2022-01-13 | 2022-01-27 | 2022-01-19 | 2022-04-27 | 2022-04-27 | 2022-06-16 | 2022-06-09 | 2027-01-29 |  | 2027-03-26 |  | 2027-07-18 |  | 2027-08-24 |  | 2027-09-14
6269 | ST-2025-023 | Mexico | S0023 | MEXI-General Hospital | 162 | 162 | 100 | 18 | ENROLLING | Dr. Daniel White | Dr. Lisa Jones | 2021-11-17 | 2021-12-14 | 2021-12-03 | 2022-01-16 | 2022-01-24 | 2022-02-10 | 2022-02-13 | 2022-02-23 | 2022-03-06 | 2022-03-06 | 2022-03-19 | 2022-05-07 | 2022-05-11 | 2022-07-09 | 2022-06-30 | 2027-02-04 |  | 2027-04-02 |  | 2027-07-01 |  | 2027-08-16 |  | 2027-09-06
6270 | ST-2025-023 | Mexico | S0024 | MEXI-Cancer Center | 93 | 75 | 80.6 | 6.2 | SCREENING | Dr. Stephanie Harris | Dr. Daniel Thomas | 2021-11-05 | 2021-12-07 | 2021-12-17 | 2022-01-04 | 2022-01-18 | 2022-01-30 | 2022-02-07 | 2022-02-15 | 2022-02-11 | 2022-03-01 | 2022-03-14 | 2022-05-19 | 2022-05-26 | 2022-07-21 | 2022-07-22 | 2027-02-16 |  | 2027-04-10 |  | 2027-07-05 |  | 2027-08-13 |  | 2027-09-05
6271 | ST-2025-023 | Mexico | S0025 | MEXI-Medical Center | 139 | 124 | 89.2 | 9.5 | ENROLLING | Dr. James Thompson | Dr. Michael Williams | 2021-11-04 | 2021-12-06 | 2021-11-22 | 2022-01-07 | 2022-01-12 | 2022-01-30 | 2022-02-09 | 2022-02-13 | 2022-02-27 | 2022-02-28 | 2022-02-17 | 2022-05-21 | 2022-05-16 | 2022-07-20 | 2022-07-13 | 2027-02-09 |  | 2027-04-09 |  | 2027-07-11 |  | 2027-08-17 |  | 2027-09-05
6272 | ST-2025-024 | United States | S0001 | UNIT-Research Institute | 13 | 13 | 100 | 1.1 | ENROLLING | Dr. Thomas Jones | Dr. Stephanie Taylor | 2024-07-22 | 2024-08-17 | 2024-08-23 | 2024-09-18 | 2024-09-05 | 2024-10-05 | 2024-09-28 | 2024-10-16 | 2024-10-25 | 2024-10-28 | 2024-11-02 | 2025-01-13 | 2025-01-13 | 2025-03-10 | 2025-03-19 | 2026-09-27 |  | 2026-11-20 |  | 2027-03-29 |  | 2027-05-11 |  | 2027-05-30
6273 | ST-2025-024 | United States | S0002 | UNIT-Research Institute | 6 | 3 | 50 | 0.2 | ENROLLING | Dr. Sarah Miller | Dr. Lisa Davis | 2024-07-12 | 2024-08-08 | 2024-07-25 | 2024-09-05 | 2024-08-29 | 2024-10-01 | 2024-10-14 | 2024-10-18 | 2024-10-27 | 2024-11-04 | 2024-10-31 | 2025-01-14 | 2025-01-10 | 2025-03-12 | 2025-03-05 | 2026-10-11 |  | 2026-12-07 |  | 2027-04-12 |  | 2027-05-23 |  | 2027-06-16
6274 | ST-2025-024 | United States | S0003 | UNIT-Clinical Center | 5 | 5 | 100 | 0.4 | SCREENING | Dr. Charles Brown | Dr. William Johnson | 2024-07-10 | 2024-08-12 | 2024-08-12 | 2024-09-07 | 2024-09-13 | 2024-10-03 | 2024-09-19 | 2024-10-19 | 2024-10-07 | 2024-11-04 | 2024-11-17 | 2025-01-17 | 2025-01-18 | 2025-03-16 | 2025-03-04 | 2026-10-12 |  | 2026-12-08 |  | 2027-04-10 |  | 2027-05-22 |  | 2027-06-10
6275 | ST-2025-024 | United States | S0004 | UNIT-Research Institute | 10 | 7 | 70 | 0.5 | SCREENING | Dr. Stephanie Williams | Dr. Nicole Smith | 2024-07-10 | 2024-08-12 | 2024-08-11 | 2024-09-06 | 2024-09-15 | 2024-09-25 | 2024-09-25 | 2024-10-07 | 2024-10-02 | 2024-10-18 | 2024-10-09 | 2025-01-30 | 2025-02-08 | 2025-03-29 | 2025-03-21 | 2026-10-21 |  | 2026-12-14 |  | 2027-04-19 |  | 2027-06-03 |  | 2027-06-21
6276 | ST-2025-024 | United States | S0005 | UNIT-Clinical Center | 5 | 5 | 100 | 0.3 | ENROLLING | Dr. James Wilson | Dr. Michelle Brown | 2024-07-12 | 2024-08-13 | 2024-08-11 | 2024-09-08 | 2024-09-06 | 2024-09-28 | 2024-09-19 | 2024-10-11 | 2024-10-12 | 2024-10-26 | 2024-10-26 | 2025-01-28 | 2025-01-27 | 2025-03-28 | 2025-03-30 | 2026-10-09 |  | 2026-12-03 |  | 2027-04-16 |  | 2027-05-24 |  | 2027-06-13
6277 | ST-2025-024 | United States | S0006 | UNIT-University Hospital | 12 | 18 | 150 | 1 | SCREENING | Dr. Robert Anderson | Dr. Stephanie Harris | 2024-07-16 | 2024-08-10 | 2024-08-13 | 2024-09-09 | 2024-09-18 | 2024-09-25 | 2024-09-16 | 2024-10-12 | 2024-10-06 | 2024-10-26 | 2024-10-24 | 2025-02-08 | 2025-02-08 | 2025-04-11 | 2025-04-06 | 2026-10-19 |  | 2026-12-13 |  | 2027-04-30 |  | 2027-06-14 |  | 2027-07-03
6278 | ST-2025-024 | Mexico | S0007 | MEXI-Medical Center | 7 | 7 | 100 | 0.5 | SCREENING | Dr. Jessica Garcia | Dr. James Johnson | 2024-07-22 | 2024-08-22 | 2024-08-08 | 2024-09-23 | 2024-10-06 | 2024-10-16 | 2024-10-18 | 2024-10-27 | 2024-11-05 | 2024-11-09 | 2024-11-18 | 2025-01-17 | 2025-01-14 | 2025-03-18 | 2025-03-19 | 2026-10-16 |  | 2026-12-09 |  | 2027-03-20 |  | 2027-04-29 |  | 2027-05-17
6279 | ST-2025-024 | Mexico | S0008 | MEXI-Clinical Center | 7 | 6 | 85.7 | 0.6 | SCREENING | Dr. William Jackson | Dr. Amanda Miller | 2024-07-22 | 2024-08-20 | 2024-08-24 | 2024-09-17 | 2024-09-08 | 2024-10-09 | 2024-10-01 | 2024-10-23 | 2024-11-02 | 2024-11-05 | 2024-11-04 | 2025-01-29 | 2025-01-23 | 2025-03-28 | 2025-04-07 | 2026-10-14 |  | 2026-12-10 |  | 2027-03-22 |  | 2027-04-29 |  | 2027-05-20
6280 | ST-2025-024 | Mexico | S0009 | MEXI-Health System | 4 | 3 | 75 | 0.2 | ENROLLING | Dr. Sarah Garcia | Dr. Michelle Williams | 2024-07-27 | 2024-08-24 | 2024-08-17 | 2024-09-24 | 2024-09-17 | 2024-10-17 | 2024-10-18 | 2024-11-02 | 2024-10-20 | 2024-11-18 | 2024-11-30 | 2025-02-02 | 2025-01-30 | 2025-04-03 | 2025-04-09 | 2026-10-22 |  | 2026-12-22 |  | 2027-04-06 |  | 2027-05-19 |  | 2027-06-11
6281 | ST-2025-024 | Mexico | S0010 | MEXI-Research Institute | 10 | 10 | 100 | 1.4 | ENROLLING | Dr. Emily Jones | Dr. Michelle Wilson | 2024-07-16 | 2024-08-18 | 2024-08-25 | 2024-09-20 | 2024-10-02 | 2024-10-08 | 2024-09-29 | 2024-10-21 | 2024-10-07 | 2024-11-05 | 2024-10-25 | 2025-02-08 | 2025-02-18 | 2025-04-08 | 2025-03-27 | 2026-10-28 |  | 2026-12-22 |  | 2027-04-07 |  | 2027-05-23 |  | 2027-06-14
6282 | ST-2025-024 | Mexico | S0011 | MEXI-Clinical Center | 6 | 5 | 83.3 | 0.6 | SCREENING | Dr. Daniel Taylor | Dr. Thomas Wilson | 2024-07-30 | 2024-08-28 | 2024-09-05 | 2024-09-26 | 2024-09-21 | 2024-10-21 | 2024-10-23 | 2024-11-01 | 2024-11-04 | 2024-11-16 | 2024-11-23 | 2025-02-19 | 2025-03-05 | 2025-04-12 | 2025-04-10 | 2026-11-13 |  | 2027-01-09 |  | 2027-04-10 |  | 2027-05-23 |  | 2027-06-12
6283 | ST-2025-024 | Mexico | S0012 | MEXI-Cancer Center | 10 | 13 | 130 | 0.8 | ENROLLING | Dr. William Davis | Dr. Thomas Taylor | 2024-07-27 | 2024-08-25 | 2024-08-23 | 2024-09-18 | 2024-09-26 | 2024-10-05 | 2024-09-30 | 2024-10-21 | 2024-10-07 | 2024-11-05 | 2024-10-27 | 2025-02-21 | 2025-03-05 | 2025-04-23 | 2025-04-24 | 2026-11-08 |  | 2026-12-31 |  | 2027-04-16 |  | 2027-05-26 |  | 2027-06-18
6284 | ST-2025-024 | Sweden | S0013 | SWED-Medical Center | 12 | 8 | 66.7 | 1.3 | CLOSED | Dr. Jennifer White | Dr. Michelle Martin | 2024-07-22 | 2024-08-20 | 2024-08-10 | 2024-09-20 | 2024-09-12 | 2024-10-12 | 2024-10-13 | 2024-10-28 | 2024-10-19 | 2024-11-10 | 2024-11-12 | 2025-02-14 | 2025-02-03 | 2025-04-10 | 2025-04-10 | 2026-10-08 |  | 2026-11-30 |  | 2027-04-04 |  | 2027-05-13 |  | 2027-06-05
6285 | ST-2025-024 | Sweden | S0014 | SWED-Cancer Center | 20 | 20 | 100 | 1.7 | CLOSED | Dr. Michael Williams | Dr. Michelle Smith | 2024-07-24 | 2024-08-18 | 2024-08-23 | 2024-09-13 | 2024-09-02 | 2024-09-29 | 2024-10-12 | 2024-10-15 | 2024-10-21 | 2024-10-27 | 2024-10-18 | 2025-02-20 | 2025-02-08 | 2025-04-22 | 2025-04-17 | 2026-10-14 |  | 2026-12-08 |  | 2027-04-10 |  | 2027-05-24 |  | 2027-06-16
6286 | ST-2025-024 | Sweden | S0015 | SWED-Cancer Center | 11 | 5 | 45.5 | 0.3 | ON_HOLD | Dr. Emily Thomas | Dr. Charles Thomas | 2024-07-22 | 2024-08-18 | 2024-08-12 | 2024-09-11 | 2024-09-21 | 2024-10-02 | 2024-09-18 | 2024-10-13 | 2024-10-20 | 2024-10-28 | 2024-11-01 | 2025-02-11 | 2025-02-22 | 2025-04-08 | 2025-03-26 | 2026-10-18 |  | 2026-12-18 |  | 2027-04-05 |  | 2027-05-12 |  | 2027-05-30
6287 | ST-2025-024 | Sweden | S0016 | SWED-Clinical Center | 19 | 0 | 0 | 0 | CLOSED | Dr. James Brown | Dr. Christopher Thomas | 2024-07-29 | 2024-08-21 | 2024-08-17 | 2024-09-19 | 2024-09-16 | 2024-10-14 | 2024-10-21 | 2024-10-29 | 2024-11-12 | 2024-11-15 | 2024-11-11 | 2025-02-15 | 2025-02-11 | 2025-04-19 | 2025-05-01 | 2026-10-21 |  | 2026-12-18 |  | 2027-04-12 |  | 2027-05-28 |  | 2027-06-18
6288 | ST-2025-024 | Switzerland | S0017 | SWIT-Medical Center | 20 | 0 | 0 | 0 | ON_HOLD | Dr. Amanda Miller | Dr. Michael Anderson | 2024-08-05 | 2024-09-07 | 2024-09-15 | 2024-10-06 | 2024-10-04 | 2024-10-28 | 2024-11-06 | 2024-11-12 | 2024-11-24 | 2024-11-23 | 2024-12-07 | 2025-02-06 | 2025-01-27 | 2025-04-09 | 2025-03-26 | 2026-10-20 |  | 2026-12-11 |  | 2027-03-21 |  | 2027-05-04 |  | 2027-05-28
6289 | ST-2025-024 | Switzerland | S0018 | SWIT-Cancer Center | 13 | 0 | 0 | 0 | SCREENING | Dr. Lisa Martin | Dr. Amanda Johnson | 2024-08-13 | 2024-09-13 | 2024-09-05 | 2024-10-10 | 2024-09-26 | 2024-10-29 | 2024-11-04 | 2024-11-11 | 2024-11-23 | 2024-11-25 | 2024-11-21 | 2025-02-15 | 2025-02-01 | 2025-04-15 | 2025-04-21 | 2026-10-30 |  | 2026-12-27 |  | 2027-04-03 |  | 2027-05-16 |  | 2027-06-08
6290 | ST-2025-024 | Japan | S0019 | JAPA-Cancer Center | 7 | 0 | 0 | 0 | CLOSED | Dr. Daniel Martin | Dr. Jennifer Moore | 2024-08-11 | 2024-09-08 | 2024-09-09 | 2024-10-11 | 2024-10-18 | 2024-11-03 | 2024-11-16 | 2024-11-15 | 2024-11-23 | 2024-11-30 | 2024-12-14 | 2025-03-02 | 2025-02-19 | 2025-04-26 | 2025-05-05 | 2026-11-15 |  | 2027-01-14 |  | 2027-03-23 |  | 2027-05-04 |  | 2027-05-25
6291 | ST-2025-024 | Japan | S0020 | JAPA-University Hospital | 10 | 0 | 0 | 0 | CLOSED | Dr. Jennifer Williams | Dr. Robert Williams | 2024-08-20 | 2024-09-15 | 2024-09-03 | 2024-10-10 | 2024-10-05 | 2024-11-03 | 2024-11-15 | 2024-11-18 | 2024-11-25 | 2024-12-05 | 2024-12-08 | 2025-03-12 | 2025-03-25 | 2025-05-11 | 2025-05-11 | 2026-11-16 |  | 2027-01-06 |  | 2027-03-28 |  | 2027-05-11 |  | 2027-06-04
6292 | ST-2025-024 | Japan | S0021 | JAPA-University Hospital | 8 | 0 | 0 | 0 | CLOSED | Dr. Lisa Thompson | Dr. William Miller | 2024-08-18 | 2024-09-11 | 2024-09-19 | 2024-10-11 | 2024-09-27 | 2024-11-06 | 2024-10-28 | 2024-11-21 | 2024-11-17 | 2024-12-03 | 2024-12-17 | 2025-03-04 | 2025-03-02 | 2025-04-25 | 2025-05-05 | 2026-11-12 |  | 2027-01-12 |  | 2027-03-29 |  | 2027-05-06 |  | 2027-05-27
6293 | ST-2025-024 | Japan | S0022 | JAPA-Cancer Center | 5 | 0 | 0 | 0 | SCREENING | Dr. Michelle Wilson | Dr. Michelle Harris | 2024-08-22 | 2024-09-18 | 2024-09-29 | 2024-10-21 | 2024-10-29 | 2024-11-13 | 2024-11-09 | 2024-11-29 | 2024-12-12 | 2024-12-10 | 2024-12-03 | 2025-03-15 | 2025-03-19 | 2025-05-05 | 2025-05-15 | 2026-11-28 |  | 2027-01-26 |  | 2027-04-11 |  | 2027-05-25 |  | 2027-06-12
6294 | ST-2025-025 | Canada | S0001 | CANA-University Hospital | -35 | -35 | 100 | -5.8 | SCREENING | Dr. David Moore | Dr. Jessica Jones | 2026-03-10 | 2026-04-12 | 2026-04-11 | 2026-05-10 | 2026-05-21 | 2026-06-01 |  | 2026-06-17 |  | 2026-07-03 |  | 2026-09-20 |  | 2026-11-19 |  | 2029-03-19 |  | 2029-05-19 |  | 2029-09-24 |  | 2029-11-08 |  | 2029-12-02
6295 | ST-2025-025 | Canada | S0002 | CANA-Research Institute | 3 | 3 | 100 | 0.3 | ENROLLING | Dr. William Jones | Dr. Daniel Martin | 2026-03-13 | 2026-04-06 | 2026-03-27 | 2026-05-03 | 2026-05-16 | 2026-05-20 |  | 2026-05-31 |  | 2026-06-11 |  | 2026-09-17 |  | 2026-11-16 |  | 2029-03-25 |  | 2029-05-18 |  | 2029-09-18 |  | 2029-11-03 |  | 2029-11-23
6296 | ST-2025-025 | Canada | S0003 | CANA-University Hospital | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. Nicole Williams | Dr. Jennifer Thompson | 2026-03-15 | 2026-04-16 | 2026-04-13 | 2026-05-09 | 2026-05-20 | 2026-05-29 |  | 2026-06-09 |  | 2026-06-24 |  | 2026-09-24 |  | 2026-11-15 |  | 2029-04-02 |  | 2029-05-29 |  | 2029-09-27 |  | 2029-11-08 |  | 2029-12-02
6297 | ST-2025-025 | United States | S0004 | UNIT-University Hospital | -1 | -1 | 100 | -0.1 | SCREENING | Dr. Amanda Thompson | Dr. Nicole Martin | 2026-04-03 | 2026-04-28 | 2026-04-18 | 2026-05-29 |  | 2026-06-24 |  | 2026-07-09 |  | 2026-07-24 |  | 2026-09-19 |  | 2026-11-08 |  | 2029-03-22 |  | 2029-05-12 |  | 2029-09-24 |  | 2029-11-07 |  | 2029-11-27
6298 | ST-2025-025 | United States | S0005 | UNIT-Clinical Center | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Charles Johnson | Dr. David Davis | 2026-03-26 | 2026-04-21 | 2026-04-16 | 2026-05-21 |  | 2026-06-16 |  | 2026-06-30 |  | 2026-07-12 |  | 2026-10-01 |  | 2026-11-23 |  | 2029-03-24 |  | 2029-05-24 |  | 2029-09-22 |  | 2029-11-07 |  | 2029-11-27
6299 | ST-2025-025 | United States | S0006 | UNIT-University Hospital | 3 | 4 | 133.3 | 0.3 | ENROLLING | Dr. Charles Miller | Dr. Jessica White | 2026-04-02 | 2026-04-26 | 2026-04-22 | 2026-05-23 |  | 2026-06-17 |  | 2026-07-01 |  | 2026-07-17 |  | 2026-10-08 |  | 2026-11-29 |  | 2029-04-01 |  | 2029-05-26 |  | 2029-10-01 |  | 2029-11-07 |  | 2029-12-01
6300 | ST-2025-025 | Spain | S0007 | SPAI-Clinical Center | -4 | -4 | 100 | -0.3 | ON_HOLD | Dr. Lisa Johnson | Dr. Christopher Thompson | 2026-03-21 | 2026-04-16 | 2026-04-07 | 2026-05-12 | 2026-04-28 | 2026-05-28 |  | 2026-06-14 |  | 2026-07-01 |  | 2026-09-23 |  | 2026-11-24 |  | 2029-03-23 |  | 2029-05-19 |  | 2029-09-14 |  | 2029-10-31 |  | 2029-11-24
6301 | ST-2025-025 | Spain | S0008 | SPAI-Health System | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. Christopher Harris | Dr. Stephanie White | 2026-03-15 | 2026-04-13 | 2026-04-05 | 2026-05-16 | 2026-05-24 | 2026-06-08 |  | 2026-06-21 |  | 2026-07-08 |  | 2026-10-02 |  | 2026-11-26 |  | 2029-03-22 |  | 2029-05-20 |  | 2029-09-19 |  | 2029-10-30 |  | 2029-11-22
6302 | ST-2025-025 | Spain | S0009 | SPAI-Research Institute | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. Thomas Wilson | Dr. Charles Smith | 2026-03-16 | 2026-04-09 | 2026-03-31 | 2026-05-04 | 2026-05-08 | 2026-05-25 |  | 2026-06-11 |  | 2026-06-28 |  | 2026-10-13 |  | 2026-12-14 |  | 2029-04-10 |  | 2029-05-31 |  | 2029-09-27 |  | 2029-11-10 |  | 2029-12-03
6303 | ST-2025-025 | Spain | S0010 | SPAI-University Hospital | 3 | 4 | 133.3 | 0.3 | SCREENING | Dr. William Williams | Dr. Amanda Williams | 2026-03-21 | 2026-04-20 | 2026-05-03 | 2026-05-17 | 2026-05-21 | 2026-06-04 |  | 2026-06-16 |  | 2026-06-28 |  | 2026-10-11 |  | 2026-12-10 |  | 2029-03-27 |  | 2029-05-27 |  | 2029-09-18 |  | 2029-10-30 |  | 2029-11-22
6304 | ST-2025-025 | Sweden | S0011 | SWED-Research Institute | -7 | -7 | 100 | -0.8 | CLOSED | Dr. Thomas Wilson | Dr. Jessica Wilson | 2026-03-28 | 2026-04-22 | 2026-04-09 | 2026-05-21 |  | 2026-06-12 |  | 2026-06-28 |  | 2026-07-15 |  | 2026-09-19 |  | 2026-11-21 |  | 2029-03-30 |  | 2029-05-21 |  | 2029-09-15 |  | 2029-10-29 |  | 2029-11-17
6305 | ST-2025-025 | Sweden | S0012 | SWED-University Hospital | 3 | 2 | 66.7 | 0.1 | CLOSED | Dr. Robert Moore | Dr. William Smith | 2026-03-24 | 2026-04-26 | 2026-04-24 | 2026-05-24 |  | 2026-06-18 |  | 2026-07-02 |  | 2026-07-14 |  | 2026-09-30 |  | 2026-11-29 |  | 2029-04-08 |  | 2029-06-01 |  | 2029-09-13 |  | 2029-10-21 |  | 2029-11-09
6306 | ST-2025-025 | Sweden | S0013 | SWED-Cancer Center | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. Amanda Jackson | Dr. Charles Smith | 2026-03-27 | 2026-04-28 | 2026-04-28 | 2026-05-23 |  | 2026-06-18 |  | 2026-07-04 |  | 2026-07-18 |  | 2026-10-08 |  | 2026-12-07 |  | 2029-04-20 |  | 2029-06-20 |  | 2029-09-29 |  | 2029-11-06 |  | 2029-11-30
6307 | ST-2025-025 | Sweden | S0014 | SWED-Clinical Center | 3 | 2 | 66.7 | 0.1 | CLOSED | Dr. Robert Jackson | Dr. Lisa Davis | 2026-03-26 | 2026-04-24 | 2026-04-30 | 2026-05-21 |  | 2026-06-16 |  | 2026-07-02 |  | 2026-07-16 |  | 2026-10-11 |  | 2026-11-29 |  | 2029-04-19 |  | 2029-06-10 |  | 2029-09-30 |  | 2029-11-07 |  | 2029-11-28
6308 | ST-2025-025 | Sweden | S0015 | SWED-General Hospital | 3 | 4 | 133.3 | 0.2 | SCREENING | Dr. Nicole Davis | Dr. Daniel Moore | 2026-03-24 | 2026-04-19 | 2026-04-20 | 2026-05-12 | 2026-05-18 | 2026-06-06 |  | 2026-06-21 |  | 2026-07-06 |  | 2026-10-16 |  | 2026-12-08 |  | 2029-05-02 |  | 2029-06-23 |  | 2029-10-11 |  | 2029-11-19 |  | 2029-12-10
6309 | ST-2025-025 | Netherlands | S0016 | NETH-University Hospital | -1 | -1 | 100 | -0.1 | CLOSED | Dr. Stephanie Miller | Dr. Christopher Harris | 2026-03-28 | 2026-04-29 | 2026-05-07 | 2026-05-24 |  | 2026-06-10 |  | 2026-06-23 |  | 2026-07-04 |  | 2026-10-08 |  | 2026-12-10 |  | 2029-04-22 |  | 2029-06-20 |  | 2029-09-12 |  | 2029-10-25 |  | 2029-11-18
6310 | ST-2025-025 | Netherlands | S0017 | NETH-Cancer Center | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Amanda Jones | Dr. Robert Anderson | 2026-04-01 | 2026-05-02 | 2026-05-16 | 2026-06-02 |  | 2026-06-25 |  | 2026-07-06 |  | 2026-07-21 |  | 2026-10-12 |  | 2026-12-09 |  | 2029-04-19 |  | 2029-06-19 |  | 2029-09-13 |  | 2029-10-23 |  | 2029-11-15
6311 | ST-2025-025 | Netherlands | S0018 | NETH-General Hospital | 3 | 2 | 66.7 | 0.3 | ON_HOLD | Dr. Amanda Taylor | Dr. Lisa White | 2026-04-06 | 2026-05-08 | 2026-05-14 | 2026-06-02 |  | 2026-06-18 |  | 2026-07-03 |  | 2026-07-17 |  | 2026-10-14 |  | 2026-12-07 |  | 2029-04-15 |  | 2029-06-05 |  | 2029-09-17 |  | 2029-11-02 |  | 2029-11-21
6312 | ST-2025-025 | Taiwan | S0019 | TAIW-Medical Center | -4 | -4 | 100 | -0.5 | SCREENING | Dr. Thomas Jackson | Dr. Charles Miller | 2021-10-18: 2026-04-28; 2021-11-15: 2026-05-25; 2021-12-10: 2026-06-17; 2021-12-29: 2026-07-04; 2022-01-14: 2026-07-15; 2022-01-25: 2026-07-30; 2022-04-30: 2026-10-23; 2022-06-28: 2026-12-16; 2027-01-24: 2029-05-08 |  | 2029-06-30 |  | 2029-09-22 |  | 2029-11-08 |  | 2029-11-26
6313 | ST-2025-025 | Taiwan | S0020 | TAIW-Clinical Center | 3 | 2 | 66.7 | 0.3 | CLOSED | Dr. Charles Miller | Dr. Nicole Brown | 2021-10-18: 2026-04-20; 2021-11-15: 2026-05-21; 2021-12-10: 2026-06-17; 2021-12-29: 2026-07-13; 2022-01-14: 2026-07-28; 2022-01-25: 2026-08-11; 2022-04-30: 2026-10-24; 2022-06-28: 2026-12-21; 2027-01-24: 2029-05-10 |  | 2029-07-05 |  | 2029-09-27 |  | 2029-11-08 |  | 2029-11-30
6314 | ST-2025-025 | Taiwan | S0021 | TAIW-Research Institute | 3 | 2 | 66.7 | 0.1 | ON_HOLD | Dr. Jessica Williams | Dr. Jennifer Brown | 2026-04-23 | 2026-05-17 | 2026-05-09 | 2026-06-19 |  | 2026-07-05 |  | 2026-07-17 |  | 2026-07-28 |  | 2026-10-31 |  | 2026-12-21 |  | 2029-05-13 |  | 2029-07-06 |  | 2029-09-27 |  | 2029-11-12 |  | 2029-12-04
6315 | ST-2025-025 | Taiwan | S0022 | TAIW-General Hospital | 3 | 3 | 100 | 0.2 | SCREENING | Dr. Sarah Martin | Dr. James Garcia | 2026-04-24 | 2026-05-19 | 2026-05-07 | 2026-06-20 |  | 2026-07-12 |  | 2026-07-23 |  | 2026-08-07 |  | 2026-11-07 |  | 2026-12-30 |  | 2029-05-21 |  | 2029-07-21 |  | 2029-10-03 |  | 2029-11-15 |  | 2029-12-06
6316 | ST-2025-025 | Australia | S0023 | AUST-Clinical Center | -10 | -10 | 100 | -1.2 | ENROLLING | Dr. Robert Moore | Dr. Stephanie Martin | 2021-10-18: 2026-05-12; 2021-11-15: 2026-06-10; 2021-12-10: 2026-07-05; 2021-12-29: 2026-07-29; 2022-01-14: 2026-08-10; 2022-01-25: 2026-08-21; 2022-04-30: 2026-11-07; 2022-06-28: 2027-01-06; 2027-01-24: 2029-05-08 |  | 2029-07-08 |  | 2029-09-22 |  | 2029-11-01 |  | 2029-11-24
6317 | ST-2025-025 | Australia | S0024 | AUST-General Hospital | 3 | 2 | 66.7 | 0.3 | ENROLLING | Dr. David Jones | Dr. David Anderson | 2021-10-18: 2026-05-12; 2021-11-15: 2026-06-14; 2021-12-10: 2026-07-15; 2021-12-29: 2026-08-09; 2022-01-14: 2026-08-21; 2022-01-25: 2026-09-04; 2022-04-30: 2026-11-14; 2022-06-28: 2027-01-04; 2027-01-24: 2029-05-13 |  | 2029-07-09 |  | 2029-09-22 |  | 2029-10-29 |  | 2029-11-20
6318 | ST-2025-025 | Australia | S0025 | AUST-Clinical Center | 3 | 1 | 33.3 | 0.1 | SCREENING | Dr. Nicole Garcia | Dr. Jessica Miller | 2021-10-18: 2026-05-06; 2021-11-15: 2026-05-30; 2021-12-10: 2026-06-30; 2021-12-29: 2026-07-17; 2022-01-14: 2026-08-02; 2022-01-25: 2026-08-17; 2022-04-30: 2026-11-10; 2022-06-28: 2026-12-30; 2027-01-24: 2029-05-16 |  | 2029-07-16 |  | 2029-09-20 |  | 2029-11-01 |  | 2029-11-21
6319 | ST-2025-025 | Australia | S0026 | AUST-Health System | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Christopher Wilson | Dr. David Smith | 2021-10-18: 2026-05-04; 2021-11-15: 2026-05-30; 2021-12-10: 2026-06-26; 2021-12-29: 2026-07-12; 2022-01-14: 2026-07-23; 2022-01-25: 2026-08-06; 2022-04-30: 2026-11-18; 2022-06-28: 2027-01-12; 2027-01-24: 2029-05-23 |  | 2029-07-14 |  | 2029-10-02 |  | 2029-11-16 |  | 2029-12-09
6320 | ST-2025-025 | Australia | S0027 | AUST-University Hospital | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. Charles Davis | Dr. Daniel Taylor | 2021-10-18: 2026-05-11; 2021-11-15: 2026-06-10; 2021-12-10: 2026-07-04; 2021-12-29: 2026-07-28; 2022-01-14: 2026-08-10; 2022-01-25: 2026-08-26; 2022-04-30: 2026-12-02; 2022-06-28: 2027-02-02; 2027-01-24: 2029-06-03 |  | 2029-08-01 |  | 2029-10-12 |  | 2029-11-27 |  | 2029-12-15
6321 | ST-2025-025 | Australia | S0028 | AUST-Health System | 3 | 7 | 233.3 | 0.5 | ENROLLING | Dr. Christopher Johnson | Dr. Michael Anderson | 2021-10-18: 2026-05-04; 2021-11-15: 2026-06-01; 2021-12-10: 2026-06-30; 2021-12-29: 2026-07-18; 2022-01-14: 2026-07-31; 2022-01-25: 2026-08-17; 2022-04-30: 2026-12-10; 2022-06-28: 2027-02-07; 2027-01-24: 2029-06-17 |  | 2029-08-15 |  | 2029-10-22 |  | 2029-12-07 |  | 2029-12-31
6322 | ST-2025-025 | Chile | S0029 | CHIL-Cancer Center | 2 | 1 | 50 | 0.1 | ENROLLING | Dr. Charles Garcia | Dr. Stephanie Davis | 2021-10-18: 2026-05-24; 2021-11-15: 2026-06-18; 2021-12-10: 2026-07-15; 2021-12-29: 2026-07-31; 2022-01-14: 2026-08-16; 2022-01-25: 2026-08-31; 2022-04-30: 2026-12-04; 2022-06-28: 2027-01-24; 2027-01-24: 2029-05-29 |  | 2029-07-21 |  | 2029-09-14 |  | 2029-10-27 |  | 2029-11-18
6323 | ST-2025-025 | Chile | S0030 | CHIL-University Hospital | 3 | 6 | 200 | 0.4 | SCREENING | Dr. Stephanie Harris | Dr. Charles Garcia | 2021-10-18: 2026-05-15; 2021-11-15: 2026-06-17; 2021-12-10: 2026-07-15; 2021-12-29: 2026-08-03; 2022-01-14: 2026-08-19; 2022-01-25: 2026-09-03; 2022-04-30: 2026-12-05; 2022-06-28: 2027-02-03; 2027-01-24: 2029-06-01 |  | 2029-07-24 |  | 2029-09-25 |  | 2029-11-06 |  | 2029-11-30
6324 | ST-2025-026 | Mexico | S0001 | MEXI-University Hospital | 10 | 10 | 100 | 1 | ON_HOLD | Dr. David Jackson | Dr. Jessica Smith | 2020-04-29 | 2020-05-26 | 2020-05-22 | 2020-06-24 | 2020-07-07 | 2020-07-18 | 2020-07-06 | 2020-08-03 | 2020-08-09 | 2020-08-20 | 2020-08-08 | 2020-10-24 | 2020-10-12 | 2020-12-16 | 2020-12-25 | 2028-08-05 |  | 2028-09-26 |  | 2029-01-21 |  | 2029-03-05 |  | 2029-03-29
6325 | ST-2025-026 | Mexico | S0002 | MEXI-University Hospital | 4 | 2 | 50 | 0.2 | ENROLLING | Dr. Emily Williams | Dr. Stephanie Thompson | 2020-04-26 | 2020-05-21 | 2020-05-23 | 2020-06-22 | 2020-07-01 | 2020-07-08 | 2020-06-28 | 2020-07-19 | 2020-07-20 | 2020-08-04 | 2020-08-05 | 2020-10-28 | 2020-10-30 | 2020-12-24 | 2020-12-31 | 2028-08-12 |  | 2028-10-09 |  | 2029-01-20 |  | 2029-03-04 |  | 2029-03-27
6326 | ST-2025-026 | Mexico | S0003 | MEXI-Clinical Center | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Stephanie Garcia | Dr. Jennifer Thomas | 2020-05-09 | 2020-06-09 | 2020-06-06 | 2020-07-03 | 2020-06-26 | 2020-07-25 | 2020-08-03 | 2020-08-05 | 2020-08-12 | 2020-08-20 | 2020-09-01 | 2020-11-07 | 2020-11-21 | 2021-01-09 | 2021-01-11 | 2028-08-22 |  | 2028-10-12 |  | 2029-02-06 |  | 2029-03-23 |  | 2029-04-15
6327 | ST-2025-026 | Mexico | S0004 | MEXI-University Hospital | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. David Martin | Dr. Jennifer Thompson | 2020-04-25 | 2020-05-27 | 2020-05-17 | 2020-06-26 | 2020-06-28 | 2020-07-14 | 2020-07-11 | 2020-07-30 | 2020-07-17 | 2020-08-16 | 2020-08-15 | 2020-11-14 | 2020-11-15 | 2021-01-16 | 2021-01-14 | 2028-08-14 |  | 2028-10-06 |  | 2029-02-03 |  | 2029-03-17 |  | 2029-04-10
6328 | ST-2025-026 | Mexico | S0005 | MEXI-Medical Center | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. David Garcia | Dr. David Johnson | 2020-04-26 | 2020-05-24 | 2020-05-19 | 2020-06-26 | 2020-06-20 | 2020-07-15 | 2020-07-07 | 2020-08-01 | 2020-07-18 | 2020-08-16 | 2020-08-25 | 2020-11-15 | 2020-11-21 | 2021-01-15 | 2021-01-19 | 2028-08-20 |  | 2028-10-11 |  | 2029-02-02 |  | 2029-03-15 |  | 2029-04-05
6329 | ST-2025-026 | Mexico | S0006 | MEXI-General Hospital | 5 | 4 | 80 | 0.5 | ENROLLING | Dr. William White | Dr. Christopher Brown | 2020-05-09 | 2020-06-05 | 2020-05-22 | 2020-07-08 | 2020-07-13 | 2020-08-01 | 2020-08-01 | 2020-08-18 | 2020-08-14 | 2020-08-29 | 2020-08-24 | 2020-11-24 | 2020-11-21 | 2021-01-19 | 2021-01-08 | 2028-08-29 |  | 2028-10-28 |  | 2029-02-13 |  | 2029-03-22 |  | 2029-04-11
6330 | ST-2025-026 | Canada | S0007 | CANA-Research Institute | 21 | 17 | 81 | 2.8 | SCREENING | Dr. Lisa Martin | Dr. Nicole Brown | 2020-05-09 | 2020-06-03 | 2020-06-02 | 2020-07-02 | 2020-06-21 | 2020-07-23 | 2020-07-24 | 2020-08-03 | 2020-07-20 | 2020-08-14 | 2020-08-04 | 2020-11-02 | 2020-11-12 | 2020-12-28 | 2021-01-04 | 2028-08-01 |  | 2028-09-22 |  | 2029-01-23 |  | 2029-03-09 |  | 2029-03-28
6331 | ST-2025-026 | Canada | S0008 | CANA-Medical Center | 9 | 6 | 66.7 | 1 | ENROLLING | Dr. James Johnson | Dr. Emily Miller | 2020-05-02 | 2020-05-31 | 2020-06-12 | 2020-06-28 | 2020-06-28 | 2020-07-18 | 2020-07-09 | 2020-07-31 | 2020-07-21 | 2020-08-14 | 2020-08-11 | 2020-11-13 | 2020-11-22 | 2021-01-03 | 2021-01-02 | 2028-08-09 |  | 2028-10-03 |  | 2029-01-19 |  | 2029-03-04 |  | 2029-03-27
6332 | ST-2025-026 | Canada | S0009 | CANA-Health System | 11 | 17 | 154.5 | 0.9 | ENROLLING | Dr. Charles Thompson | Dr. William Martin | 2020-05-09 | 2020-06-04 | 2020-05-27 | 2020-06-28 | 2020-06-29 | 2020-07-17 | 2020-07-24 | 2020-07-30 | 2020-07-24 | 2020-08-10 | 2020-07-30 | 2020-11-02 | 2020-11-01 | 2020-12-27 | 2020-12-28 | 2028-08-08 |  | 2028-10-03 |  | 2029-01-19 |  | 2029-02-27 |  | 2029-03-22
6333 | ST-2025-026 | Switzerland | S0010 | SWIT-Research Institute | 24 | 20 | 83.3 | 1.2 | ON_HOLD | Dr. Thomas Davis | Dr. Amanda Jackson | 2020-05-12 | 2020-06-14 | 2020-06-03 | 2020-07-09 | 2020-07-20 | 2020-07-30 | 2020-07-16 | 2020-08-16 | 2020-08-06 | 2020-09-02 | 2020-08-23 | 2020-11-22 | 2020-11-19 | 2021-01-24 | 2021-01-26 | 2028-08-12 |  | 2028-10-10 |  | 2029-01-17 |  | 2029-02-25 |  | 2029-03-15
6334 | ST-2025-026 | Switzerland | S0011 | SWIT-Clinical Center | 19 | 10 | 52.6 | 0.7 | SCREENING | Dr. Amanda Taylor | Dr. Emily Smith | 2020-05-10 | 2020-06-05 | 2020-05-31 | 2020-06-28 | 2020-06-29 | 2020-07-24 | 2020-07-12 | 2020-08-10 | 2020-08-20 | 2020-08-23 | 2020-08-22 | 2020-11-18 | 2020-11-11 | 2021-01-15 | 2021-01-20 | 2028-08-19 |  | 2028-10-09 |  | 2029-01-19 |  | 2029-03-04 |  | 2029-03-24
6335 | ST-2025-026 | Sweden | S0012 | SWED-Cancer Center | 9 | 8 | 88.9 | 0.9 | SCREENING | Dr. Christopher Martin | Dr. Daniel White | 2020-05-17 | 2020-06-11 | 2020-06-12 | 2020-07-07 | 2020-07-15 | 2020-07-27 | 2020-08-07 | 2020-08-13 | 2020-08-24 | 2020-08-24 | 2020-08-13 | 2020-12-01 | 2020-12-09 | 2021-01-23 | 2021-02-01 | 2028-08-20 |  | 2028-10-13 |  | 2029-01-25 |  | 2029-03-09 |  | 2029-03-28
6336 | ST-2025-026 | Sweden | S0013 | SWED-General Hospital | 7 | 7 | 100 | 0.8 | ENROLLING | Dr. Thomas Smith | Dr. Amanda Johnson | 2020-05-11 | 2020-06-06 | 2020-05-27 | 2020-07-08 | 2020-07-07 | 2020-08-03 | 2020-07-20 | 2020-08-19 | 2020-08-24 | 2020-08-31 | 2020-08-23 | 2020-11-26 | 2020-11-14 | 2021-01-15 | 2021-01-28 | 2028-08-16 |  | 2028-10-12 |  | 2029-01-20 |  | 2029-03-02 |  | 2029-03-21
6337 | ST-2025-026 | Sweden | S0014 | SWED-Cancer Center | 7 | 5 | 71.4 | 0.3 | SCREENING | Dr. Christopher Davis | Dr. Nicole Jackson | 2020-05-15 | 2020-06-15 | 2020-06-02 | 2020-07-12 | 2020-07-07 | 2020-08-07 | 2020-07-27 | 2020-08-19 | 2020-08-13 | 2020-08-31 | 2020-08-28 | 2020-11-28 | 2020-11-22 | 2021-01-22 | 2021-01-19 | 2028-08-21 |  | 2028-10-11 |  | 2029-01-28 |  | 2029-03-12 |  | 2029-04-04
6338 | ST-2025-026 | Sweden | S0015 | SWED-General Hospital | 8 | 8 | 100 | 0.5 | ENROLLING | Dr. Amanda White | Dr. Nicole Brown | 2020-05-12 | 2020-06-09 | 2020-06-03 | 2020-07-02 | 2020-07-07 | 2020-07-20 | 2020-07-09 | 2020-07-31 | 2020-07-30 | 2020-08-11 | 2020-08-02 | 2020-12-05 | 2020-11-29 | 2021-02-02 | 2021-02-03 | 2028-09-06 |  | 2028-11-01 |  | 2029-02-04 |  | 2029-03-17 |  | 2029-04-07
6339 | ST-2025-026 | Sweden | S0016 | SWED-General Hospital | 4 | 5 | 125 | 0.4 | SCREENING | Dr. David Jones | Dr. Daniel Thompson | 2020-05-13 | 2020-06-06 | 2020-06-17 | 2020-06-30 | 2020-06-27 | 2020-07-26 | 2020-08-04 | 2020-08-06 | 2020-08-16 | 2020-08-22 | 2020-08-26 | 2020-12-12 | 2020-12-14 | 2021-02-11 | 2021-02-16 | 2028-09-07 |  | 2028-10-30 |  | 2029-02-05 |  | 2029-03-19 |  | 2029-04-11
6340 | ST-2025-026 | Singapore | S0017 | SING-Cancer Center | 13 | 13 | 100 | 1 | SCREENING | Dr. Christopher Brown | Dr. Nicole Moore | 2020-05-25 | 2020-06-21 | 2020-06-25 | 2020-07-17 | 2020-07-31 | 2020-08-11 | 2020-08-17 | 2020-08-25 | 2020-09-06 | 2020-09-05 | 2020-08-28 | 2020-11-27 | 2020-11-19 | 2021-01-16 | 2021-01-24 | 2028-08-12 |  | 2028-10-12 |  | 2029-01-22 |  | 2029-03-01 |  | 2029-03-19
6341 | ST-2025-026 | Singapore | S0018 | SING-University Hospital | 21 | 4 | 19 | 0.4 | SCREENING | Dr. Jennifer Williams | Dr. Emily White | 2020-05-16 | 2020-06-09 | 2020-05-30 | 2020-07-10 | 2020-07-02 | 2020-08-04 | 2020-08-03 | 2020-08-17 | 2020-08-20 | 2020-08-30 | 2020-09-07 | 2020-11-28 | 2020-11-22 | 2021-01-23 | 2021-02-06 | 2028-08-26 |  | 2028-10-19 |  | 2029-01-25 |  | 2029-03-05 |  | 2029-03-23
6342 | ST-2025-026 | Singapore | S0019 | SING-General Hospital | 12 | 0 | 0 | 0 | SCREENING | Dr. Thomas Jackson | Dr. William Davis | 2020-05-28 | 2020-06-28 | 2020-06-30 | 2020-07-26 | 2020-07-28 | 2020-08-16 | 2020-08-27 | 2020-08-30 | 2020-08-16 | 2020-09-15 | 2020-09-06 | 2020-12-07 | 2020-12-12 | 2021-01-26 | 2021-01-20 | 2028-09-06 |  | 2028-11-02 |  | 2029-01-27 |  | 2029-03-12 |  | 2029-04-02
6343 | ST-2025-026 | New Zealand | S0020 | NEW-Clinical Center | 18 | 0 | 0 | 0 | CLOSED | Dr. Thomas Davis | Dr. Michael Taylor | 2020-05-17 | 2020-06-13 | 2020-06-26 | 2020-07-06 | 2020-07-08 | 2020-07-31 | 2020-07-19 | 2020-08-11 | 2020-08-02 | 2020-08-28 | 2020-08-28 | 2020-11-22 | 2020-12-02 | 2021-01-13 | 2021-01-15 | 2028-08-20 |  | 2028-10-16 |  | 2029-01-21 |  | 2029-03-09 |  | 2029-03-31
6344 | ST-2025-026 | New Zealand | S0021 | NEW-Clinical Center | 15 | 0 | 0 | 0 | CLOSED | Dr. Charles Moore | Dr. Stephanie Davis | 2020-05-27 | 2020-06-25 | 2020-06-11 | 2020-07-24 | 2020-08-07 | 2020-08-18 | 2020-08-29 | 2020-08-31 | 2020-09-02 | 2020-09-12 | 2020-09-12 | 2020-11-17 | 2020-11-19 | 2021-01-05 | 2021-01-13 | 2028-08-15 |  | 2028-10-14 |  | 2029-01-21 |  | 2029-03-08 |  | 2029-03-31
6345 | ST-2025-026 | New Zealand | S0022 | NEW-University Hospital | 19 | 0 | 0 | 0 | SCREENING | Dr. Jessica Williams | Dr. Emily Williams | 2020-05-19 | 2020-06-15 | 2020-06-10 | 2020-07-11 | 2020-06-28 | 2020-07-31 | 2020-08-06 | 2020-08-16 | 2020-08-06 | 2020-08-29 | 2020-09-12 | 2020-11-30 | 2020-11-24 | 2021-01-19 | 2021-01-09 | 2028-08-22 |  | 2028-10-15 |  | 2029-01-25 |  | 2029-03-11 |  | 2029-03-30
6346 | ST-2025-026 | New Zealand | S0023 | NEW-Research Institute | 15 | 0 | 0 | 0 | CLOSED | Dr. David Brown | Dr. Amanda Jones | 2020-05-27 | 2020-06-19 | 2020-06-16 | 2020-07-22 | 2020-07-18 | 2020-08-10 | 2020-07-29 | 2020-08-27 | 2020-09-04 | 2020-09-08 | 2020-09-22 | 2020-11-29 | 2020-12-02 | 2021-01-18 | 2021-01-12 | 2028-08-19 |  | 2028-10-19 |  | 2029-01-29 |  | 2029-03-17 |  | 2029-04-08
6347 | ST-2025-027 | Mexico | S0001 | MEXI-Medical Center | 2 | 1 | 50 | 0.1 | SCREENING | Dr. Robert Jones | Dr. Robert Jackson | 2022-09-18 | 2022-10-20 | 2022-10-14 | 2022-11-16 | 2022-11-02 | 2022-12-07 | 2022-12-10 | 2022-12-18 | 2022-12-25 | 2023-01-03 | 2023-01-16 | 2023-04-04 | 2023-04-14 | 2023-05-23 | 2023-06-02 | 2026-06-07 |  | 2026-08-02 |  | 2026-11-24 |  | 2027-01-04 |  | 2027-01-23
6348 | ST-2025-027 | Mexico | S0002 | MEXI-Health System | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Sarah Thomas | Dr. Lisa White | 2022-09-23 | 2022-10-22 | 2022-10-16 | 2022-11-24 | 2022-11-16 | 2022-12-14 | 2022-12-18 | 2022-12-31 | 2023-01-06 | 2023-01-16 | 2023-01-27 | 2023-04-06 | 2023-04-19 | 2023-06-03 | 2023-06-13 | 2026-06-07 |  | 2026-07-31 |  | 2026-12-03 |  | 2027-01-12 |  | 2027-02-01
6349 | ST-2025-027 | Mexico | S0003 | MEXI-General Hospital | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. Christopher Thomas | Dr. Christopher Thompson | 2022-09-19 | 2022-10-15 | 2022-10-19 | 2022-11-13 | 2022-11-14 | 2022-12-04 | 2022-12-13 | 2022-12-16 | 2022-12-07 | 2022-12-30 | 2023-01-05 | 2023-03-31 | 2023-03-26 | 2023-05-26 | 2023-05-12 | 2026-06-04 |  | 2026-08-01 |  | 2026-12-01 |  | 2027-01-09 |  | 2027-01-28
6350 | ST-2025-027 | Mexico | S0004 | MEXI-Research Institute | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Daniel Davis | Dr. Jessica Williams | 2022-09-26 | 2022-10-21 | 2022-10-19 | 2022-11-19 | 2022-11-08 | 2022-12-15 | 2022-12-24 | 2022-12-30 | 2023-01-01 | 2023-01-11 | 2023-01-01 | 2023-04-03 | 2023-04-12 | 2023-05-24 | 2023-06-03 | 2026-06-06 |  | 2026-08-02 |  | 2026-12-05 |  | 2027-01-18 |  | 2027-02-10
6351 | ST-2025-027 | Mexico | S0005 | MEXI-Research Institute | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Michael Williams | Dr. Michael Davis | 2022-09-21 | 2022-10-15 | 2022-10-25 | 2022-11-13 | 2022-11-01 | 2022-12-05 | 2022-11-29 | 2022-12-16 | 2022-12-06 | 2022-12-27 | 2023-01-02 | 2023-04-28 | 2023-05-03 | 2023-06-16 | 2023-06-02 | 2026-06-30 |  | 2026-08-30 |  | 2026-12-15 |  | 2027-01-23 |  | 2027-02-11
6352 | ST-2025-027 | Mexico | S0006 | MEXI-Medical Center | 3 | 7 | 233.3 | 0.9 | SCREENING | Dr. Sarah Williams | Dr. Jessica Moore | 2022-09-12 | 2022-10-06 | 2022-09-27 | 2022-11-06 | 2022-11-01 | 2022-11-27 | 2022-11-23 | 2022-12-14 | 2022-12-15 | 2022-12-30 | 2022-12-20 | 2023-04-22 | 2023-04-15 | 2023-06-13 | 2023-05-31 | 2026-06-26 |  | 2026-08-23 |  | 2026-12-30 |  | 2027-02-12 |  | 2027-03-08
6353 | ST-2025-027 | Canada | S0007 | CANA-Clinical Center | 4 | 2 | 50 | 0.1 | ON_HOLD | Dr. Robert Martin | Dr. Nicole Thompson | 2022-10-01 | 2022-11-03 | 2022-11-02 | 2022-12-04 | 2022-11-24 | 2022-12-21 | 2022-12-07 | 2023-01-01 | 2022-12-25 | 2023-01-18 | 2023-01-04 | 2023-04-03 | 2023-03-27 | 2023-05-23 | 2023-05-22 | 2026-06-18 |  | 2026-08-12 |  | 2026-11-25 |  | 2027-01-09 |  | 2027-02-02
6354 | ST-2025-027 | Canada | S0008 | CANA-General Hospital | 3 | 4 | 133.3 | 0.2 | ON_HOLD | Dr. Emily Jackson | Dr. James Miller | 2022-10-02 | 2022-11-04 | 2022-10-28 | 2022-12-01 | 2022-11-20 | 2022-12-20 | 2022-12-15 | 2023-01-05 | 2023-01-02 | 2023-01-19 | 2023-01-07 | 2023-04-17 | 2023-04-22 | 2023-06-19 | 2023-06-15 | 2026-06-25 |  | 2026-08-16 |  | 2026-12-05 |  | 2027-01-13 |  | 2027-01-31
6355 | ST-2025-027 | United States | S0009 | UNIT-University Hospital | 3 | 3 | 100 | 0.2 | CLOSED | Dr. Daniel Johnson | Dr. Christopher Garcia | 2022-10-03 | 2022-10-27 | 2022-10-17 | 2022-11-19 | 2022-12-03 | 2022-12-14 | 2022-12-21 | 2022-12-26 | 2023-01-02 | 2023-01-07 | 2023-01-02 | 2023-04-08 | 2023-04-13 | 2023-06-04 | 2023-06-16 | 2026-06-08 |  | 2026-08-07 |  | 2026-11-21 |  | 2027-01-07 |  | 2027-01-28
6356 | ST-2025-027 | United States | S0010 | UNIT-General Hospital | 3 | 3 | 100 | 0.2 | CLOSED | Dr. Lisa Garcia | Dr. Michael Thomas | 2022-10-03 | 2022-10-27 | 2022-11-02 | 2022-11-23 | 2022-11-13 | 2022-12-16 | 2022-12-12 | 2023-01-01 | 2022-12-22 | 2023-01-14 | 2023-01-12 | 2023-04-20 | 2023-04-20 | 2023-06-12 | 2023-06-21 | 2026-06-19 |  | 2026-08-10 |  | 2026-11-23 |  | 2027-01-01 |  | 2027-01-25
6357 | ST-2025-027 | United States | S0011 | UNIT-Cancer Center | 3 | 0 | 0 | 0 | CLOSED | Dr. Amanda Johnson | Dr. Stephanie Martin | 2022-09-26 | 2022-10-20 | 2022-10-18 | 2022-11-13 | 2022-11-10 | 2022-12-08 | 2022-12-04 | 2022-12-22 | 2022-12-23 | 2023-01-07 | 2023-01-06 | 2023-04-18 | 2023-04-19 | 2023-06-08 | 2023-06-16 | 2026-06-16 |  | 2026-08-11 |  | 2026-12-03 |  | 2027-01-11 |  | 2027-02-04
6358 | ST-2025-027 | Switzerland | S0012 | SWIT-General Hospital | 7 | 4 | 57.1 | 0.4 | ON_HOLD | Dr. Emily Anderson | Dr. Jessica Martin | 2022-10-10 | 2022-11-12 | 2022-11-15 | 2022-12-10 | 2022-12-11 | 2022-12-28 | 2022-12-31 | 2023-01-14 | 2023-01-17 | 2023-01-30 | 2023-02-11 | 2023-04-26 | 2023-04-19 | 2023-06-17 | 2023-06-15 | 2026-06-13 |  | 2026-08-09 |  | 2026-11-27 |  | 2027-01-10 |  | 2027-02-01
6359 | ST-2025-027 | Switzerland | S0013 | SWIT-Research Institute | 5 | 7 | 140 | 0.7 | ENROLLING | Dr. James Jackson | Dr. David Anderson | 2022-10-12 | 2022-11-10 | 2022-11-02 | 2022-12-11 | 2022-12-24 | 2023-01-05 | 2022-12-22 | 2023-01-22 | 2023-01-19 | 2023-02-07 | 2023-02-10 | 2023-04-27 | 2023-04-28 | 2023-06-26 | 2023-06-16 | 2026-06-13 |  | 2026-08-04 |  | 2026-11-25 |  | 2027-01-06 |  | 2027-01-24
6360 | ST-2025-027 | Spain | S0014 | SPAI-Clinical Center | 2 | 2 | 100 | 0.2 | ON_HOLD | Dr. Amanda Brown | Dr. James Thomas | 2022-10-04 | 2022-11-01 | 2022-11-13 | 2022-11-29 | 2022-11-22 | 2022-12-17 | 2022-12-04 | 2022-12-30 | 2023-01-08 | 2023-01-13 | 2023-01-03 | 2023-04-15 | 2023-04-04 | 2023-06-16 | 2023-06-24 | 2026-06-22 |  | 2026-08-20 |  | 2026-11-25 |  | 2027-01-04 |  | 2027-01-23
6361 | ST-2025-027 | Spain | S0015 | SPAI-General Hospital | 3 | 3 | 100 | 0.4 | ON_HOLD | Dr. Amanda Smith | Dr. Emily White | 2022-10-10 | 2022-11-02 | 2022-10-24 | 2022-12-01 | 2022-11-17 | 2022-12-22 | 2022-12-12 | 2023-01-02 | 2022-12-30 | 2023-01-18 | 2023-01-08 | 2023-04-20 | 2023-04-08 | 2023-06-18 | 2023-06-11 | 2026-06-24 |  | 2026-08-15 |  | 2026-12-02 |  | 2027-01-17 |  | 2027-02-10
6362 | ST-2025-027 | Spain | S0016 | SPAI-Clinical Center | 3 | 1 | 33.3 | 0.1 | SCREENING | Dr. Daniel Thompson | Dr. Robert White | 2022-10-13 | 2022-11-11 | 2022-11-07 | 2022-12-06 | 2022-12-06 | 2022-12-24 | 2023-01-04 | 2023-01-07 | 2023-01-13 | 2023-01-23 | 2023-01-31 | 2023-04-20 | 2023-04-06 | 2023-06-19 | 2023-06-14 | 2026-06-22 |  | 2026-08-16 |  | 2026-12-01 |  | 2027-01-13 |  | 2027-02-05
6363 | ST-2025-027 | Spain | S0017 | SPAI-Medical Center | 3 | 1 | 33.3 | 0.1 | SCREENING | Dr. Robert Wilson | Dr. Lisa Martin | 2022-10-04 | 2022-11-06 | 2022-11-09 | 2022-11-29 | 2022-12-07 | 2022-12-24 | 2023-01-05 | 2023-01-10 | 2023-01-04 | 2023-01-22 | 2023-01-26 | 2023-04-29 | 2023-05-01 | 2023-06-19 | 2023-06-14 | 2026-06-17 |  | 2026-08-13 |  | 2026-12-03 |  | 2027-01-19 |  | 2027-02-09
6364 | ST-2025-027 | Spain | S0018 | SPAI-Clinical Center | 3 | 3 | 100 | 0.3 | ON_HOLD | Dr. Amanda White | Dr. Jennifer Moore | 2022-10-10 | 2022-11-04 | 2022-11-02 | 2022-12-01 | 2022-11-22 | 2022-12-18 | 2022-12-30 | 2023-01-02 | 2023-01-11 | 2023-01-16 | 2023-01-19 | 2023-05-07 | 2023-05-12 | 2023-07-06 | 2023-07-18 | 2026-07-04 |  | 2026-08-30 |  | 2026-12-20 |  | 2027-01-26 |  | 2027-02-14
6365 | ST-2025-027 | United Kingdom | S0019 | UNIT-Medical Center | -3 | -3 | 100 | -0.4 | ON_HOLD | Dr. Stephanie Taylor | Dr. Sarah Garcia | 2022-10-23 | 2022-11-22 | 2022-11-21 | 2022-12-22 | 2022-12-14 | 2023-01-12 | 2023-01-06 | 2023-01-28 | 2023-01-17 | 2023-02-13 | 2023-02-02 | 2023-04-25 | 2023-04-13 | 2023-06-26 | 2023-06-23 | 2026-07-03 |  | 2026-08-25 |  | 2026-11-19 |  | 2026-12-31 |  | 2027-01-23
6366 | ST-2025-027 | United Kingdom | S0020 | UNIT-General Hospital | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. William Brown | Dr. Stephanie Martin | 2022-10-25 | 2022-11-22 | 2022-11-17 | 2022-12-15 | 2022-12-07 | 2023-01-03 | 2023-01-06 | 2023-01-16 | 2023-01-08 | 2023-01-28 | 2023-02-03 | 2023-05-02 | 2023-04-19 | 2023-06-21 | 2023-06-14 | 2026-07-03 |  | 2026-08-26 |  | 2026-12-03 |  | 2027-01-09 |  | 2027-02-02
6367 | ST-2025-027 | United Kingdom | S0021 | UNIT-Health System | 3 | 3 | 100 | 0.2 | CLOSED | Dr. Robert Taylor | Dr. Charles Thompson | 2022-10-21 | 2022-11-22 | 2022-12-02 | 2022-12-15 | 2022-12-10 | 2023-01-09 | 2023-01-07 | 2023-01-26 | 2023-01-28 | 2023-02-09 | 2023-02-01 | 2023-04-26 | 2023-04-22 | 2023-06-14 | 2023-06-24 | 2026-07-09 |  | 2026-08-30 |  | 2026-11-30 |  | 2027-01-06 |  | 2027-01-26
6368 | ST-2025-027 | United Kingdom | S0022 | UNIT-General Hospital | 3 | 2 | 66.7 | 0.1 | ON_HOLD | Dr. Robert Brown | Dr. Emily Smith | 2022-10-17 | 2022-11-11 | 2022-11-15 | 2022-12-14 | 2022-12-25 | 2022-12-31 | 2022-12-29 | 2023-01-13 | 2023-01-14 | 2023-01-27 | 2023-01-31 | 2023-05-15 | 2023-05-28 | 2023-07-14 | 2023-07-27 | 2026-07-17 |  | 2026-09-07 |  | 2026-12-09 |  | 2027-01-17 |  | 2027-02-04
6369 | ST-2025-027 | United Kingdom | S0023 | UNIT-University Hospital | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. Daniel Smith | Dr. Lisa Johnson | 2022-10-14 | 2022-11-08 | 2022-11-18 | 2022-12-11 | 2022-12-19 | 2023-01-03 | 2022-12-25 | 2023-01-14 | 2023-01-16 | 2023-01-30 | 2023-02-01 | 2023-04-29 | 2023-05-08 | 2023-06-28 | 2023-07-03 | 2026-07-09 |  | 2026-09-01 |  | 2026-12-08 |  | 2027-01-24 |  | 2027-02-12
6370 | ST-2025-027 | United Kingdom | S0024 | UNIT-General Hospital | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. James White | Dr. Nicole Anderson | 2022-10-26 | 2022-11-23 | 2022-11-16 | 2022-12-23 | 2022-12-15 | 2023-01-10 | 2023-01-15 | 2023-01-23 | 2023-01-28 | 2023-02-05 | 2023-01-24 | 2023-05-20 | 2023-05-10 | 2023-07-17 | 2023-07-21 | 2026-08-05 |  | 2026-10-01 |  | 2026-12-15 |  | 2027-01-31 |  | 2027-02-21
6371 | ST-2025-027 | India | S0025 | INDI-Health System | 6 | 5 | 83.3 | 0.6 | CLOSED | Dr. Daniel Garcia | Dr. Lisa Wilson | 2022-11-17 | 2022-12-11 | 2022-12-07 | 2023-01-03 | 2022-12-25 | 2023-01-21 | 2023-01-16 | 2023-02-07 | 2023-01-29 | 2023-02-24 | 2023-02-12 | 2023-05-21 | 2023-05-15 | 2023-07-17 | 2023-07-21 | 2026-08-01 |  | 2026-09-22 |  | 2026-11-30 |  | 2027-01-07 |  | 2027-01-28
6372 | ST-2025-027 | India | S0026 | INDI-Cancer Center | 4 | 2 | 50 | 0.3 | ON_HOLD | Dr. Lisa White | Dr. David Martin | 2022-11-11 | 2022-12-05 | 2022-12-09 | 2022-12-30 | 2022-12-31 | 2023-01-22 | 2023-01-09 | 2023-02-04 | 2023-02-01 | 2023-02-18 | 2023-03-03 | 2023-05-25 | 2023-05-20 | 2023-07-25 | 2023-07-23 | 2026-08-06 |  | 2026-10-03 |  | 2026-12-07 |  | 2027-01-15 |  | 2027-02-02
6373 | ST-2025-027 | Singapore | S0027 | SING-University Hospital | -8 | -8 | 100 | -1 | ENROLLING | Dr. James Miller | Dr. Michael Johnson | 2022-11-27 | 2022-12-30 | 2023-01-01 | 2023-01-24 | 2023-01-24 | 2023-02-16 | 2023-02-10 | 2023-03-01 | 2023-03-15 | 2023-03-16 | 2023-03-30 | 2023-06-07 | 2023-06-14 | 2023-08-04 | 2023-07-22 | 2026-07-22 |  | 2026-09-16 |  | 2026-11-15 |  | 2027-01-01 |  | 2027-01-22
6374 | ST-2025-027 | Singapore | S0028 | SING-Clinical Center | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Jessica Davis | Dr. Lisa Taylor | 2022-11-28 | 2022-12-21 | 2023-01-03 | 2023-01-16 | 2023-01-04 | 2023-02-09 | 2023-02-02 | 2023-02-20 | 2023-02-18 | 2023-03-04 | 2023-03-17 | 2023-06-12 | 2023-06-12 | 2023-08-01 | 2023-08-08 | 2026-07-26 |  | 2026-09-21 |  | 2026-11-21 |  | 2027-01-06 |  | 2027-01-27
6375 | ST-2025-027 | Singapore | S0029 | SING-Clinical Center | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Daniel White | Dr. Sarah Anderson | 2022-11-25 | 2022-12-25 | 2022-12-23 | 2023-01-27 | 2023-01-23 | 2023-02-20 | 2023-02-08 | 2023-03-09 | 2023-03-05 | 2023-03-23 | 2023-03-19 | 2023-05-31 | 2023-06-05 | 2023-07-20 | 2023-07-21 | 2026-07-24 |  | 2026-09-14 |  | 2026-11-25 |  | 2027-01-07 |  | 2027-01-26
6376 | ST-2025-027 | Singapore | S0030 | SING-Medical Center | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. William Thomas | Dr. Stephanie Davis | 2022-11-29 | 2022-12-29 | 2023-01-02 | 2023-01-22 | 2023-01-09 | 2023-02-11 | 2023-02-16 | 2023-02-25 | 2023-03-07 | 2023-03-08 | 2023-03-06 | 2023-06-11 | 2023-05-29 | 2023-08-01 | 2023-08-12 | 2026-08-02 |  | 2026-09-24 |  | 2026-12-03 |  | 2027-01-12 |  | 2027-02-01
6377 | ST-2025-027 | Singapore | S0031 | SING-Research Institute | 3 | 1 | 33.3 | 0.2 | ENROLLING | Dr. Sarah Smith | Dr. Sarah Taylor | 2022-11-24 | 2022-12-24 | 2022-12-15 | 2023-01-19 | 2023-01-07 | 2023-02-04 | 2023-01-25 | 2023-02-16 | 2023-02-04 | 2023-03-05 | 2023-02-27 | 2023-06-09 | 2023-06-07 | 2023-08-09 | 2023-07-28 | 2026-08-11 |  | 2026-10-07 |  | 2026-12-03 |  | 2027-01-13 |  | 2027-02-05
6378 | ST-2025-027 | Singapore | S0032 | SING-University Hospital | 3 | 18 | 600 | 1.8 | ENROLLING | Dr. William Brown | Dr. Stephanie Garcia | 2022-11-29 | 2022-12-29 | 2023-01-08 | 2023-01-27 | 2023-01-22 | 2023-02-20 | 2023-02-11 | 2023-03-04 | 2023-02-24 | 2023-03-20 | 2023-03-17 | 2023-06-26 | 2023-06-25 | 2023-08-18 | 2023-08-19 | 2026-08-06 |  | 2026-09-26 |  | 2026-12-03 |  | 2027-01-15 |  | 2027-02-04
6379 | ST-2025-028 | Canada | S0001 | CANA-General Hospital | 10148 | 5228 | 51.5 | 326.8 | ON_HOLD | Dr. Jessica Thomas | Dr. Emily Wilson | 2025-04-05 | 2025-04-30 | 2025-05-09 | 2025-05-29 | 2025-06-05 | 2025-06-19 | 2025-06-23 | 2025-07-05 | 2025-07-10 | 2025-07-20 | 2025-07-10 | 2025-10-08 | 2025-10-04 | 2025-12-09 | 2025-12-16 | 2028-06-23 |  | 2028-08-21 |  | 2029-01-01 |  | 2029-02-10 |  | 2029-02-28
6380 | ST-2025-028 | Canada | S0002 | CANA-Clinical Center | 10883 | 0 | 0 | 0 | ON_HOLD | Dr. William Williams | Dr. James Jones | 2025-04-05 | 2025-05-03 | 2025-05-05 | 2025-05-26 | 2025-06-04 | 2025-06-13 | 2025-05-30 | 2025-06-27 | 2025-06-27 | 2025-07-09 | 2025-07-21 | 2025-10-16 | 2025-10-29 | 2025-12-17 | 2025-12-07 | 2028-07-05 |  | 2028-08-26 |  | 2029-01-09 |  | 2029-02-21 |  | 2029-03-13
6381 | ST-2025-028 | Denmark | S0003 | DENM-Medical Center | 11480 | 0 | 0 | 0 | ON_HOLD | Dr. William Jones | Dr. Michael Taylor | 2025-04-10 | 2025-05-12 | 2025-05-04 | 2025-06-05 | 2025-06-02 | 2025-06-21 | 2025-06-13 | 2025-07-03 | 2025-06-25 | 2025-07-19 | 2025-07-26 | 2025-10-07 | 2025-10-11 | 2025-12-01 | 2025-11-17 | 2028-07-13 |  | 2028-09-10 |  | 2028-12-21 |  | 2029-02-05 |  | 2029-02-26
6382 | ST-2025-028 | Denmark | S0004 | DENM-University Hospital | 5807 | 0 | 0 | 0 | ON_HOLD | Dr. Amanda Taylor | Dr. Nicole White | 2025-04-05 | 2025-04-28 | 2025-04-27 | 2025-05-25 | 2025-05-22 | 2025-06-14 | 2025-06-11 | 2025-06-29 | 2025-07-11 | 2025-07-16 | 2025-07-19 | 2025-10-21 | 2025-10-20 | 2025-12-10 | 2025-12-12 | 2028-07-17 |  | 2028-09-13 |  | 2029-01-02 |  | 2029-02-15 |  | 2029-03-08
6383 | ST-2025-028 | Denmark | S0005 | DENM-Clinical Center | 5818 | 0 | 0 | 0 | ON_HOLD | Dr. Thomas Jones | Dr. Lisa Jackson | 2025-04-05 | 2025-04-29 | 2025-04-24 | 2025-05-24 | 2025-06-06 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-08 | 2025-07-13 | 2025-07-20 | 2025-10-20 | 2025-10-19 | 2025-12-16 | 2025-12-22 | 2028-07-25 |  | 2028-09-16 |  | 2029-01-10 |  | 2029-02-22 |  | 2029-03-15
6384 | ST-2025-028 | Denmark | S0006 | DENM-Clinical Center | 8503 | 0 | 0 | 0 | ON_HOLD | Dr. Michelle Moore | Dr. Nicole Moore | 2025-04-09 | 2025-05-03 | 2025-05-13 | 2025-05-27 | 2025-06-01 | 2025-06-13 | 2025-06-16 | 2025-06-24 | 2025-06-13 | 2025-07-10 | 2025-07-16 | 2025-10-14 | 2025-10-14 | 2025-12-11 | 2025-12-13 | 2028-07-26 |  | 2028-09-21 |  | 2028-12-30 |  | 2029-02-12 |  | 2029-03-07
6385 | ST-2025-028 | Australia | S0007 | AUST-Cancer Center | 6775 | 0 | 0 | 0 | CLOSED | Dr. Lisa Williams | Dr. Lisa Thomas | 2025-04-12 | 2025-05-15 | 2025-05-16 | 2025-06-11 | 2025-05-31 | 2025-07-03 | 2025-06-30 | 2025-07-15 | 2025-07-26 | 2025-07-27 | 2025-07-27 | 2025-10-25 | 2025-10-24 | 2025-12-20 | 2026-01-01 | 2028-07-13 |  | 2028-09-08 |  | 2028-12-23 |  | 2029-02-01 |  | 2029-02-25
6386 | ST-2025-028 | Australia | S0008 | AUST-Medical Center | 4772 | 0 | 0 | 0 | SCREENING | Dr. Amanda Moore | Dr. Nicole Jones | 2025-04-24 | 2025-05-23 | 2025-06-06 | 2025-06-15 | 2025-06-26 | 2025-07-06 | 2025-07-05 | 2025-07-23 | 2025-07-30 | 2025-08-04 | 2025-07-28 | 2025-10-26 | 2025-10-12 | 2025-12-18 | 2026-01-01 | 2028-07-14 |  | 2028-09-13 |  | 2028-12-31 |  | 2029-02-10 |  | 2029-03-06
6387 | ST-2025-028 | Australia | S0009 | AUST-Medical Center | 3814 | 0 | 0 | 0 | ON_HOLD | Dr. Amanda Jones | Dr. Jessica Harris | 2025-04-12 | 2025-05-05 | 2025-05-09 | 2025-05-28 | 2025-05-27 | 2025-06-15 | 2025-06-08 | 2025-07-02 | 2025-07-05 | 2025-07-15 | 2025-07-13 | 2025-11-08 | 2025-10-31 | 2026-01-09 | 2026-01-14 | 2028-07-26 |  | 2028-09-24 |  | 2029-01-09 |  | 2029-02-20 |  | 2029-03-11
6388 | ST-2025-029 | Mexico | S0001 | MEXI-Cancer Center | 18 | 16 | 88.9 | 2.3 | SCREENING | Dr. Emily Harris | Dr. Thomas Garcia | 2024-01-17 | 2024-02-09 | 2024-02-08 | 2024-03-12 | 2024-03-05 | 2024-04-03 | 2024-03-23 | 2024-04-15 | 2024-04-23 | 2024-05-01 | 2024-05-12 | 2024-07-14 | 2024-07-04 | 2024-09-12 | 2024-09-14 | 2026-06-22 |  | 2026-08-18 |  | 2026-12-14 |  | 2027-01-28 |  | 2027-02-16
6389 | ST-2025-029 | Mexico | S0002 | MEXI-Research Institute | 8 | 8 | 100 | 1 | ENROLLING | Dr. William Thomas | Dr. Amanda Williams | 2024-01-13 | 2024-02-11 | 2024-01-28 | 2024-03-15 | 2024-03-21 | 2024-04-04 | 2024-04-14 | 2024-04-21 | 2024-04-25 | 2024-05-06 | 2024-04-26 | 2024-07-13 | 2024-06-29 | 2024-09-05 | 2024-09-10 | 2026-06-26 |  | 2026-08-17 |  | 2026-12-13 |  | 2027-01-19 |  | 2027-02-09
6390 | ST-2025-029 | Mexico | S0003 | MEXI-Medical Center | 17 | 11 | 64.7 | 1.4 | ON_HOLD | Dr. Christopher Wilson | Dr. Nicole Wilson | 2024-01-18 | 2024-02-11 | 2024-02-04 | 2024-03-14 | 2024-03-20 | 2024-04-05 | 2024-04-19 | 2024-04-16 | 2024-04-09 | 2024-05-02 | 2024-04-27 | 2024-07-30 | 2024-07-22 | 2024-09-19 | 2024-09-22 | 2026-07-08 |  | 2026-09-07 |  | 2026-12-30 |  | 2027-02-10 |  | 2027-03-01
6391 | ST-2025-029 | United States | S0004 | UNIT-Clinical Center | 5 | 4 | 80 | 0.4 | CLOSED | Dr. Thomas Thomas | Dr. Michael White | 2024-01-20 | 2024-02-18 | 2024-03-02 | 2024-03-16 | 2024-03-05 | 2024-04-11 | 2024-03-31 | 2024-04-22 | 2024-04-22 | 2024-05-05 | 2024-05-10 | 2024-07-15 | 2024-07-04 | 2024-09-16 | 2024-09-05 | 2026-06-23 |  | 2026-08-23 |  | 2026-12-16 |  | 2027-02-01 |  | 2027-02-23
6392 | ST-2025-029 | United States | S0005 | UNIT-Health System | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. Sarah Johnson | Dr. Lisa Moore | 2024-01-13 | 2024-02-07 | 2024-02-18 | 2024-03-02 | 2024-02-17 | 2024-03-19 | 2024-03-18 | 2024-04-02 | 2024-03-21 | 2024-04-19 | 2024-04-20 | 2024-07-22 | 2024-07-28 | 2024-09-23 | 2024-09-11 | 2026-07-07 |  | 2026-08-30 |  | 2026-12-25 |  | 2027-02-01 |  | 2027-02-22
6393 | ST-2025-029 | United States | S0006 | UNIT-Medical Center | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Jessica Jackson | Dr. Jennifer Jackson | 2024-01-15 | 2024-02-13 | 2024-02-19 | 2024-03-12 | 2024-03-17 | 2024-04-07 | 2024-04-20 | 2024-04-21 | 2024-04-08 | 2024-05-08 | 2024-04-27 | 2024-07-22 | 2024-07-18 | 2024-09-11 | 2024-09-08 | 2026-07-01 |  | 2026-08-21 |  | 2026-12-24 |  | 2027-02-09 |  | 2027-03-03
6394 | ST-2025-029 | United States | S0007 | UNIT-Cancer Center | 3 | 2 | 66.7 | 0.3 | SCREENING | Dr. Charles Harris | Dr. Michael Thomas | 2024-01-18 | 2024-02-19 | 2024-02-22 | 2024-03-21 | 2024-03-07 | 2024-04-06 | 2024-04-08 | 2024-04-18 | 2024-04-20 | 2024-05-03 | 2024-05-13 | 2024-08-07 | 2024-07-28 | 2024-09-29 | 2024-09-21 | 2026-07-18 |  | 2026-09-08 |  | 2027-01-01 |  | 2027-02-16 |  | 2027-03-06
6395 | ST-2025-029 | United States | S0008 | UNIT-Clinical Center | 3 | 3 | 100 | 0.2 | CLOSED | Dr. Michelle Harris | Dr. Emily Williams | 2024-01-10 | 2024-02-05 | 2024-01-28 | 2024-02-28 | 2024-02-16 | 2024-03-20 | 2024-03-17 | 2024-04-01 | 2024-04-09 | 2024-04-13 | 2024-04-16 | 2024-08-09 | 2024-08-15 | 2024-10-08 | 2024-10-03 | 2026-07-27 |  | 2026-09-18 |  | 2027-01-14 |  | 2027-02-24 |  | 2027-03-17
6396 | ST-2025-029 | United States | S0009 | UNIT-University Hospital | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Charles White | Dr. David Jackson | 2024-01-21 | 2024-02-20 | 2024-02-24 | 2024-03-20 | 2024-03-31 | 2024-04-13 | 2024-04-23 | 2024-04-27 | 2024-05-01 | 2024-05-09 | 2024-05-04 | 2024-08-09 | 2024-07-31 | 2024-09-29 | 2024-10-10 | 2026-07-16 |  | 2026-09-15 |  | 2027-01-11 |  | 2027-02-23 |  | 2027-03-13
6397 | ST-2025-029 | Netherlands | S0010 | NETH-Clinical Center | 7 | 6 | 85.7 | 0.8 | ON_HOLD | Dr. David Taylor | Dr. Sarah Jackson | 2024-01-30 | 2024-02-29 | 2024-02-27 | 2024-03-29 | 2024-03-28 | 2024-04-21 | 2024-04-13 | 2024-05-05 | 2024-05-09 | 2024-05-20 | 2024-05-17 | 2024-08-02 | 2024-07-30 | 2024-09-24 | 2024-10-08 | 2026-07-13 |  | 2026-09-07 |  | 2026-12-28 |  | 2027-02-04 |  | 2027-02-26
6398 | ST-2025-029 | Netherlands | S0011 | NETH-Medical Center | 5 | 3 | 60 | 0.2 | SCREENING | Dr. Stephanie Martin | Dr. David Johnson | 2024-01-20 | 2024-02-19 | 2024-02-17 | 2024-03-15 | 2024-03-01 | 2024-03-31 | 2024-03-20 | 2024-04-15 | 2024-04-06 | 2024-04-28 | 2024-05-09 | 2024-08-05 | 2024-08-01 | 2024-09-29 | 2024-09-28 | 2026-07-09 |  | 2026-09-07 |  | 2027-01-03 |  | 2027-02-17 |  | 2027-03-09
6399 | ST-2025-029 | Netherlands | S0012 | NETH-University Hospital | 9 | 5 | 55.6 | 0.8 | ON_HOLD | Dr. Stephanie Wilson | Dr. William Garcia | 2024-01-24 | 2024-02-19 | 2024-02-27 | 2024-03-14 | 2024-02-29 | 2024-04-02 | 2024-04-10 | 2024-04-18 | 2024-04-14 | 2024-05-01 | 2024-04-23 | 2024-08-08 | 2024-08-08 | 2024-09-28 | 2024-10-02 | 2026-07-24 |  | 2026-09-18 |  | 2027-01-01 |  | 2027-02-07 |  | 2027-02-27
6400 | ST-2025-029 | Netherlands | S0013 | NETH-Medical Center | 6 | 4 | 66.7 | 0.5 | ENROLLING | Dr. William Jackson | Dr. Michael Anderson | 2024-02-02 | 2024-02-28 | 2024-03-07 | 2024-03-30 | 2024-04-04 | 2024-04-16 | 2024-04-30 | 2024-04-30 | 2024-05-11 | 2024-05-13 | 2024-05-26 | 2024-08-18 | 2024-08-25 | 2024-10-09 | 2024-09-27 | 2026-07-26 |  | 2026-09-18 |  | 2027-01-07 |  | 2027-02-21 |  | 2027-03-13
6401 | ST-2025-029 | Netherlands | S0014 | NETH-Cancer Center | 7 | 12 | 171.4 | 0.7 | SCREENING | Dr. Stephanie Thompson | Dr. David Wilson | 2024-01-29 | 2024-02-27 | 2024-02-21 | 2024-03-31 | 2024-03-30 | 2024-04-22 | 2024-04-11 | 2024-05-05 | 2024-04-24 | 2024-05-22 | 2024-05-22 | 2024-08-16 | 2024-08-07 | 2024-10-07 | 2024-10-12 | 2026-07-23 |  | 2026-09-12 |  | 2027-01-15 |  | 2027-02-28 |  | 2027-03-18
6402 | ST-2025-029 | Belgium | S0015 | BELG-Clinical Center | 6 | 6 | 100 | 0.5 | ENROLLING | Dr. Michelle Garcia | Dr. Stephanie Thomas | 2024-02-10 | 2024-03-07 | 2024-02-26 | 2024-04-08 | 2024-04-20 | 2024-04-24 | 2024-04-22 | 2024-05-07 | 2024-04-24 | 2024-05-18 | 2024-06-01 | 2024-08-24 | 2024-08-27 | 2024-10-24 | 2024-10-26 | 2026-07-25 |  | 2026-09-23 |  | 2026-12-19 |  | 2027-02-01 |  | 2027-02-21
6403 | ST-2025-029 | Belgium | S0016 | BELG-General Hospital | 4 | 3 | 75 | 0.2 | ENROLLING | Dr. James Moore | Dr. David Williams | 2024-02-14 | 2024-03-08 | 2024-03-05 | 2024-04-01 | 2024-03-30 | 2024-04-24 | 2024-04-12 | 2024-05-05 | 2024-05-08 | 2024-05-22 | 2024-06-01 | 2024-08-28 | 2024-08-24 | 2024-10-22 | 2024-10-23 | 2026-07-25 |  | 2026-09-18 |  | 2026-12-25 |  | 2027-02-05 |  | 2027-03-01
6404 | ST-2025-029 | Belgium | S0017 | BELG-General Hospital | 10 | 7 | 70 | 0.4 | SCREENING | Dr. Robert Taylor | Dr. Thomas Smith | 2024-02-10 | 2024-03-08 | 2024-03-01 | 2024-04-07 | 2024-03-25 | 2024-04-30 | 2024-05-12 | 2024-05-17 | 2024-05-03 | 2024-06-02 | 2024-05-23 | 2024-09-07 | 2024-08-27 | 2024-10-27 | 2024-10-23 | 2026-08-04 |  | 2026-09-29 |  | 2027-01-07 |  | 2027-02-14 |  | 2027-03-04
6405 | ST-2025-029 | Belgium | S0018 | BELG-University Hospital | 7 | 11 | 157.1 | 0.8 | ENROLLING | Dr. Nicole Taylor | Dr. Emily White | 2024-02-15 | 2024-03-15 | 2024-03-28 | 2024-04-10 | 2024-03-28 | 2024-04-28 | 2024-04-22 | 2024-05-09 | 2024-05-23 | 2024-05-21 | 2024-06-01 | 2024-09-13 | 2024-08-31 | 2024-11-15 | 2024-11-04 | 2026-08-12 |  | 2026-10-07 |  | 2027-01-15 |  | 2027-02-21 |  | 2027-03-16
6406 | ST-2025-029 | Australia | S0019 | AUST-General Hospital | 6 | 5 | 83.3 | 0.6 | ON_HOLD | Dr. Michelle Garcia | Dr. Charles Miller | 2024-02-12 | 2024-03-07 | 2024-03-07 | 2024-04-03 | 2024-03-23 | 2024-04-24 | 2024-04-14 | 2024-05-10 | 2024-05-06 | 2024-05-25 | 2024-06-07 | 2024-08-31 | 2024-08-21 | 2024-10-31 | 2024-11-10 | 2026-07-16 |  | 2026-09-09 |  | 2026-12-15 |  | 2027-01-23 |  | 2027-02-14
6407 | ST-2025-029 | Australia | S0020 | AUST-Research Institute | 6 | 4 | 66.7 | 0.4 | SCREENING | Dr. James Thomas | Dr. Amanda Smith | 2024-02-21 | 2024-03-21 | 2024-03-15 | 2024-04-23 | 2024-04-19 | 2024-05-16 | 2024-05-26 | 2024-06-01 | 2024-06-10 | 2024-06-12 | 2024-06-13 | 2024-09-01 | 2024-08-25 | 2024-10-28 | 2024-10-16 | 2026-07-18 |  | 2026-09-16 |  | 2026-12-25 |  | 2027-02-10 |  | 2027-03-03
6408 | ST-2025-029 | Australia | S0021 | AUST-Research Institute | 8 | 0 | 0 | 0 | CLOSED | Dr. Emily Martin | Dr. Christopher White | 2024-02-12 | 2024-03-07 | 2024-02-23 | 2024-04-04 | 2024-03-27 | 2024-04-28 | 2024-04-14 | 2024-05-15 | 2024-05-22 | 2024-06-01 | 2024-05-24 | 2024-08-29 | 2024-08-29 | 2024-10-27 | 2024-11-08 | 2026-07-27 |  | 2026-09-19 |  | 2026-12-21 |  | 2027-01-28 |  | 2027-02-18
6409 | ST-2025-029 | Australia | S0022 | AUST-Clinical Center | 7 | 0 | 0 | 0 | ON_HOLD | Dr. Michelle White | Dr. Daniel Taylor | 2024-02-15 | 2024-03-10 | 2024-02-29 | 2024-04-07 | 2024-04-20 | 2024-04-26 | 2024-04-28 | 2024-05-13 | 2024-05-02 | 2024-05-28 | 2024-05-18 | 2024-09-12 | 2024-09-05 | 2024-11-08 | 2024-11-05 | 2026-07-30 |  | 2026-09-24 |  | 2026-12-29 |  | 2027-02-11 |  | 2027-03-06
6410 | ST-2025-029 | Australia | S0023 | AUST-Medical Center | 7 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Thomas | Dr. Jennifer Moore | 2024-02-15 | 2024-03-18 | 2024-03-31 | 2024-04-18 | 2024-04-22 | 2024-05-07 | 2024-05-13 | 2024-05-24 | 2024-05-13 | 2024-06-07 | 2024-05-28 | 2024-09-07 | 2024-09-07 | 2024-10-27 | 2024-11-10 | 2026-07-30 |  | 2026-09-25 |  | 2026-12-31 |  | 2027-02-16 |  | 2027-03-08
6411 | ST-2025-029 | India | S0024 | INDI-Clinical Center | 16 | 0 | 0 | 0 | ON_HOLD | Dr. Emily Williams | Dr. Emily Williams | 2024-02-14 | 2024-03-11 | 2024-02-29 | 2024-04-03 | 2024-04-06 | 2024-04-26 | 2024-04-14 | 2024-05-08 | 2024-05-05 | 2024-05-21 | 2024-05-20 | 2024-08-18 | 2024-08-10 | 2024-10-13 | 2024-10-03 | 2026-08-02 |  | 2026-09-30 |  | 2026-12-14 |  | 2027-01-25 |  | 2027-02-14
6412 | ST-2025-029 | India | S0025 | INDI-General Hospital | 14 | 0 | 0 | 0 | CLOSED | Dr. Stephanie Brown | Dr. Nicole Moore | 2024-02-19 | 2024-03-21 | 2024-03-16 | 2024-04-18 | 2024-04-10 | 2024-05-04 | 2024-05-02 | 2024-05-18 | 2024-05-09 | 2024-05-31 | 2024-06-05 | 2024-08-27 | 2024-08-21 | 2024-10-16 | 2024-10-18 | 2026-07-27 |  | 2026-09-26 |  | 2026-12-17 |  | 2027-01-29 |  | 2027-02-17
6413 | ST-2025-029 | India | S0026 | INDI-Medical Center | 12 | 0 | 0 | 0 | ON_HOLD | Dr. Daniel Johnson | Dr. Jessica White | 2024-02-21 | 2024-03-21 | 2024-03-15 | 2024-04-14 | 2024-04-07 | 2024-05-10 | 2024-04-28 | 2024-05-21 | 2024-05-24 | 2024-06-06 | 2024-05-26 | 2024-08-31 | 2024-08-25 | 2024-10-20 | 2024-10-13 | 2026-08-05 |  | 2026-09-26 |  | 2026-12-17 |  | 2027-01-23 |  | 2027-02-14
6414 | ST-2025-030 | United States | S0001 | UNIT-Health System | 73 | 57 | 78.1 | 9.5 | SCREENING | Dr. Jessica Harris | Dr. Nicole Brown | 2023-10-05 | 2023-11-03 | 2023-11-14 | 2023-12-02 | 2023-11-24 | 2023-12-24 | 2023-12-21 | 2024-01-04 | 2024-01-10 | 2024-01-16 | 2024-01-11 | 2024-04-05 | 2024-04-13 | 2024-06-06 | 2024-06-11 | 2026-06-05 |  | 2026-07-30 |  | 2026-11-25 |  | 2027-01-04 |  | 2027-01-23
6415 | ST-2025-030 | United States | S0002 | UNIT-Cancer Center | 85 | 81 | 95.3 | 7.4 | ON_HOLD | Dr. Emily Smith | Dr. Lisa Johnson | 2023-09-24 | 2023-10-18 | 2023-10-06 | 2023-11-12 | 2023-11-03 | 2023-12-06 | 2023-11-27 | 2023-12-22 | 2023-12-18 | 2024-01-06 | 2024-01-20 | 2024-04-05 | 2024-04-05 | 2024-06-04 | 2024-05-25 | 2026-05-30 |  | 2026-07-23 |  | 2026-11-24 |  | 2027-01-05 |  | 2027-01-28
6416 | ST-2025-030 | Canada | S0003 | CANA-Medical Center | 37 | 24 | 64.9 | 1.4 | ENROLLING | Dr. William Johnson | Dr. Emily Johnson | 2023-10-09 | 2023-11-08 | 2023-11-05 | 2023-12-07 | 2023-12-08 | 2023-12-28 | 2024-01-01 | 2024-01-08 | 2023-12-25 | 2024-01-20 | 2024-01-21 | 2024-04-04 | 2024-04-17 | 2024-06-06 | 2024-05-30 | 2026-05-29 |  | 2026-07-21 |  | 2026-12-03 |  | 2027-01-09 |  | 2027-01-31
6417 | ST-2025-030 | Canada | S0004 | CANA-Research Institute | 16 | 16 | 100 | 2.3 | ENROLLING | Dr. Thomas Jackson | Dr. William Garcia | 2023-09-29 | 2023-10-22 | 2023-10-17 | 2023-11-23 | 2023-12-04 | 2023-12-19 | 2023-12-28 | 2024-01-01 | 2023-12-28 | 2024-01-18 | 2024-01-18 | 2024-04-07 | 2024-04-08 | 2024-06-03 | 2024-06-12 | 2026-06-09 |  | 2026-08-01 |  | 2026-11-29 |  | 2027-01-06 |  | 2027-01-24
6418 | ST-2025-030 | Canada | S0005 | CANA-University Hospital | 39 | 39 | 100 | 2.6 | ENROLLING | Dr. Emily Jones | Dr. Thomas Jones | 2023-10-07 | 2023-11-03 | 2023-11-13 | 2023-12-06 | 2023-12-13 | 2023-12-29 | 2024-01-11 | 2024-01-11 | 2024-01-24 | 2024-01-24 | 2024-02-07 | 2024-04-15 | 2024-04-27 | 2024-06-03 | 2024-06-08 | 2026-06-18 |  | 2026-08-13 |  | 2026-12-05 |  | 2027-01-16 |  | 2027-02-07
6419 | ST-2025-030 | Canada | S0006 | CANA-Cancer Center | 35 | 35 | 100 | 2.3 | ENROLLING | Dr. Christopher Brown | Dr. Daniel Thompson | 2023-10-03 | 2023-11-05 | 2023-10-22 | 2023-12-06 | 2023-11-29 | 2024-01-01 | 2024-01-05 | 2024-01-12 | 2024-01-21 | 2024-01-24 | 2024-02-01 | 2024-04-19 | 2024-04-18 | 2024-06-20 | 2024-06-17 | 2026-06-13 |  | 2026-08-13 |  | 2026-12-08 |  | 2027-01-19 |  | 2027-02-09
6420 | ST-2025-030 | Canada | S0007 | CANA-University Hospital | 32 | 29 | 90.6 | 1.9 | ENROLLING | Dr. Nicole Wilson | Dr. Thomas Martin | 2023-09-30 | 2023-10-26 | 2023-10-20 | 2023-11-24 | 2023-12-01 | 2023-12-20 | 2023-12-17 | 2023-12-31 | 2024-01-14 | 2024-01-13 | 2024-01-09 | 2024-04-26 | 2024-04-24 | 2024-06-24 | 2024-06-28 | 2026-06-19 |  | 2026-08-17 |  | 2026-12-12 |  | 2027-01-26 |  | 2027-02-14
6421 | ST-2025-030 | Canada | S0008 | CANA-University Hospital | 18 | 34 | 188.9 | 4.9 | ENROLLING | Dr. Jessica Williams | Dr. Amanda Moore | 2023-10-03 | 2023-10-30 | 2023-10-30 | 2023-11-25 | 2023-11-29 | 2023-12-11 | 2023-12-22 | 2023-12-26 | 2024-01-06 | 2024-01-10 | 2024-01-07 | 2024-05-02 | 2024-04-27 | 2024-06-25 | 2024-06-14 | 2026-07-01 |  | 2026-08-30 |  | 2026-12-15 |  | 2027-01-27 |  | 2027-02-20
6422 | ST-2025-030 | Mexico | S0009 | MEXI-Clinical Center | 47 | 42 | 89.4 | 6 | ON_HOLD | Dr. David Thompson | Dr. Daniel Taylor | 2023-10-21 | 2023-11-23 | 2023-11-24 | 2023-12-18 | 2023-12-13 | 2024-01-10 | 2023-12-29 | 2024-01-26 | 2024-02-06 | 2024-02-07 | 2024-02-02 | 2024-04-20 | 2024-04-06 | 2024-06-12 | 2024-06-12 | 2026-06-19 |  | 2026-08-17 |  | 2026-12-04 |  | 2027-01-12 |  | 2027-02-01
6423 | ST-2025-030 | Mexico | S0010 | MEXI-Cancer Center | 24 | 17 | 70.8 | 1.7 | CLOSED | Dr. Christopher Jones | Dr. Daniel Brown | 2023-10-18 | 2023-11-19 | 2023-11-09 | 2023-12-13 | 2023-12-10 | 2023-12-29 | 2024-01-12 | 2024-01-12 | 2024-01-07 | 2024-01-25 | 2024-02-05 | 2024-04-14 | 2024-04-27 | 2024-06-08 | 2024-06-10 | 2026-06-17 |  | 2026-08-17 |  | 2026-11-26 |  | 2027-01-02 |  | 2027-01-22
6424 | ST-2025-030 | Mexico | S0011 | MEXI-University Hospital | 37 | 37 | 100 | 4.1 | ON_HOLD | Dr. Charles Harris | Dr. Daniel Miller | 2023-10-26 | 2023-11-26 | 2023-11-19 | 2023-12-21 | 2023-12-08 | 2024-01-07 | 2024-01-08 | 2024-01-23 | 2024-01-20 | 2024-02-05 | 2024-01-29 | 2024-04-25 | 2024-05-06 | 2024-06-24 | 2024-07-01 | 2026-06-24 |  | 2026-08-20 |  | 2026-12-14 |  | 2027-01-21 |  | 2027-02-10
6425 | ST-2025-030 | Mexico | S0012 | MEXI-Cancer Center | 44 | 38 | 86.4 | 3.2 | SCREENING | Dr. Michael Wilson | Dr. Stephanie Garcia | 2023-10-20 | 2023-11-18 | 2023-11-22 | 2023-12-12 | 2023-12-02 | 2024-01-01 | 2024-01-08 | 2024-01-14 | 2024-01-24 | 2024-01-29 | 2024-01-21 | 2024-05-02 | 2024-04-26 | 2024-06-22 | 2024-06-12 | 2026-07-05 |  | 2026-08-31 |  | 2026-12-20 |  | 2027-01-31 |  | 2027-02-24
6426 | ST-2025-030 | Mexico | S0013 | MEXI-General Hospital | 39 | 29 | 74.4 | 2.9 | CLOSED | Dr. Emily Jones | Dr. Christopher Brown | 2023-10-17 | 2023-11-13 | 2023-11-27 | 2023-12-10 | 2023-12-22 | 2023-12-27 | 2023-12-26 | 2024-01-09 | 2023-12-29 | 2024-01-24 | 2024-01-14 | 2024-05-13 | 2024-05-15 | 2024-07-11 | 2024-07-11 | 2026-07-04 |  | 2026-09-01 |  | 2026-12-13 |  | 2027-01-25 |  | 2027-02-18
6427 | ST-2025-030 | Mexico | S0014 | MEXI-General Hospital | 19 | 0 | 0 | 0 | SCREENING | Dr. James Harris | Dr. Jennifer Wilson | 2023-10-22 | 2023-11-24 | 2023-12-04 | 2023-12-22 | 2023-12-21 | 2024-01-14 | 2024-01-02 | 2024-01-27 | 2024-02-06 | 2024-02-10 | 2024-01-31 | 2024-05-17 | 2024-05-22 | 2024-07-11 | 2024-07-06 | 2026-07-14 |  | 2026-09-10 |  | 2026-12-22 |  | 2027-02-05 |  | 2027-02-23
6428 | ST-2025-030 | Poland | S0015 | POLA-Research Institute | 21 | 18 | 85.7 | 1.6 | SCREENING | Dr. Sarah Jackson | Dr. Stephanie Miller | 2023-10-31 | 2023-12-01 | 2023-11-29 | 2023-12-29 | 2024-01-05 | 2024-01-16 | 2024-01-02 | 2024-01-31 | 2024-01-31 | 2024-02-15 | 2024-02-26 | 2024-05-10 | 2024-05-20 | 2024-07-07 | 2024-07-20 | 2026-07-06 |  | 2026-08-30 |  | 2026-11-16 |  | 2026-12-29 |  | 2027-01-17
6429 | ST-2025-030 | Poland | S0016 | POLA-Research Institute | 40 | 27 | 67.5 | 3 | ON_HOLD | Dr. Jennifer Wilson | Dr. Daniel Martin | 2023-11-04 | 2023-11-27 | 2023-11-28 | 2023-12-21 | 2023-12-29 | 2024-01-06 | 2024-01-02 | 2024-01-19 | 2024-02-01 | 2024-02-05 | 2024-01-23 | 2024-05-11 | 2024-04-30 | 2024-06-30 | 2024-07-09 | 2026-07-02 |  | 2026-08-31 |  | 2026-11-22 |  | 2027-01-02 |  | 2027-01-24
6430 | ST-2025-030 | Poland | S0017 | POLA-Health System | 33 | 29 | 87.9 | 2.4 | SCREENING | Dr. Sarah Davis | Dr. Emily Davis | 2023-10-30 | 2023-11-22 | 2023-11-12 | 2023-12-18 | 2023-12-13 | 2024-01-11 | 2024-01-17 | 2024-01-23 | 2024-01-18 | 2024-02-07 | 2024-02-16 | 2024-05-17 | 2024-05-03 | 2024-07-12 | 2024-07-23 | 2026-07-04 |  | 2026-08-27 |  | 2026-12-06 |  | 2027-01-22 |  | 2027-02-15
6431 | ST-2025-030 | Poland | S0018 | POLA-Medical Center | 26 | 23 | 88.5 | 3.8 | SCREENING | Dr. William Davis | Dr. Michael Moore | 2023-11-02 | 2023-11-28 | 2023-11-17 | 2023-12-22 | 2023-12-23 | 2024-01-08 | 2023-12-25 | 2024-01-19 | 2024-01-31 | 2024-01-31 | 2024-02-02 | 2024-05-18 | 2024-05-18 | 2024-07-20 | 2024-07-18 | 2026-07-06 |  | 2026-09-03 |  | 2026-11-30 |  | 2027-01-09 |  | 2027-01-28
6432 | ST-2025-030 | Poland | S0019 | POLA-Medical Center | 50 | 31 | 62 | 3.1 | SCREENING | Dr. Charles Jackson | Dr. Charles Brown | 2023-10-23 | 2023-11-19 | 2023-11-19 | 2023-12-18 | 2023-12-31 | 2024-01-10 | 2024-01-17 | 2024-01-22 | 2024-01-27 | 2024-02-08 | 2024-01-28 | 2024-05-08 | 2024-05-07 | 2024-07-09 | 2024-06-29 | 2026-07-14 |  | 2026-09-11 |  | 2026-11-29 |  | 2027-01-14 |  | 2027-02-06
6433 | ST-2025-030 | Poland | S0020 | POLA-University Hospital | 20 | 8 | 40 | 0.5 | CLOSED | Dr. William Martin | Dr. David Garcia | 2023-10-24 | 2023-11-18 | 2023-11-13 | 2023-12-21 | 2023-12-28 | 2024-01-09 | 2023-12-29 | 2024-01-21 | 2024-01-25 | 2024-02-05 | 2024-02-06 | 2024-06-02 | 2024-05-30 | 2024-08-01 | 2024-08-08 | 2026-07-26 |  | 2026-09-18 |  | 2026-12-19 |  | 2027-02-01 |  | 2027-02-21
6434 | ST-2025-030 | Spain | S0021 | SPAI-Medical Center | 76 | 72 | 94.7 | 9 | ON_HOLD | Dr. Nicole Anderson | Dr. Lisa Garcia | 2023-10-18 | 2023-11-11 | 2023-10-28 | 2023-12-11 | 2023-12-15 | 2024-01-02 | 2023-12-28 | 2024-01-19 | 2024-01-06 | 2024-02-02 | 2024-02-08 | 2024-04-26 | 2024-05-02 | 2024-06-14 | 2024-06-28 | 2026-06-14 |  | 2026-08-11 |  | 2026-11-25 |  | 2027-01-10 |  | 2027-01-31
6435 | ST-2025-030 | Spain | S0022 | SPAI-Research Institute | 49 | 49 | 100 | 3.1 | ENROLLING | Dr. Jennifer Garcia | Dr. Thomas Harris | 2023-10-19 | 2023-11-11 | 2023-11-24 | 2023-12-09 | 2023-12-11 | 2023-12-27 | 2023-12-19 | 2024-01-10 | 2024-01-07 | 2024-01-26 | 2024-02-09 | 2024-05-06 | 2024-05-14 | 2024-06-28 | 2024-06-30 | 2026-06-15 |  | 2026-08-07 |  | 2026-12-04 |  | 2027-01-18 |  | 2027-02-11
6436 | ST-2025-030 | Spain | S0023 | SPAI-University Hospital | 45 | 31 | 68.9 | 5.2 | ON_HOLD | Dr. Nicole White | Dr. Thomas Smith | 2023-10-13 | 2023-11-07 | 2023-11-17 | 2023-12-10 | 2023-12-17 | 2023-12-28 | 2023-12-23 | 2024-01-10 | 2024-01-08 | 2024-01-26 | 2024-01-14 | 2024-05-13 | 2024-05-25 | 2024-07-10 | 2024-07-16 | 2026-06-23 |  | 2026-08-20 |  | 2026-12-04 |  | 2027-01-14 |  | 2027-02-07
6437 | ST-2025-030 | Switzerland | S0024 | SWIT-Cancer Center | 21 | 21 | 100 | 3.5 | CLOSED | Dr. Jessica Davis | Dr. Daniel Thompson | 2023-10-30 | 2023-12-01 | 2023-12-09 | 2024-01-03 | 2023-12-30 | 2024-01-21 | 2024-01-25 | 2024-02-05 | 2024-02-09 | 2024-02-21 | 2024-02-18 | 2024-05-12 | 2024-05-16 | 2024-07-08 | 2024-07-13 | 2026-06-25 |  | 2026-08-25 |  | 2026-11-23 |  | 2027-01-03 |  | 2027-01-22
6438 | ST-2025-030 | Switzerland | S0025 | SWIT-University Hospital | 21 | 19 | 90.5 | 1.1 | SCREENING | Dr. Emily Brown | Dr. Jessica Taylor | 2023-10-24 | 2023-11-16 | 2023-11-09 | 2023-12-09 | 2023-12-19 | 2023-12-27 | 2024-01-07 | 2024-01-08 | 2024-01-17 | 2024-01-19 | 2024-01-30 | 2024-05-14 | 2024-05-07 | 2024-07-03 | 2024-06-22 | 2026-06-26 |  | 2026-08-26 |  | 2026-11-28 |  | 2027-01-09 |  | 2027-02-02
6439 | ST-2025-030 | Switzerland | S0026 | SWIT-Clinical Center | 15 | 13 | 86.7 | 1 | CLOSED | Dr. Amanda Moore | Dr. William Martin | 2023-10-25 | 2023-11-23 | 2023-11-29 | 2023-12-22 | 2024-01-03 | 2024-01-08 | 2023-12-25 | 2024-01-19 | 2024-01-10 | 2024-02-03 | 2024-01-30 | 2024-05-15 | 2024-05-04 | 2024-07-04 | 2024-07-12 | 2026-06-26 |  | 2026-08-17 |  | 2026-12-05 |  | 2027-01-16 |  | 2027-02-07
6440 | ST-2025-030 | Switzerland | S0027 | SWIT-Research Institute | 32 | 23 | 71.9 | 2.1 | ON_HOLD | Dr. James Thomas | Dr. Jessica Taylor | 2023-10-25 | 2023-11-27 | 2023-12-06 | 2023-12-29 | 2023-12-20 | 2024-01-22 | 2024-01-21 | 2024-02-03 | 2024-02-15 | 2024-02-15 | 2024-02-17 | 2024-05-15 | 2024-05-26 | 2024-07-10 | 2024-07-21 | 2026-07-03 |  | 2026-09-02 |  | 2026-12-02 |  | 2027-01-11 |  | 2027-01-30
6441 | ST-2025-030 | Switzerland | S0028 | SWIT-Health System | 37 | 24 | 64.9 | 1.3 | CLOSED | Dr. Nicole Brown | Dr. William Thompson | 2023-11-01 | 2023-11-24 | 2023-11-27 | 2023-12-27 | 2024-01-09 | 2024-01-22 | 2024-01-10 | 2024-02-02 | 2024-01-29 | 2024-02-14 | 2024-02-05 | 2024-05-10 | 2024-05-17 | 2024-07-10 | 2024-07-19 | 2026-06-27 |  | 2026-08-17 |  | 2026-12-02 |  | 2027-01-14 |  | 2027-02-05
6442 | ST-2025-030 | Switzerland | S0029 | SWIT-General Hospital | 30 | 12 | 40 | 0.8 | SCREENING | Dr. Robert White | Dr. Lisa Jones | 2023-11-03 | 2023-12-06 | 2023-12-11 | 2024-01-06 | 2024-01-20 | 2024-01-29 | 2024-02-01 | 2024-02-10 | 2024-02-23 | 2024-02-27 | 2024-02-17 | 2024-06-04 | 2024-06-15 | 2024-08-01 | 2024-07-20 | 2026-07-30 |  | 2026-09-26 |  | 2026-12-27 |  | 2027-02-07 |  | 2027-02-27
6443 | ST-2025-030 | China | S0030 | CHIN-General Hospital | 104 | 64 | 61.5 | 5.3 | ON_HOLD | Dr. David Williams | Dr. David Jackson | 2023-10-24 | 2023-11-22 | 2023-11-09 | 2023-12-16 | 2023-12-21 | 2024-01-10 | 2024-01-13 | 2024-01-21 | 2024-01-17 | 2024-02-02 | 2024-01-19 | 2024-05-03 | 2024-04-26 | 2024-06-29 | 2024-07-11 | 2026-06-20 |  | 2026-08-11 |  | 2026-11-28 |  | 2027-01-11 |  | 2027-01-30
6444 | ST-2025-030 | China | S0031 | CHIN-General Hospital | 63 | 0 | 0 | 0 | ON_HOLD | Dr. Michelle Harris | Dr. Daniel Garcia | 2023-10-28 | 2023-11-24 | 2023-12-07 | 2023-12-23 | 2023-12-25 | 2024-01-13 | 2024-01-18 | 2024-01-24 | 2024-01-26 | 2024-02-10 | 2024-02-05 | 2024-05-11 | 2024-05-09 | 2024-07-01 | 2024-07-06 | 2026-06-27 |  | 2026-08-18 |  | 2026-12-12 |  | 2027-01-27 |  | 2027-02-15
6445 | ST-2025-030 | Japan | S0032 | JAPA-Medical Center | 32 | 0 | 0 | 0 | CLOSED | Dr. Thomas Brown | Dr. Stephanie Harris | 2023-11-24 | 2023-12-18 | 2024-01-01 | 2024-01-19 | 2024-01-29 | 2024-02-11 | 2024-01-29 | 2024-02-24 | 2024-02-14 | 2024-03-11 | 2024-03-03 | 2024-05-20 | 2024-05-23 | 2024-07-08 | 2024-07-20 | 2026-07-10 |  | 2026-09-05 |  | 2026-11-21 |  | 2026-12-31 |  | 2027-01-20
6446 | ST-2025-030 | Japan | S0033 | JAPA-Health System | 48 | 0 | 0 | 0 | ON_HOLD | Dr. Jessica Brown | Dr. James Martin | 2023-11-27 | 2023-12-30 | 2023-12-29 | 2024-01-22 | 2024-01-27 | 2024-02-10 | 2024-02-19 | 2024-02-24 | 2024-02-29 | 2024-03-06 | 2024-02-23 | 2024-06-07 | 2024-06-21 | 2024-08-04 | 2024-08-07 | 2026-07-25 |  | 2026-09-23 |  | 2026-11-23 |  | 2027-01-04 |  | 2027-01-22
6447 | ST-2025-030 | Japan | S0034 | JAPA-General Hospital | 56 | 0 | 0 | 0 | ON_HOLD | Dr. Robert Thompson | Dr. Jessica Moore | 2023-11-15 | 2023-12-12 | 2023-12-23 | 2024-01-04 | 2024-01-17 | 2024-01-21 | 2024-02-04 | 2024-02-01 | 2024-01-25 | 2024-02-15 | 2024-02-01 | 2024-06-06 | 2024-05-24 | 2024-07-28 | 2024-07-14 | 2026-07-24 |  | 2026-09-18 |  | 2026-12-02 |  | 2027-01-15 |  | 2027-02-04
6448 | ST-2025-030 | Japan | S0035 | JAPA-General Hospital | 36 | 0 | 0 | 0 | ON_HOLD | Dr. Nicole Anderson | Dr. Michael Anderson | 2023-11-25 | 2023-12-21 | 2023-12-19 | 2024-01-21 | 2024-01-31 | 2024-02-15 | 2024-02-13 | 2024-03-03 | 2024-03-11 | 2024-03-17 | 2024-03-07 | 2024-06-17 | 2024-06-16 | 2024-08-15 | 2024-08-23 | 2026-08-03 |  | 2026-09-23 |  | 2026-12-13 |  | 2027-01-26 |  | 2027-02-13
6449 | ST-2025-031 | Canada | S0001 | CANA-University Hospital | -2 | -2 | 100 | -0.1 | CLOSED | Dr. Jessica Brown | Dr. Emily Martin | 2023-10-07: 2026-07-07; 2023-11-03: 2026-07-31; 2023-12-06: 2026-08-30; 2023-12-29: 2026-09-16; 2024-01-11: 2026-10-01; 2024-01-24: 2026-10-14; 2024-04-15: 2027-01-12; 2024-06-03: 2027-03-05; 2026-06-18: 2029-08-18 |  | 2029-10-14 |  | 2030-02-05 |  | 2030-03-17 |  | 2030-04-05
6450 | ST-2025-031 | Canada | S0002 | CANA-University Hospital | 3 | 2 | 66.7 | 0.3 | CLOSED | Dr. Michelle Taylor | Dr. James Davis | 2023-10-07: 2026-07-05; 2023-11-03: 2026-07-31; 2023-12-06: 2026-08-29; 2023-12-29: 2026-09-22; 2024-01-11: 2026-10-07; 2024-01-24: 2026-10-18; 2024-04-15: 2027-01-22; 2024-06-03: 2027-03-12; 2026-06-18: 2029-08-29 |  | 2029-10-22 |  | 2030-02-08 |  | 2030-03-18 |  | 2030-04-05
6451 | ST-2025-031 | Canada | S0003 | CANA-Cancer Center | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Charles Thomas | Dr. Michael Garcia | 2023-10-07: 2026-07-07; 2023-11-03: 2026-08-03; 2023-12-06: 2026-08-26; 2023-12-29: 2026-09-16; 2024-01-11: 2026-09-29; 2024-01-24: 2026-10-14; 2024-04-15: 2027-01-22; 2024-06-03: 2027-03-26; 2026-06-18: 2029-08-21 |  | 2029-10-15 |  | 2030-02-12 |  | 2030-03-30 |  | 2030-04-20
6452 | ST-2025-031 | Canada | S0004 | CANA-Research Institute | 3 | 0 | 0 | 0 | CLOSED | Dr. Lisa Thompson | Dr. Daniel Anderson | 2023-10-07: 2026-07-06; 2023-11-03: 2026-08-08; 2023-12-06: 2026-09-01; 2023-12-29: 2026-09-18; 2024-01-11: 2026-10-01; 2024-01-24: 2026-10-16; 2024-04-15: 2027-01-23; 2024-06-03: 2027-03-20; 2026-06-18: 2029-09-06 |  | 2029-11-01 |  | 2030-02-21 |  | 2030-04-06 |  | 2030-04-29
6453 | ST-2025-031 | Canada | S0005 | CANA-Clinical Center | 3 | 0 | 0 | 0 | SCREENING | Dr. Michelle Brown | Dr. Nicole Wilson | 2023-10-07: 2026-07-10; 2023-11-03: 2026-08-10; 2023-12-06: 2026-09-06; 2023-12-29: 2026-10-02; 2024-01-11: 2026-10-14; 2024-01-24: 2026-10-29; 2024-04-15: 2027-02-04; 2024-06-03: 2027-03-29; 2026-06-18: 2029-09-01 |  | 2029-10-30 |  | 2030-02-27 |  | 2030-04-06 |  | 2030-04-24
6454 | ST-2025-031 | United States | S0006 | UNIT-Medical Center | 1 | 0 | 0 | 0 | SCREENING | Dr. Michelle Taylor | Dr. Sarah Davis | 2023-10-07: 2026-07-15; 2023-11-03: 2026-08-16; 2023-12-06: 2026-09-15; 2023-12-29: 2026-10-05; 2024-01-11: 2026-10-16; 2024-01-24: 2026-10-28; 2024-04-15: 2027-01-23; 2024-06-03: 2027-03-15; 2026-06-18: 2029-08-24 |  | 2029-10-22 |  | 2030-02-06 |  | 2030-03-19 |  | 2030-04-11
6455 | ST-2025-031 | United States | S0007 | UNIT-Clinical Center | 3 | 0 | 0 | 0 | CLOSED | Dr. Sarah Thomas | Dr. Michael White | 2023-10-07: 2026-07-10; 2023-11-03: 2026-08-07; 2023-12-06: 2026-09-01; 2023-12-29: 2026-09-17; 2024-01-11: 2026-09-29; 2024-01-24: 2026-10-15; 2024-04-15: 2027-01-21; 2024-06-03: 2027-03-21; 2026-06-18: 2029-08-28 |  | 2029-10-25 |  | 2030-02-09 |  | 2030-03-18 |  | 2030-04-08
6456 | ST-2025-031 | United States | S0008 | UNIT-Health System | 3 | 0 | 0 | 0 | CLOSED | Dr. Michael Moore | Dr. Nicole Jones | 2023-10-07: 2026-07-13; 2023-11-03: 2026-08-09; 2023-12-06: 2026-09-10; 2023-12-29: 2026-10-02; 2024-01-11: 2026-10-15; 2024-01-24: 2026-11-01; 2024-04-15: 2027-01-22; 2024-06-03: 2027-03-12; 2026-06-18: 2029-08-27 |  | 2029-10-26 |  | 2030-02-21 |  | 2030-04-06 |  | 2030-04-24
6457 | ST-2025-031 | Mexico | S0009 | MEXI-Cancer Center | -10 | -10 | 100 | -0.6 | SCREENING | Dr. Michelle Jackson | Dr. James Moore | 2023-10-07: 2026-07-18; 2023-11-03: 2026-08-17; 2023-12-06: 2026-09-09; 2023-12-29: 2026-09-28; 2024-01-11: 2026-10-10; 2024-01-24: 2026-10-24; 2024-04-15: 2027-01-18; 2024-06-03: 2027-03-18; 2026-06-18: 2029-08-30 |  | 2029-10-28 |  | 2030-02-06 |  | 2030-03-25 |  | 2030-04-14
6458 | ST-2025-031 | Mexico | S0010 | MEXI-Clinical Center | 3 | 3 | 100 | 0.5 | ON_HOLD | Dr. Charles Jones | Dr. Stephanie White | 2023-10-07: 2026-07-24; 2023-11-03: 2026-08-21; 2023-12-06: 2026-09-13; 2023-12-29: 2026-10-08; 2024-01-11: 2026-10-25; 2024-01-24: 2026-11-07; 2024-04-15: 2027-02-01; 2024-06-03: 2027-04-04; 2026-06-18: 2029-09-09 |  | 2029-11-03 |  | 2030-02-17 |  | 2030-03-29 |  | 2030-04-22
6459 | ST-2025-031 | Mexico | S0011 | MEXI-Health System | 3 | 3 | 100 | 0.4 | SCREENING | Dr. Christopher Brown | Dr. Amanda Thomas | 2023-10-07: 2026-07-23; 2023-11-03: 2026-08-24; 2023-12-06: 2026-09-22; 2023-12-29: 2026-10-14; 2024-01-11: 2026-10-31; 2024-01-24: 2026-11-16; 2024-04-15: 2027-02-03; 2024-06-03: 2027-04-04; 2026-06-18: 2029-09-09 |  | 2029-10-30 |  | 2030-02-11 |  | 2030-03-28 |  | 2030-04-18
6460 | ST-2025-031 | Mexico | S0012 | MEXI-University Hospital | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. Sarah Davis | Dr. Lisa Williams | 2023-10-07: 2026-07-26; 2023-11-03: 2026-08-28; 2023-12-06: 2026-09-24; 2023-12-29: 2026-10-18; 2024-01-11: 2026-11-01; 2024-01-24: 2026-11-15; 2024-04-15: 2027-02-14; 2024-06-03: 2027-04-15; 2026-06-18: 2029-09-22 |  | 2029-11-20 |  | 2030-03-02 |  | 2030-04-10 |  | 2030-05-01
6461 | ST-2025-031 | Mexico | S0013 | MEXI-Health System | 3 | 1 | 33.3 | 0.2 | SCREENING | Dr. Stephanie Moore | Dr. Sarah Smith | 2023-10-07: 2026-07-26; 2023-11-03: 2026-08-21; 2023-12-06: 2026-09-15; 2023-12-29: 2026-10-01; 2024-01-11: 2026-10-14; 2024-01-24: 2026-10-31; 2024-04-15: 2027-02-13; 2024-06-03: 2027-04-07; 2026-06-18: 2029-09-12 |  | 2029-11-05 |  | 2030-03-04 |  | 2030-04-14 |  | 2030-05-04
6462 | ST-2025-031 | Mexico | S0014 | MEXI-Cancer Center | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Sarah Williams | Dr. Sarah Jones | 2023-10-07: 2026-07-12; 2023-11-03: 2026-08-13; 2023-12-06: 2026-09-09; 2023-12-29: 2026-09-30; 2024-01-11: 2026-10-13; 2024-01-24: 2026-10-29; 2024-04-15: 2027-02-13; 2024-06-03: 2027-04-15; 2026-06-18: 2029-09-27 |  | 2029-11-26 |  | 2030-03-02 |  | 2030-04-09 |  | 2030-04-29
6463 | ST-2025-031 | United Kingdom | S0015 | UNIT-Health System | -3 | -3 | 100 | -0.3 | ON_HOLD | Dr. Amanda Davis | Dr. Christopher Anderson | 2023-10-07: 2026-08-06; 2023-11-03: 2026-09-02; 2023-12-06: 2026-09-27; 2023-12-29: 2026-10-20; 2024-01-11: 2026-11-03; 2024-01-24: 2026-11-14; 2024-04-15: 2027-02-13; 2024-06-03: 2027-04-03; 2026-06-18: 2029-09-13 |  | 2029-11-03 |  | 2030-02-08 |  | 2030-03-24 |  | 2030-04-16
6464 | ST-2025-031 | United Kingdom | S0016 | UNIT-Research Institute | 3 | 2 | 66.7 | 0.1 | CLOSED | Dr. Jessica Davis | Dr. Daniel Wilson | 2023-10-07: 2026-08-04; 2023-11-03: 2026-09-02; 2023-12-06: 2026-09-25; 2023-12-29: 2026-10-20; 2024-01-11: 2026-10-31; 2024-01-24: 2026-11-13; 2024-04-15: 2027-02-26; 2024-06-03: 2027-04-25; 2026-06-18: 2029-09-20 |  | 2029-11-15 |  | 2030-02-10 |  | 2030-03-26 |  | 2030-04-14
6465 | ST-2025-031 | United Kingdom | S0017 | UNIT-Research Institute | 3 | 1 | 33.3 | 0.1 | CLOSED | Dr. Daniel Brown | Dr. Sarah Thomas | 2023-10-07: 2026-08-13; 2023-11-03: 2026-09-09; 2023-12-06: 2026-10-06; 2023-12-29: 2026-10-29; 2024-01-11: 2026-11-10; 2024-01-24: 2026-11-22; 2024-04-15: 2027-02-23; 2024-06-03: 2027-04-15; 2026-06-18: 2029-09-15 |  | 2029-11-14 |  | 2030-02-20 |  | 2030-03-29 |  | 2030-04-17
6466 | ST-2025-031 | United Kingdom | S0018 | UNIT-Clinical Center | 3 | 0 | 0 | 0 | CLOSED | Dr. Nicole Wilson | Dr. Michael Miller | 2023-10-07: 2026-08-01; 2023-11-03: 2026-08-26; 2023-12-06: 2026-09-28; 2023-12-29: 2026-10-22; 2024-01-11: 2026-11-08; 2024-01-24: 2026-11-22; 2024-04-15: 2027-02-23; 2024-06-03: 2027-04-18; 2026-06-18: 2029-09-14 |  | 2029-11-12 |  | 2030-02-14 |  | 2030-03-23 |  | 2030-04-15
6467 | ST-2025-031 | United Kingdom | S0019 | UNIT-University Hospital | 3 | 0 | 0 | 0 | SCREENING | Dr. Jessica Moore | Dr. David Brown | 2023-10-07: 2026-08-05; 2023-11-03: 2026-08-28; 2023-12-06: 2026-09-30; 2023-12-29: 2026-10-21; 2024-01-11: 2026-11-05; 2024-01-24: 2026-11-21; 2024-04-15: 2027-03-06; 2024-06-03: 2027-05-03; 2026-06-18: 2029-10-07 |  | 2029-12-02 |  | 2030-03-04 |  | 2030-04-11 |  | 2030-05-03
6468 | ST-2025-031 | United Kingdom | S0020 | UNIT-Research Institute | 3 | 0 | 0 | 0 | SCREENING | Dr. Sarah Davis | Dr. Christopher Harris | 2023-10-07: 2026-08-09; 2023-11-03: 2026-09-02; 2023-12-06: 2026-09-28; 2023-12-29: 2026-10-17; 2024-01-11: 2026-10-30; 2024-01-24: 2026-11-14; 2024-04-15: 2027-03-04; 2024-06-03: 2027-05-05; 2026-06-18: 2029-10-10 |  | 2029-12-10 |  | 2030-03-02 |  | 2030-04-09 |  | 2030-05-02
6469 | ST-2025-031 | France | S0021 | FRAN-Research Institute | 6 | 0 | 0 | 0 | CLOSED | Dr. Charles Anderson | Dr. Michael Johnson | 2023-10-07: 2026-08-17; 2023-11-03: 2026-09-11; 2023-12-06: 2026-10-04; 2023-12-29: 2026-10-25; 2024-01-11: 2026-11-09; 2024-01-24: 2026-11-26; 2024-04-15: 2027-02-16; 2024-06-03: 2027-04-11; 2026-06-18: 2029-09-25 |  | 2029-11-25 |  | 2030-02-13 |  | 2030-03-29 |  | 2030-04-18
6470 | ST-2025-031 | France | S0022 | FRAN-Research Institute | 3 | 0 | 0 | 0 | ON_HOLD | Dr. Nicole Smith | Dr. Charles Jackson | 2023-10-07: 2026-08-15; 2023-11-03: 2026-09-12; 2023-12-06: 2026-10-05; 2023-12-29: 2026-10-25; 2024-01-11: 2026-11-06; 2024-01-24: 2026-11-21; 2024-04-15: 2027-02-16; 2024-06-03: 2027-04-07; 2026-06-18: 2029-10-03 |  | 2029-11-26 |  | 2030-02-18 |  | 2030-04-04 |  | 2030-04-27
6471 | ST-2025-031 | Belgium | S0023 | BELG-Cancer Center | 0 | 0 | 0 | 0 | SCREENING | Dr. Thomas Wilson | Dr. David Smith | 2023-10-07: 2026-08-12; 2023-11-03: 2026-09-13; 2023-12-06: 2026-10-11; 2023-12-29: 2026-10-30; 2024-01-11: 2026-11-13; 2024-01-24: 2026-11-30; 2024-04-15: 2027-02-25; 2024-06-03: 2027-04-15; 2026-06-18: 2029-09-23 |  | 2029-11-15 |  | 2030-02-09 |  | 2030-03-28 |  | 2030-04-15
6472 | ST-2025-031 | Belgium | S0024 | BELG-Research Institute | 3 | 0 | 0 | 0 | CLOSED | Dr. Stephanie White | Dr. Sarah Brown | 2023-10-07: 2026-08-18; 2023-11-03: 2026-09-13; 2023-12-06: 2026-10-15; 2023-12-29: 2026-11-08; 2024-01-11: 2026-11-23; 2024-01-24: 2026-12-09; 2024-04-15: 2027-03-03; 2024-06-03: 2027-05-02; 2026-06-18: 2029-09-26 |  | 2029-11-24 |  | 2030-02-11 |  | 2030-03-28 |  | 2030-04-21
6473 | ST-2025-031 | Belgium | S0025 | BELG-Health System | 3 | 0 | 0 | 0 | CLOSED | Dr. Jessica Moore | Dr. Christopher White | 2023-10-07: 2026-08-11; 2023-11-03: 2026-09-13; 2023-12-06: 2026-10-14; 2023-12-29: 2026-11-07; 2024-01-11: 2026-11-21; 2024-01-24: 2026-12-04; 2024-04-15: 2027-02-25; 2024-06-03: 2027-04-18; 2026-06-18: 2029-10-01 |  | 2029-11-30 |  | 2030-02-12 |  | 2030-03-24 |  | 2030-04-13
6474 | ST-2025-031 | Belgium | S0026 | BELG-Health System | 3 | 0 | 0 | 0 | CLOSED | Dr. Daniel Wilson | Dr. Jennifer Jackson | 2023-10-07: 2026-08-16; 2023-11-03: 2026-09-13; 2023-12-06: 2026-10-09; 2023-12-29: 2026-11-01; 2024-01-11: 2026-11-14; 2024-01-24: 2026-11-30; 2024-04-15: 2027-02-27; 2024-06-03: 2027-04-28; 2026-06-18: 2029-09-26 |  | 2029-11-23 |  | 2030-02-19 |  | 2030-04-02 |  | 2030-04-20
6475 | ST-2025-031 | Taiwan | S0027 | TAIW-Medical Center | 5 | 0 | 0 | 0 | CLOSED | Dr. William Williams | Dr. Lisa Moore | 2023-10-07: 2026-08-13; 2023-11-03: 2026-09-06; 2023-12-06: 2026-10-04; 2023-12-29: 2026-10-30; 2024-01-11: 2026-11-13; 2024-01-24: 2026-11-28; 2024-04-15: 2027-02-16; 2024-06-03: 2027-04-13; 2026-06-18: 2029-09-19 |  | 2029-11-15 |  | 2030-02-14 |  | 2030-04-01 |  | 2030-04-25
6476 | ST-2025-031 | Taiwan | S0028 | TAIW-Research Institute | 6 | 0 | 0 | 0 | CLOSED | Dr. Charles Johnson | Dr. William Thomas | 2023-10-07: 2026-08-07; 2023-11-03: 2026-09-07; 2023-12-06: 2026-10-03; 2023-12-29: 2026-10-25; 2024-01-11: 2026-11-10; 2024-01-24: 2026-11-25; 2024-04-15: 2027-03-01; 2024-06-03: 2027-04-21; 2026-06-18: 2029-09-22 |  | 2029-11-16 |  | 2030-02-21 |  | 2030-04-04 |  | 2030-04-24
6477 | ST-2025-031 | Japan | S0029 | JAPA-Clinical Center | -7 | -7 | 100 | -0.5 | SCREENING | Dr. Christopher Smith | Dr. Christopher Johnson | 2023-10-07: 2026-09-07; 2023-11-03: 2026-10-06; 2023-12-06: 2026-11-06; 2023-12-29: 2026-11-24; 2024-01-11: 2026-12-09; 2024-01-24: 2026-12-23; 2024-04-15: 2027-03-20; 2024-06-03: 2027-05-22; 2026-06-18: 2029-10-18 |  | 2029-12-11 |  | 2030-02-19 |  | 2030-04-04 |  | 2030-04-22
6478 | ST-2025-031 | Japan | S0030 | JAPA-Research Institute | 3 | 2 | 66.7 | 0.2 | CLOSED | Dr. Michelle Miller | Dr. Stephanie Johnson | 2023-10-07: 2026-09-07; 2023-11-03: 2026-10-04; 2023-12-06: 2026-11-04; 2023-12-29: 2026-11-27; 2024-01-11: 2026-12-13; 2024-01-24: 2026-12-24; 2024-04-15: 2027-03-15; 2024-06-03: 2027-05-16; 2026-06-18: 2029-10-09 |  | 2029-12-05 |  | 2030-02-20 |  | 2030-03-31 |  | 2030-04-18
6479 | ST-2025-031 | Japan | S0031 | JAPA-Health System | 3 | 3 | 100 | 0.4 | ON_HOLD | Dr. Michelle Taylor | Dr. Michael Harris | 2023-10-07: 2026-09-14; 2023-11-03: 2026-10-15; 2023-12-06: 2026-11-13; 2023-12-29: 2026-12-05; 2024-01-11: 2026-12-18; 2024-01-24: 2026-12-30; 2024-04-15: 2027-03-21; 2024-06-03: 2027-05-20; 2026-06-18: 2029-10-19 |  | 2029-12-12 |  | 2030-02-26 |  | 2030-04-05 |  | 2030-04-25
6480 | ST-2025-031 | Japan | S0032 | JAPA-University Hospital | 3 | 2 | 66.7 | 0.2 | ON_HOLD | Dr. William Martin | Dr. Robert Davis | 2023-10-07: 2026-09-15; 2023-11-03: 2026-10-13; 2023-12-06: 2026-11-14; 2023-12-29: 2026-12-09; 2024-01-11: 2026-12-24; 2024-01-24: 2027-01-04; 2024-04-15: 2027-04-09; 2024-06-03: 2027-05-28; 2026-06-18: 2029-10-26 |  | 2029-12-21 |  | 2030-03-15 |  | 2030-04-27 |  | 2030-05-20
6481 | ST-2025-031 | Japan | S0033 | JAPA-General Hospital | 3 | 0 | 0 | 0 | SCREENING | Dr. Sarah Davis | Dr. Emily Johnson | 2023-10-07: 2026-09-14; 2023-11-03: 2026-10-13; 2023-12-06: 2026-11-09; 2023-12-29: 2026-12-02; 2024-01-11: 2026-12-18; 2024-01-24: 2026-12-30; 2024-04-15: 2027-04-07; 2024-06-03: 2027-05-28; 2026-06-18: 2029-11-03 |  | 2030-01-02 |  | 2030-03-14 |  | 2030-04-21 |  | 2030-05-10
6482 | ST-2025-032 | Canada | S0001 | CANA-Cancer Center | 62 | 25 | 40.3 | 1.8 | CLOSED | Dr. Sarah Smith | Dr. Lisa Jones | 2024-11-12 | 2024-12-14 | 2024-12-24 | 2025-01-11 | 2024-12-31 | 2025-02-06 | 2025-01-30 | 2025-02-22 | 2025-02-17 | 2025-03-08 | 2025-03-09 | 2025-05-22 | 2025-05-18 | 2025-07-15 | 2025-07-02 | 2029-09-28 |  | 2029-11-20 |  | 2030-03-29 |  | 2030-05-14 |  | 2030-06-03
6483 | ST-2025-032 | Canada | S0002 | CANA-Health System | 56 | 0 | 0 | 0 | SCREENING | Dr. David Wilson | Dr. Nicole Jones | 2024-11-17 | 2024-12-18 | 2024-12-30 | 2025-01-19 | 2025-01-28 | 2025-02-12 | 2025-02-26 | 2025-03-01 | 2025-03-10 | 2025-03-15 | 2025-03-07 | 2025-05-25 | 2025-05-24 | 2025-07-18 | 2025-07-20 | 2029-10-02 |  | 2029-11-27 |  | 2030-03-28 |  | 2030-05-06 |  | 2030-05-24
6484 | ST-2025-032 | Mexico | S0003 | MEXI-General Hospital | 26 | 0 | 0 | 0 | SCREENING | Dr. James White | Dr. Michael Martin | 2024-11-19 | 2024-12-21 | 2025-01-04 | 2025-01-18 | 2025-01-09 | 2025-02-04 | 2025-01-30 | 2025-02-17 | 2025-02-11 | 2025-03-02 | 2025-03-07 | 2025-05-14 | 2025-05-24 | 2025-07-03 | 2025-06-22 | 2029-10-02 |  | 2029-11-26 |  | 2030-03-23 |  | 2030-05-06 |  | 2030-05-25
6485 | ST-2025-032 | Mexico | S0004 | MEXI-Health System | 17 | 0 | 0 | 0 | SCREENING | Dr. Jennifer Johnson | Dr. Stephanie Wilson | 2024-11-15 | 2024-12-12 | 2024-12-26 | 2025-01-06 | 2025-01-09 | 2025-01-23 | 2025-01-26 | 2025-02-04 | 2025-02-15 | 2025-02-19 | 2025-02-11 | 2025-06-01 | 2025-05-18 | 2025-07-28 | 2025-07-29 | 2029-10-17 |  | 2029-12-09 |  | 2030-03-23 |  | 2030-05-08 |  | 2030-05-26
6486 | ST-2025-032 | Mexico | S0005 | MEXI-Health System | 24 | 0 | 0 | 0 | CLOSED | Dr. Lisa Thomas | Dr. Nicole Thompson | 2024-11-05 | 2024-12-03 | 2024-12-11 | 2024-12-29 | 2025-01-06 | 2025-01-18 | 2025-01-31 | 2025-02-02 | 2025-01-22 | 2025-02-16 | 2025-02-16 | 2025-06-04 | 2025-06-18 | 2025-07-30 | 2025-07-29 | 2029-10-18 |  | 2029-12-10 |  | 2030-04-04 |  | 2030-05-15 |  | 2030-06-02
6487 | ST-2025-032 | Mexico | S0006 | MEXI-General Hospital | 15 | 0 | 0 | 0 | ON_HOLD | Dr. Lisa Anderson | Dr. Nicole Martin | 2024-11-06 | 2024-12-01 | 2024-12-03 | 2024-12-28 | 2024-12-24 | 2025-01-23 | 2025-01-17 | 2025-02-03 | 2025-02-03 | 2025-02-16 | 2025-02-22 | 2025-06-07 | 2025-06-16 | 2025-07-27 | 2025-07-29 | 2029-10-23 |  | 2029-12-16 |  | 2030-03-31 |  | 2030-05-12 |  | 2030-05-31
6488 | ST-2025-032 | United Kingdom | S0007 | UNIT-Cancer Center | 17 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Harris | Dr. Thomas Davis | 2024-11-21 | 2024-12-19 | 2025-01-02 | 2025-01-11 | 2025-01-17 | 2025-02-02 | 2025-01-20 | 2025-02-13 | 2025-02-19 | 2025-03-01 | 2025-03-07 | 2025-06-09 | 2025-05-26 | 2025-08-05 | 2025-07-29 | 2029-10-22 |  | 2029-12-15 |  | 2030-03-27 |  | 2030-05-13 |  | 2030-06-06
6489 | ST-2025-032 | United Kingdom | S0008 | UNIT-General Hospital | 10 | 0 | 0 | 0 | SCREENING | Dr. Jennifer Harris | Dr. Thomas Brown | 2024-11-26 | 2024-12-22 | 2024-12-14 | 2025-01-24 | 2025-01-30 | 2025-02-12 | 2025-02-26 | 2025-02-25 | 2025-02-13 | 2025-03-11 | 2025-03-13 | 2025-06-02 | 2025-06-15 | 2025-07-28 | 2025-08-06 | 2029-11-02 |  | 2029-12-25 |  | 2030-03-29 |  | 2030-05-09 |  | 2030-05-28
6490 | ST-2025-032 | United Kingdom | S0009 | UNIT-Research Institute | 10 | 0 | 0 | 0 | ON_HOLD | Dr. Robert Martin | Dr. Nicole White | 2024-11-20 | 2024-12-19 | 2024-12-17 | 2025-01-12 | 2025-01-18 | 2025-02-04 | 2025-02-08 | 2025-02-19 | 2025-02-12 | 2025-03-06 | 2025-03-12 | 2025-06-12 | 2025-06-09 | 2025-08-11 | 2025-08-12 | 2029-10-31 |  | 2029-12-21 |  | 2030-04-06 |  | 2030-05-17 |  | 2030-06-08
6491 | ST-2025-032 | United Kingdom | S0010 | UNIT-General Hospital | 11 | 0 | 0 | 0 | SCREENING | Dr. Jessica Wilson | Dr. Daniel Miller | 2024-11-22 | 2024-12-19 | 2024-12-20 | 2025-01-14 | 2025-01-09 | 2025-02-03 | 2025-01-23 | 2025-02-19 | 2025-02-12 | 2025-03-05 | 2025-02-22 | 2025-06-18 | 2025-07-02 | 2025-08-18 | 2025-09-01 | 2029-11-10 |  | 2030-01-06 |  | 2030-04-11 |  | 2030-05-23 |  | 2030-06-14
6492 | ST-2025-032 | Norway | S0011 | NORW-Clinical Center | 18 | 0 | 0 | 0 | ON_HOLD | Dr. William Johnson | Dr. William Martin | 2024-11-24 | 2024-12-23 | 2024-12-20 | 2025-01-22 | 2025-01-30 | 2025-02-12 | 2025-02-10 | 2025-02-24 | 2025-03-04 | 2025-03-12 | 2025-03-02 | 2025-05-31 | 2025-06-10 | 2025-07-20 | 2025-08-03 | 2029-10-22 |  | 2029-12-19 |  | 2030-03-28 |  | 2030-05-14 |  | 2030-06-01
6493 | ST-2025-032 | Norway | S0012 | NORW-General Hospital | 14 | 0 | 0 | 0 | ON_HOLD | Dr. Sarah Anderson | Dr. Christopher White | 2024-12-02 | 2025-01-01 | 2025-01-04 | 2025-02-02 | 2025-02-12 | 2025-02-24 | 2025-02-20 | 2025-03-12 | 2025-03-06 | 2025-03-24 | 2025-03-31 | 2025-05-29 | 2025-05-25 | 2025-07-21 | 2025-07-20 | 2029-10-28 |  | 2029-12-26 |  | 2030-03-30 |  | 2030-05-12 |  | 2030-05-30
6494 | ST-2025-032 | Norway | S0013 | NORW-University Hospital | 6 | 0 | 0 | 0 | SCREENING | Dr. Michelle Miller | Dr. Emily Taylor | 2024-11-27 | 2024-12-26 | 2024-12-26 | 2025-01-24 | 2025-01-23 | 2025-02-13 | 2025-02-06 | 2025-02-24 | 2025-02-28 | 2025-03-09 | 2025-03-23 | 2025-06-09 | 2025-05-31 | 2025-08-08 | 2025-08-11 | 2029-10-31 |  | 2029-12-26 |  | 2030-04-10 |  | 2030-05-17 |  | 2030-06-06
6495 | ST-2025-032 | Norway | S0014 | NORW-University Hospital | 14 | 0 | 0 | 0 | CLOSED | Dr. James Smith | Dr. Charles Williams | 2024-11-30 | 2024-12-24 | 2025-01-01 | 2025-01-25 | 2025-01-21 | 2025-02-19 | 2025-02-16 | 2025-03-04 | 2025-03-14 | 2025-03-16 | 2025-03-26 | 2025-06-12 | 2025-06-15 | 2025-08-08 | 2025-07-27 | 2029-10-29 |  | 2029-12-19 |  | 2030-04-07 |  | 2030-05-15 |  | 2030-06-08
6496 | ST-2025-033 | Mexico | S0001 | MEXI-Research Institute | -11 | -11 | 100 | -0.9 | SCREENING | Dr. Jessica Thomas | Dr. Charles Wilson | 2021-10-15 | 2021-11-10 | 2021-11-06 | 2021-12-08 | 2021-12-07 | 2022-01-01 | 2021-12-24 | 2022-01-13 | 2022-01-16 | 2022-01-25 | 2022-02-03 | 2022-04-22 | 2022-04-15 | 2022-06-18 | 2022-06-04 | 2025-07-27 | 2025-07-14 | 2025-09-19 | 2025-10-02 | 2026-01-11 | 2025-12-28 | 2026-02-19 | 2026-03-01 | 2026-03-11 | 2026-03-13
6497 | ST-2025-033 | Mexico | S0002 | MEXI-Health System | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. David Williams | Dr. Robert Brown | 2021-10-13 | 2021-11-12 | 2021-11-01 | 2021-12-05 | 2021-12-17 | 2021-12-23 | 2022-01-03 | 2022-01-05 | 2022-01-03 | 2022-01-18 | 2022-01-24 | 2022-04-12 | 2022-04-10 | 2022-06-03 | 2022-05-24 | 2025-08-03 | 2025-08-15 | 2025-09-26 | 2025-10-05 | 2026-01-10 | 2026-01-24 | 2026-02-20 | 2026-02-14 | 2026-03-15 | 2026-03-28
6498 | ST-2025-033 | Mexico | S0003 | MEXI-General Hospital | 3 | 1 | 33.3 | 0.1 | ENROLLING | Dr. Jennifer Wilson | Dr. Emily Jones | 2021-10-08 | 2021-11-08 | 2021-11-06 | 2021-12-07 | 2021-11-29 | 2021-12-23 | 2022-01-04 | 2022-01-03 | 2022-01-08 | 2022-01-19 | 2022-02-01 | 2022-04-27 | 2022-04-22 | 2022-06-23 | 2022-07-04 | 2025-08-04 | 2025-07-31 | 2025-09-26 | 2025-09-25 | 2026-01-13 | 2026-01-15 | 2026-02-28 | 2026-03-09 | 2026-03-24 | 2026-03-10
6499 | ST-2025-033 | Mexico | S0004 | MEXI-Cancer Center | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Charles Taylor | Dr. William Martin | 2021-10-14 | 2021-11-09 | 2021-11-12 | 2021-12-03 | 2021-11-27 | 2021-12-23 | 2021-12-24 | 2022-01-08 | 2022-01-03 | 2022-01-23 | 2022-01-31 | 2022-04-27 | 2022-04-30 | 2022-06-21 | 2022-06-23 | 2025-08-05 | 2025-07-29 | 2025-10-01 | 2025-09-29 | 2026-01-19 | 2026-01-05 | 2026-02-28 | 2026-03-01 | 2026-03-21 | 2026-03-30
6500 | ST-2025-033 | Mexico | S0005 | MEXI-University Hospital | 3 | 7 | 233.3 | 0.9 | ENROLLING | Dr. Lisa Miller | Dr. Michael Jones | 2021-10-12 | 2021-11-12 | 2021-11-16 | 2021-12-06 | 2021-11-25 | 2021-12-29 | 2022-01-04 | 2022-01-10 | 2022-01-05 | 2022-01-25 | 2022-01-21 | 2022-04-25 | 2022-04-15 | 2022-06-19 | 2022-06-30 | 2025-08-18 | 2025-08-24 | 2025-10-11 | 2025-09-29 | 2026-01-30 | 2026-01-19 | 2026-03-13 | 2026-03-16 | 2026-04-03 | 2026-03-25
6501 | ST-2025-033 | Canada | S0006 | CANA-University Hospital | -1 | -1 | 100 | -0.1 | ENROLLING | Dr. Stephanie Martin | Dr. Thomas Anderson | 2021-10-19 | 2021-11-20 | 2021-11-30 | 2021-12-16 | 2021-12-17 | 2022-01-02 | 2021-12-27 | 2022-01-14 | 2022-01-13 | 2022-01-28 | 2022-01-23 | 2022-04-29 | 2022-05-08 | 2022-06-30 | 2022-06-26 | 2025-07-25 | 2025-08-06 | 2025-09-22 | 2025-09-12 | 2026-01-24 | 2026-01-11 | 2026-03-05 | 2026-03-01 | 2026-03-23 | 2026-03-31
6502 | ST-2025-033 | Canada | S0007 | CANA-Health System | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. Lisa Moore | Dr. Charles Jackson | 2021-10-18 | 2021-11-10 | 2021-11-06 | 2021-12-07 | 2021-12-07 | 2021-12-26 | 2022-01-03 | 2022-01-12 | 2022-01-13 | 2022-01-27 | 2022-01-29 | 2022-05-07 | 2022-05-10 | 2022-07-02 | 2022-07-15 | 2025-07-31 | 2025-08-09 | 2025-09-27 | 2025-10-06 | 2026-01-25 | 2026-01-13 | 2026-03-13 | 2026-03-02 | 2026-04-01 | 2026-03-31
6503 | ST-2025-033 | Canada | S0008 | CANA-Cancer Center | 3 | 3 | 100 | 0.2 | SCREENING | Dr. Nicole Thomas | Dr. Jessica Thompson | 2021-10-18 | 2021-11-12 | 2021-11-13 | 2021-12-05 | 2021-11-26 | 2021-12-23 | 2021-12-29 | 2022-01-07 | 2022-01-18 | 2022-01-23 | 2022-01-25 | 2022-05-02 | 2022-05-03 | 2022-06-22 | 2022-06-12 | 2025-08-01 | 2025-08-10 | 2025-09-28 | 2025-10-11 | 2026-01-27 | 2026-01-30 | 2026-03-05 | 2026-03-04 | 2026-03-26 | 2026-03-24
6504 | ST-2025-033 | Switzerland | S0009 | SWIT-University Hospital | 2 | 1 | 50 | 0.1 | CLOSED | Dr. William Jones | Dr. Stephanie Moore | 2021-10-26 | 2021-11-24 | 2021-11-14 | 2021-12-21 | 2021-12-16 | 2022-01-16 | 2022-01-18 | 2022-01-29 | 2022-02-05 | 2022-02-13 | 2022-02-05 | 2022-05-05 | 2022-05-16 | 2022-07-02 | 2022-07-07 | 2025-08-16 | 2025-08-24 | 2025-10-11 | 2025-10-08 | 2026-01-19 | 2026-01-21 | 2026-03-07 | 2026-03-12 | 2026-03-26 | 2026-03-20
6505 | ST-2025-033 | Switzerland | S0010 | SWIT-Clinical Center | 3 | 2 | 66.7 | 0.2 | CLOSED | Dr. William Brown | Dr. Michelle White | 2021-10-28 | 2021-11-25 | 2021-11-26 | 2021-12-20 | 2021-12-08 | 2022-01-07 | 2021-12-24 | 2022-01-22 | 2022-01-17 | 2022-02-07 | 2022-02-15 | 2022-05-17 | 2022-05-09 | 2022-07-12 | 2022-07-04 | 2025-08-06 | 2025-08-14 | 2025-10-01 | 2025-09-20 | 2026-01-20 | 2026-01-23 | 2026-02-28 | 2026-02-28 | 2026-03-19 | 2026-03-15
6506 | ST-2025-033 | Poland | S0011 | POLA-Cancer Center | 2 | 2 | 100 | 0.2 | ON_HOLD | Dr. Amanda White | Dr. David Moore | 2021-10-25 | 2021-11-24 | 2021-11-16 | 2021-12-26 | 2021-12-20 | 2022-01-13 | 2022-01-08 | 2022-01-24 | 2022-02-05 | 2022-02-06 | 2022-02-19 | 2022-05-11 | 2022-05-10 | 2022-07-07 | 2022-07-11 | 2025-08-07 | 2025-08-16 | 2025-09-30 | 2025-09-25 | 2026-01-19 | 2026-01-16 | 2026-03-07 | 2026-03-12 | 2026-03-25 | 2026-04-04
6507 | ST-2025-033 | Poland | S0012 | POLA-University Hospital | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Jennifer Smith | Dr. David Harris | 2021-10-20 | 2021-11-20 | 2021-11-14 | 2021-12-21 | 2021-12-25 | 2022-01-16 | 2022-01-05 | 2022-02-01 | 2022-01-22 | 2022-02-13 | 2022-02-24 | 2022-05-06 | 2022-05-08 | 2022-07-03 | 2022-07-07 | 2025-07-30 | 2025-08-05 | 2025-09-20 | 2025-09-30 | 2026-01-21 | 2026-01-19 | 2026-03-03 | 2026-02-27 | 2026-03-22 | 2026-03-26
6508 | ST-2025-034 | Canada | S0001 | CANA-University Hospital | 5 | 4 | 80 | 0.2 | ENROLLING | Dr. Christopher Harris | Dr. Stephanie Jackson | 2022-12-31 | 2023-02-01 | 2023-02-06 | 2023-02-28 | 2023-02-18 | 2023-03-25 | 2023-03-15 | 2023-04-10 | 2023-04-01 | 2023-04-24 | 2023-04-25 | 2023-07-03 | 2023-07-16 | 2023-08-23 | 2023-08-09 | 2026-08-22 |  | 2026-10-15 |  | 2027-02-26 |  | 2027-04-05 |  | 2027-04-29
6509 | ST-2025-034 | Canada | S0002 | CANA-Clinical Center | 3 | 3 | 100 | 0.3 | SCREENING | Dr. Amanda Taylor | Dr. Nicole Jackson | 2023-01-05 | 2023-01-28 | 2023-01-17 | 2023-02-22 | 2023-02-15 | 2023-03-18 | 2023-03-21 | 2023-04-04 | 2023-04-02 | 2023-04-18 | 2023-04-16 | 2023-07-10 | 2023-07-20 | 2023-09-07 | 2023-09-05 | 2026-09-02 |  | 2026-10-28 |  | 2027-03-03 |  | 2027-04-17 |  | 2027-05-11
6510 | ST-2025-034 | France | S0003 | FRAN-Health System | 0 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Wilson | Dr. Charles Smith | 2022-12-28 | 2023-01-24 | 2023-01-18 | 2023-02-24 | 2023-03-04 | 2023-03-17 | 2023-03-07 | 2023-04-01 | 2023-04-13 | 2023-04-12 | 2023-04-11 | 2023-07-17 | 2023-07-20 | 2023-09-13 | 2023-09-13 | 2026-09-21 |  | 2026-11-14 |  | 2027-02-23 |  | 2027-04-11 |  | 2027-05-05
6511 | ST-2025-034 | France | S0004 | FRAN-University Hospital | 3 | 3 | 100 | 0.2 | SCREENING | Dr. Jessica Thompson | Dr. David Jones | 2023-01-04 | 2023-01-31 | 2023-02-07 | 2023-03-05 | 2023-03-02 | 2023-03-22 | 2023-03-31 | 2023-04-06 | 2023-04-05 | 2023-04-20 | 2023-04-12 | 2023-07-18 | 2023-07-23 | 2023-09-10 | 2023-09-13 | 2026-09-15 |  | 2026-11-05 |  | 2027-03-03 |  | 2027-04-16 |  | 2027-05-10
6512 | ST-2025-034 | France | S0005 | FRAN-University Hospital | 3 | 1 | 33.3 | 0.1 | ON_HOLD | Dr. Sarah Williams | Dr. Jessica Jones | 2023-01-06 | 2023-02-01 | 2023-02-05 | 2023-03-02 | 2023-02-25 | 2023-03-23 | 2023-03-19 | 2023-04-04 | 2023-03-24 | 2023-04-20 | 2023-04-17 | 2023-07-16 | 2023-07-10 | 2023-09-06 | 2023-09-08 | 2026-09-28 |  | 2026-11-23 |  | 2027-03-14 |  | 2027-04-23 |  | 2027-05-11
6513 | ST-2025-034 | New Zealand | S0006 | NEW-Medical Center | -3 | -3 | 100 | -0.4 | ENROLLING | Dr. David White | Dr. Michael Davis | 2023-01-09 | 2023-02-05 | 2023-02-09 | 2023-02-28 | 2023-03-12 | 2023-03-26 | 2023-03-12 | 2023-04-08 | 2023-04-21 | 2023-04-24 | 2023-05-02 | 2023-07-17 | 2023-07-18 | 2023-09-10 | 2023-09-15 | 2026-09-08 |  | 2026-11-02 |  | 2027-02-20 |  | 2027-04-08 |  | 2027-04-26
6514 | ST-2025-034 | New Zealand | S0007 | NEW-University Hospital | 3 | 3 | 100 | 0.2 | SCREENING | Dr. Amanda Smith | Dr. Nicole Garcia | 2023-01-07 | 2023-02-01 | 2023-01-22 | 2023-03-03 | 2023-03-11 | 2023-03-29 | 2023-04-07 | 2023-04-15 | 2023-04-06 | 2023-04-30 | 2023-05-13 | 2023-07-27 | 2023-08-09 | 2023-09-15 | 2023-09-05 | 2026-09-13 |  | 2026-11-08 |  | 2027-02-21 |  | 2027-04-08 |  | 2027-05-01
6515 | ST-2025-034 | New Zealand | S0008 | NEW-Research Institute | 3 | 2 | 66.7 | 0.3 | ENROLLING | Dr. Michelle Jackson | Dr. David Martin | 2023-01-13 | 2023-02-06 | 2023-02-11 | 2023-03-01 | 2023-03-10 | 2023-03-24 | 2023-03-10 | 2023-04-09 | 2023-04-05 | 2023-04-25 | 2023-05-07 | 2023-07-15 | 2023-07-22 | 2023-09-07 | 2023-09-20 | 2026-09-14 |  | 2026-11-12 |  | 2027-02-25 |  | 2027-04-06 |  | 2027-04-29
6516 | ST-2025-034 | New Zealand | S0009 | NEW-General Hospital | 3 | 4 | 133.3 | 0.3 | ENROLLING | Dr. Lisa Brown | Dr. Charles Jones | 2023-01-14 | 2023-02-08 | 2023-01-31 | 2023-03-12 | 2023-03-24 | 2023-04-02 | 2023-04-12 | 2023-04-17 | 2023-04-19 | 2023-04-28 | 2023-04-18 | 2023-08-09 | 2023-08-18 | 2023-10-03 | 2023-09-27 | 2026-10-04 |  | 2026-12-04 |  | 2027-03-18 |  | 2027-04-24 |  | 2027-05-12
6517 | ST-2025-035 | Canada | S0001 | CANA-Health System | -35 | -35 | 100 | -2.9 | ENROLLING | Dr. Jessica Wilson | Dr. James White | 2024-12-21 | 2025-01-13 | 2025-01-16 | 2025-02-09 | 2025-02-06 | 2025-03-06 | 2025-02-23 | 2025-03-18 | 2025-03-14 | 2025-04-03 | 2025-04-03 | 2025-06-26 | 2025-06-30 | 2025-08-20 | 2025-09-01 | 2026-12-16 |  | 2027-02-15 |  | 2027-06-20 |  | 2027-07-31 |  | 2027-08-20
6518 | ST-2025-035 | Canada | S0002 | CANA-University Hospital | 3 | 3 | 100 | 0.5 | ENROLLING | Dr. Robert Wilson | Dr. William Harris | 2024-12-23 | 2025-01-22 | 2025-02-01 | 2025-02-15 | 2025-02-06 | 2025-03-04 | 2025-03-15 | 2025-03-15 | 2025-03-01 | 2025-03-27 | 2025-03-19 | 2025-07-05 | 2025-07-11 | 2025-08-24 | 2025-08-21 | 2026-12-22 |  | 2027-02-16 |  | 2027-07-05 |  | 2027-08-21 |  | 2027-09-08
6519 | ST-2025-035 | Canada | S0003 | CANA-Health System | 3 | 3 | 100 | 0.2 | SCREENING | Dr. Thomas Brown | Dr. Lisa Davis | 2024-12-28 | 2025-01-23 | 2025-01-31 | 2025-02-19 | 2025-02-14 | 2025-03-17 | 2025-03-08 | 2025-04-02 | 2025-03-27 | 2025-04-19 | 2025-04-09 | 2025-06-30 | 2025-07-04 | 2025-08-29 | 2025-08-25 | 2027-01-04 |  | 2027-02-26 |  | 2027-07-03 |  | 2027-08-09 |  | 2027-08-30
6520 | ST-2025-035 | Canada | S0004 | CANA-Medical Center | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Lisa Williams | Dr. Jessica Harris | 2024-12-27 | 2025-01-22 | 2025-01-26 | 2025-02-18 | 2025-02-15 | 2025-03-09 | 2025-03-06 | 2025-03-21 | 2025-03-31 | 2025-04-03 | 2025-04-09 | 2025-07-04 | 2025-07-06 | 2025-09-02 | 2025-09-02 | 2027-01-02 |  | 2027-02-26 |  | 2027-07-03 |  | 2027-08-16 |  | 2027-09-05
6521 | ST-2025-035 | Canada | S0005 | CANA-Health System | 3 | 3 | 100 | 0.2 | SCREENING | Dr. Thomas Moore | Dr. Charles Martin | 2024-12-24 | 2025-01-18 | 2025-01-25 | 2025-02-10 | 2025-02-21 | 2025-03-07 | 2025-03-02 | 2025-03-21 | 2025-03-13 | 2025-04-02 | 2025-03-29 | 2025-07-21 | 2025-07-29 | 2025-09-17 | 2025-09-19 | 2027-01-11 |  | 2027-03-09 |  | 2027-07-20 |  | 2027-09-05 |  | 2027-09-29
6522 | ST-2025-035 | Canada | S0006 | CANA-Health System | 3 | 4 | 133.3 | 0.7 | ENROLLING | Dr. Thomas Taylor | Dr. Amanda Harris | 2024-12-25 | 2025-01-21 | 2025-01-28 | 2025-02-14 | 2025-02-20 | 2025-03-10 | 2025-03-01 | 2025-03-27 | 2025-03-28 | 2025-04-08 | 2025-03-29 | 2025-07-16 | 2025-07-16 | 2025-09-06 | 2025-09-10 | 2027-01-14 |  | 2027-03-10 |  | 2027-07-14 |  | 2027-08-21 |  | 2027-09-12
6523 | ST-2025-035 | Mexico | S0007 | MEXI-Health System | 2 | 1 | 50 | 0.1 | ENROLLING | Dr. Charles Wilson | Dr. Charles Johnson | 2024-12-31 | 2025-01-29 | 2025-01-30 | 2025-03-03 | 2025-02-27 | 2025-03-28 | 2025-03-24 | 2025-04-08 | 2025-04-14 | 2025-04-21 | 2025-05-05 | 2025-07-06 | 2025-06-25 | 2025-08-25 | 2025-08-16 | 2027-01-04 |  | 2027-03-01 |  | 2027-06-12 |  | 2027-07-21 |  | 2027-08-11
6524 | ST-2025-035 | Mexico | S0008 | MEXI-General Hospital | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. Nicole Moore | Dr. Amanda Williams | 2024-12-26 | 2025-01-20 | 2025-01-28 | 2025-02-19 | 2025-02-18 | 2025-03-15 | 2025-03-24 | 2025-03-27 | 2025-03-25 | 2025-04-13 | 2025-04-14 | 2025-07-02 | 2025-07-14 | 2025-08-27 | 2025-08-20 | 2027-01-13 |  | 2027-03-14 |  | 2027-06-26 |  | 2027-08-11 |  | 2027-09-02
6525 | ST-2025-035 | United States | S0009 | UNIT-General Hospital | -1 | -1 | 100 | -0.1 | ENROLLING | Dr. Robert Garcia | Dr. Amanda White | 2024-12-22 | 2025-01-23 | 2025-01-22 | 2025-02-20 | 2025-03-02 | 2025-03-15 | 2025-03-09 | 2025-03-31 | 2025-04-04 | 2025-04-14 | 2025-04-12 | 2025-06-24 | 2025-06-28 | 2025-08-12 | 2025-07-29 | 2027-01-04 |  | 2027-02-27 |  | 2027-06-27 |  | 2027-08-04 |  | 2027-08-25
6526 | ST-2025-035 | United States | S0010 | UNIT-Clinical Center | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Jessica Moore | Dr. Nicole Davis | 2024-12-19 | 2025-01-15 | 2025-01-10 | 2025-02-16 | 2025-02-27 | 2025-03-12 | 2025-03-22 | 2025-03-24 | 2025-03-14 | 2025-04-08 | 2025-04-19 | 2025-07-05 | 2025-07-02 | 2025-08-25 | 2025-08-25 | 2026-12-26 |  | 2027-02-25 |  | 2027-06-27 |  | 2027-08-03 |  | 2027-08-21
6527 | ST-2025-035 | United States | S0011 | UNIT-Clinical Center | 3 | 4 | 133.3 | 0.3 | ENROLLING | Dr. Charles Brown | Dr. Emily Jackson | 2024-12-24 | 2025-01-16 | 2025-01-04 | 2025-02-18 | 2025-02-27 | 2025-03-08 | 2025-03-01 | 2025-03-20 | 2025-03-10 | 2025-04-01 | 2025-04-08 | 2025-07-02 | 2025-07-05 | 2025-08-24 | 2025-09-06 | 2026-12-30 |  | 2027-02-21 |  | 2027-06-30 |  | 2027-08-09 |  | 2027-08-30
6528 | ST-2025-035 | Sweden | S0012 | SWED-Health System | -10 | -10 | 100 | -1 | SCREENING | Dr. Amanda Brown | Dr. Thomas Thompson | 2025-01-02 | 2025-02-01 | 2025-02-13 | 2025-02-26 | 2025-02-26 | 2025-03-19 | 2025-03-27 | 2025-03-30 | 2025-03-23 | 2025-04-13 | 2025-04-23 | 2025-07-09 | 2025-06-28 | 2025-09-06 | 2025-09-04 | 2027-01-14 |  | 2027-03-09 |  | 2027-06-20 |  | 2027-08-06 |  | 2027-08-27
6529 | ST-2025-035 | Sweden | S0013 | SWED-Health System | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. Lisa Jackson | Dr. Nicole Harris | 2025-01-14 | 2025-02-08 | 2025-01-27 | 2025-03-09 | 2025-03-06 | 2025-03-30 | 2025-03-31 | 2025-04-12 | 2025-04-19 | 2025-04-29 | 2025-05-08 | 2025-07-14 | 2025-07-18 | 2025-09-12 | 2025-08-29 | 2027-01-24 |  | 2027-03-22 |  | 2027-06-25 |  | 2027-08-07 |  | 2027-08-29
6530 | ST-2025-035 | Sweden | S0014 | SWED-Research Institute | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Jennifer Jackson | Dr. Jessica Smith | 2025-01-11 | 2025-02-05 | 2025-02-11 | 2025-03-03 | 2025-02-24 | 2025-03-24 | 2025-03-14 | 2025-04-06 | 2025-04-07 | 2025-04-19 | 2025-04-11 | 2025-07-15 | 2025-07-02 | 2025-09-15 | 2025-09-07 | 2027-01-14 |  | 2027-03-15 |  | 2027-06-28 |  | 2027-08-10 |  | 2027-08-28
6531 | ST-2025-035 | Sweden | S0015 | SWED-Health System | 3 | 3 | 100 | 0.3 | SCREENING | Dr. Jennifer Brown | Dr. Charles White | 2025-01-03 | 2025-01-31 | 2025-01-25 | 2025-03-01 | 2025-02-28 | 2025-03-27 | 2025-03-18 | 2025-04-08 | 2025-03-30 | 2025-04-22 | 2025-04-20 | 2025-07-14 | 2025-07-21 | 2025-09-05 | 2025-09-07 | 2027-01-23 |  | 2027-03-21 |  | 2027-07-04 |  | 2027-08-17 |  | 2027-09-04
6532 | ST-2025-035 | Sweden | S0016 | SWED-Clinical Center | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. James Davis | Dr. Robert Thompson | 2025-01-09 | 2025-02-02 | 2025-02-06 | 2025-03-02 | 2025-03-04 | 2025-03-28 | 2025-03-26 | 2025-04-13 | 2025-04-20 | 2025-04-24 | 2025-04-24 | 2025-08-05 | 2025-07-22 | 2025-10-06 | 2025-10-07 | 2027-02-08 |  | 2027-03-31 |  | 2027-07-10 |  | 2027-08-21 |  | 2027-09-09
6533 | ST-2025-035 | Sweden | S0017 | SWED-Medical Center | 3 | 5 | 166.7 | 0.3 | ON_HOLD | Dr. Stephanie Smith | Dr. Thomas Davis | 2025-01-12 | 2025-02-10 | 2025-02-07 | 2025-03-11 | 2025-03-21 | 2025-03-27 | 2025-03-28 | 2025-04-09 | 2025-04-17 | 2025-04-23 | 2025-04-19 | 2025-08-01 | 2025-08-14 | 2025-09-30 | 2025-10-03 | 2027-02-14 |  | 2027-04-07 |  | 2027-07-19 |  | 2027-09-01 |  | 2027-09-23
6534 | ST-2025-035 | Netherlands | S0018 | NETH-Clinical Center | -4 | -4 | 100 | -0.3 | CLOSED | Dr. David Garcia | Dr. Christopher Thomas | 2025-01-08 | 2025-02-02 | 2025-02-06 | 2025-03-03 | 2025-02-25 | 2025-03-27 | 2025-03-19 | 2025-04-13 | 2025-04-15 | 2025-04-27 | 2025-05-09 | 2025-07-24 | 2025-07-29 | 2025-09-21 | 2025-09-30 | 2027-01-19 |  | 2027-03-13 |  | 2027-06-18 |  | 2027-07-30 |  | 2027-08-22
6535 | ST-2025-035 | Netherlands | S0019 | NETH-General Hospital | 3 | 2 | 66.7 | 0.2 | SCREENING | Dr. Nicole Miller | Dr. Thomas Jones | 2025-01-13 | 2025-02-05 | 2025-02-02 | 2025-03-07 | 2025-03-01 | 2025-03-27 | 2025-03-26 | 2025-04-07 | 2025-04-03 | 2025-04-18 | 2025-04-25 | 2025-07-30 | 2025-07-25 | 2025-09-24 | 2025-10-04 | 2027-01-31 |  | 2027-03-28 |  | 2027-06-24 |  | 2027-08-09 |  | 2027-09-01
6536 | ST-2025-035 | Netherlands | S0020 | NETH-Research Institute | 3 | 3 | 100 | 0.4 | SCREENING | Dr. David Harris | Dr. Christopher Davis | 2025-01-15 | 2025-02-11 | 2025-01-31 | 2025-03-08 | 2025-03-05 | 2025-03-28 | 2025-04-06 | 2025-04-10 | 2025-03-28 | 2025-04-24 | 2025-04-27 | 2025-07-23 | 2025-08-01 | 2025-09-17 | 2025-09-15 | 2027-02-04 |  | 2027-03-31 |  | 2027-07-10 |  | 2027-08-16 |  | 2027-09-07
6537 | ST-2025-035 | Netherlands | S0021 | NETH-General Hospital | 3 | 2 | 66.7 | 0.1 | ON_HOLD | Dr. Lisa Garcia | Dr. Christopher Thompson | 2025-01-08 | 2025-02-08 | 2025-02-13 | 2025-03-04 | 2025-02-25 | 2025-03-22 | 2025-04-03 | 2025-04-07 | 2025-04-21 | 2025-04-19 | 2025-05-01 | 2025-07-31 | 2025-08-09 | 2025-09-25 | 2025-10-07 | 2027-02-03 |  | 2027-03-30 |  | 2027-07-03 |  | 2027-08-16 |  | 2027-09-08
6538 | ST-2025-035 | Italy | S0022 | ITAL-University Hospital | -1 | -1 | 100 | -0.1 | SCREENING | Dr. Michael Smith | Dr. Sarah White | 2025-02-09 | 2025-03-04 | 2025-03-13 | 2025-03-28 | 2025-03-16 | 2025-04-18 | 2025-04-14 | 2025-05-01 | 2025-05-07 | 2025-05-12 | 2025-05-21 | 2025-08-10 | 2025-08-05 | 2025-10-07 | 2025-10-06 | 2027-02-25 |  | 2027-04-27 |  | 2027-06-25 |  | 2027-08-07 |  | 2027-08-29
6539 | ST-2025-035 | Italy | S0023 | ITAL-Cancer Center | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. Charles Williams | Dr. Stephanie Wilson | 2025-02-04 | 2025-03-03 | 2025-03-05 | 2025-04-05 | 2025-04-08 | 2025-04-22 | 2025-05-05 | 2025-05-09 | 2025-05-20 | 2025-05-23 | 2025-05-16 | 2025-08-13 | 2025-08-21 | 2025-10-13 | 2025-10-24 | 2027-02-21 |  | 2027-04-22 |  | 2027-07-02 |  | 2027-08-12 |  | 2027-09-03
6540 | ST-2025-035 | Italy | S0024 | ITAL-General Hospital | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. Michelle Smith | Dr. Christopher Martin | 2025-02-11 | 2025-03-13 | 2025-03-18 | 2025-04-08 | 2025-04-06 | 2025-04-30 | 2025-04-21 | 2025-05-13 | 2025-05-20 | 2025-05-29 | 2025-05-24 | 2025-08-24 | 2025-08-18 | 2025-10-24 | 2025-10-10 | 2027-02-21 |  | 2027-04-17 |  | 2027-07-07 |  | 2027-08-23 |  | 2027-09-10
6541 | ST-2025-035 | Germany | S0025 | GERM-Clinical Center | -7 | -7 | 100 | -0.6 | ENROLLING | Dr. Emily Jones | Dr. William Brown | 2025-01-27 | 2025-02-25 | 2025-02-18 | 2025-03-30 | 2025-03-16 | 2025-04-17 | 2025-04-25 | 2025-04-30 | 2025-04-26 | 2025-05-13 | 2025-05-06 | 2025-08-11 | 2025-07-30 | 2025-10-08 | 2025-10-13 | 2027-02-06 |  | 2027-04-08 |  | 2027-06-22 |  | 2027-07-30 |  | 2027-08-18
6542 | ST-2025-035 | Germany | S0026 | GERM-General Hospital | 3 | 2 | 66.7 | 0.2 | ENROLLING | Dr. Stephanie Taylor | Dr. Robert Davis | 2025-02-07 | 2025-03-11 | 2025-03-07 | 2025-04-10 | 2025-04-06 | 2025-05-05 | 2025-05-01 | 2025-05-19 | 2025-05-16 | 2025-06-04 | 2025-06-16 | 2025-08-17 | 2025-08-17 | 2025-10-10 | 2025-09-30 | 2027-02-06 |  | 2027-04-04 |  | 2027-06-28 |  | 2027-08-12 |  | 2027-08-30
6543 | ST-2025-035 | Germany | S0027 | GERM-Cancer Center | 3 | 3 | 100 | 0.2 | ENROLLING | Dr. William Brown | Dr. Thomas Williams | 2025-02-07 | 2025-03-09 | 2025-03-13 | 2025-04-04 | 2025-03-23 | 2025-04-28 | 2025-05-04 | 2025-05-14 | 2025-05-15 | 2025-05-26 | 2025-05-29 | 2025-08-23 | 2025-08-20 | 2025-10-17 | 2025-10-05 | 2027-02-07 |  | 2027-04-05 |  | 2027-06-26 |  | 2027-08-12 |  | 2027-09-05
6544 | ST-2025-035 | Germany | S0028 | GERM-Clinical Center | 3 | 2 | 66.7 | 0.1 | ENROLLING | Dr. Lisa Wilson | Dr. Thomas Anderson | 2025-02-04 | 2025-03-04 | 2025-02-23 | 2025-03-31 | 2025-04-05 | 2025-04-20 | 2025-04-17 | 2025-05-07 | 2025-05-11 | 2025-05-20 | 2025-05-19 | 2025-08-20 | 2025-08-19 | 2025-10-18 | 2025-10-28 | 2027-02-10 |  | 2027-04-02 |  | 2027-06-28 |  | 2027-08-13 |  | 2027-09-04
6545 | ST-2025-035 | Germany | S0029 | GERM-General Hospital | 3 | 5 | 166.7 | 0.4 | ENROLLING | Dr. Christopher Wilson | Dr. William Johnson | 2025-01-31 | 2025-03-03 | 2025-02-23 | 2025-04-02 | 2025-03-22 | 2025-04-21 | 2025-04-25 | 2025-05-05 | 2025-04-30 | 2025-05-20 | 2025-05-11 | 2025-08-15 | 2025-08-28 | 2025-10-09 | 2025-09-30 | 2027-02-12 |  | 2027-04-05 |  | 2027-06-27 |  | 2027-08-09 |  | 2027-08-28
6546 | ST-2025-035 | Australia | S0030 | AUST-General Hospital | -4 | -4 | 100 | -0.5 | CLOSED | Dr. Jessica Martin | Dr. Christopher Anderson | 2025-02-18 | 2025-03-19 | 2025-03-16 | 2025-04-19 | 2025-04-25 | 2025-05-11 | 2025-04-30 | 2025-05-24 | 2025-05-31 | 2025-06-10 | 2025-06-24 | 2025-08-20 | 2025-08-27 | 2025-10-14 | 2025-10-20 | 2027-02-22 |  | 2027-04-23 |  | 2027-06-26 |  | 2027-08-07 |  | 2027-08-31
6547 | ST-2025-035 | Australia | S0031 | AUST-University Hospital | 3 | 2 | 66.7 | 0.1 | CLOSED | Dr. Robert Jones | Dr. Jessica Jackson | 2025-02-12 | 2025-03-15 | 2025-03-28 | 2025-04-15 | 2025-04-06 | 2025-05-09 | 2025-05-07 | 2025-05-23 | 2025-05-18 | 2025-06-04 | 2025-05-21 | 2025-09-05 | 2025-09-08 | 2025-10-30 | 2025-11-11 | 2027-02-21 |  | 2027-04-20 |  | 2027-07-02 |  | 2027-08-15 |  | 2027-09-03
6548 | ST-2025-035 | Australia | S0032 | AUST-Research Institute | 3 | 2 | 66.7 | 0.1 | SCREENING | Dr. James Miller | Dr. Jessica Jones | 2025-02-14 | 2025-03-19 | 2025-03-05 | 2025-04-13 | 2025-04-18 | 2025-05-09 | 2025-05-02 | 2025-05-20 | 2025-05-10 | 2025-06-03 | 2025-06-08 | 2025-09-02 | 2025-09-07 | 2025-10-31 | 2025-11-02 | 2027-02-21 |  | 2027-04-19 |  | 2027-07-05 |  | 2027-08-14 |  | 2027-09-06
6549 | ST-2025-035 | Australia | S0033 | AUST-Health System | 3 | 2 | 66.7 | 0.3 | ON_HOLD | Dr. Amanda Thompson | Dr. Daniel Jackson | 2025-02-16 | 2025-03-20 | 2025-03-17 | 2025-04-18 | 2025-04-04 | 2025-05-04 | 2025-05-13 | 2025-05-17 | 2025-05-22 | 2025-06-01 | 2025-06-15 | 2025-09-10 | 2025-09-21 | 2025-10-31 | 2025-11-06 | 2027-03-10 |  | 2027-05-10 |  | 2027-07-20 |  | 2027-09-05 |  | 2027-09-23
6550 | ST-2025-036 | Mexico | S0001 | MEXI-General Hospital | 16 | 15 | 93.8 | 1 | ENROLLING | Dr. David Jones | Dr. David Anderson | 2021-04-29 | 2021-05-25 | 2021-05-20 | 2021-06-19 | 2021-06-07 | 2021-07-12 | 2021-07-26 | 2021-07-25 | 2021-07-11 | 2021-08-10 | 2021-08-02 | 2021-11-01 | 2021-11-05 | 2021-12-23 | 2021-12-23 | 2027-09-27 |  | 2027-11-24 |  | 2028-03-25 |  | 2028-05-06 |  | 2028-05-25
6551 | ST-2025-036 | Mexico | S0002 | MEXI-University Hospital | 12 | 12 | 100 | 1.7 | ENROLLING | Dr. Michelle Johnson | Dr. Robert Moore | 2021-05-01 | 2021-06-02 | 2021-05-24 | 2021-07-02 | 2021-06-25 | 2021-07-21 | 2021-07-21 | 2021-08-07 | 2021-08-16 | 2021-08-19 | 2021-08-07 | 2021-10-30 | 2021-10-16 | 2021-12-26 | 2022-01-04 | 2027-10-09 |  | 2027-11-30 |  | 2028-04-04 |  | 2028-05-16 |  | 2028-06-09
6552 | ST-2025-036 | Mexico | S0003 | MEXI-Research Institute | 20 | 18 | 90 | 2.6 | ENROLLING | Dr. Thomas Davis | Dr. David Miller | 2021-05-01 | 2021-05-30 | 2021-06-09 | 2021-06-30 | 2021-07-05 | 2021-07-23 | 2021-07-29 | 2021-08-09 | 2021-08-12 | 2021-08-23 | 2021-08-31 | 2021-10-25 | 2021-10-11 | 2021-12-25 | 2021-12-25 | 2027-10-06 |  | 2027-11-30 |  | 2028-04-04 |  | 2028-05-12 |  | 2028-06-04
6553 | ST-2025-036 | Mexico | S0004 | MEXI-Research Institute | 14 | 11 | 78.6 | 1.4 | ENROLLING | Dr. William Davis | Dr. David Thomas | 2021-05-02 | 2021-05-25 | 2021-05-31 | 2021-06-21 | 2021-06-21 | 2021-07-13 | 2021-07-12 | 2021-07-30 | 2021-08-10 | 2021-08-16 | 2021-08-05 | 2021-11-12 | 2021-11-01 | 2022-01-12 | 2022-01-02 | 2027-10-08 |  | 2027-12-03 |  | 2028-04-10 |  | 2028-05-25 |  | 2028-06-17
6554 | ST-2025-036 | Mexico | S0005 | MEXI-Medical Center | 16 | 22 | 137.5 | 2.8 | ENROLLING | Dr. Emily Jackson | Dr. James Harris | 2021-05-03 | 2021-06-04 | 2021-05-24 | 2021-06-28 | 2021-06-24 | 2021-07-16 | 2021-07-22 | 2021-07-29 | 2021-08-06 | 2021-08-12 | 2021-07-31 | 2021-11-23 | 2021-11-23 | 2022-01-16 | 2022-01-30 | 2027-10-22 |  | 2027-12-15 |  | 2028-04-23 |  | 2028-06-02 |  | 2028-06-22
6555 | ST-2025-036 | United States | S0006 | UNIT-Medical Center | 48 | 34 | 70.8 | 2.6 | ENROLLING | Dr. Charles Miller | Dr. David Jackson | 2021-05-04 | 2021-05-30 | 2021-06-04 | 2021-06-26 | 2021-06-13 | 2021-07-17 | 2021-07-27 | 2021-07-30 | 2021-07-20 | 2021-08-15 | 2021-08-05 | 2021-11-08 | 2021-11-10 | 2022-01-01 | 2021-12-27 | 2027-10-14 |  | 2027-12-11 |  | 2028-03-21 |  | 2028-05-06 |  | 2028-05-26
6556 | ST-2025-036 | United States | S0007 | UNIT-Health System | 47 | 61 | 129.8 | 8.7 | ENROLLING | Dr. Jennifer Thompson | Dr. Daniel Brown | 2021-05-06 | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-05 | 2021-07-26 | 2021-08-02 | 2021-08-11 | 2021-08-06 | 2021-08-24 | 2021-08-14 | 2021-11-07 | 2021-11-16 | 2022-01-06 | 2022-01-17 | 2027-10-06 |  | 2027-12-05 |  | 2028-03-29 |  | 2028-05-09 |  | 2028-05-30
6557 | ST-2025-036 | Poland | S0008 | POLA-Health System | 12 | 10 | 83.3 | 1.4 | ENROLLING | Dr. James Smith | Dr. Charles White | 2021-05-11 | 2021-06-12 | 2021-06-16 | 2021-07-09 | 2021-06-25 | 2021-07-31 | 2021-07-25 | 2021-08-13 | 2021-08-10 | 2021-08-29 | 2021-09-07 | 2021-11-19 | 2021-11-21 | 2022-01-07 | 2022-01-16 | 2027-11-02 |  | 2027-12-26 |  | 2028-04-01 |  | 2028-05-12 |  | 2028-05-31
6558 | ST-2025-036 | Poland | S0009 | POLA-Clinical Center | 10 | 7 | 70 | 1 | ENROLLING | Dr. Amanda Anderson | Dr. Michael White | 2021-05-17 | 2021-06-15 | 2021-06-13 | 2021-07-15 | 2021-07-28 | 2021-08-09 | 2021-08-10 | 2021-08-21 | 2021-08-27 | 2021-09-03 | 2021-08-25 | 2021-12-02 | 2021-12-15 | 2022-01-22 | 2022-01-24 | 2027-11-04 |  | 2028-01-02 |  | 2028-04-03 |  | 2028-05-18 |  | 2028-06-07
6559 | ST-2025-036 | Poland | S0010 | POLA-Cancer Center | 22 | 14 | 63.6 | 0.9 | ENROLLING | Dr. Lisa Williams | Dr. Charles Martin | 2021-05-16 | 2021-06-14 | 2021-06-24 | 2021-07-07 | 2021-07-16 | 2021-08-02 | 2021-08-13 | 2021-08-13 | 2021-08-02 | 2021-08-26 | 2021-09-01 | 2021-11-28 | 2021-11-20 | 2022-01-20 | 2022-01-17 | 2027-11-01 |  | 2027-12-25 |  | 2028-04-03 |  | 2028-05-14 |  | 2028-06-05
6560 | ST-2025-036 | Poland | S0011 | POLA-Medical Center | 19 | 17 | 89.5 | 1.7 | SCREENING | Dr. Thomas Johnson | Dr. Robert Davis | 2021-05-18 | 2021-06-20 | 2021-06-16 | 2021-07-13 | 2021-07-15 | 2021-08-06 | 2021-07-25 | 2021-08-18 | 2021-08-12 | 2021-09-03 | 2021-09-06 | 2021-12-03 | 2021-12-06 | 2022-01-26 | 2022-02-08 | 2027-11-13 |  | 2028-01-03 |  | 2028-04-12 |  | 2028-05-29 |  | 2028-06-16
6561 | ST-2025-036 | Poland | S0012 | POLA-University Hospital | 13 | 11 | 84.6 | 0.7 | ENROLLING | Dr. Robert Thompson | Dr. Robert Jones | 2021-05-22 | 2021-06-15 | 2021-06-23 | 2021-07-08 | 2021-07-16 | 2021-07-31 | 2021-07-31 | 2021-08-15 | 2021-08-06 | 2021-08-30 | 2021-08-17 | 2021-12-12 | 2021-12-17 | 2022-02-02 | 2022-01-27 | 2027-11-16 |  | 2028-01-08 |  | 2028-04-25 |  | 2028-06-04 |  | 2028-06-23
6562 | ST-2025-036 | Poland | S0013 | POLA-General Hospital | 23 | 40 | 173.9 | 3.1 | ENROLLING | Dr. Sarah Miller | Dr. Jessica Thomas | 2021-05-10 | 2021-06-05 | 2021-06-05 | 2021-06-29 | 2021-06-18 | 2021-07-17 | 2021-07-20 | 2021-08-01 | 2021-08-15 | 2021-08-14 | 2021-08-25 | 2021-12-10 | 2021-11-27 | 2022-01-31 | 2022-01-27 | 2027-11-16 |  | 2028-01-09 |  | 2028-04-25 |  | 2028-06-10 |  | 2028-07-01
6563 | ST-2025-036 | United Kingdom | S0014 | UNIT-Medical Center | 12 | 8 | 66.7 | 0.4 | ENROLLING | Dr. James Martin | Dr. David Anderson | 2021-05-14 | 2021-06-09 | 2021-06-10 | 2021-07-09 | 2021-07-04 | 2021-07-26 | 2021-07-30 | 2021-08-09 | 2021-07-26 | 2021-08-20 | 2021-08-24 | 2021-11-25 | 2021-11-24 | 2022-01-16 | 2022-01-29 | 2027-10-22 |  | 2027-12-20 |  | 2028-03-25 |  | 2028-05-04 |  | 2028-05-26
6564 | ST-2025-036 | United Kingdom | S0015 | UNIT-Clinical Center | 11 | 11 | 100 | 0.7 | SCREENING | Dr. William Taylor | Dr. James Smith | 2021-05-24 | 2021-06-23 | 2021-06-22 | 2021-07-26 | 2021-07-31 | 2021-08-14 | 2021-08-08 | 2021-08-29 | 2021-08-30 | 2021-09-15 | 2021-09-21 | 2021-12-05 | 2021-11-26 | 2022-02-01 | 2022-01-28 | 2027-11-09 |  | 2028-01-06 |  | 2028-03-23 |  | 2028-05-03 |  | 2028-05-27
6565 | ST-2025-036 | United Kingdom | S0016 | UNIT-Research Institute | 7 | 7 | 100 | 1.2 | SCREENING | Dr. Sarah Jones | Dr. Stephanie Johnson | 2021-05-21 | 2021-06-17 | 2021-06-12 | 2021-07-20 | 2021-07-26 | 2021-08-09 | 2021-08-09 | 2021-08-22 | 2021-08-11 | 2021-09-08 | 2021-09-18 | 2021-12-05 | 2021-11-26 | 2022-01-26 | 2022-01-27 | 2027-11-04 |  | 2027-12-29 |  | 2028-04-04 |  | 2028-05-19 |  | 2028-06-10
6566 | ST-2025-036 | United Kingdom | S0017 | UNIT-Health System | 5 | 4 | 80 | 0.3 | ON_HOLD | Dr. Daniel Garcia | Dr. Jennifer Brown | 2021-05-27 | 2021-06-27 | 2021-06-27 | 2021-07-27 | 2021-07-23 | 2021-08-19 | 2021-08-25 | 2021-08-31 | 2021-09-07 | 2021-09-12 | 2021-09-15 | 2021-11-25 | 2021-12-07 | 2022-01-25 | 2022-01-16 | 2027-11-02 |  | 2028-01-02 |  | 2028-03-26 |  | 2028-05-03 |  | 2028-05-27
6567 | ST-2025-036 | United Kingdom | S0018 | UNIT-Medical Center | 8 | 7 | 87.5 | 0.6 | ENROLLING | Dr. Michael White | Dr. Michael Brown | 2021-05-14 | 2021-06-09 | 2021-06-14 | 2021-07-05 | 2021-06-27 | 2021-07-25 | 2021-07-29 | 2021-08-09 | 2021-08-16 | 2021-08-22 | 2021-08-12 | 2021-12-05 | 2021-12-01 | 2022-02-04 | 2022-01-26 | 2027-11-10 |  | 2028-01-07 |  | 2028-03-29 |  | 2028-05-15 |  | 2028-06-04
6568 | ST-2025-036 | Switzerland | S0019 | SWIT-Research Institute | 24 | 24 | 100 | 1.5 | ON_HOLD | Dr. Amanda Brown | Dr. Nicole Martin | 2021-06-03 | 2021-06-28 | 2021-07-07 | 2021-07-23 | 2021-07-17 | 2021-08-17 | 2021-08-10 | 2021-09-02 | 2021-08-27 | 2021-09-14 | 2021-09-15 | 2021-12-03 | 2021-12-16 | 2022-01-29 | 2022-02-10 | 2027-11-01 |  | 2028-01-01 |  | 2028-03-24 |  | 2028-05-06 |  | 2028-05-30
6569 | ST-2025-036 | Switzerland | S0020 | SWIT-General Hospital | 14 | 8 | 57.1 | 0.5 | ENROLLING | Dr. Robert Davis | Dr. Daniel Jones | 2021-05-30 | 2021-06-26 | 2021-06-25 | 2021-07-24 | 2021-07-10 | 2021-08-14 | 2021-08-24 | 2021-08-31 | 2021-08-29 | 2021-09-16 | 2021-09-03 | 2021-12-07 | 2021-12-06 | 2022-02-01 | 2022-01-29 | 2027-11-02 |  | 2027-12-29 |  | 2028-03-28 |  | 2028-05-10 |  | 2028-06-03
6570 | ST-2025-036 | Switzerland | S0021 | SWIT-Cancer Center | 13 | 11 | 84.6 | 1.4 | ENROLLING | Dr. Michael Brown | Dr. Charles Anderson | 2021-05-30 | 2021-06-29 | 2021-06-25 | 2021-07-26 | 2021-07-25 | 2021-08-11 | 2021-08-22 | 2021-08-28 | 2021-08-26 | 2021-09-13 | 2021-09-09 | 2021-12-12 | 2021-12-15 | 2022-02-02 | 2022-02-05 | 2027-11-15 |  | 2028-01-09 |  | 2028-03-30 |  | 2028-05-11 |  | 2028-05-29
6571 | ST-2025-036 | Switzerland | S0022 | SWIT-Health System | 20 | 20 | 100 | 2.9 | ENROLLING | Dr. Lisa Wilson | Dr. Jennifer Anderson | 2021-06-09 | 2021-07-05 | 2021-07-06 | 2021-08-06 | 2021-08-15 | 2021-08-30 | 2021-09-03 | 2021-09-13 | 2021-09-14 | 2021-09-30 | 2021-09-17 | 2021-12-19 | 2021-12-29 | 2022-02-07 | 2022-02-14 | 2027-11-12 |  | 2028-01-05 |  | 2028-04-03 |  | 2028-05-15 |  | 2028-06-07
6572 | ST-2025-036 | Switzerland | S0023 | SWIT-Research Institute | 13 | 9 | 69.2 | 0.5 | SCREENING | Dr. Daniel Thompson | Dr. William Jones | 2021-06-11 | 2021-07-11 | 2021-07-14 | 2021-08-06 | 2021-08-03 | 2021-08-26 | 2021-08-26 | 2021-09-10 | 2021-09-05 | 2021-09-25 | 2021-09-14 | 2021-12-20 | 2021-12-21 | 2022-02-07 | 2022-01-28 | 2027-11-11 |  | 2028-01-01 |  | 2028-04-10 |  | 2028-05-22 |  | 2028-06-11
6573 | ST-2025-036 | Switzerland | S0024 | SWIT-Research Institute | 20 | 12 | 60 | 1 | SCREENING | Dr. Robert Johnson | Dr. Charles Johnson | 2021-05-29 | 2021-06-26 | 2021-06-19 | 2021-07-25 | 2021-07-21 | 2021-08-12 | 2021-08-16 | 2021-08-29 | 2021-09-01 | 2021-09-10 | 2021-09-20 | 2022-01-08 | 2022-01-15 | 2022-03-02 | 2022-02-24 | 2027-12-05 |  | 2028-01-28 |  | 2028-04-24 |  | 2028-06-01 |  | 2028-06-22
6574 | ST-2025-036 | Australia | S0025 | AUST-University Hospital | 33 | 20 | 60.6 | 2.5 | ON_HOLD | Dr. Thomas Smith | Dr. Nicole Martin | 2021-06-13 | 2021-07-10 | 2021-07-24 | 2021-08-02 | 2021-07-25 | 2021-08-20 | 2021-08-11 | 2021-09-06 | 2021-09-02 | 2021-09-23 | 2021-09-23 | 2021-12-07 | 2021-11-30 | 2022-02-07 | 2022-02-07 | 2027-11-16 |  | 2028-01-11 |  | 2028-03-23 |  | 2028-05-06 |  | 2028-05-29
6575 | ST-2025-036 | Australia | S0026 | AUST-Cancer Center | 36 | 0 | 0 | 0 | SCREENING | Dr. Charles Harris | Dr. David Harris | 2021-06-03 | 2021-07-06 | 2021-07-04 | 2021-08-02 | 2021-08-13 | 2021-08-22 | 2021-08-23 | 2021-09-06 | 2021-09-17 | 2021-09-22 | 2021-09-09 | 2021-12-24 | 2022-01-05 | 2022-02-11 | 2022-02-13 | 2027-11-10 |  | 2028-01-01 |  | 2028-04-01 |  | 2028-05-14 |  | 2028-06-04
6576 | ST-2025-036 | Australia | S0027 | AUST-Health System | 12 | 0 | 0 | 0 | CLOSED | Dr. Christopher Brown | Dr. William Thompson | 2021-06-08 | 2021-07-06 | 2021-07-10 | 2021-07-29 | 2021-07-25 | 2021-08-23 | 2021-08-29 | 2021-09-06 | 2021-08-25 | 2021-09-17 | 2021-09-26 | 2021-12-19 | 2021-12-07 | 2022-02-19 | 2022-02-23 | 2027-11-21 |  | 2028-01-16 |  | 2028-03-31 |  | 2028-05-14 |  | 2028-06-03
6577 | ST-2025-037 | Mexico | S0001 | MEXI-General Hospital | 276 | 0 | 0 | 0 | SCREENING | Dr. Michael Williams | Dr. Charles Wilson | 2026-02-13 | 2026-03-09 | 2026-03-01 | 2026-04-09 | 2026-04-19 | 2026-04-27 | 2026-04-15 | 2026-05-14 | 2026-05-24 | 2026-05-29 |  | 2026-08-17 |  | 2026-10-18 |  | 2027-11-18 |  | 2028-01-17 |  | 2028-05-14 |  | 2028-06-29 |  | 2028-07-22
6578 | ST-2025-037 | Mexico | S0002 | MEXI-University Hospital | 318 | 0 | 0 | 0 | ON_HOLD | Dr. Michelle Thomas | Dr. Charles Jones | 2026-02-18 | 2026-03-17 | 2026-03-17 | 2026-04-16 | 2026-04-18 | 2026-05-09 | 2026-05-19 | 2026-05-25 |  | 2026-06-06 |  | 2026-08-19 |  | 2026-10-12 |  | 2027-11-23 |  | 2028-01-15 |  | 2028-05-22 |  | 2028-07-07 |  | 2028-07-27
6579 | ST-2025-037 | Mexico | S0003 | MEXI-Clinical Center | 179 | 0 | 0 | 0 | CLOSED | Dr. Jessica Williams | Dr. Thomas Davis | 2026-02-18 | 2026-03-19 | 2026-03-15 | 2026-04-11 | 2026-04-10 | 2026-05-03 | 2026-04-23 | 2026-05-18 | 2026-05-12 | 2026-05-31 |  | 2026-08-15 |  | 2026-10-12 |  | 2027-12-11 |  | 2028-02-06 |  | 2028-05-18 |  | 2028-06-24 |  | 2028-07-13
6580 | ST-2025-037 | Mexico | S0004 | MEXI-Clinical Center | 133 | 0 | 0 | 0 | SCREENING | Dr. Michelle Jones | Dr. William Smith | 2026-02-14 | 2026-03-19 | 2026-03-11 | 2026-04-16 | 2026-04-26 | 2026-05-10 | 2026-04-30 | 2026-05-24 |  | 2026-06-09 |  | 2026-09-02 |  | 2026-10-24 |  | 2027-12-18 |  | 2028-02-16 |  | 2028-05-31 |  | 2028-07-16 |  | 2028-08-04
6581 | ST-2025-037 | Mexico | S0005 | MEXI-Clinical Center | 235 | 0 | 0 | 0 | CLOSED | Dr. Lisa Davis | Dr. Lisa Harris | 2026-02-07 | 2026-03-03 | 2026-03-16 | 2026-03-26 | 2026-03-22 | 2026-04-19 | 2026-04-12 | 2026-05-04 | 2026-05-11 | 2026-05-21 |  | 2026-08-16 |  | 2026-10-16 |  | 2027-12-01 |  | 2028-01-29 |  | 2028-05-24 |  | 2028-07-01 |  | 2028-07-21
6582 | ST-2025-037 | Mexico | S0006 | MEXI-General Hospital | 307 | 0 | 0 | 0 | SCREENING | Dr. Robert Smith | Dr. Jessica Davis | 2026-02-09 | 2026-03-06 | 2026-03-04 | 2026-04-04 | 2026-03-21 | 2026-04-24 | 2026-04-24 | 2026-05-06 | 2026-05-19 | 2026-05-18 | 2026-05-27 | 2026-09-01 |  | 2026-10-25 |  | 2027-12-03 |  | 2028-01-25 |  | 2028-05-30 |  | 2028-07-07 |  | 2028-07-31
6583 | ST-2025-037 | United States | S0007 | UNIT-University Hospital | 422 | 0 | 0 | 0 | CLOSED | Dr. Charles Jackson | Dr. William Thomas | 2026-02-17 | 2026-03-18 | 2026-03-09 | 2026-04-10 | 2026-04-12 | 2026-05-03 | 2026-05-07 | 2026-05-17 | 2026-05-26 | 2026-05-31 |  | 2026-08-16 |  | 2026-10-07 |  | 2027-11-30 |  | 2028-01-26 |  | 2028-05-26 |  | 2028-07-03 |  | 2028-07-21
6584 | ST-2025-037 | United States | S0008 | UNIT-Cancer Center | 389 | 0 | 0 | 0 | ON_HOLD | Dr. Stephanie Thomas | Dr. Amanda Davis | 2026-02-16 | 2026-03-14 | 2026-03-25 | 2026-04-07 | 2026-04-09 | 2026-04-30 | 2026-04-27 | 2026-05-16 | 2026-05-17 | 2026-05-31 |  | 2026-08-23 |  | 2026-10-22 |  | 2027-11-28 |  | 2028-01-24 |  | 2028-05-25 |  | 2028-07-04 |  | 2028-07-22
6585 | ST-2025-037 | United States | S0009 | UNIT-Research Institute | 282 | 0 | 0 | 0 | ON_HOLD | Dr. Michael Jones | Dr. Thomas Davis | 2026-02-15 | 2026-03-17 | 2026-03-29 | 2026-04-09 | 2026-03-28 | 2026-04-25 | 2026-04-24 | 2026-05-09 | 2026-05-22 | 2026-05-26 |  | 2026-08-26 |  | 2026-10-20 |  | 2027-12-08 |  | 2028-01-29 |  | 2028-05-29 |  | 2028-07-10 |  | 2028-07-30
6586 | ST-2025-037 | United States | S0010 | UNIT-Cancer Center | 269 | 0 | 0 | 0 | CLOSED | Dr. Robert Brown | Dr. Daniel Martin | 2026-02-17 | 2026-03-13 | 2026-03-03 | 2026-04-15 | 2026-04-28 | 2026-05-11 | 2026-05-04 | 2026-05-28 |  | 2026-06-11 |  | 2026-09-12 |  | 2026-11-07 |  | 2027-12-04 |  | 2028-01-28 |  | 2028-06-12 |  | 2028-07-24 |  | 2028-08-11
6587 | ST-2025-037 | Canada | S0011 | CANA-University Hospital | 945 | 0 | 0 | 0 | ON_HOLD | Dr. Michelle Davis | Dr. Christopher Wilson | 2026-02-17 | 2026-03-14 | 2026-03-23 | 2026-04-14 | 2026-04-21 | 2026-05-02 | 2026-04-27 | 2026-05-14 | 2026-05-11 | 2026-05-30 |  | 2026-09-09 |  | 2026-11-09 |  | 2027-12-02 |  | 2028-01-22 |  | 2028-05-25 |  | 2028-07-04 |  | 2028-07-28
6588 | ST-2025-037 | Canada | S0012 | CANA-Health System | 551 | 0 | 0 | 0 | ON_HOLD | Dr. Christopher Martin | Dr. Stephanie Williams | 2026-03-02 | 2026-03-27 | 2026-04-07 | 2026-04-25 | 2026-04-16 | 2026-05-13 | 2026-04-29 | 2026-05-25 |  | 2026-06-09 |  | 2026-09-09 |  | 2026-11-08 |  | 2027-12-19 |  | 2028-02-18 |  | 2028-05-23 |  | 2028-07-04 |  | 2028-07-22
6589 | ST-2025-037 | Denmark | S0013 | DENM-Research Institute | 382 | 0 | 0 | 0 | CLOSED | Dr. Robert Williams | Dr. Amanda Williams | 2026-02-28 | 2026-03-29 | 2026-03-16 | 2026-05-01 | 2026-05-10 | 2026-05-22 |  | 2026-06-08 |  | 2026-06-21 |  | 2026-09-05 |  | 2026-10-29 |  | 2027-11-29 |  | 2028-01-19 |  | 2028-05-11 |  | 2028-06-17 |  | 2028-07-08
6590 | ST-2025-037 | Denmark | S0014 | DENM-General Hospital | 176 | 0 | 0 | 0 | CLOSED | Dr. William Smith | Dr. Nicole White | 2026-03-10 | 2026-04-08 | 2026-04-05 | 2026-05-01 | 2026-05-15 | 2026-05-25 |  | 2026-06-08 |  | 2026-06-25 |  | 2026-09-11 |  | 2026-11-10 |  | 2027-12-13 |  | 2028-02-04 |  | 2028-05-14 |  | 2028-06-21 |  | 2028-07-09
6591 | ST-2025-037 | Denmark | S0015 | DENM-General Hospital | 277 | 0 | 0 | 0 | SCREENING | Dr. Charles Miller | Dr. Christopher Anderson | 2026-03-02 | 2026-03-26 | 2026-04-01 | 2026-04-19 | 2026-04-05 | 2026-05-12 | 2026-05-07 | 2026-05-26 |  | 2026-06-09 |  | 2026-09-15 |  | 2026-11-17 |  | 2027-12-13 |  | 2028-02-09 |  | 2028-05-14 |  | 2028-06-29 |  | 2028-07-23
6592 | ST-2025-037 | Netherlands | S0016 | NETH-Health System | 686 | 0 | 0 | 0 | CLOSED | Dr. Stephanie Jones | Dr. Michelle Taylor | 2026-03-16 | 2026-04-12 | 2026-04-24 | 2026-05-07 | 2026-05-20 | 2026-05-28 |  | 2026-06-13 |  | 2026-06-28 |  | 2026-09-09 |  | 2026-11-06 |  | 2027-12-20 |  | 2028-02-10 |  | 2028-05-18 |  | 2028-07-01 |  | 2028-07-24
6593 | ST-2025-037 | Netherlands | S0017 | NETH-Cancer Center | 775 | 0 | 0 | 0 | CLOSED | Dr. Sarah Thomas | Dr. Emily Williams | 2026-03-04 | 2026-03-30 | 2026-03-19 | 2026-04-30 | 2026-04-23 | 2026-05-18 | 2026-05-11 | 2026-06-04 |  | 2026-06-16 |  | 2026-09-12 |  | 2026-11-10 |  | 2027-12-16 |  | 2028-02-06 |  | 2028-05-22 |  | 2028-07-02 |  | 2028-07-24
6594 | ST-2025-037 | United Kingdom | S0018 | UNIT-Medical Center | 163 | 0 | 0 | 0 | SCREENING | Dr. Emily Jackson | Dr. Charles White | 2026-03-10 | 2026-04-12 | 2026-04-26 | 2026-05-09 | 2026-04-29 | 2026-05-30 |  | 2026-06-15 |  | 2026-06-29 |  | 2026-09-15 |  | 2026-11-12 |  | 2027-12-13 |  | 2028-02-10 |  | 2028-05-24 |  | 2028-07-04 |  | 2028-07-28
6595 | ST-2025-037 | United Kingdom | S0019 | UNIT-Clinical Center | 149 | 0 | 0 | 0 | ON_HOLD | Dr. Robert Taylor | Dr. Jennifer Brown | 2026-03-04 | 2026-04-06 | 2026-03-29 | 2026-05-01 | 2026-04-22 | 2026-05-26 |  | 2026-06-11 |  | 2026-06-28 |  | 2026-09-09 |  | 2026-11-08 |  | 2027-12-23 |  | 2028-02-18 |  | 2028-05-29 |  | 2028-07-05 |  | 2028-07-29
6596 | ST-2025-037 | United Kingdom | S0020 | UNIT-Research Institute | 178 | 0 | 0 | 0 | SCREENING | Dr. Stephanie Wilson | Dr. Nicole Williams | 2026-03-09 | 2026-04-01 | 2026-04-14 | 2026-04-27 | 2026-05-09 | 2026-05-15 | 2026-05-19 | 2026-05-29 |  | 2026-06-11 |  | 2026-09-09 |  | 2026-11-06 |  | 2027-12-16 |  | 2028-02-12 |  | 2028-05-24 |  | 2028-07-03 |  | 2028-07-26
6597 | ST-2025-037 | United Kingdom | S0021 | UNIT-University Hospital | 178 | 0 | 0 | 0 | ON_HOLD | Dr. David Davis | Dr. Amanda Williams | 2026-03-02 | 2026-04-01 | 2026-04-15 | 2026-05-03 | 2026-04-24 | 2026-05-23 |  | 2026-06-07 |  | 2026-06-21 |  | 2026-09-18 |  | 2026-11-17 |  | 2027-12-21 |  | 2028-02-20 |  | 2028-06-04 |  | 2028-07-16 |  | 2028-08-05
6598 | ST-2025-037 | United Kingdom | S0022 | UNIT-Research Institute | 108 | 0 | 0 | 0 | SCREENING | Dr. Daniel Wilson | Dr. James Johnson | 2026-03-11 | 2026-04-10 | 2026-04-07 | 2026-05-11 | 2026-05-10 | 2026-06-03 |  | 2026-06-19 |  | 2026-06-30 |  | 2026-09-28 |  | 2026-11-29 |  | 2027-12-23 |  | 2028-02-20 |  | 2028-06-01 |  | 2028-07-09 |  | 2028-08-02
6599 | ST-2025-037 | United Kingdom | S0023 | UNIT-Health System | 159 | 0 | 0 | 0 | CLOSED | Dr. Amanda Brown | Dr. Jennifer Smith | 2026-03-07 | 2026-04-01 | 2026-04-01 | 2026-04-25 | 2026-04-24 | 2026-05-14 | 2026-05-17 | 2026-05-28 |  | 2026-06-14 |  | 2026-10-02 |  | 2026-11-21 |  | 2028-01-08 |  | 2028-03-03 |  | 2028-06-12 |  | 2028-07-24 |  | 2028-08-13
6600 | ST-2025-037 | Italy | S0024 | ITAL-Health System | 799 | 0 | 0 | 0 | ON_HOLD | Dr. Michael Garcia | Dr. David Martin | 2026-03-02 | 2026-04-02 | 2026-04-11 | 2026-04-27 | 2026-05-06 | 2026-05-19 | 2026-05-16 | 2026-06-05 |  | 2026-06-20 |  | 2026-09-02 |  | 2026-10-23 |  | 2027-12-13 |  | 2028-02-12 |  | 2028-05-14 |  | 2028-06-20 |  | 2028-07-09
6601 | ST-2025-037 | Italy | S0025 | ITAL-University Hospital | 560 | 0 | 0 | 0 | SCREENING | Dr. Amanda Brown | Dr. Robert Thomas | 2026-03-13 | 2026-04-07 | 2026-04-04 | 2026-05-09 | 2026-04-30 | 2026-06-02 |  | 2026-06-17 |  | 2026-06-28 |  | 2026-09-16 |  | 2026-11-12 |  | 2027-12-10 |  | 2028-02-07 |  | 2028-05-19 |  | 2028-07-03 |  | 2028-07-22
6602 | ST-2025-037 | Italy | S0026 | ITAL-Health System | 274 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Thompson | Dr. Robert Harris | 2026-03-03 | 2026-04-05 | 2026-04-18 | 2026-05-08 | 2026-04-30 | 2026-06-02 |  | 2026-06-14 |  | 2026-07-01 |  | 2026-09-18 |  | 2026-11-18 |  | 2027-12-16 |  | 2028-02-07 |  | 2028-05-24 |  | 2028-07-09 |  | 2028-07-30
6603 | ST-2025-037 | Taiwan | S0027 | TAIW-Research Institute | 125 | 0 | 0 | 0 | ON_HOLD | Dr. Jennifer Thompson | Dr. Jennifer Brown | 2026-04-04 | 2026-05-01 | 2026-05-09 | 2026-05-30 |  | 2026-06-23 |  | 2026-07-07 |  | 2026-07-21 |  | 2026-10-13 |  | 2026-12-06 |  | 2028-01-09 |  | 2028-03-04 |  | 2028-05-16 |  | 2028-06-23 |  | 2028-07-13
6604 | ST-2025-037 | Taiwan | S0028 | TAIW-Clinical Center | 125 | 0 | 0 | 0 | CLOSED | Dr. Robert Taylor | Dr. Christopher Moore | 2026-04-02 | 2026-04-28 | 2026-05-09 | 2026-05-30 |  | 2026-06-24 |  | 2026-07-05 |  | 2026-07-16 |  | 2026-10-23 |  | 2026-12-17 |  | 2028-01-14 |  | 2028-03-07 |  | 2028-05-28 |  | 2028-07-06 |  | 2028-07-30
6605 | ST-2025-037 | Taiwan | S0029 | TAIW-Cancer Center | 241 | 0 | 0 | 0 | ON_HOLD | Dr. Emily Moore | Dr. Michael Taylor | 2026-04-01 | 2026-04-30 | 2026-04-20 | 2026-05-25 |  | 2026-06-20 |  | 2026-07-04 |  | 2026-07-18 |  | 2026-10-29 |  | 2026-12-20 |  | 2028-01-24 |  | 2028-03-20 |  | 2028-05-31 |  | 2028-07-10 |  | 2028-07-30
6606 | ST-2025-037 | Taiwan | S0030 | TAIW-University Hospital | 339 | 0 | 0 | 0 | SCREENING | Dr. Lisa Martin | Dr. David Jackson | 2026-03-30 | 2026-05-01 | 2026-05-03 | 2026-06-03 |  | 2026-06-21 |  | 2026-07-03 |  | 2026-07-17 |  | 2026-10-27 |  | 2026-12-25 |  | 2028-01-30 |  | 2028-03-26 |  | 2028-06-04 |  | 2028-07-21 |  | 2028-08-08

## Performance Drivers
id | study_id | driver_type | entity_type | entity_id | entity_name | gap_to_target | percent_above_target | rank
830 | ST-2024-002 | UNDERPERFORMING | COUNTRY | Poland | Poland | -43 | -100 | 1
831 | ST-2024-002 | UNDERPERFORMING | COUNTRY | Netherlands | Netherlands | -41 | -100 | 2
832 | ST-2024-002 | UNDERPERFORMING | COUNTRY | New Zealand | New Zealand | -25 | -100 | 3
833 | ST-2024-003 | UNDERPERFORMING | COUNTRY | France | France | -18 | -100 | 1
834 | ST-2024-003 | UNDERPERFORMING | COUNTRY | Sweden | Sweden | -29 | -100 | 2
835 | ST-2024-003 | UNDERPERFORMING | COUNTRY | New Zealand | New Zealand | -22 | -100 | 3
836 | ST-2024-004 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -13 | -100 | 1
837 | ST-2024-004 | UNDERPERFORMING | COUNTRY | Norway | Norway | -30 | -100 | 2
838 | ST-2024-004 | UNDERPERFORMING | COUNTRY | Belgium | Belgium | -17 | -100 | 3
839 | ST-2024-005 | UNDERPERFORMING | COUNTRY | China | China | -16 | -100 | 1
840 | ST-2024-005 | UNDERPERFORMING | COUNTRY | New Zealand | New Zealand | -7 | -46.7 | 2
841 | ST-2024-005 | UNDERPERFORMING | COUNTRY | Denmark | Denmark | -5 | -25 | 3
842 | ST-2024-006 | UNDERPERFORMING | COUNTRY | South Korea | South Korea | -7 | -50 | 1
843 | ST-2024-006 | UNDERPERFORMING | COUNTRY | Switzerland | Switzerland | -6 | -22.2 | 2
844 | ST-2024-006 | UNDERPERFORMING | COUNTRY | United Kingdom | United Kingdom | -2 | -16.7 | 3
845 | ST-2024-007 | UNDERPERFORMING | COUNTRY | Canada | Canada | -8 | -100 | 1
846 | ST-2024-007 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -9 | -100 | 2
847 | ST-2024-007 | UNDERPERFORMING | COUNTRY | Spain | Spain | -6 | -100 | 3
848 | ST-2024-008 | UNDERPERFORMING | COUNTRY | Sweden | Sweden | -7 | -31.8 | 1
849 | ST-2024-008 | UNDERPERFORMING | COUNTRY | United States | United States | -2 | -10.5 | 2
850 | ST-2024-009 | UNDERPERFORMING | COUNTRY | United States | United States | -75 | -100 | 1
851 | ST-2024-009 | UNDERPERFORMING | COUNTRY | Sweden | Sweden | -35 | -100 | 2
852 | ST-2024-009 | UNDERPERFORMING | COUNTRY | Norway | Norway | -77 | -100 | 3
853 | ST-2024-010 | UNDERPERFORMING | COUNTRY | Australia | Australia | -1136 | -100 | 1
854 | ST-2024-010 | UNDERPERFORMING | COUNTRY | United Kingdom | United Kingdom | -1292 | -49.5 | 2
855 | ST-2024-010 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -92 | -7.3 | 3
856 | ST-2024-011 | UNDERPERFORMING | COUNTRY | France | France | -38 | -100 | 1
857 | ST-2024-011 | UNDERPERFORMING | COUNTRY | Singapore | Singapore | -52 | -100 | 2
858 | ST-2024-011 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -23 | -100 | 3
859 | ST-2024-012 | UNDERPERFORMING | COUNTRY | Singapore | Singapore | -5 | -100 | 1
860 | ST-2024-012 | UNDERPERFORMING | COUNTRY | Chile | Chile | -5 | -100 | 2
861 | ST-2024-012 | UNDERPERFORMING | COUNTRY | Norway | Norway | -3 | -50 | 3
862 | ST-2024-013 | UNDERPERFORMING | COUNTRY | Chile | Chile | -5 | -100 | 1
863 | ST-2024-013 | UNDERPERFORMING | COUNTRY | South Korea | South Korea | -4 | -80 | 2
864 | ST-2024-014 | UNDERPERFORMING | COUNTRY | Netherlands | Netherlands | -5 | -100 | 1
865 | ST-2024-014 | UNDERPERFORMING | COUNTRY | Denmark | Denmark | -5 | -100 | 2
866 | ST-2024-014 | UNDERPERFORMING | COUNTRY | Taiwan | Taiwan | -5 | -100 | 3
867 | ST-2024-015 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -13 | -100 | 1
868 | ST-2024-015 | UNDERPERFORMING | COUNTRY | Sweden | Sweden | -31 | -100 | 2
869 | ST-2024-015 | UNDERPERFORMING | COUNTRY | Norway | Norway | -22 | -100 | 3
870 | ST-2024-016 | UNDERPERFORMING | COUNTRY | Belgium | Belgium | -11 | -100 | 1
871 | ST-2024-016 | UNDERPERFORMING | COUNTRY | Australia | Australia | -17 | -100 | 2
872 | ST-2024-016 | UNDERPERFORMING | COUNTRY | Poland | Poland | -11 | -64.7 | 3
873 | ST-2024-017 | UNDERPERFORMING | COUNTRY | Spain | Spain | -12 | -100 | 1
874 | ST-2024-017 | UNDERPERFORMING | COUNTRY | China | China | -25 | -100 | 2
875 | ST-2024-017 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -15 | -65.2 | 3
876 | ST-2024-019 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -39 | -100 | 1
877 | ST-2024-019 | UNDERPERFORMING | COUNTRY | United States | United States | -69 | -100 | 2
878 | ST-2024-019 | UNDERPERFORMING | COUNTRY | Poland | Poland | -55 | -100 | 3
879 | ST-2024-020 | UNDERPERFORMING | COUNTRY | Canada | Canada | 0 | -100 | 1
880 | ST-2024-020 | UNDERPERFORMING | COUNTRY | Netherlands | Netherlands | -2 | -40 | 2
881 | ST-2024-020 | UNDERPERFORMING | COUNTRY | Japan | Japan | -1 | -20 | 3
882 | ST-2025-021 | UNDERPERFORMING | COUNTRY | Belgium | Belgium | -3 | -9.1 | 1
883 | ST-2025-021 | OVERPERFORMING | COUNTRY | Australia | Australia | 3 | 10.3 | 1
884 | ST-2025-022 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -3 | -33.3 | 1
885 | ST-2025-022 | UNDERPERFORMING | COUNTRY | Poland | Poland | -3 | -30 | 2
886 | ST-2025-022 | UNDERPERFORMING | COUNTRY | China | China | -3 | -27.3 | 3
887 | ST-2025-022 | OVERPERFORMING | COUNTRY | Chile | Chile | 12 | 109.1 | 1
888 | ST-2025-023 | UNDERPERFORMING | COUNTRY | Poland | Poland | -84 | -26.8 | 1
889 | ST-2025-023 | UNDERPERFORMING | COUNTRY | Canada | Canada | -37 | -20 | 2
890 | ST-2025-023 | UNDERPERFORMING | COUNTRY | Italy | Italy | -41 | -19.9 | 3
891 | ST-2025-024 | UNDERPERFORMING | COUNTRY | Switzerland | Switzerland | -33 | -100 | 1
892 | ST-2025-024 | UNDERPERFORMING | COUNTRY | Japan | Japan | -30 | -100 | 2
893 | ST-2025-024 | UNDERPERFORMING | COUNTRY | Sweden | Sweden | -29 | -46.8 | 3
894 | ST-2025-025 | UNDERPERFORMING | COUNTRY | Spain | Spain | -2 | -40 | 1
895 | ST-2025-025 | UNDERPERFORMING | COUNTRY | Sweden | Sweden | -2 | -40 | 2
896 | ST-2025-025 | UNDERPERFORMING | COUNTRY | Netherlands | Netherlands | -2 | -40 | 3
897 | ST-2025-025 | OVERPERFORMING | COUNTRY | Chile | Chile | 2 | 40 | 1
898 | ST-2025-026 | UNDERPERFORMING | COUNTRY | New Zealand | New Zealand | -67 | -100 | 1
899 | ST-2025-026 | UNDERPERFORMING | COUNTRY | Singapore | Singapore | -29 | -63 | 2
900 | ST-2025-026 | UNDERPERFORMING | COUNTRY | Switzerland | Switzerland | -13 | -30.2 | 3
901 | ST-2025-027 | UNDERPERFORMING | COUNTRY | United States | United States | -3 | -33.3 | 1
902 | ST-2025-027 | UNDERPERFORMING | COUNTRY | United Kingdom | United Kingdom | -4 | -33.3 | 2
903 | ST-2025-027 | UNDERPERFORMING | COUNTRY | India | India | -3 | -30 | 3
904 | ST-2025-027 | OVERPERFORMING | COUNTRY | Singapore | Singapore | 10 | 142.9 | 1
905 | ST-2025-028 | UNDERPERFORMING | COUNTRY | Denmark | Denmark | -31608 | -100 | 1
906 | ST-2025-028 | UNDERPERFORMING | COUNTRY | Australia | Australia | -15361 | -100 | 2
907 | ST-2025-028 | UNDERPERFORMING | COUNTRY | Canada | Canada | -15803 | -75.1 | 3
908 | ST-2025-029 | UNDERPERFORMING | COUNTRY | India | India | -42 | -100 | 1
909 | ST-2025-029 | UNDERPERFORMING | COUNTRY | Australia | Australia | -25 | -73.5 | 2
910 | ST-2025-029 | UNDERPERFORMING | COUNTRY | United States | United States | -5 | -25 | 3
911 | ST-2025-030 | UNDERPERFORMING | COUNTRY | Japan | Japan | -172 | -100 | 1
912 | ST-2025-030 | UNDERPERFORMING | COUNTRY | China | China | -103 | -61.7 | 2
913 | ST-2025-030 | UNDERPERFORMING | COUNTRY | Poland | Poland | -54 | -28.4 | 3
914 | ST-2025-031 | UNDERPERFORMING | COUNTRY | Canada | Canada | -10 | -100 | 1
915 | ST-2025-031 | UNDERPERFORMING | COUNTRY | United States | United States | -7 | -100 | 2
916 | ST-2025-031 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -5 | -100 | 3
917 | ST-2025-032 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -82 | -100 | 1
918 | ST-2025-032 | UNDERPERFORMING | COUNTRY | United Kingdom | United Kingdom | -48 | -100 | 2
919 | ST-2025-032 | UNDERPERFORMING | COUNTRY | Norway | Norway | -52 | -100 | 3
920 | ST-2025-033 | UNDERPERFORMING | COUNTRY | Switzerland | Switzerland | -2 | -40 | 1
921 | ST-2025-033 | UNDERPERFORMING | COUNTRY | Poland | Poland | -1 | -20 | 2
922 | ST-2025-034 | UNDERPERFORMING | COUNTRY | France | France | -2 | -33.3 | 1
923 | ST-2025-034 | UNDERPERFORMING | COUNTRY | Canada | Canada | -1 | -12.5 | 2
924 | ST-2025-035 | UNDERPERFORMING | COUNTRY | Australia | Australia | -3 | -60 | 1
925 | ST-2025-035 | UNDERPERFORMING | COUNTRY | Netherlands | Netherlands | -2 | -40 | 2
926 | ST-2025-035 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -1 | -20 | 3
927 | ST-2025-036 | UNDERPERFORMING | COUNTRY | Australia | Australia | -61 | -75.3 | 1
928 | ST-2025-036 | UNDERPERFORMING | COUNTRY | Switzerland | Switzerland | -20 | -19.2 | 2
929 | ST-2025-036 | UNDERPERFORMING | COUNTRY | United Kingdom | United Kingdom | -6 | -14 | 3
930 | ST-2025-037 | UNDERPERFORMING | COUNTRY | Mexico | Mexico | -1448 | -100 | 1
931 | ST-2025-037 | UNDERPERFORMING | COUNTRY | United States | United States | -1362 | -100 | 2
932 | ST-2025-037 | UNDERPERFORMING | COUNTRY | Canada | Canada | -1496 | -100 | 3

## Site Detail
id | site_id | site_name | study_id | enrollment_history | site_status | target_enrollment | actual_enrollment | enrollment_percent | current_rate | principal_investigator | site_coordinator
5855 | S0001 | UNIT-Medical Center | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 5 | 4 | 80 | 0.4 | Dr. Sarah Taylor | Dr. Michael Thompson
5856 | S0002 | UNIT-University Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | CLOSED | 4 | 3 | 75 | 0.3 | Dr. Nicole Miller | Dr. Michelle Jones
5857 | S0003 | UNIT-General Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 3 | 1 | 33.3 | 0.1 | Dr. Nicole Davis | Dr. Nicole White
5858 | S0004 | UNIT-University Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | SCREENING | 3 | 3 | 100 | 0.4 | Dr. Stephanie Thomas | Dr. Stephanie White
5859 | S0005 | UNIT-Clinical Center | ST-2024-002 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Emily Johnson | Dr. Charles Taylor
5860 | S0006 | MEXI-University Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 2, 'cumulative': 5}, {'month': 3, 'enrolled': 2, 'cumulative': 7}, {'month': 4, 'enrolled': 1, 'cumulative': 8}, {'month': 5, 'enrolled': 3, 'cumulative': 11}, {'month': 6, 'enrolled': 5, 'cumulative': 16}] | SCREENING | 23 | 21 | 91.3 | 2.1 | Dr. Lisa Williams | Dr. Christopher Moore
5861 | S0007 | MEXI-Medical Center | ST-2024-002 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 3, 'cumulative': 5}, {'month': 3, 'enrolled': 0, 'cumulative': 5}, {'month': 4, 'enrolled': 0, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 10 | 6 | 60 | 1 | Dr. Michelle Smith | Dr. Michael Davis
5862 | S0008 | MEXI-University Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 0, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 3, 'cumulative': 9}, {'month': 6, 'enrolled': 1, 'cumulative': 10}] | SCREENING | 11 | 14 | 127.3 | 1.2 | Dr. Nicole Miller | Dr. Charles Johnson
5863 | S0009 | POLA-Research Institute | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | CLOSED | 15 | 0 | 0 | 0 | Dr. Michelle Martin | Dr. Robert Miller
5864 | S0010 | POLA-Research Institute | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 10 | 0 | 0 | 0 | Dr. Michelle Johnson | Dr. Thomas Johnson
5865 | S0011 | POLA-Medical Center | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 18 | 0 | 0 | 0 | Dr. Daniel Thompson | Dr. Jennifer Johnson
5866 | S0012 | NETH-University Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | SCREENING | 23 | 0 | 0 | 0 | Dr. Lisa Johnson | Dr. Michael White
5867 | S0013 | NETH-General Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 2, 'cumulative': 2}] | CLOSED | 8 | 0 | 0 | 0 | Dr. Daniel Taylor | Dr. William Miller
5868 | S0014 | NETH-General Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 10 | 0 | 0 | 0 | Dr. Lisa Wilson | Dr. Charles Jones
5869 | S0015 | NEW-University Hospital | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | ON_HOLD | 8 | 0 | 0 | 0 | Dr. Robert Thomas | Dr. Michael Davis
5870 | S0016 | NEW-Research Institute | ST-2024-002 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 4 | 0 | 0 | 0 | Dr. Christopher Moore | Dr. Jessica Thompson
5871 | S0017 | NEW-Medical Center | ST-2024-002 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 4 | 0 | 0 | 0 | Dr. Jessica Brown | Dr. Robert Wilson
5872 | S0018 | NEW-Medical Center | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 6 | 0 | 0 | 0 | Dr. Michelle Jones | Dr. William Anderson
5873 | S0019 | NEW-Health System | ST-2024-002 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Thomas Miller | Dr. William Thompson
5874 | S0001 | CANA-Cancer Center | ST-2024-003 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 0, 'cumulative': 3}, {'month': 3, 'enrolled': 4, 'cumulative': 7}, {'month': 4, 'enrolled': 0, 'cumulative': 7}, {'month': 5, 'enrolled': 1, 'cumulative': 8}, {'month': 6, 'enrolled': 1, 'cumulative': 9}] | ON_HOLD | 20 | 16 | 80 | 1.3 | Dr. Michelle Davis | Dr. Nicole Davis
5875 | S0002 | CANA-Research Institute | ST-2024-003 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 1, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 3, 'cumulative': 7}] | SCREENING | 11 | 11 | 100 | 0.9 | Dr. James Jackson | Dr. Thomas Jackson
5876 | S0003 | MEXI-Clinical Center | ST-2024-003 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 3, 'cumulative': 5}, {'month': 3, 'enrolled': 3, 'cumulative': 8}, {'month': 4, 'enrolled': 3, 'cumulative': 11}, {'month': 5, 'enrolled': 0, 'cumulative': 11}, {'month': 6, 'enrolled': 3, 'cumulative': 14}] | ON_HOLD | 8 | 8 | 100 | 1 | Dr. Jennifer Johnson | Dr. William Jackson
5877 | S0004 | MEXI-Research Institute | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | ON_HOLD | 6 | 5 | 83.3 | 0.6 | Dr. Thomas Taylor | Dr. Charles Wilson
5878 | S0005 | MEXI-Cancer Center | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ON_HOLD | 6 | 3 | 50 | 0.2 | Dr. Michael Martin | Dr. James Moore
5879 | S0006 | MEXI-Medical Center | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 7 | 0 | 0 | 0 | Dr. Michael Johnson | Dr. James Davis
5880 | S0007 | MEXI-University Hospital | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | CLOSED | 4 | 0 | 0 | 0 | Dr. Robert Davis | Dr. Robert Martin
5881 | S0008 | FRAN-General Hospital | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 10 | 0 | 0 | 0 | Dr. Jennifer Brown | Dr. Jennifer Anderson
5882 | S0009 | FRAN-Medical Center | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 8 | 0 | 0 | 0 | Dr. Jessica Jackson | Dr. Charles Miller
5883 | S0010 | SWED-Clinical Center | ST-2024-003 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 4 | 0 | 0 | 0 | Dr. Michael Thompson | Dr. Thomas Smith
5884 | S0011 | SWED-Cancer Center | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | 5 | 0 | 0 | 0 | Dr. Emily White | Dr. Amanda Harris
5885 | S0012 | SWED-General Hospital | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 5 | 0 | 0 | 0 | Dr. Jennifer Thompson | Dr. William Moore
5886 | S0013 | SWED-Cancer Center | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Stephanie Wilson | Dr. Thomas Davis
5887 | S0014 | SWED-Cancer Center | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ON_HOLD | 6 | 0 | 0 | 0 | Dr. Christopher Davis | Dr. Christopher Jackson
5888 | S0015 | SWED-Research Institute | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 6 | 0 | 0 | 0 | Dr. Thomas Garcia | Dr. Nicole Miller
5889 | S0016 | NEW-Health System | ST-2024-003 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | CLOSED | 9 | 0 | 0 | 0 | Dr. David Williams | Dr. Lisa White
5890 | S0017 | NEW-Clinical Center | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 6 | 0 | 0 | 0 | Dr. Nicole Martin | Dr. Christopher Smith
5891 | S0018 | NEW-Medical Center | ST-2024-003 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 7 | 0 | 0 | 0 | Dr. Charles Davis | Dr. Jessica Thomas
5892 | S0019 | SOUT-Health System | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 2 | 0 | 0 | 0 | Dr. Jennifer Miller | Dr. David Martin
5893 | S0020 | SOUT-Research Institute | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Daniel Anderson | Dr. Emily Miller
5894 | S0021 | SOUT-Research Institute | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Jennifer Anderson | Dr. James Moore
5895 | S0022 | SOUT-University Hospital | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Sarah Moore | Dr. Jessica Jones
5896 | S0023 | SOUT-General Hospital | ST-2024-003 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Emily Smith | Dr. Jessica Martin
5897 | S0024 | SOUT-Clinical Center | ST-2024-003 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Jennifer Johnson | Dr. William Martin
5898 | S0001 | CANA-Cancer Center | ST-2024-004 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 6 | 4 | 66.7 | 0.5 | Dr. Jennifer Williams | Dr. Charles Davis
5899 | S0002 | CANA-Clinical Center | ST-2024-004 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 3, 'cumulative': 6}, {'month': 3, 'enrolled': 0, 'cumulative': 6}, {'month': 4, 'enrolled': 2, 'cumulative': 8}, {'month': 5, 'enrolled': 3, 'cumulative': 11}, {'month': 6, 'enrolled': 0, 'cumulative': 11}] | SCREENING | 12 | 11 | 91.7 | 0.7 | Dr. Lisa Harris | Dr. William Harris
5900 | S0003 | CANA-Research Institute | ST-2024-004 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 0, 'cumulative': 3}, {'month': 3, 'enrolled': 3, 'cumulative': 6}, {'month': 4, 'enrolled': 1, 'cumulative': 7}, {'month': 5, 'enrolled': 2, 'cumulative': 9}, {'month': 6, 'enrolled': 0, 'cumulative': 9}] | SCREENING | 7 | 6 | 85.7 | 0.4 | Dr. Christopher Anderson | Dr. Michelle Garcia
5901 | S0004 | CANA-Medical Center | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 8 | 2 | 25 | 0.2 | Dr. Jessica White | Dr. William Harris
5902 | S0005 | MEXI-General Hospital | ST-2024-004 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 4 | 0 | 0 | 0 | Dr. Charles Wilson | Dr. James Johnson
5903 | S0006 | MEXI-Health System | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Jessica Davis | Dr. Amanda Davis
5904 | S0007 | MEXI-General Hospital | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | CLOSED | 3 | 0 | 0 | 0 | Dr. William Jones | Dr. Emily Johnson
5905 | S0008 | MEXI-Research Institute | ST-2024-004 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 1, 'cumulative': 5}, {'month': 4, 'enrolled': 0, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 2, 'cumulative': 7}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Sarah Thomas | Dr. Robert Williams
5906 | S0009 | NORW-Health System | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 12 | 0 | 0 | 0 | Dr. William Martin | Dr. Jessica Taylor
5907 | S0010 | NORW-Cancer Center | ST-2024-004 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 6 | 0 | 0 | 0 | Dr. Michael Jones | Dr. Lisa Jackson
5908 | S0011 | NORW-Cancer Center | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 7 | 0 | 0 | 0 | Dr. Amanda Williams | Dr. Charles Smith
5909 | S0012 | NORW-Research Institute | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 5 | 0 | 0 | 0 | Dr. Christopher Thomas | Dr. William Jackson
5910 | S0013 | BELG-University Hospital | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | SCREENING | 9 | 0 | 0 | 0 | Dr. Michelle Taylor | Dr. Lisa Williams
5911 | S0014 | BELG-General Hospital | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 8 | 0 | 0 | 0 | Dr. Jessica White | Dr. Emily Jones
5912 | S0015 | DENM-Research Institute | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 1 | 0 | 0 | 0 | Dr. Michelle White | Dr. Robert White
5913 | S0016 | DENM-General Hospital | ST-2024-004 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Stephanie Wilson | Dr. Sarah Thomas
5914 | S0017 | DENM-University Hospital | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 5 | 0 | 0 | 0 | Dr. Lisa Thomas | Dr. Emily Thomas
5915 | S0018 | DENM-Health System | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 2, 'cumulative': 7}, {'month': 6, 'enrolled': 2, 'cumulative': 9}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Sarah Jackson | Dr. William Miller
5916 | S0019 | SOUT-Medical Center | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 15 | 0 | 0 | 0 | Dr. James Johnson | Dr. Thomas Davis
5917 | S0020 | SOUT-University Hospital | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | 13 | 0 | 0 | 0 | Dr. David Williams | Dr. Michelle Miller
5918 | S0021 | CHIN-Health System | ST-2024-004 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 4 | 0 | 0 | 0 | Dr. Robert Jones | Dr. Michelle Wilson
5919 | S0022 | CHIN-Cancer Center | ST-2024-004 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 5 | 0 | 0 | 0 | Dr. James Jones | Dr. James Thomas
5920 | S0023 | CHIN-Cancer Center | ST-2024-004 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Thomas Smith | Dr. Jennifer Wilson
5921 | S0001 | MEXI-Research Institute | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ENROLLING | 5 | 3 | 60 | 0.2 | Dr. Daniel Garcia | Dr. Sarah Davis
5922 | S0002 | MEXI-General Hospital | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | SCREENING | 4 | 2 | 50 | 0.2 | Dr. Daniel Thompson | Dr. Jennifer Thomas
5923 | S0003 | MEXI-Research Institute | ST-2024-005 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | SCREENING | 4 | 2 | 50 | 0.2 | Dr. Stephanie Taylor | Dr. Sarah Taylor
5924 | S0004 | MEXI-Medical Center | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | 3 | 3 | 100 | 0.3 | Dr. Michelle Jackson | Dr. Jessica Wilson
5925 | S0005 | MEXI-General Hospital | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 3, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 3 | 8 | 266.7 | 0.5 | Dr. Robert Taylor | Dr. Michael Jones
5926 | S0006 | UNIT-General Hospital | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 2 | 1 | 50 | 0.1 | Dr. Daniel Williams | Dr. Stephanie Thompson
5927 | S0007 | UNIT-Research Institute | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ENROLLING | 3 | 2 | 66.7 | 0.3 | Dr. Jessica Garcia | Dr. David Taylor
5928 | S0008 | UNIT-Cancer Center | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Lisa Jones | Dr. Robert Williams
5929 | S0009 | UNIT-Research Institute | ST-2024-005 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 2, 'cumulative': 5}, {'month': 4, 'enrolled': 1, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Daniel Moore | Dr. Daniel Johnson
5930 | S0010 | UNIT-General Hospital | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Robert Jackson | Dr. Robert Garcia
5931 | S0011 | UNIT-University Hospital | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 2, 'cumulative': 7}, {'month': 6, 'enrolled': 2, 'cumulative': 9}] | SCREENING | 3 | 8 | 266.7 | 0.5 | Dr. Jennifer Harris | Dr. Sarah White
5932 | S0012 | FRAN-Health System | ST-2024-005 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 3, 'cumulative': 9}] | ON_HOLD | 6 | 6 | 100 | 0.6 | Dr. Christopher Davis | Dr. Michelle Davis
5933 | S0013 | FRAN-Research Institute | ST-2024-005 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 3, 'cumulative': 8}] | SCREENING | 7 | 6 | 85.7 | 0.3 | Dr. David Thomas | Dr. Christopher Harris
5934 | S0014 | DENM-Clinical Center | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 3, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 10 | 9 | 90 | 1.1 | Dr. Robert Wilson | Dr. Sarah Martin
5935 | S0015 | DENM-Cancer Center | ST-2024-005 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 3, 'cumulative': 8}, {'month': 6, 'enrolled': 2, 'cumulative': 10}] | CLOSED | 10 | 6 | 60 | 0.5 | Dr. Emily Thompson | Dr. Emily Anderson
5936 | S0016 | NEW-Health System | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | ON_HOLD | 8 | 6 | 75 | 0.8 | Dr. Michael Davis | Dr. Christopher Thomas
5937 | S0017 | NEW-Medical Center | ST-2024-005 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 7 | 2 | 28.6 | 0.2 | Dr. Charles Thompson | Dr. Amanda Davis
5938 | S0018 | CHIN-Cancer Center | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 4 | 0 | 0 | 0 | Dr. Robert Martin | Dr. Christopher Smith
5939 | S0019 | CHIN-Medical Center | ST-2024-005 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. David Jones | Dr. Michelle Thompson
5940 | S0020 | CHIN-Clinical Center | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Lisa Anderson | Dr. Emily Johnson
5941 | S0021 | CHIN-University Hospital | ST-2024-005 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Christopher Williams | Dr. Emily Martin
5942 | S0022 | CHIN-Health System | ST-2024-005 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Daniel Davis | Dr. Robert Anderson
5943 | S0001 | UNIT-General Hospital | ST-2024-006 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 2, 'cumulative': 5}, {'month': 3, 'enrolled': 3, 'cumulative': 8}, {'month': 4, 'enrolled': 1, 'cumulative': 9}, {'month': 5, 'enrolled': 3, 'cumulative': 12}, {'month': 6, 'enrolled': 3, 'cumulative': 15}] | SCREENING | 13 | 8 | 61.5 | 0.4 | Dr. William Miller | Dr. Stephanie Smith
5944 | S0002 | UNIT-Clinical Center | ST-2024-006 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 4 | 9 | 225 | 0.6 | Dr. Jessica Anderson | Dr. Nicole Davis
5945 | S0003 | UNIT-University Hospital | ST-2024-006 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. Robert Taylor | Dr. Thomas Thomas
5946 | S0004 | UNIT-Clinical Center | ST-2024-006 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Daniel Moore | Dr. Emily Taylor
5947 | S0005 | UNIT-University Hospital | ST-2024-006 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. William Harris | Dr. Lisa Jones
5948 | S0006 | UNIT-Medical Center | ST-2024-006 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 3 | 5 | 166.7 | 0.8 | Dr. Charles White | Dr. Lisa Garcia
5949 | S0007 | SWIT-University Hospital | ST-2024-006 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 4, 'cumulative': 7}, {'month': 3, 'enrolled': 2, 'cumulative': 9}, {'month': 4, 'enrolled': 4, 'cumulative': 13}, {'month': 5, 'enrolled': 2, 'cumulative': 15}, {'month': 6, 'enrolled': 4, 'cumulative': 19}] | SCREENING | 13 | 13 | 100 | 0.7 | Dr. Nicole Thompson | Dr. Christopher Martin
5950 | S0008 | SWIT-Research Institute | ST-2024-006 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 3, 'cumulative': 6}, {'month': 3, 'enrolled': 2, 'cumulative': 8}, {'month': 4, 'enrolled': 3, 'cumulative': 11}, {'month': 5, 'enrolled': 1, 'cumulative': 12}, {'month': 6, 'enrolled': 2, 'cumulative': 14}] | SCREENING | 14 | 8 | 57.1 | 0.6 | Dr. Michael Jackson | Dr. Daniel Harris
5951 | S0009 | SOUT-Cancer Center | ST-2024-006 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | CLOSED | 8 | 5 | 62.5 | 0.3 | Dr. Nicole Anderson | Dr. Michelle Smith
5952 | S0010 | SOUT-Cancer Center | ST-2024-006 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.3 | Dr. Robert Wilson | Dr. Amanda Jackson
5953 | S0011 | SOUT-Research Institute | ST-2024-006 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Sarah Moore | Dr. David Thomas
5954 | S0001 | CANA-General Hospital | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | SCREENING | -1 | -1 | 100 | -0.1 | Dr. James Moore | Dr. Jennifer White
5955 | S0002 | CANA-General Hospital | ST-2024-007 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. David Anderson | Dr. Thomas Anderson
5956 | S0003 | CANA-General Hospital | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Lisa Moore | Dr. Sarah Garcia
5957 | S0004 | CANA-Clinical Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 2, 'cumulative': 2}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Charles Martin | Dr. Jennifer Anderson
5958 | S0005 | MEXI-Medical Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 6 | 0 | 0 | 0 | Dr. Christopher Moore | Dr. Daniel Martin
5959 | S0006 | MEXI-University Hospital | ST-2024-007 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. William Miller | Dr. Emily Taylor
5960 | S0007 | SPAI-Cancer Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | -6 | -6 | 100 | -0.4 | Dr. Stephanie Thompson | Dr. Thomas Williams
5961 | S0008 | SPAI-Clinical Center | ST-2024-007 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Jennifer Jones | Dr. Nicole Taylor
5962 | S0009 | SPAI-University Hospital | ST-2024-007 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 3 | 100 | 0.5 | Dr. Charles Davis | Dr. Christopher Wilson
5963 | S0010 | SPAI-Research Institute | ST-2024-007 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 2, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | CLOSED | 3 | 1 | 33.3 | 0.1 | Dr. James Wilson | Dr. Amanda Davis
5964 | S0011 | SPAI-Medical Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Christopher Anderson | Dr. Jennifer Jackson
5965 | S0012 | ITAL-General Hospital | ST-2024-007 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 0 | 0 | 0 | 0 | Dr. Lisa Davis | Dr. Robert Martin
5966 | S0013 | ITAL-University Hospital | ST-2024-007 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Amanda White | Dr. Michelle Martin
5967 | S0014 | ITAL-Cancer Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | CLOSED | 3 | 0 | 0 | 0 | Dr. David Davis | Dr. Michael Thompson
5968 | S0015 | INDI-Medical Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -4 | -4 | 100 | -0.2 | Dr. Nicole Williams | Dr. Daniel Harris
5969 | S0016 | INDI-Cancer Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 2 | 66.7 | 0.3 | Dr. Robert Thompson | Dr. Stephanie Harris
5970 | S0017 | INDI-Health System | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 3 | 2 | 66.7 | 0.3 | Dr. Christopher Anderson | Dr. James Jackson
5971 | S0018 | INDI-Research Institute | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | CLOSED | 3 | 0 | 0 | 0 | Dr. David Williams | Dr. Sarah White
5972 | S0019 | INDI-Research Institute | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Michelle Johnson | Dr. Michael Martin
5973 | S0020 | INDI-Medical Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Jennifer Jones | Dr. Stephanie Thomas
5974 | S0021 | SING-Clinical Center | ST-2024-007 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 7 | 0 | 0 | 0 | Dr. Michelle Jones | Dr. Amanda Brown
5975 | S0022 | SING-University Hospital | ST-2024-007 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Daniel Jones | Dr. Lisa Smith
5976 | S0001 | UNIT-General Hospital | ST-2024-008 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 2, 'cumulative': 5}, {'month': 4, 'enrolled': 1, 'cumulative': 6}, {'month': 5, 'enrolled': 2, 'cumulative': 8}, {'month': 6, 'enrolled': 0, 'cumulative': 8}] | ENROLLING | 8 | 7 | 87.5 | 0.6 | Dr. Jessica Garcia | Dr. Lisa Jackson
5977 | S0002 | UNIT-General Hospital | ST-2024-008 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | SCREENING | 4 | 4 | 100 | 0.3 | Dr. Charles Jones | Dr. Michael Thompson
5978 | S0003 | UNIT-General Hospital | ST-2024-008 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | 7 | 6 | 85.7 | 0.5 | Dr. Emily White | Dr. Lisa Williams
5979 | S0004 | SWED-Clinical Center | ST-2024-008 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 3, 'cumulative': 6}, {'month': 4, 'enrolled': 2, 'cumulative': 8}, {'month': 5, 'enrolled': 1, 'cumulative': 9}, {'month': 6, 'enrolled': 2, 'cumulative': 11}] | ON_HOLD | 9 | 9 | 100 | 0.5 | Dr. James Wilson | Dr. Christopher Martin
5980 | S0005 | SWED-University Hospital | ST-2024-008 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 3, 'cumulative': 6}, {'month': 4, 'enrolled': 0, 'cumulative': 6}, {'month': 5, 'enrolled': 1, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | CLOSED | 13 | 6 | 46.2 | 0.5 | Dr. Charles White | Dr. Jennifer Jackson
5981 | S0006 | TAIW-Medical Center | ST-2024-008 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ENROLLING | -6 | -6 | 100 | -0.6 | Dr. Amanda Wilson | Dr. Emily Jones
5982 | S0007 | TAIW-Medical Center | ST-2024-008 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Christopher Moore | Dr. Michelle Thompson
5983 | S0008 | TAIW-Clinical Center | ST-2024-008 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ENROLLING | 3 | 3 | 100 | 0.4 | Dr. Michael Thomas | Dr. Michelle Williams
5984 | S0009 | TAIW-Health System | ST-2024-008 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Charles Smith | Dr. Jessica White
5985 | S0010 | TAIW-Clinical Center | ST-2024-008 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ENROLLING | 3 | 1 | 33.3 | 0.1 | Dr. Michelle Davis | Dr. Daniel Garcia
5986 | S0011 | TAIW-General Hospital | ST-2024-008 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 7 | 233.3 | 0.6 | Dr. Robert Wilson | Dr. Jessica Wilson
5987 | S0001 | CANA-Health System | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 3, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | CLOSED | 13 | 12 | 92.3 | 1.7 | Dr. Jennifer Thomas | Dr. Thomas Miller
5988 | S0002 | CANA-Clinical Center | ST-2024-009 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 17 | 0 | 0 | 0 | Dr. Nicole Thompson | Dr. Thomas Jackson
5989 | S0003 | CANA-Health System | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 18 | 0 | 0 | 0 | Dr. Emily Thomas | Dr. Amanda Harris
5990 | S0004 | UNIT-Health System | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 16 | 0 | 0 | 0 | Dr. Robert Jackson | Dr. Stephanie Garcia
5991 | S0005 | UNIT-Clinical Center | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 16 | 0 | 0 | 0 | Dr. Jennifer Moore | Dr. Jennifer Martin
5992 | S0006 | UNIT-Research Institute | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | SCREENING | 14 | 0 | 0 | 0 | Dr. Thomas Harris | Dr. Sarah Thomas
5993 | S0007 | UNIT-Medical Center | ST-2024-009 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 9 | 0 | 0 | 0 | Dr. David Jackson | Dr. Michelle Thompson
5994 | S0008 | UNIT-General Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 13 | 0 | 0 | 0 | Dr. Nicole White | Dr. Christopher Martin
5995 | S0009 | UNIT-University Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 7 | 0 | 0 | 0 | Dr. James Davis | Dr. Jessica Johnson
5996 | S0010 | SWED-Cancer Center | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 8 | 0 | 0 | 0 | Dr. Michelle Johnson | Dr. Christopher Moore
5997 | S0011 | SWED-University Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 7 | 0 | 0 | 0 | Dr. Lisa Anderson | Dr. Sarah Harris
5998 | S0012 | SWED-Research Institute | ST-2024-009 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 2, 'cumulative': 6}, {'month': 4, 'enrolled': 0, 'cumulative': 6}, {'month': 5, 'enrolled': 1, 'cumulative': 7}, {'month': 6, 'enrolled': 0, 'cumulative': 7}] | SCREENING | 4 | 0 | 0 | 0 | Dr. Christopher Brown | Dr. Lisa Miller
5999 | S0013 | SWED-Cancer Center | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 7 | 0 | 0 | 0 | Dr. Amanda White | Dr. Jennifer Jones
6000 | S0014 | SWED-Cancer Center | ST-2024-009 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 9 | 0 | 0 | 0 | Dr. Sarah Thomas | Dr. Michelle Wilson
6001 | S0015 | NORW-University Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 18 | 0 | 0 | 0 | Dr. Sarah Wilson | Dr. Robert Jones
6002 | S0016 | NORW-University Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | CLOSED | 10 | 0 | 0 | 0 | Dr. Thomas Davis | Dr. Charles Martin
6003 | S0017 | NORW-University Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | 22 | 0 | 0 | 0 | Dr. William White | Dr. Charles Harris
6004 | S0018 | NORW-Medical Center | ST-2024-009 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | SCREENING | 11 | 0 | 0 | 0 | Dr. Charles Thompson | Dr. William Thomas
6005 | S0019 | NORW-Clinical Center | ST-2024-009 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 2, 'cumulative': 7}, {'month': 6, 'enrolled': 0, 'cumulative': 7}] | ON_HOLD | 16 | 0 | 0 | 0 | Dr. James Williams | Dr. Christopher Thomas
6006 | S0020 | SING-University Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 15 | 0 | 0 | 0 | Dr. Thomas Johnson | Dr. Sarah Brown
6007 | S0021 | SING-General Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 13 | 0 | 0 | 0 | Dr. James Brown | Dr. Jennifer Harris
6008 | S0022 | SING-Clinical Center | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 9 | 0 | 0 | 0 | Dr. David Jones | Dr. Jessica Garcia
6009 | S0023 | SING-Cancer Center | ST-2024-009 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | SCREENING | 15 | 0 | 0 | 0 | Dr. Amanda Wilson | Dr. Michael Thomas
6010 | S0024 | SING-General Hospital | ST-2024-009 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 13 | 0 | 0 | 0 | Dr. Sarah Jackson | Dr. Jessica Davis
6011 | S0001 | MEXI-University Hospital | ST-2024-010 | [{'month': 1, 'enrolled': 45, 'cumulative': 45}, {'month': 2, 'enrolled': 43, 'cumulative': 88}, {'month': 3, 'enrolled': 46, 'cumulative': 134}, {'month': 4, 'enrolled': 43, 'cumulative': 177}, {'month': 5, 'enrolled': 46, 'cumulative': 223}, {'month': 6, 'enrolled': 42, 'cumulative': 265}] | SCREENING | 283 | 269 | 95.1 | 20.7 | Dr. Thomas White | Dr. Emily Moore
6012 | S0002 | MEXI-Research Institute | ST-2024-010 | [{'month': 1, 'enrolled': 40, 'cumulative': 40}, {'month': 2, 'enrolled': 39, 'cumulative': 79}, {'month': 3, 'enrolled': 40, 'cumulative': 119}, {'month': 4, 'enrolled': 41, 'cumulative': 160}, {'month': 5, 'enrolled': 40, 'cumulative': 200}, {'month': 6, 'enrolled': 39, 'cumulative': 239}] | ENROLLING | 344 | 238 | 69.2 | 13.2 | Dr. Christopher Anderson | Dr. Christopher Wilson
6013 | S0003 | MEXI-Cancer Center | ST-2024-010 | [{'month': 1, 'enrolled': 111, 'cumulative': 111}, {'month': 2, 'enrolled': 111, 'cumulative': 222}, {'month': 3, 'enrolled': 109, 'cumulative': 331}, {'month': 4, 'enrolled': 110, 'cumulative': 441}, {'month': 5, 'enrolled': 109, 'cumulative': 550}, {'month': 6, 'enrolled': 108, 'cumulative': 658}] | ENROLLING | 627 | 655 | 104.5 | 93.6 | Dr. Jennifer Anderson | Dr. Sarah Miller
6014 | S0004 | UNIT-Research Institute | ST-2024-010 | [{'month': 1, 'enrolled': 133, 'cumulative': 133}, {'month': 2, 'enrolled': 135, 'cumulative': 268}, {'month': 3, 'enrolled': 137, 'cumulative': 405}, {'month': 4, 'enrolled': 134, 'cumulative': 539}, {'month': 5, 'enrolled': 133, 'cumulative': 672}, {'month': 6, 'enrolled': 135, 'cumulative': 807}] | SCREENING | 997 | 811 | 81.3 | 101.4 | Dr. Charles Harris | Dr. Michelle Moore
6015 | S0005 | UNIT-University Hospital | ST-2024-010 | [{'month': 1, 'enrolled': 82, 'cumulative': 82}, {'month': 2, 'enrolled': 85, 'cumulative': 167}, {'month': 3, 'enrolled': 86, 'cumulative': 253}, {'month': 4, 'enrolled': 84, 'cumulative': 337}, {'month': 5, 'enrolled': 86, 'cumulative': 423}, {'month': 6, 'enrolled': 83, 'cumulative': 506}] | ON_HOLD | 616 | 507 | 82.3 | 72.4 | Dr. Emily Jones | Dr. Emily Smith
6016 | S0006 | UNIT-Medical Center | ST-2024-010 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 2, 'cumulative': 2}] | SCREENING | 440 | 0 | 0 | 0 | Dr. Robert Miller | Dr. Charles Thomas
6017 | S0007 | UNIT-General Hospital | ST-2024-010 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 557 | 0 | 0 | 0 | Dr. Michael Wilson | Dr. Michael Smith
6018 | S0008 | AUST-Medical Center | ST-2024-010 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 368 | 0 | 0 | 0 | Dr. Sarah Garcia | Dr. Stephanie Jackson
6019 | S0009 | AUST-Clinical Center | ST-2024-010 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | ON_HOLD | 170 | 0 | 0 | 0 | Dr. Stephanie Garcia | Dr. Amanda Miller
6020 | S0010 | AUST-University Hospital | ST-2024-010 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 279 | 0 | 0 | 0 | Dr. Christopher Jones | Dr. Sarah Davis
6021 | S0011 | AUST-General Hospital | ST-2024-010 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 319 | 0 | 0 | 0 | Dr. Stephanie Moore | Dr. Nicole Johnson
6022 | S0001 | UNIT-Clinical Center | ST-2024-011 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 7 | 4 | 57.1 | 0.4 | Dr. Charles Brown | Dr. Nicole Davis
6023 | S0002 | UNIT-University Hospital | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | SCREENING | 10 | 1 | 10 | 0.1 | Dr. Sarah Anderson | Dr. James Taylor
6024 | S0003 | UNIT-Research Institute | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | SCREENING | 10 | 0 | 0 | 0 | Dr. Thomas Garcia | Dr. Charles Garcia
6025 | S0004 | FRAN-University Hospital | ST-2024-011 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 1, 'cumulative': 5}, {'month': 4, 'enrolled': 0, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ON_HOLD | 11 | 0 | 0 | 0 | Dr. Jennifer Johnson | Dr. Emily Taylor
6026 | S0005 | FRAN-University Hospital | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ON_HOLD | 7 | 0 | 0 | 0 | Dr. Michelle Moore | Dr. William Anderson
6027 | S0006 | FRAN-Research Institute | ST-2024-011 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | SCREENING | 9 | 0 | 0 | 0 | Dr. Sarah Jackson | Dr. Michelle Martin
6028 | S0007 | FRAN-University Hospital | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | ON_HOLD | 4 | 0 | 0 | 0 | Dr. James White | Dr. Michael Anderson
6029 | S0008 | FRAN-Cancer Center | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | CLOSED | 7 | 0 | 0 | 0 | Dr. Nicole Miller | Dr. Emily Smith
6030 | S0009 | SING-Cancer Center | ST-2024-011 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 12 | 0 | 0 | 0 | Dr. Nicole Wilson | Dr. Michael Moore
6031 | S0010 | SING-Clinical Center | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 17 | 0 | 0 | 0 | Dr. Charles Thomas | Dr. Jennifer Harris
6032 | S0011 | SING-Medical Center | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 23 | 0 | 0 | 0 | Dr. Christopher Wilson | Dr. Lisa Wilson
6033 | S0012 | MEXI-Cancer Center | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | SCREENING | 9 | 0 | 0 | 0 | Dr. Michelle Johnson | Dr. Charles Thompson
6034 | S0013 | MEXI-Clinical Center | ST-2024-011 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | CLOSED | 4 | 0 | 0 | 0 | Dr. Nicole Davis | Dr. Nicole Anderson
6035 | S0014 | MEXI-Medical Center | ST-2024-011 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 7 | 0 | 0 | 0 | Dr. Sarah Thompson | Dr. Daniel Jones
6036 | S0015 | MEXI-Medical Center | ST-2024-011 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Jennifer Garcia | Dr. David Miller
6037 | S0001 | MEXI-Cancer Center | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | -12 | -12 | 100 | -0.9 | Dr. Amanda Thompson | Dr. Jessica Garcia
6038 | S0002 | MEXI-Cancer Center | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 3 | 2 | 66.7 | 0.1 | Dr. Jennifer Anderson | Dr. Emily Martin
6039 | S0003 | MEXI-University Hospital | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 3 | 3 | 100 | 0.2 | Dr. Michelle Garcia | Dr. Thomas Williams
6040 | S0004 | MEXI-University Hospital | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Jessica White | Dr. Thomas Thomas
6041 | S0005 | MEXI-Research Institute | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 2 | 66.7 | 0.1 | Dr. Christopher Brown | Dr. Nicole Johnson
6042 | S0006 | MEXI-Cancer Center | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | CLOSED | 3 | 5 | 166.7 | 0.3 | Dr. Michael Martin | Dr. David Thompson
6043 | S0007 | CANA-Clinical Center | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -7 | -7 | 100 | -0.9 | Dr. Jennifer Williams | Dr. Nicole Taylor
6044 | S0008 | CANA-General Hospital | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | SCREENING | 3 | 3 | 100 | 0.4 | Dr. Sarah Smith | Dr. Christopher Wilson
6045 | S0009 | CANA-University Hospital | ST-2024-012 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Jennifer Martin | Dr. Michael Jones
6046 | S0010 | CANA-Health System | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 3 | 3 | 100 | 0.2 | Dr. Stephanie Jackson | Dr. Stephanie Martin
6047 | S0011 | CANA-Clinical Center | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 3 | 3 | 100 | 0.5 | Dr. Michelle Miller | Dr. Amanda Smith
6048 | S0012 | BELG-Research Institute | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | -3 | -3 | 100 | -0.3 | Dr. Emily Jackson | Dr. Daniel Anderson
6049 | S0013 | BELG-University Hospital | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | ENROLLING | 3 | 3 | 100 | 0.4 | Dr. Jessica Anderson | Dr. Christopher Thompson
6050 | S0014 | BELG-Health System | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Stephanie Jones | Dr. Thomas Martin
6051 | S0015 | BELG-Research Institute | ST-2024-012 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ENROLLING | 3 | 4 | 133.3 | 0.2 | Dr. Jennifer Jackson | Dr. James Davis
6052 | S0016 | NORW-Medical Center | ST-2024-012 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 0 | 0 | 0 | 0 | Dr. Sarah Jackson | Dr. William Moore
6053 | S0017 | NORW-Health System | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.3 | Dr. Sarah Brown | Dr. James Johnson
6054 | S0018 | NORW-General Hospital | ST-2024-012 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. Christopher Jackson | Dr. Emily Moore
6055 | S0019 | SING-General Hospital | ST-2024-012 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 2 | 0 | 0 | 0 | Dr. Jessica White | Dr. Emily Thompson
6056 | S0020 | SING-Research Institute | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Robert White | Dr. Emily Thompson
6057 | S0021 | CHIL-University Hospital | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ON_HOLD | -1 | -1 | 100 | -0.1 | Dr. Daniel Miller | Dr. Amanda White
6058 | S0022 | CHIL-Research Institute | ST-2024-012 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | SCREENING | 3 | 1 | 33.3 | 0.1 | Dr. Michelle Martin | Dr. David Martin
6059 | S0023 | CHIL-Research Institute | ST-2024-012 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 3 | 0 | 0 | 0 | Dr. James Williams | Dr. Emily Martin
6060 | S0001 | MEXI-Cancer Center | ST-2024-013 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -12 | -12 | 100 | -0.7 | Dr. Thomas Moore | Dr. David Miller
6061 | S0002 | MEXI-University Hospital | ST-2024-013 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Jessica Thomas | Dr. Robert Garcia
6062 | S0003 | MEXI-Health System | ST-2024-013 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | SCREENING | 3 | 4 | 133.3 | 0.3 | Dr. Thomas Brown | Dr. Amanda Moore
6063 | S0004 | POLA-Clinical Center | ST-2024-013 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 2 | 2 | 100 | 0.1 | Dr. Michelle Anderson | Dr. Stephanie Smith
6064 | S0005 | POLA-Health System | ST-2024-013 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 1, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | ENROLLING | 3 | 3 | 100 | 0.4 | Dr. Charles Jones | Dr. Sarah Johnson
6065 | S0006 | SOUT-Medical Center | ST-2024-013 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | -7 | -7 | 100 | -0.6 | Dr. Emily Moore | Dr. Lisa Moore
6066 | S0007 | SOUT-Clinical Center | ST-2024-013 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 3 | 100 | 0.3 | Dr. Jessica Johnson | Dr. Charles Jackson
6067 | S0008 | SOUT-Clinical Center | ST-2024-013 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | CLOSED | 3 | 2 | 66.7 | 0.1 | Dr. Thomas Moore | Dr. Sarah Smith
6068 | S0009 | SOUT-General Hospital | ST-2024-013 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 3 | 3 | 100 | 0.3 | Dr. Christopher Davis | Dr. Amanda Moore
6069 | S0010 | SOUT-General Hospital | ST-2024-013 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 3 | 0 | 0 | 0 | Dr. David Anderson | Dr. Christopher Garcia
6070 | S0011 | CHIL-Cancer Center | ST-2024-013 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -7 | -7 | 100 | -0.7 | Dr. Thomas Harris | Dr. Robert Johnson
6071 | S0012 | CHIL-University Hospital | ST-2024-013 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.2 | Dr. Sarah Anderson | Dr. Nicole Moore
6072 | S0013 | CHIL-Research Institute | ST-2024-013 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 3 | 2 | 66.7 | 0.3 | Dr. Thomas Thompson | Dr. Lisa Garcia
6073 | S0014 | CHIL-Health System | ST-2024-013 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.3 | Dr. Jennifer White | Dr. Michelle Moore
6074 | S0015 | CHIL-Clinical Center | ST-2024-013 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. Lisa Miller | Dr. Thomas Taylor
6075 | S0001 | MEXI-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | -14 | -14 | 100 | -1.8 | Dr. Jennifer Garcia | Dr. Robert Martin
6076 | S0002 | MEXI-Research Institute | ST-2024-014 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ENROLLING | 3 | 2 | 66.7 | 0.3 | Dr. Nicole Davis | Dr. Michael Wilson
6077 | S0003 | MEXI-Research Institute | ST-2024-014 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. David Thompson | Dr. Amanda Jackson
6078 | S0004 | MEXI-Clinical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | ENROLLING | 3 | 5 | 166.7 | 0.4 | Dr. Sarah Taylor | Dr. Emily Thompson
6079 | S0005 | CANA-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | -4 | -4 | 100 | -0.2 | Dr. Daniel Wilson | Dr. Charles Davis
6080 | S0006 | CANA-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Amanda Martin | Dr. Nicole Smith
6081 | S0007 | CANA-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Jennifer Davis | Dr. Michael Thompson
6082 | S0008 | CANA-General Hospital | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ENROLLING | 3 | 4 | 133.3 | 0.4 | Dr. Robert Garcia | Dr. Jennifer Thomas
6083 | S0009 | UNIT-Clinical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 2 | 1 | 50 | 0.1 | Dr. Emily Martin | Dr. Nicole Martin
6084 | S0010 | UNIT-University Hospital | ST-2024-014 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. Stephanie Smith | Dr. Lisa Johnson
6085 | S0011 | POLA-General Hospital | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | -10 | -10 | 100 | -1.7 | Dr. Jessica Williams | Dr. David Harris
6086 | S0012 | POLA-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 3 | 3 | 100 | 0.2 | Dr. Jennifer Davis | Dr. Stephanie Jones
6087 | S0013 | POLA-Cancer Center | ST-2024-014 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Daniel Wilson | Dr. Jennifer Taylor
6088 | S0014 | POLA-Clinical Center | ST-2024-014 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | ON_HOLD | 3 | 2 | 66.7 | 0.1 | Dr. Michael Davis | Dr. Charles Jackson
6089 | S0015 | POLA-University Hospital | ST-2024-014 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ENROLLING | 3 | 3 | 100 | 0.4 | Dr. David Thompson | Dr. Daniel White
6090 | S0016 | POLA-Cancer Center | ST-2024-014 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 3 | 4 | 133.3 | 0.5 | Dr. Emily Garcia | Dr. Nicole Johnson
6091 | S0017 | NORW-Medical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | -4 | -4 | 100 | -0.2 | Dr. Stephanie Thompson | Dr. Stephanie Thomas
6092 | S0018 | NORW-Cancer Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 3 | 100 | 0.5 | Dr. Daniel White | Dr. Lisa Martin
6093 | S0019 | NORW-Cancer Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 2 | 66.7 | 0.1 | Dr. Amanda Brown | Dr. Stephanie Jones
6094 | S0020 | NORW-Research Institute | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Michael Anderson | Dr. Michelle White
6095 | S0021 | NETH-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | ON_HOLD | -1 | -1 | 100 | -0.2 | Dr. David Taylor | Dr. Stephanie Thomas
6096 | S0022 | NETH-Medical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. William Wilson | Dr. Michelle White
6097 | S0023 | NETH-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 0 | 0 | 0 | Dr. William Jackson | Dr. David White
6098 | S0024 | DENM-Medical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -10 | -10 | 100 | -0.6 | Dr. Christopher Garcia | Dr. Emily Miller
6099 | S0025 | DENM-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 3 | 100 | 0.2 | Dr. Michelle Johnson | Dr. Jennifer Jackson
6100 | S0026 | DENM-General Hospital | ST-2024-014 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 3 | 2 | 66.7 | 0.3 | Dr. Robert Martin | Dr. Stephanie Williams
6101 | S0027 | DENM-Medical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Amanda Williams | Dr. Sarah Jackson
6102 | S0028 | DENM-Clinical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 3 | 3 | 100 | 0.2 | Dr. Daniel Anderson | Dr. Sarah Garcia
6103 | S0029 | DENM-General Hospital | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. James Miller | Dr. Daniel Anderson
6104 | S0030 | TAIW-Medical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | -7 | -7 | 100 | -0.7 | Dr. Amanda Jackson | Dr. Charles Miller
6105 | S0031 | TAIW-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.3 | Dr. Michael Williams | Dr. Michelle Anderson
6106 | S0032 | TAIW-General Hospital | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.1 | Dr. Amanda Thomas | Dr. William Davis
6107 | S0033 | TAIW-Health System | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | ON_HOLD | 3 | 3 | 100 | 0.3 | Dr. Charles Smith | Dr. William Garcia
6108 | S0034 | TAIW-Clinical Center | ST-2024-014 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Michelle Williams | Dr. Daniel Anderson
6109 | S0001 | CANA-Health System | ST-2024-015 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 3, 'cumulative': 6}, {'month': 3, 'enrolled': 0, 'cumulative': 6}, {'month': 4, 'enrolled': 0, 'cumulative': 6}, {'month': 5, 'enrolled': 3, 'cumulative': 9}, {'month': 6, 'enrolled': 0, 'cumulative': 9}] | ON_HOLD | 7 | 7 | 100 | 0.6 | Dr. Lisa Garcia | Dr. Charles Jackson
6110 | S0002 | CANA-University Hospital | ST-2024-015 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 7 | 5 | 71.4 | 0.5 | Dr. Stephanie Davis | Dr. Daniel Wilson
6111 | S0003 | CANA-Research Institute | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | CLOSED | 7 | 0 | 0 | 0 | Dr. Michelle Wilson | Dr. Stephanie Miller
6112 | S0004 | CANA-Cancer Center | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 6 | 0 | 0 | 0 | Dr. Robert Anderson | Dr. Emily Harris
6113 | S0005 | MEXI-University Hospital | ST-2024-015 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | SCREENING | 8 | 0 | 0 | 0 | Dr. Robert Johnson | Dr. Michelle Smith
6114 | S0006 | MEXI-University Hospital | ST-2024-015 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 5 | 0 | 0 | 0 | Dr. William Jones | Dr. Christopher Smith
6115 | S0007 | SWED-Research Institute | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 7 | 0 | 0 | 0 | Dr. Sarah Wilson | Dr. Charles Williams
6116 | S0008 | SWED-Health System | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 5 | 0 | 0 | 0 | Dr. David Wilson | Dr. Charles Smith
6117 | S0009 | SWED-Medical Center | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | CLOSED | 7 | 0 | 0 | 0 | Dr. Lisa Jackson | Dr. Christopher Davis
6118 | S0010 | SWED-General Hospital | ST-2024-015 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 6 | 0 | 0 | 0 | Dr. Christopher Brown | Dr. Daniel Miller
6119 | S0011 | SWED-Clinical Center | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | CLOSED | 6 | 0 | 0 | 0 | Dr. Jessica Taylor | Dr. Jennifer Johnson
6120 | S0012 | NORW-Clinical Center | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 12 | 0 | 0 | 0 | Dr. David Thomas | Dr. Sarah Miller
6121 | S0013 | NORW-Medical Center | ST-2024-015 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 10 | 0 | 0 | 0 | Dr. Stephanie Taylor | Dr. James Garcia
6122 | S0014 | SWIT-General Hospital | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 8 | 0 | 0 | 0 | Dr. Amanda Williams | Dr. Lisa Garcia
6123 | S0015 | SWIT-Clinical Center | ST-2024-015 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 6 | 0 | 0 | 0 | Dr. Thomas Johnson | Dr. Sarah Thomas
6124 | S0016 | SWIT-General Hospital | ST-2024-015 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 1, 'cumulative': 7}, {'month': 6, 'enrolled': 0, 'cumulative': 7}] | CLOSED | 5 | 0 | 0 | 0 | Dr. Michelle Brown | Dr. Robert Martin
6125 | S0017 | SWIT-University Hospital | ST-2024-015 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 4 | 0 | 0 | 0 | Dr. Amanda Harris | Dr. David Smith
6126 | S0018 | INDI-Medical Center | ST-2024-015 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 12 | 0 | 0 | 0 | Dr. Christopher Moore | Dr. Jessica Moore
6127 | S0019 | INDI-General Hospital | ST-2024-015 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 1, 'cumulative': 5}, {'month': 4, 'enrolled': 0, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 2, 'cumulative': 7}] | SCREENING | 8 | 0 | 0 | 0 | Dr. Jennifer Moore | Dr. Amanda Taylor
6128 | S0001 | UNIT-Cancer Center | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ON_HOLD | 5 | 3 | 60 | 0.4 | Dr. Michelle Miller | Dr. Nicole Jackson
6129 | S0002 | UNIT-General Hospital | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Michelle Thompson | Dr. Lisa Davis
6130 | S0003 | UNIT-Medical Center | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. Thomas Williams | Dr. Emily White
6131 | S0004 | UNIT-Clinical Center | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 4 | 4 | 100 | 0.4 | Dr. David Taylor | Dr. Amanda Smith
6132 | S0005 | UNIT-Cancer Center | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Amanda Harris | Dr. Robert Harris
6133 | S0006 | CANA-Research Institute | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 5 | 3 | 60 | 0.4 | Dr. Michael Brown | Dr. Sarah Davis
6134 | S0007 | CANA-Health System | ST-2024-016 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 4, 'cumulative': 7}, {'month': 3, 'enrolled': 4, 'cumulative': 11}, {'month': 4, 'enrolled': 4, 'cumulative': 15}, {'month': 5, 'enrolled': 4, 'cumulative': 19}, {'month': 6, 'enrolled': 4, 'cumulative': 23}] | ENROLLING | 12 | 14 | 116.7 | 1.8 | Dr. James Taylor | Dr. Emily Anderson
6135 | S0008 | GERM-Clinical Center | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 1 | 0 | 0 | 0 | Dr. Robert Smith | Dr. Charles Thompson
6136 | S0009 | GERM-Medical Center | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 2, 'cumulative': 7}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Sarah Anderson | Dr. David Wilson
6137 | S0010 | GERM-Medical Center | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. James Williams | Dr. Charles Wilson
6138 | S0011 | GERM-General Hospital | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | SCREENING | 3 | 5 | 166.7 | 0.3 | Dr. Emily Smith | Dr. Jessica Jackson
6139 | S0012 | POLA-Medical Center | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 3, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 3, 'cumulative': 7}, {'month': 5, 'enrolled': 0, 'cumulative': 7}, {'month': 6, 'enrolled': 2, 'cumulative': 9}] | ON_HOLD | 8 | 6 | 75 | 0.5 | Dr. Michelle Williams | Dr. Jennifer Miller
6140 | S0013 | POLA-Health System | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | CLOSED | 9 | 0 | 0 | 0 | Dr. James Johnson | Dr. Lisa Thompson
6141 | S0014 | BELG-Research Institute | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | -4 | -4 | 100 | -0.3 | Dr. Michelle Wilson | Dr. Lisa Jones
6142 | S0015 | BELG-Research Institute | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | CLOSED | 3 | 3 | 100 | 0.2 | Dr. Robert Williams | Dr. Charles Thompson
6143 | S0016 | BELG-General Hospital | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | 3 | 1 | 33.3 | 0.1 | Dr. Lisa White | Dr. Lisa Jones
6144 | S0017 | BELG-Clinical Center | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Thomas Harris | Dr. Michelle Jones
6145 | S0018 | BELG-University Hospital | ST-2024-016 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 2, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Michelle Miller | Dr. Robert Anderson
6146 | S0019 | BELG-General Hospital | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Robert White | Dr. Robert Garcia
6147 | S0020 | AUST-University Hospital | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 5 | 0 | 0 | 0 | Dr. Thomas White | Dr. Stephanie Anderson
6148 | S0021 | AUST-Clinical Center | ST-2024-016 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 5 | 0 | 0 | 0 | Dr. William Jones | Dr. David Brown
6149 | S0022 | AUST-University Hospital | ST-2024-016 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 7 | 0 | 0 | 0 | Dr. William Davis | Dr. Lisa Davis
6150 | S0001 | MEXI-Medical Center | ST-2024-017 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 2, 'cumulative': 6}, {'month': 4, 'enrolled': 0, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | ON_HOLD | 5 | 5 | 100 | 0.8 | Dr. Emily Miller | Dr. Stephanie White
6151 | S0002 | MEXI-Medical Center | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 4 | 2 | 50 | 0.2 | Dr. Michelle Miller | Dr. James Miller
6152 | S0003 | MEXI-General Hospital | ST-2024-017 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 5 | 1 | 20 | 0.1 | Dr. Michael Anderson | Dr. Jessica Thompson
6153 | S0004 | MEXI-Health System | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 4 | 0 | 0 | 0 | Dr. Emily Taylor | Dr. Thomas Jackson
6154 | S0005 | MEXI-General Hospital | ST-2024-017 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 5 | 0 | 0 | 0 | Dr. James Garcia | Dr. David Taylor
6155 | S0006 | SPAI-Cancer Center | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | -3 | -3 | 100 | -0.2 | Dr. Sarah Thompson | Dr. Jessica Taylor
6156 | S0007 | SPAI-Health System | ST-2024-017 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. David Taylor | Dr. Amanda Williams
6157 | S0008 | SPAI-University Hospital | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 3 | 1 | 33.3 | 0.1 | Dr. Thomas Jackson | Dr. Michelle Garcia
6158 | S0009 | SPAI-Health System | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Jennifer Brown | Dr. Jessica Taylor
6159 | S0010 | SPAI-General Hospital | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Stephanie Williams | Dr. Nicole Davis
6160 | S0011 | SPAI-Research Institute | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. David Thompson | Dr. Jessica Garcia
6161 | S0012 | CHIN-Health System | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ON_HOLD | 4 | 0 | 0 | 0 | Dr. Robert Brown | Dr. Daniel Jones
6162 | S0013 | CHIN-University Hospital | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 5 | 0 | 0 | 0 | Dr. Christopher Jackson | Dr. Daniel Brown
6163 | S0014 | CHIN-Medical Center | ST-2024-017 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | SCREENING | 5 | 0 | 0 | 0 | Dr. Michael Taylor | Dr. Christopher Johnson
6164 | S0015 | CHIN-Medical Center | ST-2024-017 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | CLOSED | 5 | 0 | 0 | 0 | Dr. Jessica Smith | Dr. Jessica Miller
6165 | S0016 | CHIN-Research Institute | ST-2024-017 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Jessica Wilson | Dr. Michelle Taylor
6166 | S0017 | CHIN-Cancer Center | ST-2024-017 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Emily Wilson | Dr. Robert Garcia
6167 | S0001 | UNIT-Health System | ST-2024-018 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Jennifer Harris | Dr. Daniel White
6168 | S0002 | UNIT-Health System | ST-2024-018 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ENROLLING | 4 | 4 | 100 | 0.3 | Dr. Amanda Davis | Dr. Jennifer White
6169 | S0003 | UNIT-Health System | ST-2024-018 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 4 | 133.3 | 0.7 | Dr. Nicole Davis | Dr. Daniel Wilson
6170 | S0004 | DENM-Medical Center | ST-2024-018 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Amanda Brown | Dr. Nicole Williams
6171 | S0005 | DENM-University Hospital | ST-2024-018 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 4 | 133.3 | 0.2 | Dr. Daniel Wilson | Dr. Christopher Thompson
6172 | S0006 | SOUT-Research Institute | ST-2024-018 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | -4 | -4 | 100 | -0.3 | Dr. Thomas Moore | Dr. James Martin
6173 | S0007 | SOUT-Clinical Center | ST-2024-018 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ENROLLING | 3 | 1 | 33.3 | 0.1 | Dr. Thomas White | Dr. Amanda Anderson
6174 | S0008 | SOUT-Research Institute | ST-2024-018 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Jessica Wilson | Dr. Sarah Martin
6175 | S0009 | SOUT-Health System | ST-2024-018 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 3 | 100 | 0.4 | Dr. Sarah Anderson | Dr. James Anderson
6176 | S0010 | SOUT-Clinical Center | ST-2024-018 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 0, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 3, 'cumulative': 6}, {'month': 5, 'enrolled': 1, 'cumulative': 7}, {'month': 6, 'enrolled': 2, 'cumulative': 9}] | ENROLLING | 3 | 6 | 200 | 0.9 | Dr. Daniel Williams | Dr. William Wilson
6177 | S0001 | MEXI-University Hospital | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 25 | 0 | 0 | 0 | Dr. David Brown | Dr. Christopher Wilson
6178 | S0002 | MEXI-Medical Center | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | SCREENING | 14 | 0 | 0 | 0 | Dr. Michael Wilson | Dr. Christopher Smith
6179 | S0003 | UNIT-Health System | ST-2024-019 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 19 | 0 | 0 | 0 | Dr. Nicole White | Dr. Charles Williams
6180 | S0004 | UNIT-Health System | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 7 | 0 | 0 | 0 | Dr. Charles Martin | Dr. Emily Moore
6181 | S0005 | UNIT-Research Institute | ST-2024-019 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 13 | 0 | 0 | 0 | Dr. Jessica Jackson | Dr. Sarah Williams
6182 | S0006 | UNIT-Research Institute | ST-2024-019 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | ON_HOLD | 17 | 0 | 0 | 0 | Dr. Michael Harris | Dr. Jessica Miller
6183 | S0007 | UNIT-University Hospital | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 13 | 0 | 0 | 0 | Dr. Charles Miller | Dr. Jessica Jackson
6184 | S0008 | POLA-General Hospital | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 24 | 0 | 0 | 0 | Dr. Sarah Miller | Dr. James Davis
6185 | S0009 | POLA-Clinical Center | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | SCREENING | 18 | 0 | 0 | 0 | Dr. Michelle Anderson | Dr. Nicole Moore
6186 | S0010 | POLA-Cancer Center | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 13 | 0 | 0 | 0 | Dr. James Johnson | Dr. Thomas Johnson
6187 | S0011 | DENM-University Hospital | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | CLOSED | 33 | 0 | 0 | 0 | Dr. Daniel Harris | Dr. Michelle Jones
6188 | S0012 | DENM-General Hospital | ST-2024-019 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | SCREENING | 46 | 0 | 0 | 0 | Dr. Michael Johnson | Dr. Robert Martin
6189 | S0013 | UNIT-Medical Center | ST-2024-019 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 40 | 0 | 0 | 0 | Dr. Robert Smith | Dr. Jennifer Johnson
6190 | S0014 | UNIT-Research Institute | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | SCREENING | 32 | 0 | 0 | 0 | Dr. Christopher Garcia | Dr. Michael Brown
6191 | S0015 | AUST-Medical Center | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 14 | 0 | 0 | 0 | Dr. Michelle Jones | Dr. Thomas Miller
6192 | S0016 | AUST-Cancer Center | ST-2024-019 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 21 | 0 | 0 | 0 | Dr. Jennifer Taylor | Dr. Michael Brown
6193 | S0017 | AUST-Research Institute | ST-2024-019 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ON_HOLD | 22 | 0 | 0 | 0 | Dr. Jennifer Thomas | Dr. Michelle Garcia
6194 | S0018 | AUST-Clinical Center | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | 11 | 0 | 0 | 0 | Dr. Sarah Jones | Dr. Emily Jackson
6195 | S0019 | AUST-Cancer Center | ST-2024-019 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 14 | 0 | 0 | 0 | Dr. Nicole Williams | Dr. James Smith
6196 | S0001 | CANA-Cancer Center | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | -9 | -9 | 100 | -0.6 | Dr. David Davis | Dr. Thomas Thomas
6197 | S0002 | CANA-Research Institute | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.1 | Dr. Stephanie Wilson | Dr. Sarah Williams
6198 | S0003 | CANA-Research Institute | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 3 | 3 | 100 | 0.3 | Dr. Nicole Thompson | Dr. Daniel Brown
6199 | S0004 | CANA-Clinical Center | ST-2024-020 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 4 | 133.3 | 0.2 | Dr. Michelle Anderson | Dr. Christopher Thomas
6200 | S0005 | NORW-Medical Center | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ENROLLING | -4 | -4 | 100 | -0.3 | Dr. Jessica Williams | Dr. Emily Garcia
6201 | S0006 | NORW-Research Institute | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 2, 'cumulative': 2}] | SCREENING | 3 | 3 | 100 | 0.4 | Dr. Robert Martin | Dr. Robert Miller
6202 | S0007 | NORW-Health System | ST-2024-020 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Jessica White | Dr. Michelle Jones
6203 | S0008 | NORW-Clinical Center | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ENROLLING | 3 | 4 | 133.3 | 0.4 | Dr. Christopher Smith | Dr. Jessica Miller
6204 | S0009 | NETH-General Hospital | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | -4 | -4 | 100 | -0.2 | Dr. Nicole Thompson | Dr. Michelle Harris
6205 | S0010 | NETH-Clinical Center | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | CLOSED | 3 | 2 | 66.7 | 0.2 | Dr. Robert Anderson | Dr. Jennifer Wilson
6206 | S0011 | NETH-University Hospital | ST-2024-020 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. Jessica Johnson | Dr. Robert Thomas
6207 | S0012 | NETH-Research Institute | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 3 | 3 | 100 | 0.2 | Dr. Jennifer Moore | Dr. Jessica Garcia
6208 | S0013 | JAPA-Research Institute | ST-2024-020 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ENROLLING | -4 | -4 | 100 | -0.3 | Dr. Christopher Wilson | Dr. Amanda Garcia
6209 | S0014 | JAPA-University Hospital | ST-2024-020 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.1 | Dr. Sarah Taylor | Dr. Amanda Jones
6210 | S0015 | JAPA-Research Institute | ST-2024-020 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. Jennifer Moore | Dr. Jessica Brown
6211 | S0016 | JAPA-Medical Center | ST-2024-020 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 3 | 5 | 166.7 | 0.4 | Dr. Robert Harris | Dr. Thomas Jones
6212 | S0001 | MEXI-Medical Center | ST-2025-021 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | SCREENING | 9 | 5 | 55.6 | 0.5 | Dr. James Brown | Dr. Emily Miller
6213 | S0002 | MEXI-Health System | ST-2025-021 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 8 | 5 | 62.5 | 0.6 | Dr. Amanda Smith | Dr. Michael Jones
6214 | S0003 | MEXI-Cancer Center | ST-2025-021 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 3, 'cumulative': 4}] | ENROLLING | 17 | 12 | 70.6 | 0.7 | Dr. Amanda Thomas | Dr. Jennifer Thompson
6215 | S0004 | MEXI-Cancer Center | ST-2025-021 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 3, 'cumulative': 5}, {'month': 3, 'enrolled': 5, 'cumulative': 10}, {'month': 4, 'enrolled': 6, 'cumulative': 16}, {'month': 5, 'enrolled': 4, 'cumulative': 20}, {'month': 6, 'enrolled': 3, 'cumulative': 23}] | SCREENING | 14 | 26 | 185.7 | 1.5 | Dr. Lisa Thompson | Dr. Michael Brown
6216 | S0005 | UNIT-General Hospital | ST-2025-021 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 5, 'cumulative': 8}, {'month': 3, 'enrolled': 5, 'cumulative': 13}, {'month': 4, 'enrolled': 1, 'cumulative': 14}, {'month': 5, 'enrolled': 1, 'cumulative': 15}, {'month': 6, 'enrolled': 5, 'cumulative': 20}] | ENROLLING | 25 | 22 | 88 | 2.4 | Dr. Jennifer Moore | Dr. James Brown
6217 | S0006 | UNIT-University Hospital | ST-2025-021 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 5, 'cumulative': 10}, {'month': 3, 'enrolled': 3, 'cumulative': 13}, {'month': 4, 'enrolled': 4, 'cumulative': 17}, {'month': 5, 'enrolled': 5, 'cumulative': 22}, {'month': 6, 'enrolled': 5, 'cumulative': 27}] | SCREENING | 23 | 26 | 113 | 1.9 | Dr. Nicole Thomas | Dr. Jennifer Harris
6218 | S0007 | BELG-Health System | ST-2025-021 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 2, 'cumulative': 6}, {'month': 3, 'enrolled': 4, 'cumulative': 10}, {'month': 4, 'enrolled': 2, 'cumulative': 12}, {'month': 5, 'enrolled': 4, 'cumulative': 16}, {'month': 6, 'enrolled': 4, 'cumulative': 20}] | SCREENING | 13 | 13 | 100 | 1.4 | Dr. Emily Taylor | Dr. Emily Harris
6219 | S0008 | BELG-Medical Center | ST-2025-021 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ENROLLING | 6 | 5 | 83.3 | 0.4 | Dr. Nicole Thomas | Dr. Jessica Moore
6220 | S0009 | BELG-General Hospital | ST-2025-021 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 3, 'cumulative': 5}, {'month': 3, 'enrolled': 3, 'cumulative': 8}, {'month': 4, 'enrolled': 3, 'cumulative': 11}, {'month': 5, 'enrolled': 0, 'cumulative': 11}, {'month': 6, 'enrolled': 0, 'cumulative': 11}] | ENROLLING | 14 | 12 | 85.7 | 2 | Dr. Thomas Martin | Dr. Emily Jackson
6221 | S0010 | SWED-Health System | ST-2025-021 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 3, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | ENROLLING | 8 | 8 | 100 | 0.7 | Dr. Stephanie Miller | Dr. Michael Martin
6222 | S0011 | SWED-General Hospital | ST-2025-021 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 3, 'cumulative': 8}] | ENROLLING | 11 | 9 | 81.8 | 0.8 | Dr. James Martin | Dr. Emily Jackson
6223 | S0012 | SWED-Clinical Center | ST-2025-021 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 3, 'cumulative': 5}, {'month': 3, 'enrolled': 3, 'cumulative': 8}, {'month': 4, 'enrolled': 3, 'cumulative': 11}, {'month': 5, 'enrolled': 2, 'cumulative': 13}, {'month': 6, 'enrolled': 2, 'cumulative': 15}] | SCREENING | 8 | 10 | 125 | 0.7 | Dr. Michael Brown | Dr. Robert Jackson
6224 | S0013 | AUST-University Hospital | ST-2025-021 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 0, 'cumulative': 3}, {'month': 3, 'enrolled': 3, 'cumulative': 6}, {'month': 4, 'enrolled': 0, 'cumulative': 6}, {'month': 5, 'enrolled': 2, 'cumulative': 8}, {'month': 6, 'enrolled': 1, 'cumulative': 9}] | ENROLLING | 14 | 9 | 64.3 | 1.3 | Dr. David Taylor | Dr. David Jackson
6225 | S0014 | AUST-Medical Center | ST-2025-021 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 5, 'cumulative': 9}, {'month': 3, 'enrolled': 4, 'cumulative': 13}, {'month': 4, 'enrolled': 5, 'cumulative': 18}, {'month': 5, 'enrolled': 3, 'cumulative': 21}, {'month': 6, 'enrolled': 3, 'cumulative': 24}] | ENROLLING | 15 | 23 | 153.3 | 2.6 | Dr. Nicole Wilson | Dr. William Jackson
6226 | S0001 | UNIT-Cancer Center | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | SCREENING | 0 | 0 | 0 | 0 | Dr. Michelle Garcia | Dr. Sarah Martin
6227 | S0002 | UNIT-Cancer Center | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ENROLLING | 3 | 2 | 66.7 | 0.3 | Dr. Michael Taylor | Dr. Jessica Williams
6228 | S0003 | UNIT-Clinical Center | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. Michael Jackson | Dr. Robert Davis
6229 | S0004 | UNIT-Medical Center | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 3 | 5 | 166.7 | 0.3 | Dr. Daniel Brown | Dr. Daniel Thompson
6230 | S0005 | MEXI-Medical Center | ST-2025-022 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 4 | 2 | 50 | 0.1 | Dr. Thomas Jackson | Dr. Lisa White
6231 | S0006 | MEXI-University Hospital | ST-2025-022 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 5 | 4 | 80 | 0.5 | Dr. Jennifer Miller | Dr. William Harris
6232 | S0007 | POLA-Clinical Center | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 1 | 1 | 100 | 0.1 | Dr. William Jones | Dr. Amanda Martin
6233 | S0008 | POLA-General Hospital | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. James Johnson | Dr. Sarah Davis
6234 | S0009 | POLA-Research Institute | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.1 | Dr. Jessica Thomas | Dr. Emily Moore
6235 | S0010 | POLA-Cancer Center | ST-2025-022 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. Charles Smith | Dr. Charles Wilson
6236 | S0011 | SWED-Research Institute | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | -5 | -5 | 100 | -0.7 | Dr. Nicole White | Dr. Thomas White
6237 | S0012 | SWED-Cancer Center | ST-2025-022 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ENROLLING | 3 | 2 | 66.7 | 0.3 | Dr. William Thompson | Dr. Michael Thomas
6238 | S0013 | SWED-Clinical Center | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | 3 | 3 | 100 | 0.2 | Dr. Michelle Taylor | Dr. Christopher Smith
6239 | S0014 | SWED-Cancer Center | ST-2025-022 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 3 | 2 | 66.7 | 0.3 | Dr. Jennifer Harris | Dr. Robert Smith
6240 | S0015 | SWED-Clinical Center | ST-2025-022 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 3 | 100 | 0.3 | Dr. Jessica Taylor | Dr. Michael Brown
6241 | S0016 | SWED-University Hospital | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 3 | 3 | 100 | 0.3 | Dr. Robert White | Dr. Thomas Harris
6242 | S0017 | CHIN-General Hospital | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | 5 | 3 | 60 | 0.2 | Dr. Jessica Miller | Dr. Michael White
6243 | S0018 | CHIN-Research Institute | ST-2025-022 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 6 | 5 | 83.3 | 0.6 | Dr. Charles Davis | Dr. James Smith
6244 | S0019 | CHIL-University Hospital | ST-2025-022 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | SCREENING | 5 | 5 | 100 | 0.5 | Dr. Jennifer Johnson | Dr. Charles White
6245 | S0020 | CHIL-Health System | ST-2025-022 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 3 | 3 | 100 | 0.3 | Dr. Michael Thomas | Dr. Jennifer Brown
6246 | S0021 | CHIL-Medical Center | ST-2025-022 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 4, 'cumulative': 9}] | SCREENING | 3 | 15 | 500 | 0.9 | Dr. Stephanie Harris | Dr. Nicole Brown
6247 | S0001 | UNIT-Medical Center | ST-2025-023 | [{'month': 1, 'enrolled': 16, 'cumulative': 16}, {'month': 2, 'enrolled': 18, 'cumulative': 34}, {'month': 3, 'enrolled': 15, 'cumulative': 49}, {'month': 4, 'enrolled': 18, 'cumulative': 67}, {'month': 5, 'enrolled': 15, 'cumulative': 82}, {'month': 6, 'enrolled': 16, 'cumulative': 98}] | ON_HOLD | 106 | 106 | 100 | 8.8 | Dr. James Smith | Dr. Charles Brown
6248 | S0002 | UNIT-Medical Center | ST-2025-023 | [{'month': 1, 'enrolled': 15, 'cumulative': 15}, {'month': 2, 'enrolled': 11, 'cumulative': 26}, {'month': 3, 'enrolled': 15, 'cumulative': 41}, {'month': 4, 'enrolled': 13, 'cumulative': 54}, {'month': 5, 'enrolled': 14, 'cumulative': 68}, {'month': 6, 'enrolled': 14, 'cumulative': 82}] | ON_HOLD | 93 | 78 | 83.9 | 9.8 | Dr. Nicole Harris | Dr. Charles Martin
6249 | S0003 | CANA-General Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 9, 'cumulative': 9}, {'month': 2, 'enrolled': 7, 'cumulative': 16}, {'month': 3, 'enrolled': 7, 'cumulative': 23}, {'month': 4, 'enrolled': 7, 'cumulative': 30}, {'month': 5, 'enrolled': 5, 'cumulative': 35}, {'month': 6, 'enrolled': 7, 'cumulative': 42}] | SCREENING | 47 | 47 | 100 | 3.9 | Dr. Michael Jones | Dr. Robert Smith
6250 | S0004 | CANA-University Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 14, 'cumulative': 14}, {'month': 2, 'enrolled': 14, 'cumulative': 28}, {'month': 3, 'enrolled': 11, 'cumulative': 39}, {'month': 4, 'enrolled': 13, 'cumulative': 52}, {'month': 5, 'enrolled': 13, 'cumulative': 65}, {'month': 6, 'enrolled': 11, 'cumulative': 76}] | ENROLLING | 75 | 75 | 100 | 10.7 | Dr. David Smith | Dr. David Martin
6251 | S0005 | CANA-General Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 6, 'cumulative': 6}, {'month': 2, 'enrolled': 6, 'cumulative': 12}, {'month': 3, 'enrolled': 6, 'cumulative': 18}, {'month': 4, 'enrolled': 5, 'cumulative': 23}, {'month': 5, 'enrolled': 4, 'cumulative': 27}, {'month': 6, 'enrolled': 5, 'cumulative': 32}] | ON_HOLD | 63 | 26 | 41.3 | 3.2 | Dr. Lisa White | Dr. Michelle Miller
6252 | S0006 | ITAL-Medical Center | ST-2025-023 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 5, 'cumulative': 9}, {'month': 3, 'enrolled': 3, 'cumulative': 12}, {'month': 4, 'enrolled': 3, 'cumulative': 15}, {'month': 5, 'enrolled': 7, 'cumulative': 22}, {'month': 6, 'enrolled': 5, 'cumulative': 27}] | ON_HOLD | 32 | 32 | 100 | 2.5 | Dr. Lisa Miller | Dr. Jessica Jackson
6253 | S0007 | ITAL-Medical Center | ST-2025-023 | [{'month': 1, 'enrolled': 11, 'cumulative': 11}, {'month': 2, 'enrolled': 9, 'cumulative': 20}, {'month': 3, 'enrolled': 12, 'cumulative': 32}, {'month': 4, 'enrolled': 12, 'cumulative': 44}, {'month': 5, 'enrolled': 10, 'cumulative': 54}, {'month': 6, 'enrolled': 9, 'cumulative': 63}] | ENROLLING | 64 | 64 | 100 | 5.8 | Dr. Emily White | Dr. Stephanie Martin
6254 | S0008 | ITAL-General Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 6, 'cumulative': 8}, {'month': 3, 'enrolled': 6, 'cumulative': 14}, {'month': 4, 'enrolled': 4, 'cumulative': 18}, {'month': 5, 'enrolled': 6, 'cumulative': 24}, {'month': 6, 'enrolled': 4, 'cumulative': 28}] | ON_HOLD | 33 | 28 | 84.8 | 1.9 | Dr. Michelle Anderson | Dr. Sarah Martin
6255 | S0009 | ITAL-Clinical Center | ST-2025-023 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 4, 'cumulative': 9}, {'month': 3, 'enrolled': 4, 'cumulative': 13}, {'month': 4, 'enrolled': 8, 'cumulative': 21}, {'month': 5, 'enrolled': 8, 'cumulative': 29}, {'month': 6, 'enrolled': 6, 'cumulative': 35}] | ON_HOLD | 46 | 40 | 87 | 3.1 | Dr. Nicole Davis | Dr. Sarah Thompson
6256 | S0010 | ITAL-Medical Center | ST-2025-023 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 31 | 1 | 3.2 | 0.1 | Dr. Thomas Moore | Dr. Michael Wilson
6257 | S0011 | POLA-University Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 11, 'cumulative': 11}, {'month': 2, 'enrolled': 11, 'cumulative': 22}, {'month': 3, 'enrolled': 13, 'cumulative': 35}, {'month': 4, 'enrolled': 11, 'cumulative': 46}, {'month': 5, 'enrolled': 9, 'cumulative': 55}, {'month': 6, 'enrolled': 9, 'cumulative': 64}] | SCREENING | 70 | 70 | 100 | 5 | Dr. Thomas Harris | Dr. Robert Anderson
6258 | S0012 | POLA-General Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 5, 'cumulative': 7}, {'month': 3, 'enrolled': 4, 'cumulative': 11}, {'month': 4, 'enrolled': 6, 'cumulative': 17}, {'month': 5, 'enrolled': 2, 'cumulative': 19}, {'month': 6, 'enrolled': 5, 'cumulative': 24}] | ON_HOLD | 43 | 26 | 60.5 | 1.5 | Dr. Stephanie Thomas | Dr. Nicole Garcia
6259 | S0013 | POLA-Health System | ST-2025-023 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 4, 'cumulative': 9}, {'month': 3, 'enrolled': 7, 'cumulative': 16}, {'month': 4, 'enrolled': 7, 'cumulative': 23}, {'month': 5, 'enrolled': 7, 'cumulative': 30}, {'month': 6, 'enrolled': 7, 'cumulative': 37}] | ON_HOLD | 46 | 35 | 76.1 | 3.9 | Dr. Michael Martin | Dr. Robert Garcia
6260 | S0014 | POLA-University Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 5, 'cumulative': 9}, {'month': 3, 'enrolled': 5, 'cumulative': 14}, {'month': 4, 'enrolled': 5, 'cumulative': 19}, {'month': 5, 'enrolled': 7, 'cumulative': 26}, {'month': 6, 'enrolled': 4, 'cumulative': 30}] | CLOSED | 47 | 33 | 70.2 | 4.1 | Dr. Nicole Brown | Dr. Stephanie Martin
6261 | S0015 | POLA-Research Institute | ST-2025-023 | [{'month': 1, 'enrolled': 10, 'cumulative': 10}, {'month': 2, 'enrolled': 11, 'cumulative': 21}, {'month': 3, 'enrolled': 8, 'cumulative': 29}, {'month': 4, 'enrolled': 7, 'cumulative': 36}, {'month': 5, 'enrolled': 9, 'cumulative': 45}, {'month': 6, 'enrolled': 11, 'cumulative': 56}] | SCREENING | 68 | 54 | 79.4 | 6 | Dr. Michelle Johnson | Dr. James Thomas
6262 | S0016 | POLA-Research Institute | ST-2025-023 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 1, 'cumulative': 5}, {'month': 3, 'enrolled': 2, 'cumulative': 7}, {'month': 4, 'enrolled': 3, 'cumulative': 10}, {'month': 5, 'enrolled': 0, 'cumulative': 10}, {'month': 6, 'enrolled': 1, 'cumulative': 11}] | CLOSED | 40 | 12 | 30 | 1.1 | Dr. Jennifer Garcia | Dr. Daniel Johnson
6263 | S0017 | JAPA-University Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 9, 'cumulative': 9}, {'month': 2, 'enrolled': 9, 'cumulative': 18}, {'month': 3, 'enrolled': 6, 'cumulative': 24}, {'month': 4, 'enrolled': 6, 'cumulative': 30}, {'month': 5, 'enrolled': 6, 'cumulative': 36}, {'month': 6, 'enrolled': 9, 'cumulative': 45}] | ON_HOLD | 50 | 50 | 100 | 2.9 | Dr. Emily Johnson | Dr. Christopher Harris
6264 | S0018 | JAPA-Cancer Center | ST-2025-023 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 6, 'cumulative': 10}, {'month': 3, 'enrolled': 4, 'cumulative': 14}, {'month': 4, 'enrolled': 6, 'cumulative': 20}, {'month': 5, 'enrolled': 3, 'cumulative': 23}, {'month': 6, 'enrolled': 5, 'cumulative': 28}] | ENROLLING | 30 | 30 | 100 | 1.7 | Dr. Emily Brown | Dr. Michelle Johnson
6265 | S0019 | JAPA-Health System | ST-2025-023 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 4, 'cumulative': 9}, {'month': 3, 'enrolled': 5, 'cumulative': 14}, {'month': 4, 'enrolled': 5, 'cumulative': 19}, {'month': 5, 'enrolled': 5, 'cumulative': 24}, {'month': 6, 'enrolled': 4, 'cumulative': 28}] | ENROLLING | 22 | 22 | 100 | 3.1 | Dr. Emily Miller | Dr. Amanda Garcia
6266 | S0020 | JAPA-General Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 6, 'cumulative': 10}, {'month': 3, 'enrolled': 5, 'cumulative': 15}, {'month': 4, 'enrolled': 5, 'cumulative': 20}, {'month': 5, 'enrolled': 5, 'cumulative': 25}, {'month': 6, 'enrolled': 5, 'cumulative': 30}] | ON_HOLD | 26 | 26 | 100 | 2.6 | Dr. Christopher Thompson | Dr. Nicole Brown
6267 | S0021 | JAPA-University Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 6, 'cumulative': 6}, {'month': 2, 'enrolled': 4, 'cumulative': 10}, {'month': 3, 'enrolled': 4, 'cumulative': 14}, {'month': 4, 'enrolled': 7, 'cumulative': 21}, {'month': 5, 'enrolled': 4, 'cumulative': 25}, {'month': 6, 'enrolled': 6, 'cumulative': 31}] | SCREENING | 38 | 35 | 92.1 | 2.2 | Dr. Thomas Jones | Dr. Emily Miller
6268 | S0022 | JAPA-Clinical Center | ST-2025-023 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 2, 'cumulative': 6}, {'month': 3, 'enrolled': 5, 'cumulative': 11}, {'month': 4, 'enrolled': 5, 'cumulative': 16}, {'month': 5, 'enrolled': 1, 'cumulative': 17}, {'month': 6, 'enrolled': 2, 'cumulative': 19}] | ENROLLING | 36 | 19 | 52.8 | 1.6 | Dr. Lisa Martin | Dr. Thomas Anderson
6269 | S0023 | MEXI-General Hospital | ST-2025-023 | [{'month': 1, 'enrolled': 28, 'cumulative': 28}, {'month': 2, 'enrolled': 28, 'cumulative': 56}, {'month': 3, 'enrolled': 25, 'cumulative': 81}, {'month': 4, 'enrolled': 26, 'cumulative': 107}, {'month': 5, 'enrolled': 29, 'cumulative': 136}, {'month': 6, 'enrolled': 27, 'cumulative': 163}] | ENROLLING | 162 | 162 | 100 | 18 | Dr. Daniel White | Dr. Lisa Jones
6270 | S0024 | MEXI-Cancer Center | ST-2025-023 | [{'month': 1, 'enrolled': 10, 'cumulative': 10}, {'month': 2, 'enrolled': 14, 'cumulative': 24}, {'month': 3, 'enrolled': 13, 'cumulative': 37}, {'month': 4, 'enrolled': 10, 'cumulative': 47}, {'month': 5, 'enrolled': 10, 'cumulative': 57}, {'month': 6, 'enrolled': 12, 'cumulative': 69}] | SCREENING | 93 | 75 | 80.6 | 6.2 | Dr. Stephanie Harris | Dr. Daniel Thomas
6271 | S0025 | MEXI-Medical Center | ST-2025-023 | [{'month': 1, 'enrolled': 22, 'cumulative': 22}, {'month': 2, 'enrolled': 20, 'cumulative': 42}, {'month': 3, 'enrolled': 18, 'cumulative': 60}, {'month': 4, 'enrolled': 22, 'cumulative': 82}, {'month': 5, 'enrolled': 19, 'cumulative': 101}, {'month': 6, 'enrolled': 18, 'cumulative': 119}] | ENROLLING | 139 | 124 | 89.2 | 9.5 | Dr. James Thompson | Dr. Michael Williams
6272 | S0001 | UNIT-Research Institute | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 3, 'cumulative': 5}, {'month': 4, 'enrolled': 3, 'cumulative': 8}, {'month': 5, 'enrolled': 2, 'cumulative': 10}, {'month': 6, 'enrolled': 0, 'cumulative': 10}] | ENROLLING | 13 | 13 | 100 | 1.1 | Dr. Thomas Jones | Dr. Stephanie Taylor
6273 | S0002 | UNIT-Research Institute | ST-2025-024 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ENROLLING | 6 | 3 | 50 | 0.2 | Dr. Sarah Miller | Dr. Lisa Davis
6274 | S0003 | UNIT-Clinical Center | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 5 | 5 | 100 | 0.4 | Dr. Charles Brown | Dr. William Johnson
6275 | S0004 | UNIT-Research Institute | ST-2025-024 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 10 | 7 | 70 | 0.5 | Dr. Stephanie Williams | Dr. Nicole Smith
6276 | S0005 | UNIT-Clinical Center | ST-2025-024 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | 5 | 5 | 100 | 0.3 | Dr. James Wilson | Dr. Michelle Brown
6277 | S0006 | UNIT-University Hospital | ST-2025-024 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 3, 'cumulative': 7}, {'month': 4, 'enrolled': 3, 'cumulative': 10}, {'month': 5, 'enrolled': 1, 'cumulative': 11}, {'month': 6, 'enrolled': 1, 'cumulative': 12}] | SCREENING | 12 | 18 | 150 | 1 | Dr. Robert Anderson | Dr. Stephanie Harris
6278 | S0007 | MEXI-Medical Center | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 3, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | SCREENING | 7 | 7 | 100 | 0.5 | Dr. Jessica Garcia | Dr. James Johnson
6279 | S0008 | MEXI-Clinical Center | ST-2025-024 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 7 | 6 | 85.7 | 0.6 | Dr. William Jackson | Dr. Amanda Miller
6280 | S0009 | MEXI-Health System | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ENROLLING | 4 | 3 | 75 | 0.2 | Dr. Sarah Garcia | Dr. Michelle Williams
6281 | S0010 | MEXI-Research Institute | ST-2025-024 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 2, 'cumulative': 5}, {'month': 3, 'enrolled': 0, 'cumulative': 5}, {'month': 4, 'enrolled': 2, 'cumulative': 7}, {'month': 5, 'enrolled': 3, 'cumulative': 10}, {'month': 6, 'enrolled': 0, 'cumulative': 10}] | ENROLLING | 10 | 10 | 100 | 1.4 | Dr. Emily Jones | Dr. Michelle Wilson
6282 | S0011 | MEXI-Clinical Center | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 6 | 5 | 83.3 | 0.6 | Dr. Daniel Taylor | Dr. Thomas Wilson
6283 | S0012 | MEXI-Cancer Center | ST-2025-024 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 3, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 4, 'cumulative': 10}] | ENROLLING | 10 | 13 | 130 | 0.8 | Dr. William Davis | Dr. Thomas Taylor
6284 | S0013 | SWED-Medical Center | ST-2025-024 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 3, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 12 | 8 | 66.7 | 1.3 | Dr. Jennifer White | Dr. Michelle Martin
6285 | S0014 | SWED-Cancer Center | ST-2025-024 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 4, 'cumulative': 7}, {'month': 3, 'enrolled': 4, 'cumulative': 11}, {'month': 4, 'enrolled': 1, 'cumulative': 12}, {'month': 5, 'enrolled': 5, 'cumulative': 17}, {'month': 6, 'enrolled': 4, 'cumulative': 21}] | CLOSED | 20 | 20 | 100 | 1.7 | Dr. Michael Williams | Dr. Michelle Smith
6286 | S0015 | SWED-Cancer Center | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | ON_HOLD | 11 | 5 | 45.5 | 0.3 | Dr. Emily Thomas | Dr. Charles Thomas
6287 | S0016 | SWED-Clinical Center | ST-2025-024 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | CLOSED | 19 | 0 | 0 | 0 | Dr. James Brown | Dr. Christopher Thomas
6288 | S0017 | SWIT-Medical Center | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 20 | 0 | 0 | 0 | Dr. Amanda Miller | Dr. Michael Anderson
6289 | S0018 | SWIT-Cancer Center | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 13 | 0 | 0 | 0 | Dr. Lisa Martin | Dr. Amanda Johnson
6290 | S0019 | JAPA-Cancer Center | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 7 | 0 | 0 | 0 | Dr. Daniel Martin | Dr. Jennifer Moore
6291 | S0020 | JAPA-University Hospital | ST-2025-024 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 10 | 0 | 0 | 0 | Dr. Jennifer Williams | Dr. Robert Williams
6292 | S0021 | JAPA-University Hospital | ST-2025-024 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 2, 'cumulative': 2}] | CLOSED | 8 | 0 | 0 | 0 | Dr. Lisa Thompson | Dr. William Miller
6293 | S0022 | JAPA-Cancer Center | ST-2025-024 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 2, 'cumulative': 7}] | SCREENING | 5 | 0 | 0 | 0 | Dr. Michelle Wilson | Dr. Michelle Harris
6294 | S0001 | CANA-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -35 | -35 | 100 | -5.8 | Dr. David Moore | Dr. Jessica Jones
6295 | S0002 | CANA-Research Institute | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ENROLLING | 3 | 3 | 100 | 0.3 | Dr. William Jones | Dr. Daniel Martin
6296 | S0003 | CANA-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. Nicole Williams | Dr. Jennifer Thompson
6297 | S0004 | UNIT-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | -1 | -1 | 100 | -0.1 | Dr. Amanda Thompson | Dr. Nicole Martin
6298 | S0005 | UNIT-Clinical Center | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Charles Johnson | Dr. David Davis
6299 | S0006 | UNIT-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ENROLLING | 3 | 4 | 133.3 | 0.3 | Dr. Charles Miller | Dr. Jessica White
6300 | S0007 | SPAI-Clinical Center | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | -4 | -4 | 100 | -0.3 | Dr. Lisa Johnson | Dr. Christopher Thompson
6301 | S0008 | SPAI-Health System | ST-2025-025 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. Christopher Harris | Dr. Stephanie White
6302 | S0009 | SPAI-Research Institute | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. Thomas Wilson | Dr. Charles Smith
6303 | S0010 | SPAI-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 3 | 4 | 133.3 | 0.3 | Dr. William Williams | Dr. Amanda Williams
6304 | S0011 | SWED-Research Institute | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | -7 | -7 | 100 | -0.8 | Dr. Thomas Wilson | Dr. Jessica Wilson
6305 | S0012 | SWED-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 3 | 2 | 66.7 | 0.1 | Dr. Robert Moore | Dr. William Smith
6306 | S0013 | SWED-Cancer Center | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. Amanda Jackson | Dr. Charles Smith
6307 | S0014 | SWED-Clinical Center | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.1 | Dr. Robert Jackson | Dr. Lisa Davis
6308 | S0015 | SWED-General Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 3 | 4 | 133.3 | 0.2 | Dr. Nicole Davis | Dr. Daniel Moore
6309 | S0016 | NETH-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | -1 | -1 | 100 | -0.1 | Dr. Stephanie Miller | Dr. Christopher Harris
6310 | S0017 | NETH-Cancer Center | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Amanda Jones | Dr. Robert Anderson
6311 | S0018 | NETH-General Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 2 | 66.7 | 0.3 | Dr. Amanda Taylor | Dr. Lisa White
6312 | S0019 | TAIW-Medical Center | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | -4 | -4 | 100 | -0.5 | Dr. Thomas Jackson | Dr. Charles Miller
6313 | S0020 | TAIW-Clinical Center | ST-2025-025 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.3 | Dr. Charles Miller | Dr. Nicole Brown
6314 | S0021 | TAIW-Research Institute | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | ON_HOLD | 3 | 2 | 66.7 | 0.1 | Dr. Jessica Williams | Dr. Jennifer Brown
6315 | S0022 | TAIW-General Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 3 | 3 | 100 | 0.2 | Dr. Sarah Martin | Dr. James Garcia
6316 | S0023 | AUST-Clinical Center | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | -10 | -10 | 100 | -1.2 | Dr. Robert Moore | Dr. Stephanie Martin
6317 | S0024 | AUST-General Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 2 | 66.7 | 0.3 | Dr. David Jones | Dr. David Anderson
6318 | S0025 | AUST-Clinical Center | ST-2025-025 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | SCREENING | 3 | 1 | 33.3 | 0.1 | Dr. Nicole Garcia | Dr. Jessica Miller
6319 | S0026 | AUST-Health System | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Christopher Wilson | Dr. David Smith
6320 | S0027 | AUST-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. Charles Davis | Dr. Daniel Taylor
6321 | S0028 | AUST-Health System | ST-2025-025 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 3, 'cumulative': 7}, {'month': 4, 'enrolled': 0, 'cumulative': 7}, {'month': 5, 'enrolled': 3, 'cumulative': 10}, {'month': 6, 'enrolled': 3, 'cumulative': 13}] | ENROLLING | 3 | 7 | 233.3 | 0.5 | Dr. Christopher Johnson | Dr. Michael Anderson
6322 | S0029 | CHIL-Cancer Center | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 2 | 1 | 50 | 0.1 | Dr. Charles Garcia | Dr. Stephanie Davis
6323 | S0030 | CHIL-University Hospital | ST-2025-025 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 3, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 3 | 6 | 200 | 0.4 | Dr. Stephanie Harris | Dr. Charles Garcia
6324 | S0001 | MEXI-University Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 0, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 3, 'cumulative': 7}, {'month': 6, 'enrolled': 3, 'cumulative': 10}] | ON_HOLD | 10 | 10 | 100 | 1 | Dr. David Jackson | Dr. Jessica Smith
6325 | S0002 | MEXI-University Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 4 | 2 | 50 | 0.2 | Dr. Emily Williams | Dr. Stephanie Thompson
6326 | S0003 | MEXI-Clinical Center | ST-2025-026 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 2, 'cumulative': 6}, {'month': 4, 'enrolled': 0, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Stephanie Garcia | Dr. Jennifer Thomas
6327 | S0004 | MEXI-University Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. David Martin | Dr. Jennifer Thompson
6328 | S0005 | MEXI-Medical Center | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. David Garcia | Dr. David Johnson
6329 | S0006 | MEXI-General Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ENROLLING | 5 | 4 | 80 | 0.5 | Dr. William White | Dr. Christopher Brown
6330 | S0007 | CANA-Research Institute | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 4, 'cumulative': 6}, {'month': 4, 'enrolled': 3, 'cumulative': 9}, {'month': 5, 'enrolled': 1, 'cumulative': 10}, {'month': 6, 'enrolled': 3, 'cumulative': 13}] | SCREENING | 21 | 17 | 81 | 2.8 | Dr. Lisa Martin | Dr. Nicole Brown
6331 | S0008 | CANA-Medical Center | ST-2025-026 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 9 | 6 | 66.7 | 1 | Dr. James Johnson | Dr. Emily Miller
6332 | S0009 | CANA-Health System | ST-2025-026 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 3, 'cumulative': 5}, {'month': 5, 'enrolled': 3, 'cumulative': 8}, {'month': 6, 'enrolled': 2, 'cumulative': 10}] | ENROLLING | 11 | 17 | 154.5 | 0.9 | Dr. Charles Thompson | Dr. William Martin
6333 | S0010 | SWIT-Research Institute | ST-2025-026 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 5, 'cumulative': 8}, {'month': 4, 'enrolled': 4, 'cumulative': 12}, {'month': 5, 'enrolled': 3, 'cumulative': 15}, {'month': 6, 'enrolled': 4, 'cumulative': 19}] | ON_HOLD | 24 | 20 | 83.3 | 1.2 | Dr. Thomas Davis | Dr. Amanda Jackson
6334 | S0011 | SWIT-Clinical Center | ST-2025-026 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 2, 'cumulative': 5}, {'month': 4, 'enrolled': 2, 'cumulative': 7}, {'month': 5, 'enrolled': 0, 'cumulative': 7}, {'month': 6, 'enrolled': 3, 'cumulative': 10}] | SCREENING | 19 | 10 | 52.6 | 0.7 | Dr. Amanda Taylor | Dr. Emily Smith
6335 | S0012 | SWED-Cancer Center | ST-2025-026 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 3, 'cumulative': 5}, {'month': 5, 'enrolled': 2, 'cumulative': 7}, {'month': 6, 'enrolled': 0, 'cumulative': 7}] | SCREENING | 9 | 8 | 88.9 | 0.9 | Dr. Christopher Martin | Dr. Daniel White
6336 | S0013 | SWED-General Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 3, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 2, 'cumulative': 7}] | ENROLLING | 7 | 7 | 100 | 0.8 | Dr. Thomas Smith | Dr. Amanda Johnson
6337 | S0014 | SWED-Cancer Center | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 7 | 5 | 71.4 | 0.3 | Dr. Christopher Davis | Dr. Nicole Jackson
6338 | S0015 | SWED-General Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | ENROLLING | 8 | 8 | 100 | 0.5 | Dr. Amanda White | Dr. Nicole Brown
6339 | S0016 | SWED-General Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 4 | 5 | 125 | 0.4 | Dr. David Jones | Dr. Daniel Thompson
6340 | S0017 | SING-Cancer Center | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 3, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | SCREENING | 13 | 13 | 100 | 1 | Dr. Christopher Brown | Dr. Nicole Moore
6341 | S0018 | SING-University Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 21 | 4 | 19 | 0.4 | Dr. Jennifer Williams | Dr. Emily White
6342 | S0019 | SING-General Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | SCREENING | 12 | 0 | 0 | 0 | Dr. Thomas Jackson | Dr. William Davis
6343 | S0020 | NEW-Clinical Center | ST-2025-026 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 18 | 0 | 0 | 0 | Dr. Thomas Davis | Dr. Michael Taylor
6344 | S0021 | NEW-Clinical Center | ST-2025-026 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 15 | 0 | 0 | 0 | Dr. Charles Moore | Dr. Stephanie Davis
6345 | S0022 | NEW-University Hospital | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | SCREENING | 19 | 0 | 0 | 0 | Dr. Jessica Williams | Dr. Emily Williams
6346 | S0023 | NEW-Research Institute | ST-2025-026 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | CLOSED | 15 | 0 | 0 | 0 | Dr. David Brown | Dr. Amanda Jones
6347 | S0001 | MEXI-Medical Center | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 2, 'cumulative': 2}] | SCREENING | 2 | 1 | 50 | 0.1 | Dr. Robert Jones | Dr. Robert Jackson
6348 | S0002 | MEXI-Health System | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Sarah Thomas | Dr. Lisa White
6349 | S0003 | MEXI-General Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. Christopher Thomas | Dr. Christopher Thompson
6350 | S0004 | MEXI-Research Institute | ST-2025-027 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Daniel Davis | Dr. Jessica Williams
6351 | S0005 | MEXI-Research Institute | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Michael Williams | Dr. Michael Davis
6352 | S0006 | MEXI-Medical Center | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 3, 'cumulative': 3}, {'month': 3, 'enrolled': 3, 'cumulative': 6}, {'month': 4, 'enrolled': 1, 'cumulative': 7}, {'month': 5, 'enrolled': 1, 'cumulative': 8}, {'month': 6, 'enrolled': 2, 'cumulative': 10}] | SCREENING | 3 | 7 | 233.3 | 0.9 | Dr. Sarah Williams | Dr. Jessica Moore
6353 | S0007 | CANA-Clinical Center | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 4 | 2 | 50 | 0.1 | Dr. Robert Martin | Dr. Nicole Thompson
6354 | S0008 | CANA-General Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 4 | 133.3 | 0.2 | Dr. Emily Jackson | Dr. James Miller
6355 | S0009 | UNIT-University Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | CLOSED | 3 | 3 | 100 | 0.2 | Dr. Daniel Johnson | Dr. Christopher Garcia
6356 | S0010 | UNIT-General Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | CLOSED | 3 | 3 | 100 | 0.2 | Dr. Lisa Garcia | Dr. Michael Thomas
6357 | S0011 | UNIT-Cancer Center | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Amanda Johnson | Dr. Stephanie Martin
6358 | S0012 | SWIT-General Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ON_HOLD | 7 | 4 | 57.1 | 0.4 | Dr. Emily Anderson | Dr. Jessica Martin
6359 | S0013 | SWIT-Research Institute | ST-2025-027 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 3, 'cumulative': 5}, {'month': 3, 'enrolled': 2, 'cumulative': 7}, {'month': 4, 'enrolled': 3, 'cumulative': 10}, {'month': 5, 'enrolled': 2, 'cumulative': 12}, {'month': 6, 'enrolled': 2, 'cumulative': 14}] | ENROLLING | 5 | 7 | 140 | 0.7 | Dr. James Jackson | Dr. David Anderson
6360 | S0014 | SPAI-Clinical Center | ST-2025-027 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 2 | 2 | 100 | 0.2 | Dr. Amanda Brown | Dr. James Thomas
6361 | S0015 | SPAI-General Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | ON_HOLD | 3 | 3 | 100 | 0.4 | Dr. Amanda Smith | Dr. Emily White
6362 | S0016 | SPAI-Clinical Center | ST-2025-027 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 3 | 1 | 33.3 | 0.1 | Dr. Daniel Thompson | Dr. Robert White
6363 | S0017 | SPAI-Medical Center | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 3 | 1 | 33.3 | 0.1 | Dr. Robert Wilson | Dr. Lisa Martin
6364 | S0018 | SPAI-Clinical Center | ST-2025-027 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 3 | 3 | 100 | 0.3 | Dr. Amanda White | Dr. Jennifer Moore
6365 | S0019 | UNIT-Medical Center | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | ON_HOLD | -3 | -3 | 100 | -0.4 | Dr. Stephanie Taylor | Dr. Sarah Garcia
6366 | S0020 | UNIT-General Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. William Brown | Dr. Stephanie Martin
6367 | S0021 | UNIT-Health System | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | CLOSED | 3 | 3 | 100 | 0.2 | Dr. Robert Taylor | Dr. Charles Thompson
6368 | S0022 | UNIT-General Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | 3 | 2 | 66.7 | 0.1 | Dr. Robert Brown | Dr. Emily Smith
6369 | S0023 | UNIT-University Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. Daniel Smith | Dr. Lisa Johnson
6370 | S0024 | UNIT-General Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. James White | Dr. Nicole Anderson
6371 | S0025 | INDI-Health System | ST-2025-027 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | CLOSED | 6 | 5 | 83.3 | 0.6 | Dr. Daniel Garcia | Dr. Lisa Wilson
6372 | S0026 | INDI-Cancer Center | ST-2025-027 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 4 | 2 | 50 | 0.3 | Dr. Lisa White | Dr. David Martin
6373 | S0027 | SING-University Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | -8 | -8 | 100 | -1 | Dr. James Miller | Dr. Michael Johnson
6374 | S0028 | SING-Clinical Center | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Jessica Davis | Dr. Lisa Taylor
6375 | S0029 | SING-Clinical Center | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Daniel White | Dr. Sarah Anderson
6376 | S0030 | SING-Medical Center | ST-2025-027 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. William Thomas | Dr. Stephanie Davis
6377 | S0031 | SING-Research Institute | ST-2025-027 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 1 | 33.3 | 0.2 | Dr. Sarah Smith | Dr. Sarah Taylor
6378 | S0032 | SING-University Hospital | ST-2025-027 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 5, 'cumulative': 6}, {'month': 3, 'enrolled': 1, 'cumulative': 7}, {'month': 4, 'enrolled': 4, 'cumulative': 11}, {'month': 5, 'enrolled': 4, 'cumulative': 15}, {'month': 6, 'enrolled': 1, 'cumulative': 16}] | ENROLLING | 3 | 18 | 600 | 1.8 | Dr. William Brown | Dr. Stephanie Garcia
6379 | S0001 | CANA-General Hospital | ST-2025-028 | [{'month': 1, 'enrolled': 872, 'cumulative': 872}, {'month': 2, 'enrolled': 870, 'cumulative': 1742}, {'month': 3, 'enrolled': 870, 'cumulative': 2612}, {'month': 4, 'enrolled': 870, 'cumulative': 3482}, {'month': 5, 'enrolled': 869, 'cumulative': 4351}, {'month': 6, 'enrolled': 870, 'cumulative': 5221}] | ON_HOLD | 10148 | 5228 | 51.5 | 326.8 | Dr. Jessica Thomas | Dr. Emily Wilson
6380 | S0002 | CANA-Clinical Center | ST-2025-028 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 10883 | 0 | 0 | 0 | Dr. William Williams | Dr. James Jones
6381 | S0003 | DENM-Medical Center | ST-2025-028 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 11480 | 0 | 0 | 0 | Dr. William Jones | Dr. Michael Taylor
6382 | S0004 | DENM-University Hospital | ST-2025-028 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | 5807 | 0 | 0 | 0 | Dr. Amanda Taylor | Dr. Nicole White
6383 | S0005 | DENM-Clinical Center | ST-2025-028 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 5818 | 0 | 0 | 0 | Dr. Thomas Jones | Dr. Lisa Jackson
6384 | S0006 | DENM-Clinical Center | ST-2025-028 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 8503 | 0 | 0 | 0 | Dr. Michelle Moore | Dr. Nicole Moore
6385 | S0007 | AUST-Cancer Center | ST-2025-028 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 6775 | 0 | 0 | 0 | Dr. Lisa Williams | Dr. Lisa Thomas
6386 | S0008 | AUST-Medical Center | ST-2025-028 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 4772 | 0 | 0 | 0 | Dr. Amanda Moore | Dr. Nicole Jones
6387 | S0009 | AUST-Medical Center | ST-2025-028 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 3814 | 0 | 0 | 0 | Dr. Amanda Jones | Dr. Jessica Harris
6388 | S0001 | MEXI-Cancer Center | ST-2025-029 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 3, 'cumulative': 7}, {'month': 3, 'enrolled': 0, 'cumulative': 7}, {'month': 4, 'enrolled': 1, 'cumulative': 8}, {'month': 5, 'enrolled': 3, 'cumulative': 11}, {'month': 6, 'enrolled': 0, 'cumulative': 11}] | SCREENING | 18 | 16 | 88.9 | 2.3 | Dr. Emily Harris | Dr. Thomas Garcia
6389 | S0002 | MEXI-Research Institute | ST-2025-029 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 2, 'cumulative': 5}, {'month': 4, 'enrolled': 2, 'cumulative': 7}, {'month': 5, 'enrolled': 0, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | ENROLLING | 8 | 8 | 100 | 1 | Dr. William Thomas | Dr. Amanda Williams
6390 | S0003 | MEXI-Medical Center | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 3, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | ON_HOLD | 17 | 11 | 64.7 | 1.4 | Dr. Christopher Wilson | Dr. Nicole Wilson
6391 | S0004 | UNIT-Clinical Center | ST-2025-029 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 5 | 4 | 80 | 0.4 | Dr. Thomas Thomas | Dr. Michael White
6392 | S0005 | UNIT-Health System | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. Sarah Johnson | Dr. Lisa Moore
6393 | S0006 | UNIT-Medical Center | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Jessica Jackson | Dr. Jennifer Jackson
6394 | S0007 | UNIT-Cancer Center | ST-2025-029 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | SCREENING | 3 | 2 | 66.7 | 0.3 | Dr. Charles Harris | Dr. Michael Thomas
6395 | S0008 | UNIT-Clinical Center | ST-2025-029 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 3 | 3 | 100 | 0.2 | Dr. Michelle Harris | Dr. Emily Williams
6396 | S0009 | UNIT-University Hospital | ST-2025-029 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Charles White | Dr. David Jackson
6397 | S0010 | NETH-Clinical Center | ST-2025-029 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 0, 'cumulative': 3}, {'month': 3, 'enrolled': 3, 'cumulative': 6}, {'month': 4, 'enrolled': 2, 'cumulative': 8}, {'month': 5, 'enrolled': 1, 'cumulative': 9}, {'month': 6, 'enrolled': 3, 'cumulative': 12}] | ON_HOLD | 7 | 6 | 85.7 | 0.8 | Dr. David Taylor | Dr. Sarah Jackson
6398 | S0011 | NETH-Medical Center | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 5 | 3 | 60 | 0.2 | Dr. Stephanie Martin | Dr. David Johnson
6399 | S0012 | NETH-University Hospital | ST-2025-029 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 9 | 5 | 55.6 | 0.8 | Dr. Stephanie Wilson | Dr. William Garcia
6400 | S0013 | NETH-Medical Center | ST-2025-029 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ENROLLING | 6 | 4 | 66.7 | 0.5 | Dr. William Jackson | Dr. Michael Anderson
6401 | S0014 | NETH-Cancer Center | ST-2025-029 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 2, 'cumulative': 5}, {'month': 3, 'enrolled': 1, 'cumulative': 6}, {'month': 4, 'enrolled': 1, 'cumulative': 7}, {'month': 5, 'enrolled': 1, 'cumulative': 8}, {'month': 6, 'enrolled': 2, 'cumulative': 10}] | SCREENING | 7 | 12 | 171.4 | 0.7 | Dr. Stephanie Thompson | Dr. David Wilson
6402 | S0015 | BELG-Clinical Center | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 3, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ENROLLING | 6 | 6 | 100 | 0.5 | Dr. Michelle Garcia | Dr. Stephanie Thomas
6403 | S0016 | BELG-General Hospital | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 4 | 3 | 75 | 0.2 | Dr. James Moore | Dr. David Williams
6404 | S0017 | BELG-General Hospital | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 3, 'cumulative': 5}, {'month': 4, 'enrolled': 0, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 10 | 7 | 70 | 0.4 | Dr. Robert Taylor | Dr. Thomas Smith
6405 | S0018 | BELG-University Hospital | ST-2025-029 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ENROLLING | 7 | 11 | 157.1 | 0.8 | Dr. Nicole Taylor | Dr. Emily White
6406 | S0019 | AUST-General Hospital | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 6 | 5 | 83.3 | 0.6 | Dr. Michelle Garcia | Dr. Charles Miller
6407 | S0020 | AUST-Research Institute | ST-2025-029 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | SCREENING | 6 | 4 | 66.7 | 0.4 | Dr. James Thomas | Dr. Amanda Smith
6408 | S0021 | AUST-Research Institute | ST-2025-029 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 8 | 0 | 0 | 0 | Dr. Emily Martin | Dr. Christopher White
6409 | S0022 | AUST-Clinical Center | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 7 | 0 | 0 | 0 | Dr. Michelle White | Dr. Daniel Taylor
6410 | S0023 | AUST-Medical Center | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 2, 'cumulative': 7}] | ON_HOLD | 7 | 0 | 0 | 0 | Dr. Stephanie Thomas | Dr. Jennifer Moore
6411 | S0024 | INDI-Clinical Center | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 16 | 0 | 0 | 0 | Dr. Emily Williams | Dr. Emily Williams
6412 | S0025 | INDI-General Hospital | ST-2025-029 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | CLOSED | 14 | 0 | 0 | 0 | Dr. Stephanie Brown | Dr. Nicole Moore
6413 | S0026 | INDI-Medical Center | ST-2025-029 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | 12 | 0 | 0 | 0 | Dr. Daniel Johnson | Dr. Jessica White
6414 | S0001 | UNIT-Health System | ST-2025-030 | [{'month': 1, 'enrolled': 9, 'cumulative': 9}, {'month': 2, 'enrolled': 11, 'cumulative': 20}, {'month': 3, 'enrolled': 7, 'cumulative': 27}, {'month': 4, 'enrolled': 7, 'cumulative': 34}, {'month': 5, 'enrolled': 10, 'cumulative': 44}, {'month': 6, 'enrolled': 9, 'cumulative': 53}] | SCREENING | 73 | 57 | 78.1 | 9.5 | Dr. Jessica Harris | Dr. Nicole Brown
6415 | S0002 | UNIT-Cancer Center | ST-2025-030 | [{'month': 1, 'enrolled': 11, 'cumulative': 11}, {'month': 2, 'enrolled': 14, 'cumulative': 25}, {'month': 3, 'enrolled': 13, 'cumulative': 38}, {'month': 4, 'enrolled': 11, 'cumulative': 49}, {'month': 5, 'enrolled': 11, 'cumulative': 60}, {'month': 6, 'enrolled': 13, 'cumulative': 73}] | ON_HOLD | 85 | 81 | 95.3 | 7.4 | Dr. Emily Smith | Dr. Lisa Johnson
6416 | S0003 | CANA-Medical Center | ST-2025-030 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 4, 'cumulative': 7}, {'month': 3, 'enrolled': 4, 'cumulative': 11}, {'month': 4, 'enrolled': 6, 'cumulative': 17}, {'month': 5, 'enrolled': 6, 'cumulative': 23}, {'month': 6, 'enrolled': 3, 'cumulative': 26}] | ENROLLING | 37 | 24 | 64.9 | 1.4 | Dr. William Johnson | Dr. Emily Johnson
6417 | S0004 | CANA-Research Institute | ST-2025-030 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 3, 'cumulative': 7}, {'month': 6, 'enrolled': 4, 'cumulative': 11}] | ENROLLING | 16 | 16 | 100 | 2.3 | Dr. Thomas Jackson | Dr. William Garcia
6418 | S0005 | CANA-University Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 6, 'cumulative': 10}, {'month': 3, 'enrolled': 5, 'cumulative': 15}, {'month': 4, 'enrolled': 4, 'cumulative': 19}, {'month': 5, 'enrolled': 7, 'cumulative': 26}, {'month': 6, 'enrolled': 6, 'cumulative': 32}] | ENROLLING | 39 | 39 | 100 | 2.6 | Dr. Emily Jones | Dr. Thomas Jones
6419 | S0006 | CANA-Cancer Center | ST-2025-030 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 6, 'cumulative': 10}, {'month': 3, 'enrolled': 6, 'cumulative': 16}, {'month': 4, 'enrolled': 6, 'cumulative': 22}, {'month': 5, 'enrolled': 3, 'cumulative': 25}, {'month': 6, 'enrolled': 5, 'cumulative': 30}] | ENROLLING | 35 | 35 | 100 | 2.3 | Dr. Christopher Brown | Dr. Daniel Thompson
6420 | S0007 | CANA-University Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 6, 'cumulative': 10}, {'month': 3, 'enrolled': 4, 'cumulative': 14}, {'month': 4, 'enrolled': 3, 'cumulative': 17}, {'month': 5, 'enrolled': 6, 'cumulative': 23}, {'month': 6, 'enrolled': 5, 'cumulative': 28}] | ENROLLING | 32 | 29 | 90.6 | 1.9 | Dr. Nicole Wilson | Dr. Thomas Martin
6421 | S0008 | CANA-University Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 7, 'cumulative': 12}, {'month': 3, 'enrolled': 4, 'cumulative': 16}, {'month': 4, 'enrolled': 4, 'cumulative': 20}, {'month': 5, 'enrolled': 5, 'cumulative': 25}, {'month': 6, 'enrolled': 4, 'cumulative': 29}] | ENROLLING | 18 | 34 | 188.9 | 4.9 | Dr. Jessica Williams | Dr. Amanda Moore
6422 | S0009 | MEXI-Clinical Center | ST-2025-030 | [{'month': 1, 'enrolled': 8, 'cumulative': 8}, {'month': 2, 'enrolled': 9, 'cumulative': 17}, {'month': 3, 'enrolled': 6, 'cumulative': 23}, {'month': 4, 'enrolled': 7, 'cumulative': 30}, {'month': 5, 'enrolled': 7, 'cumulative': 37}, {'month': 6, 'enrolled': 5, 'cumulative': 42}] | ON_HOLD | 47 | 42 | 89.4 | 6 | Dr. David Thompson | Dr. Daniel Taylor
6423 | S0010 | MEXI-Cancer Center | ST-2025-030 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 4, 'cumulative': 6}, {'month': 3, 'enrolled': 3, 'cumulative': 9}, {'month': 4, 'enrolled': 4, 'cumulative': 13}, {'month': 5, 'enrolled': 1, 'cumulative': 14}, {'month': 6, 'enrolled': 3, 'cumulative': 17}] | CLOSED | 24 | 17 | 70.8 | 1.7 | Dr. Christopher Jones | Dr. Daniel Brown
6424 | S0011 | MEXI-University Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 7, 'cumulative': 7}, {'month': 2, 'enrolled': 4, 'cumulative': 11}, {'month': 3, 'enrolled': 5, 'cumulative': 16}, {'month': 4, 'enrolled': 8, 'cumulative': 24}, {'month': 5, 'enrolled': 7, 'cumulative': 31}, {'month': 6, 'enrolled': 6, 'cumulative': 37}] | ON_HOLD | 37 | 37 | 100 | 4.1 | Dr. Charles Harris | Dr. Daniel Miller
6425 | S0012 | MEXI-Cancer Center | ST-2025-030 | [{'month': 1, 'enrolled': 8, 'cumulative': 8}, {'month': 2, 'enrolled': 6, 'cumulative': 14}, {'month': 3, 'enrolled': 7, 'cumulative': 21}, {'month': 4, 'enrolled': 6, 'cumulative': 27}, {'month': 5, 'enrolled': 7, 'cumulative': 34}, {'month': 6, 'enrolled': 7, 'cumulative': 41}] | SCREENING | 44 | 38 | 86.4 | 3.2 | Dr. Michael Wilson | Dr. Stephanie Garcia
6426 | S0013 | MEXI-General Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 5, 'cumulative': 10}, {'month': 3, 'enrolled': 5, 'cumulative': 15}, {'month': 4, 'enrolled': 2, 'cumulative': 17}, {'month': 5, 'enrolled': 6, 'cumulative': 23}, {'month': 6, 'enrolled': 2, 'cumulative': 25}] | CLOSED | 39 | 29 | 74.4 | 2.9 | Dr. Emily Jones | Dr. Christopher Brown
6427 | S0014 | MEXI-General Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 19 | 0 | 0 | 0 | Dr. James Harris | Dr. Jennifer Wilson
6428 | S0015 | POLA-Research Institute | ST-2025-030 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 5, 'cumulative': 10}, {'month': 3, 'enrolled': 3, 'cumulative': 13}, {'month': 4, 'enrolled': 2, 'cumulative': 15}, {'month': 5, 'enrolled': 5, 'cumulative': 20}, {'month': 6, 'enrolled': 5, 'cumulative': 25}] | SCREENING | 21 | 18 | 85.7 | 1.6 | Dr. Sarah Jackson | Dr. Stephanie Miller
6429 | S0016 | POLA-Research Institute | ST-2025-030 | [{'month': 1, 'enrolled': 6, 'cumulative': 6}, {'month': 2, 'enrolled': 4, 'cumulative': 10}, {'month': 3, 'enrolled': 2, 'cumulative': 12}, {'month': 4, 'enrolled': 5, 'cumulative': 17}, {'month': 5, 'enrolled': 3, 'cumulative': 20}, {'month': 6, 'enrolled': 5, 'cumulative': 25}] | ON_HOLD | 40 | 27 | 67.5 | 3 | Dr. Jennifer Wilson | Dr. Daniel Martin
6430 | S0017 | POLA-Health System | ST-2025-030 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 5, 'cumulative': 7}, {'month': 3, 'enrolled': 6, 'cumulative': 13}, {'month': 4, 'enrolled': 5, 'cumulative': 18}, {'month': 5, 'enrolled': 2, 'cumulative': 20}, {'month': 6, 'enrolled': 2, 'cumulative': 22}] | SCREENING | 33 | 29 | 87.9 | 2.4 | Dr. Sarah Davis | Dr. Emily Davis
6431 | S0018 | POLA-Medical Center | ST-2025-030 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 3, 'cumulative': 4}, {'month': 3, 'enrolled': 1, 'cumulative': 5}, {'month': 4, 'enrolled': 3, 'cumulative': 8}, {'month': 5, 'enrolled': 5, 'cumulative': 13}, {'month': 6, 'enrolled': 1, 'cumulative': 14}] | SCREENING | 26 | 23 | 88.5 | 3.8 | Dr. William Davis | Dr. Michael Moore
6432 | S0019 | POLA-Medical Center | ST-2025-030 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 7, 'cumulative': 12}, {'month': 3, 'enrolled': 6, 'cumulative': 18}, {'month': 4, 'enrolled': 5, 'cumulative': 23}, {'month': 5, 'enrolled': 3, 'cumulative': 26}, {'month': 6, 'enrolled': 3, 'cumulative': 29}] | SCREENING | 50 | 31 | 62 | 3.1 | Dr. Charles Jackson | Dr. Charles Brown
6433 | S0020 | POLA-University Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 3, 'cumulative': 6}, {'month': 3, 'enrolled': 0, 'cumulative': 6}, {'month': 4, 'enrolled': 0, 'cumulative': 6}, {'month': 5, 'enrolled': 3, 'cumulative': 9}, {'month': 6, 'enrolled': 0, 'cumulative': 9}] | CLOSED | 20 | 8 | 40 | 0.5 | Dr. William Martin | Dr. David Garcia
6434 | S0021 | SPAI-Medical Center | ST-2025-030 | [{'month': 1, 'enrolled': 14, 'cumulative': 14}, {'month': 2, 'enrolled': 13, 'cumulative': 27}, {'month': 3, 'enrolled': 11, 'cumulative': 38}, {'month': 4, 'enrolled': 11, 'cumulative': 49}, {'month': 5, 'enrolled': 11, 'cumulative': 60}, {'month': 6, 'enrolled': 12, 'cumulative': 72}] | ON_HOLD | 76 | 72 | 94.7 | 9 | Dr. Nicole Anderson | Dr. Lisa Garcia
6435 | S0022 | SPAI-Research Institute | ST-2025-030 | [{'month': 1, 'enrolled': 8, 'cumulative': 8}, {'month': 2, 'enrolled': 6, 'cumulative': 14}, {'month': 3, 'enrolled': 9, 'cumulative': 23}, {'month': 4, 'enrolled': 10, 'cumulative': 33}, {'month': 5, 'enrolled': 7, 'cumulative': 40}, {'month': 6, 'enrolled': 6, 'cumulative': 46}] | ENROLLING | 49 | 49 | 100 | 3.1 | Dr. Jennifer Garcia | Dr. Thomas Harris
6436 | S0023 | SPAI-University Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 3, 'cumulative': 6}, {'month': 3, 'enrolled': 4, 'cumulative': 10}, {'month': 4, 'enrolled': 7, 'cumulative': 17}, {'month': 5, 'enrolled': 3, 'cumulative': 20}, {'month': 6, 'enrolled': 7, 'cumulative': 27}] | ON_HOLD | 45 | 31 | 68.9 | 5.2 | Dr. Nicole White | Dr. Thomas Smith
6437 | S0024 | SWIT-Cancer Center | ST-2025-030 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 2, 'cumulative': 5}, {'month': 4, 'enrolled': 1, 'cumulative': 6}, {'month': 5, 'enrolled': 4, 'cumulative': 10}, {'month': 6, 'enrolled': 1, 'cumulative': 11}] | CLOSED | 21 | 21 | 100 | 3.5 | Dr. Jessica Davis | Dr. Daniel Thompson
6438 | S0025 | SWIT-University Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 4, 'cumulative': 9}, {'month': 3, 'enrolled': 4, 'cumulative': 13}, {'month': 4, 'enrolled': 1, 'cumulative': 14}, {'month': 5, 'enrolled': 1, 'cumulative': 15}, {'month': 6, 'enrolled': 3, 'cumulative': 18}] | SCREENING | 21 | 19 | 90.5 | 1.1 | Dr. Emily Brown | Dr. Jessica Taylor
6439 | S0026 | SWIT-Clinical Center | ST-2025-030 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 3, 'cumulative': 6}, {'month': 3, 'enrolled': 1, 'cumulative': 7}, {'month': 4, 'enrolled': 1, 'cumulative': 8}, {'month': 5, 'enrolled': 4, 'cumulative': 12}, {'month': 6, 'enrolled': 2, 'cumulative': 14}] | CLOSED | 15 | 13 | 86.7 | 1 | Dr. Amanda Moore | Dr. William Martin
6440 | S0027 | SWIT-Research Institute | ST-2025-030 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 4, 'cumulative': 9}, {'month': 3, 'enrolled': 5, 'cumulative': 14}, {'month': 4, 'enrolled': 1, 'cumulative': 15}, {'month': 5, 'enrolled': 4, 'cumulative': 19}, {'month': 6, 'enrolled': 2, 'cumulative': 21}] | ON_HOLD | 32 | 23 | 71.9 | 2.1 | Dr. James Thomas | Dr. Jessica Taylor
6441 | S0028 | SWIT-Health System | ST-2025-030 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 3, 'cumulative': 5}, {'month': 3, 'enrolled': 3, 'cumulative': 8}, {'month': 4, 'enrolled': 3, 'cumulative': 11}, {'month': 5, 'enrolled': 3, 'cumulative': 14}, {'month': 6, 'enrolled': 6, 'cumulative': 20}] | CLOSED | 37 | 24 | 64.9 | 1.3 | Dr. Nicole Brown | Dr. William Thompson
6442 | S0029 | SWIT-General Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 1, 'cumulative': 5}, {'month': 3, 'enrolled': 3, 'cumulative': 8}, {'month': 4, 'enrolled': 3, 'cumulative': 11}, {'month': 5, 'enrolled': 2, 'cumulative': 13}, {'month': 6, 'enrolled': 2, 'cumulative': 15}] | SCREENING | 30 | 12 | 40 | 0.8 | Dr. Robert White | Dr. Lisa Jones
6443 | S0030 | CHIN-General Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 8, 'cumulative': 8}, {'month': 2, 'enrolled': 12, 'cumulative': 20}, {'month': 3, 'enrolled': 11, 'cumulative': 31}, {'month': 4, 'enrolled': 10, 'cumulative': 41}, {'month': 5, 'enrolled': 10, 'cumulative': 51}, {'month': 6, 'enrolled': 11, 'cumulative': 62}] | ON_HOLD | 104 | 64 | 61.5 | 5.3 | Dr. David Williams | Dr. David Jackson
6444 | S0031 | CHIN-General Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 63 | 0 | 0 | 0 | Dr. Michelle Harris | Dr. Daniel Garcia
6445 | S0032 | JAPA-Medical Center | ST-2025-030 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | CLOSED | 32 | 0 | 0 | 0 | Dr. Thomas Brown | Dr. Stephanie Harris
6446 | S0033 | JAPA-Health System | ST-2025-030 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ON_HOLD | 48 | 0 | 0 | 0 | Dr. Jessica Brown | Dr. James Martin
6447 | S0034 | JAPA-General Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 56 | 0 | 0 | 0 | Dr. Robert Thompson | Dr. Jessica Moore
6448 | S0035 | JAPA-General Hospital | ST-2025-030 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 36 | 0 | 0 | 0 | Dr. Nicole Anderson | Dr. Michael Anderson
6449 | S0001 | CANA-University Hospital | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | -2 | -2 | 100 | -0.1 | Dr. Jessica Brown | Dr. Emily Martin
6450 | S0002 | CANA-University Hospital | ST-2025-031 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 3 | 2 | 66.7 | 0.3 | Dr. Michelle Taylor | Dr. James Davis
6451 | S0003 | CANA-Cancer Center | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Charles Thomas | Dr. Michael Garcia
6452 | S0004 | CANA-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Lisa Thompson | Dr. Daniel Anderson
6453 | S0005 | CANA-Clinical Center | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Michelle Brown | Dr. Nicole Wilson
6454 | S0006 | UNIT-Medical Center | ST-2025-031 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 1 | 0 | 0 | 0 | Dr. Michelle Taylor | Dr. Sarah Davis
6455 | S0007 | UNIT-Clinical Center | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Sarah Thomas | Dr. Michael White
6456 | S0008 | UNIT-Health System | ST-2025-031 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Michael Moore | Dr. Nicole Jones
6457 | S0009 | MEXI-Cancer Center | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -10 | -10 | 100 | -0.6 | Dr. Michelle Jackson | Dr. James Moore
6458 | S0010 | MEXI-Clinical Center | ST-2025-031 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | ON_HOLD | 3 | 3 | 100 | 0.5 | Dr. Charles Jones | Dr. Stephanie White
6459 | S0011 | MEXI-Health System | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 3 | 100 | 0.4 | Dr. Christopher Brown | Dr. Amanda Thomas
6460 | S0012 | MEXI-University Hospital | ST-2025-031 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. Sarah Davis | Dr. Lisa Williams
6461 | S0013 | MEXI-Health System | ST-2025-031 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 1, 'cumulative': 5}, {'month': 4, 'enrolled': 2, 'cumulative': 7}, {'month': 5, 'enrolled': 0, 'cumulative': 7}, {'month': 6, 'enrolled': 2, 'cumulative': 9}] | SCREENING | 3 | 1 | 33.3 | 0.2 | Dr. Stephanie Moore | Dr. Sarah Smith
6462 | S0014 | MEXI-Cancer Center | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 2, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Sarah Williams | Dr. Sarah Jones
6463 | S0015 | UNIT-Health System | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | -3 | -3 | 100 | -0.3 | Dr. Amanda Davis | Dr. Christopher Anderson
6464 | S0016 | UNIT-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 3 | 2 | 66.7 | 0.1 | Dr. Jessica Davis | Dr. Daniel Wilson
6465 | S0017 | UNIT-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 3 | 1 | 33.3 | 0.1 | Dr. Daniel Brown | Dr. Sarah Thomas
6466 | S0018 | UNIT-Clinical Center | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Nicole Wilson | Dr. Michael Miller
6467 | S0019 | UNIT-University Hospital | ST-2025-031 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Jessica Moore | Dr. David Brown
6468 | S0020 | UNIT-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Sarah Davis | Dr. Christopher Harris
6469 | S0021 | FRAN-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 6 | 0 | 0 | 0 | Dr. Charles Anderson | Dr. Michael Johnson
6470 | S0022 | FRAN-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | ON_HOLD | 3 | 0 | 0 | 0 | Dr. Nicole Smith | Dr. Charles Jackson
6471 | S0023 | BELG-Cancer Center | ST-2025-031 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 0 | 0 | 0 | 0 | Dr. Thomas Wilson | Dr. David Smith
6472 | S0024 | BELG-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Stephanie White | Dr. Sarah Brown
6473 | S0025 | BELG-Health System | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Jessica Moore | Dr. Christopher White
6474 | S0026 | BELG-Health System | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | CLOSED | 3 | 0 | 0 | 0 | Dr. Daniel Wilson | Dr. Jennifer Jackson
6475 | S0027 | TAIW-Medical Center | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 5 | 0 | 0 | 0 | Dr. William Williams | Dr. Lisa Moore
6476 | S0028 | TAIW-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | CLOSED | 6 | 0 | 0 | 0 | Dr. Charles Johnson | Dr. William Thomas
6477 | S0029 | JAPA-Clinical Center | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -7 | -7 | 100 | -0.5 | Dr. Christopher Smith | Dr. Christopher Johnson
6478 | S0030 | JAPA-Research Institute | ST-2025-031 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 3 | 2 | 66.7 | 0.2 | Dr. Michelle Miller | Dr. Stephanie Johnson
6479 | S0031 | JAPA-Health System | ST-2025-031 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | ON_HOLD | 3 | 3 | 100 | 0.4 | Dr. Michelle Taylor | Dr. Michael Harris
6480 | S0032 | JAPA-University Hospital | ST-2025-031 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 2 | 66.7 | 0.2 | Dr. William Martin | Dr. Robert Davis
6481 | S0033 | JAPA-General Hospital | ST-2025-031 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 3 | 0 | 0 | 0 | Dr. Sarah Davis | Dr. Emily Johnson
6482 | S0001 | CANA-Cancer Center | ST-2025-032 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 6, 'cumulative': 10}, {'month': 3, 'enrolled': 2, 'cumulative': 12}, {'month': 4, 'enrolled': 2, 'cumulative': 14}, {'month': 5, 'enrolled': 6, 'cumulative': 20}, {'month': 6, 'enrolled': 3, 'cumulative': 23}] | CLOSED | 62 | 25 | 40.3 | 1.8 | Dr. Sarah Smith | Dr. Lisa Jones
6483 | S0002 | CANA-Health System | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | SCREENING | 56 | 0 | 0 | 0 | Dr. David Wilson | Dr. Nicole Jones
6484 | S0003 | MEXI-General Hospital | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 1, 'cumulative': 1}] | SCREENING | 26 | 0 | 0 | 0 | Dr. James White | Dr. Michael Martin
6485 | S0004 | MEXI-Health System | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 17 | 0 | 0 | 0 | Dr. Jennifer Johnson | Dr. Stephanie Wilson
6486 | S0005 | MEXI-Health System | ST-2025-032 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | CLOSED | 24 | 0 | 0 | 0 | Dr. Lisa Thomas | Dr. Nicole Thompson
6487 | S0006 | MEXI-General Hospital | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | 15 | 0 | 0 | 0 | Dr. Lisa Anderson | Dr. Nicole Martin
6488 | S0007 | UNIT-Cancer Center | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 17 | 0 | 0 | 0 | Dr. Stephanie Harris | Dr. Thomas Davis
6489 | S0008 | UNIT-General Hospital | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | SCREENING | 10 | 0 | 0 | 0 | Dr. Jennifer Harris | Dr. Thomas Brown
6490 | S0009 | UNIT-Research Institute | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 10 | 0 | 0 | 0 | Dr. Robert Martin | Dr. Nicole White
6491 | S0010 | UNIT-General Hospital | ST-2025-032 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 11 | 0 | 0 | 0 | Dr. Jessica Wilson | Dr. Daniel Miller
6492 | S0011 | NORW-Clinical Center | ST-2025-032 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 18 | 0 | 0 | 0 | Dr. William Johnson | Dr. William Martin
6493 | S0012 | NORW-General Hospital | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 14 | 0 | 0 | 0 | Dr. Sarah Anderson | Dr. Christopher White
6494 | S0013 | NORW-University Hospital | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 1, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 6 | 0 | 0 | 0 | Dr. Michelle Miller | Dr. Emily Taylor
6495 | S0014 | NORW-University Hospital | ST-2025-032 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 14 | 0 | 0 | 0 | Dr. James Smith | Dr. Charles Williams
6496 | S0001 | MEXI-Research Institute | ST-2025-033 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -11 | -11 | 100 | -0.9 | Dr. Jessica Thomas | Dr. Charles Wilson
6497 | S0002 | MEXI-Health System | ST-2025-033 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. David Williams | Dr. Robert Brown
6498 | S0003 | MEXI-General Hospital | ST-2025-033 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 3 | 1 | 33.3 | 0.1 | Dr. Jennifer Wilson | Dr. Emily Jones
6499 | S0004 | MEXI-Cancer Center | ST-2025-033 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Charles Taylor | Dr. William Martin
6500 | S0005 | MEXI-University Hospital | ST-2025-033 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 3, 'cumulative': 5}, {'month': 4, 'enrolled': 0, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | ENROLLING | 3 | 7 | 233.3 | 0.9 | Dr. Lisa Miller | Dr. Michael Jones
6501 | S0006 | CANA-University Hospital | ST-2025-033 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ENROLLING | -1 | -1 | 100 | -0.1 | Dr. Stephanie Martin | Dr. Thomas Anderson
6502 | S0007 | CANA-Health System | ST-2025-033 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. Lisa Moore | Dr. Charles Jackson
6503 | S0008 | CANA-Cancer Center | ST-2025-033 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 3 | 3 | 100 | 0.2 | Dr. Nicole Thomas | Dr. Jessica Thompson
6504 | S0009 | SWIT-University Hospital | ST-2025-033 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 2, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 2 | 1 | 50 | 0.1 | Dr. William Jones | Dr. Stephanie Moore
6505 | S0010 | SWIT-Clinical Center | ST-2025-033 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 3 | 2 | 66.7 | 0.2 | Dr. William Brown | Dr. Michelle White
6506 | S0011 | POLA-Cancer Center | ST-2025-033 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 1, 'cumulative': 3}] | ON_HOLD | 2 | 2 | 100 | 0.2 | Dr. Amanda White | Dr. David Moore
6507 | S0012 | POLA-University Hospital | ST-2025-033 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Jennifer Smith | Dr. David Harris
6508 | S0001 | CANA-University Hospital | ST-2025-034 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ENROLLING | 5 | 4 | 80 | 0.2 | Dr. Christopher Harris | Dr. Stephanie Jackson
6509 | S0002 | CANA-Clinical Center | ST-2025-034 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 3 | 3 | 100 | 0.3 | Dr. Amanda Taylor | Dr. Nicole Jackson
6510 | S0003 | FRAN-Health System | ST-2025-034 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 0 | 0 | 0 | 0 | Dr. Stephanie Wilson | Dr. Charles Smith
6511 | S0004 | FRAN-University Hospital | ST-2025-034 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | SCREENING | 3 | 3 | 100 | 0.2 | Dr. Jessica Thompson | Dr. David Jones
6512 | S0005 | FRAN-University Hospital | ST-2025-034 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 3 | 1 | 33.3 | 0.1 | Dr. Sarah Williams | Dr. Jessica Jones
6513 | S0006 | NEW-Medical Center | ST-2025-034 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | -3 | -3 | 100 | -0.4 | Dr. David White | Dr. Michael Davis
6514 | S0007 | NEW-University Hospital | ST-2025-034 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | SCREENING | 3 | 3 | 100 | 0.2 | Dr. Amanda Smith | Dr. Nicole Garcia
6515 | S0008 | NEW-Research Institute | ST-2025-034 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 3 | 2 | 66.7 | 0.3 | Dr. Michelle Jackson | Dr. David Martin
6516 | S0009 | NEW-General Hospital | ST-2025-034 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 4 | 133.3 | 0.3 | Dr. Lisa Brown | Dr. Charles Jones
6517 | S0001 | CANA-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | -35 | -35 | 100 | -2.9 | Dr. Jessica Wilson | Dr. James White
6518 | S0002 | CANA-University Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ENROLLING | 3 | 3 | 100 | 0.5 | Dr. Robert Wilson | Dr. William Harris
6519 | S0003 | CANA-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 3 | 3 | 100 | 0.2 | Dr. Thomas Brown | Dr. Lisa Davis
6520 | S0004 | CANA-Medical Center | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Lisa Williams | Dr. Jessica Harris
6521 | S0005 | CANA-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 3 | 3 | 100 | 0.2 | Dr. Thomas Moore | Dr. Charles Martin
6522 | S0006 | CANA-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 4 | 133.3 | 0.7 | Dr. Thomas Taylor | Dr. Amanda Harris
6523 | S0007 | MEXI-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ENROLLING | 2 | 1 | 50 | 0.1 | Dr. Charles Wilson | Dr. Charles Johnson
6524 | S0008 | MEXI-General Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 2, 'cumulative': 6}, {'month': 5, 'enrolled': 0, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. Nicole Moore | Dr. Amanda Williams
6525 | S0009 | UNIT-General Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | -1 | -1 | 100 | -0.1 | Dr. Robert Garcia | Dr. Amanda White
6526 | S0010 | UNIT-Clinical Center | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Jessica Moore | Dr. Nicole Davis
6527 | S0011 | UNIT-Clinical Center | ST-2025-035 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 4 | 133.3 | 0.3 | Dr. Charles Brown | Dr. Emily Jackson
6528 | S0012 | SWED-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | -10 | -10 | 100 | -1 | Dr. Amanda Brown | Dr. Thomas Thompson
6529 | S0013 | SWED-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 1, 'cumulative': 6}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. Lisa Jackson | Dr. Nicole Harris
6530 | S0014 | SWED-Research Institute | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Jennifer Jackson | Dr. Jessica Smith
6531 | S0015 | SWED-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 3 | 3 | 100 | 0.3 | Dr. Jennifer Brown | Dr. Charles White
6532 | S0016 | SWED-Clinical Center | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 1, 'cumulative': 7}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. James Davis | Dr. Robert Thompson
6533 | S0017 | SWED-Medical Center | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | ON_HOLD | 3 | 5 | 166.7 | 0.3 | Dr. Stephanie Smith | Dr. Thomas Davis
6534 | S0018 | NETH-Clinical Center | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | -4 | -4 | 100 | -0.3 | Dr. David Garcia | Dr. Christopher Thomas
6535 | S0019 | NETH-General Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | SCREENING | 3 | 2 | 66.7 | 0.2 | Dr. Nicole Miller | Dr. Thomas Jones
6536 | S0020 | NETH-Research Institute | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | SCREENING | 3 | 3 | 100 | 0.4 | Dr. David Harris | Dr. Christopher Davis
6537 | S0021 | NETH-General Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 3 | 2 | 66.7 | 0.1 | Dr. Lisa Garcia | Dr. Christopher Thompson
6538 | S0022 | ITAL-University Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | SCREENING | -1 | -1 | 100 | -0.1 | Dr. Michael Smith | Dr. Sarah White
6539 | S0023 | ITAL-Cancer Center | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. Charles Williams | Dr. Stephanie Wilson
6540 | S0024 | ITAL-General Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. Michelle Smith | Dr. Christopher Martin
6541 | S0025 | GERM-Clinical Center | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ENROLLING | -7 | -7 | 100 | -0.6 | Dr. Emily Jones | Dr. William Brown
6542 | S0026 | GERM-General Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ENROLLING | 3 | 2 | 66.7 | 0.2 | Dr. Stephanie Taylor | Dr. Robert Davis
6543 | S0027 | GERM-Cancer Center | ST-2025-035 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | ENROLLING | 3 | 3 | 100 | 0.2 | Dr. William Brown | Dr. Thomas Williams
6544 | S0028 | GERM-Clinical Center | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ENROLLING | 3 | 2 | 66.7 | 0.1 | Dr. Lisa Wilson | Dr. Thomas Anderson
6545 | S0029 | GERM-General Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | ENROLLING | 3 | 5 | 166.7 | 0.4 | Dr. Christopher Wilson | Dr. William Johnson
6546 | S0030 | AUST-General Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | -4 | -4 | 100 | -0.5 | Dr. Jessica Martin | Dr. Christopher Anderson
6547 | S0031 | AUST-University Hospital | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | CLOSED | 3 | 2 | 66.7 | 0.1 | Dr. Robert Jones | Dr. Jessica Jackson
6548 | S0032 | AUST-Research Institute | ST-2025-035 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | SCREENING | 3 | 2 | 66.7 | 0.1 | Dr. James Miller | Dr. Jessica Jones
6549 | S0033 | AUST-Health System | ST-2025-035 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 3 | 2 | 66.7 | 0.3 | Dr. Amanda Thompson | Dr. Daniel Jackson
6550 | S0001 | MEXI-General Hospital | ST-2025-036 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 2, 'cumulative': 5}, {'month': 4, 'enrolled': 3, 'cumulative': 8}, {'month': 5, 'enrolled': 4, 'cumulative': 12}, {'month': 6, 'enrolled': 3, 'cumulative': 15}] | ENROLLING | 16 | 15 | 93.8 | 1 | Dr. David Jones | Dr. David Anderson
6551 | S0002 | MEXI-University Hospital | ST-2025-036 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 4, 'cumulative': 6}, {'month': 4, 'enrolled': 2, 'cumulative': 8}, {'month': 5, 'enrolled': 0, 'cumulative': 8}, {'month': 6, 'enrolled': 2, 'cumulative': 10}] | ENROLLING | 12 | 12 | 100 | 1.7 | Dr. Michelle Johnson | Dr. Robert Moore
6552 | S0003 | MEXI-Research Institute | ST-2025-036 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 1, 'cumulative': 5}, {'month': 3, 'enrolled': 5, 'cumulative': 10}, {'month': 4, 'enrolled': 2, 'cumulative': 12}, {'month': 5, 'enrolled': 1, 'cumulative': 13}, {'month': 6, 'enrolled': 2, 'cumulative': 15}] | ENROLLING | 20 | 18 | 90 | 2.6 | Dr. Thomas Davis | Dr. David Miller
6553 | S0004 | MEXI-Research Institute | ST-2025-036 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 3, 'cumulative': 5}, {'month': 5, 'enrolled': 1, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ENROLLING | 14 | 11 | 78.6 | 1.4 | Dr. William Davis | Dr. David Thomas
6554 | S0005 | MEXI-Medical Center | ST-2025-036 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 3, 'cumulative': 6}, {'month': 3, 'enrolled': 4, 'cumulative': 10}, {'month': 4, 'enrolled': 4, 'cumulative': 14}, {'month': 5, 'enrolled': 5, 'cumulative': 19}, {'month': 6, 'enrolled': 1, 'cumulative': 20}] | ENROLLING | 16 | 22 | 137.5 | 2.8 | Dr. Emily Jackson | Dr. James Harris
6555 | S0006 | UNIT-Medical Center | ST-2025-036 | [{'month': 1, 'enrolled': 7, 'cumulative': 7}, {'month': 2, 'enrolled': 4, 'cumulative': 11}, {'month': 3, 'enrolled': 6, 'cumulative': 17}, {'month': 4, 'enrolled': 7, 'cumulative': 24}, {'month': 5, 'enrolled': 4, 'cumulative': 28}, {'month': 6, 'enrolled': 4, 'cumulative': 32}] | ENROLLING | 48 | 34 | 70.8 | 2.6 | Dr. Charles Miller | Dr. David Jackson
6556 | S0007 | UNIT-Health System | ST-2025-036 | [{'month': 1, 'enrolled': 9, 'cumulative': 9}, {'month': 2, 'enrolled': 8, 'cumulative': 17}, {'month': 3, 'enrolled': 9, 'cumulative': 26}, {'month': 4, 'enrolled': 10, 'cumulative': 36}, {'month': 5, 'enrolled': 12, 'cumulative': 48}, {'month': 6, 'enrolled': 12, 'cumulative': 60}] | ENROLLING | 47 | 61 | 129.8 | 8.7 | Dr. Jennifer Thompson | Dr. Daniel Brown
6557 | S0008 | POLA-Health System | ST-2025-036 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 3, 'cumulative': 3}, {'month': 3, 'enrolled': 3, 'cumulative': 6}, {'month': 4, 'enrolled': 3, 'cumulative': 9}, {'month': 5, 'enrolled': 0, 'cumulative': 9}, {'month': 6, 'enrolled': 3, 'cumulative': 12}] | ENROLLING | 12 | 10 | 83.3 | 1.4 | Dr. James Smith | Dr. Charles White
6558 | S0009 | POLA-Clinical Center | ST-2025-036 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 3, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 3, 'cumulative': 7}, {'month': 5, 'enrolled': 0, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | ENROLLING | 10 | 7 | 70 | 1 | Dr. Amanda Anderson | Dr. Michael White
6559 | S0010 | POLA-Cancer Center | ST-2025-036 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 4, 'cumulative': 6}, {'month': 5, 'enrolled': 1, 'cumulative': 7}, {'month': 6, 'enrolled': 1, 'cumulative': 8}] | ENROLLING | 22 | 14 | 63.6 | 0.9 | Dr. Lisa Williams | Dr. Charles Martin
6560 | S0011 | POLA-Medical Center | ST-2025-036 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 4, 'cumulative': 8}, {'month': 3, 'enrolled': 3, 'cumulative': 11}, {'month': 4, 'enrolled': 1, 'cumulative': 12}, {'month': 5, 'enrolled': 2, 'cumulative': 14}, {'month': 6, 'enrolled': 0, 'cumulative': 14}] | SCREENING | 19 | 17 | 89.5 | 1.7 | Dr. Thomas Johnson | Dr. Robert Davis
6561 | S0012 | POLA-University Hospital | ST-2025-036 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 1, 'cumulative': 3}, {'month': 3, 'enrolled': 2, 'cumulative': 5}, {'month': 4, 'enrolled': 3, 'cumulative': 8}, {'month': 5, 'enrolled': 2, 'cumulative': 10}, {'month': 6, 'enrolled': 2, 'cumulative': 12}] | ENROLLING | 13 | 11 | 84.6 | 0.7 | Dr. Robert Thompson | Dr. Robert Jones
6562 | S0013 | POLA-General Hospital | ST-2025-036 | [{'month': 1, 'enrolled': 7, 'cumulative': 7}, {'month': 2, 'enrolled': 6, 'cumulative': 13}, {'month': 3, 'enrolled': 5, 'cumulative': 18}, {'month': 4, 'enrolled': 6, 'cumulative': 24}, {'month': 5, 'enrolled': 4, 'cumulative': 28}, {'month': 6, 'enrolled': 4, 'cumulative': 32}] | ENROLLING | 23 | 40 | 173.9 | 3.1 | Dr. Sarah Miller | Dr. Jessica Thomas
6563 | S0014 | UNIT-Medical Center | ST-2025-036 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 3, 'cumulative': 4}, {'month': 3, 'enrolled': 1, 'cumulative': 5}, {'month': 4, 'enrolled': 0, 'cumulative': 5}, {'month': 5, 'enrolled': 3, 'cumulative': 8}, {'month': 6, 'enrolled': 3, 'cumulative': 11}] | ENROLLING | 12 | 8 | 66.7 | 0.4 | Dr. James Martin | Dr. David Anderson
6564 | S0015 | UNIT-Clinical Center | ST-2025-036 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | SCREENING | 11 | 11 | 100 | 0.7 | Dr. William Taylor | Dr. James Smith
6565 | S0016 | UNIT-Research Institute | ST-2025-036 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | SCREENING | 7 | 7 | 100 | 1.2 | Dr. Sarah Jones | Dr. Stephanie Johnson
6566 | S0017 | UNIT-Health System | ST-2025-036 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 5 | 4 | 80 | 0.3 | Dr. Daniel Garcia | Dr. Jennifer Brown
6567 | S0018 | UNIT-Medical Center | ST-2025-036 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 3, 'cumulative': 6}, {'month': 6, 'enrolled': 0, 'cumulative': 6}] | ENROLLING | 8 | 7 | 87.5 | 0.6 | Dr. Michael White | Dr. Michael Brown
6568 | S0019 | SWIT-Research Institute | ST-2025-036 | [{'month': 1, 'enrolled': 3, 'cumulative': 3}, {'month': 2, 'enrolled': 5, 'cumulative': 8}, {'month': 3, 'enrolled': 3, 'cumulative': 11}, {'month': 4, 'enrolled': 4, 'cumulative': 15}, {'month': 5, 'enrolled': 4, 'cumulative': 19}, {'month': 6, 'enrolled': 2, 'cumulative': 21}] | ON_HOLD | 24 | 24 | 100 | 1.5 | Dr. Amanda Brown | Dr. Nicole Martin
6569 | S0020 | SWIT-General Hospital | ST-2025-036 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 3, 'cumulative': 3}, {'month': 3, 'enrolled': 1, 'cumulative': 4}, {'month': 4, 'enrolled': 3, 'cumulative': 7}, {'month': 5, 'enrolled': 0, 'cumulative': 7}, {'month': 6, 'enrolled': 3, 'cumulative': 10}] | ENROLLING | 14 | 8 | 57.1 | 0.5 | Dr. Robert Davis | Dr. Daniel Jones
6570 | S0021 | SWIT-Cancer Center | ST-2025-036 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 1, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 3, 'cumulative': 8}] | ENROLLING | 13 | 11 | 84.6 | 1.4 | Dr. Michael Brown | Dr. Charles Anderson
6571 | S0022 | SWIT-Health System | ST-2025-036 | [{'month': 1, 'enrolled': 5, 'cumulative': 5}, {'month': 2, 'enrolled': 4, 'cumulative': 9}, {'month': 3, 'enrolled': 2, 'cumulative': 11}, {'month': 4, 'enrolled': 1, 'cumulative': 12}, {'month': 5, 'enrolled': 3, 'cumulative': 15}, {'month': 6, 'enrolled': 3, 'cumulative': 18}] | ENROLLING | 20 | 20 | 100 | 2.9 | Dr. Lisa Wilson | Dr. Jennifer Anderson
6572 | S0023 | SWIT-Research Institute | ST-2025-036 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 2, 'cumulative': 5}, {'month': 6, 'enrolled': 2, 'cumulative': 7}] | SCREENING | 13 | 9 | 69.2 | 0.5 | Dr. Daniel Thompson | Dr. William Jones
6573 | S0024 | SWIT-Research Institute | ST-2025-036 | [{'month': 1, 'enrolled': 4, 'cumulative': 4}, {'month': 2, 'enrolled': 1, 'cumulative': 5}, {'month': 3, 'enrolled': 3, 'cumulative': 8}, {'month': 4, 'enrolled': 2, 'cumulative': 10}, {'month': 5, 'enrolled': 1, 'cumulative': 11}, {'month': 6, 'enrolled': 4, 'cumulative': 15}] | SCREENING | 20 | 12 | 60 | 1 | Dr. Robert Johnson | Dr. Charles Johnson
6574 | S0025 | AUST-University Hospital | ST-2025-036 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 5, 'cumulative': 7}, {'month': 4, 'enrolled': 5, 'cumulative': 12}, {'month': 5, 'enrolled': 3, 'cumulative': 15}, {'month': 6, 'enrolled': 2, 'cumulative': 17}] | ON_HOLD | 33 | 20 | 60.6 | 2.5 | Dr. Thomas Smith | Dr. Nicole Martin
6575 | S0026 | AUST-Cancer Center | ST-2025-036 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 36 | 0 | 0 | 0 | Dr. Charles Harris | Dr. David Harris
6576 | S0027 | AUST-Health System | ST-2025-036 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 2, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 12 | 0 | 0 | 0 | Dr. Christopher Brown | Dr. William Thompson
6577 | S0001 | MEXI-General Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 1, 'cumulative': 1}, {'month': 5, 'enrolled': 2, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 276 | 0 | 0 | 0 | Dr. Michael Williams | Dr. Charles Wilson
6578 | S0002 | MEXI-University Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 2, 'cumulative': 6}, {'month': 6, 'enrolled': 2, 'cumulative': 8}] | ON_HOLD | 318 | 0 | 0 | 0 | Dr. Michelle Thomas | Dr. Charles Jones
6579 | S0003 | MEXI-Clinical Center | ST-2025-037 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 1, 'cumulative': 5}, {'month': 4, 'enrolled': 2, 'cumulative': 7}, {'month': 5, 'enrolled': 0, 'cumulative': 7}, {'month': 6, 'enrolled': 0, 'cumulative': 7}] | CLOSED | 179 | 0 | 0 | 0 | Dr. Jessica Williams | Dr. Thomas Davis
6580 | S0004 | MEXI-Clinical Center | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 1, 'cumulative': 2}] | SCREENING | 133 | 0 | 0 | 0 | Dr. Michelle Jones | Dr. William Smith
6581 | S0005 | MEXI-Clinical Center | ST-2025-037 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | CLOSED | 235 | 0 | 0 | 0 | Dr. Lisa Davis | Dr. Lisa Harris
6582 | S0006 | MEXI-General Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 1, 'cumulative': 4}, {'month': 6, 'enrolled': 2, 'cumulative': 6}] | SCREENING | 307 | 0 | 0 | 0 | Dr. Robert Smith | Dr. Jessica Davis
6583 | S0007 | UNIT-University Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | CLOSED | 422 | 0 | 0 | 0 | Dr. Charles Jackson | Dr. William Thomas
6584 | S0008 | UNIT-Cancer Center | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 2, 'cumulative': 2}, {'month': 6, 'enrolled': 2, 'cumulative': 4}] | ON_HOLD | 389 | 0 | 0 | 0 | Dr. Stephanie Thomas | Dr. Amanda Davis
6585 | S0009 | UNIT-Research Institute | ST-2025-037 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 2, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 282 | 0 | 0 | 0 | Dr. Michael Jones | Dr. Thomas Davis
6586 | S0010 | UNIT-Cancer Center | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 1, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 2, 'cumulative': 3}] | CLOSED | 269 | 0 | 0 | 0 | Dr. Robert Brown | Dr. Daniel Martin
6587 | S0011 | CANA-University Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 2, 'cumulative': 3}, {'month': 4, 'enrolled': 2, 'cumulative': 5}, {'month': 5, 'enrolled': 0, 'cumulative': 5}, {'month': 6, 'enrolled': 2, 'cumulative': 7}] | ON_HOLD | 945 | 0 | 0 | 0 | Dr. Michelle Davis | Dr. Christopher Wilson
6588 | S0012 | CANA-Health System | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 551 | 0 | 0 | 0 | Dr. Christopher Martin | Dr. Stephanie Williams
6589 | S0013 | DENM-Research Institute | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 1, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | CLOSED | 382 | 0 | 0 | 0 | Dr. Robert Williams | Dr. Amanda Williams
6590 | S0014 | DENM-General Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 2, 'cumulative': 4}, {'month': 3, 'enrolled': 0, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 1, 'cumulative': 5}, {'month': 6, 'enrolled': 0, 'cumulative': 5}] | CLOSED | 176 | 0 | 0 | 0 | Dr. William Smith | Dr. Nicole White
6591 | S0015 | DENM-General Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | SCREENING | 277 | 0 | 0 | 0 | Dr. Charles Miller | Dr. Christopher Anderson
6592 | S0016 | NETH-Health System | ST-2025-037 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 1, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | CLOSED | 686 | 0 | 0 | 0 | Dr. Stephanie Jones | Dr. Michelle Taylor
6593 | S0017 | NETH-Cancer Center | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 2, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | CLOSED | 775 | 0 | 0 | 0 | Dr. Sarah Thomas | Dr. Emily Williams
6594 | S0018 | UNIT-Medical Center | ST-2025-037 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 163 | 0 | 0 | 0 | Dr. Emily Jackson | Dr. Charles White
6595 | S0019 | UNIT-Clinical Center | ST-2025-037 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 1, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | ON_HOLD | 149 | 0 | 0 | 0 | Dr. Robert Taylor | Dr. Jennifer Brown
6596 | S0020 | UNIT-Research Institute | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 1, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 1, 'cumulative': 4}] | SCREENING | 178 | 0 | 0 | 0 | Dr. Stephanie Wilson | Dr. Nicole Williams
6597 | S0021 | UNIT-University Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 0, 'cumulative': 0}, {'month': 3, 'enrolled': 0, 'cumulative': 0}, {'month': 4, 'enrolled': 0, 'cumulative': 0}, {'month': 5, 'enrolled': 0, 'cumulative': 0}, {'month': 6, 'enrolled': 0, 'cumulative': 0}] | ON_HOLD | 178 | 0 | 0 | 0 | Dr. David Davis | Dr. Amanda Williams
6598 | S0022 | UNIT-Research Institute | ST-2025-037 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 0, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | SCREENING | 108 | 0 | 0 | 0 | Dr. Daniel Wilson | Dr. James Johnson
6599 | S0023 | UNIT-Health System | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 2, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | CLOSED | 159 | 0 | 0 | 0 | Dr. Amanda Brown | Dr. Jennifer Smith
6600 | S0024 | ITAL-Health System | ST-2025-037 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 1, 'cumulative': 3}, {'month': 6, 'enrolled': 0, 'cumulative': 3}] | ON_HOLD | 799 | 0 | 0 | 0 | Dr. Michael Garcia | Dr. David Martin
6601 | S0025 | ITAL-University Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 1, 'cumulative': 3}, {'month': 4, 'enrolled': 0, 'cumulative': 3}, {'month': 5, 'enrolled': 0, 'cumulative': 3}, {'month': 6, 'enrolled': 2, 'cumulative': 5}] | SCREENING | 560 | 0 | 0 | 0 | Dr. Amanda Brown | Dr. Robert Thomas
6602 | S0026 | ITAL-Health System | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 1, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | ON_HOLD | 274 | 0 | 0 | 0 | Dr. Jennifer Thompson | Dr. Robert Harris
6603 | S0027 | TAIW-Research Institute | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 1, 'cumulative': 1}, {'month': 3, 'enrolled': 0, 'cumulative': 1}, {'month': 4, 'enrolled': 0, 'cumulative': 1}, {'month': 5, 'enrolled': 0, 'cumulative': 1}, {'month': 6, 'enrolled': 0, 'cumulative': 1}] | ON_HOLD | 125 | 0 | 0 | 0 | Dr. Jennifer Thompson | Dr. Jennifer Brown
6604 | S0028 | TAIW-Clinical Center | ST-2025-037 | [{'month': 1, 'enrolled': 1, 'cumulative': 1}, {'month': 2, 'enrolled': 2, 'cumulative': 3}, {'month': 3, 'enrolled': 0, 'cumulative': 3}, {'month': 4, 'enrolled': 1, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 1, 'cumulative': 5}] | CLOSED | 125 | 0 | 0 | 0 | Dr. Robert Taylor | Dr. Christopher Moore
6605 | S0029 | TAIW-Cancer Center | ST-2025-037 | [{'month': 1, 'enrolled': 2, 'cumulative': 2}, {'month': 2, 'enrolled': 0, 'cumulative': 2}, {'month': 3, 'enrolled': 2, 'cumulative': 4}, {'month': 4, 'enrolled': 0, 'cumulative': 4}, {'month': 5, 'enrolled': 0, 'cumulative': 4}, {'month': 6, 'enrolled': 0, 'cumulative': 4}] | ON_HOLD | 241 | 0 | 0 | 0 | Dr. Emily Moore | Dr. Michael Taylor
6606 | S0030 | TAIW-University Hospital | ST-2025-037 | [{'month': 1, 'enrolled': 0, 'cumulative': 0}, {'month': 2, 'enrolled': 2, 'cumulative': 2}, {'month': 3, 'enrolled': 0, 'cumulative': 2}, {'month': 4, 'enrolled': 0, 'cumulative': 2}, {'month': 5, 'enrolled': 0, 'cumulative': 2}, {'month': 6, 'enrolled': 0, 'cumulative': 2}] | SCREENING | 339 | 0 | 0 | 0 | Dr. Lisa Martin | Dr. David Jackson

## Protocols
protocol_id | title | phase | therapeutic_area | indication | full_summary | inclusion_criteria | exclusion_criteria | target_enrollment | actual_enrollment | planned_start_date | actual_end_date | planned_duration_months | actual_duration_months | lessons_learned
NCT06567015 | Phase I/II First-In-Human Open-label Trial to Assess Safety and Efficacy of STX-241 in Participants With Locally Advanced or Metastatic Non-small Cell Lung Cancer (NSCLC) Resistant to EGFR Tyrosine Kinase Inhibitors (TKIs). | PHASE_I | Oncology | Non-small Cell Lung Cancer (NSCLC) | The goal of this First-In-Human (FIH) Phase I/II trial is to establish the safety profile, determine the Recommended Phase II Dose (RP2D), explore the pharmacokinetic (PK) exposure and pharmacodynamic (PD) properties as well as assess the efficacy of STX-241/PFL-241, a mutant selective Central Nervous System (CNS)-penetrant fourth generation EGFR TKI, in participants with locally advanced or metastatic NSCLC that progressed during or following third generation EGFR TKI such as osimertinib due to C797X double acquired (secondary) mutations. | 1. Signed and dated informed consent for participation in the trial obtained according to International Council for Harmonisation of Technical Requirements of Pharmaceuticals for Human Use (ICH) Good Clinical Practice (GCP), and national/local regulations. 2. Male or female ≥ 18 years of age at the time of signing informed consent. 3. Histological confirmation of locally advanced or metastatic, EGFR-mutant (ex19del or L858R mutations) non-small cell lung cancer (NSCLC) Stage IIIB/C or IV (AJCC 8th edition) not eligible for curative intent surgery or chemoradiation. 4. Part 1\&2 Disease progression on a 3rd generation EGFR TKI-based therapy (monotherapy or in combination) received at any prior line of treatment. 5. Tumor mutation profile: • Part 1 (backfilling component) and Part 2: Presence of C797X and absence of T790M mutations documented locally (as part of clinical practice) on a sample (blood or tissue) collected after progression on treatment with 3rd generation EGFR TKI. 6. Part 1 (Backfilling component), Part 2: At least one measurable target lesion according to RECIST v1.1. 7. Eastern cooperative oncology group (ECOG) performance status 0-1. 8. Adequate organ function as defined below: * Absolute neutrophil count (ANC) ≥ 1.5 x 10\^9/L * Platelets ≥ 75 x 10\^9/L * Hemoglobin ≥ 90 g/L. * Serum total bilirubin ≤ 1.5 x ULN or ≤ 3.0 × ULN for participants with documented Gilbert's syndrome. * Alanine aminotransferase (ALT) and aspartate aminotransferase (AST) ≤ 3.0 x ULN. If the participant has liver metastases, AST and ALT ≤5 × ULN. * Estimated glomerular filtration rate (GFR) ≥ 50 mL/min by CKD-EPI equation 9. Adequate cardiac function as defined below: * Mean QT interval corrected for heart rate according to Fridericia's formula (QTcF) value ≤ 470 msec for women and ≤ 450 msec for men and no history of long QT syndrome or risk factors for torsade de pointe. * Left ventricular ejection fraction (LVEF) ≥ 50% . * Systolic blood pressure \< 150 mmHg and diastolic blood pressure \< 100 mmHg 10. Female participants of childbearing potential: * Negative highly sensitive serum β-HCG test performed within 7 days prior to first dose of STX-241 (C1D1) and a negative urine pregnancy test performed prior to C1D1. * Agreement to use one highly effective contraceptive method (as defined in protocol and according to local regulations), starting at screening period, throughout the trial and until at least 182 days (i.e. more than 5 estimated STX- 241 half-lives (2 days) plus 6 months (180 days)) after the last dose of STX-241. If the highly effective method of contraception is a hormonal contraceptive method, it must be supplemented by one additional effective (barrier) method of contraception. * Agreement to not donate eggs (ova, oocytes) for the purpose of assisted reproduction during the trial and for a period of 182 days after the last dose of STX-241. Note: a female participant of childbearing potential is a woman who is not permanently sterilized or not postmenopausal (postmenopausal is defined as 12 months with no menses without an alternative medical cause). 11. Male participants/partners with female spouse/partners of childbearing potential must agree to take appropriate precautions to avoid fathering a child, i.e.: * Consistently use a barrier method \[e.g., condom with spermicidal foam / gel / film /cream/suppository\], and his female partner use a highly effective method of contraception as defined in protocol and according to local regulations), starting at screening and continuing throughout the trial period and for 92 days (ie. more than 5 estimated STX-241 half-lives (2 days) plus 3 months (90 days)) after the last dose of STX-241. * Not donate sperm from Day 1 (first administration of STX-241) until at least 92 days after the last dose of STX-241. NOTE: Other protocol defined inclusion criteria may apply. | 1. Participant candidate for targeted therapies available to them (such as but not limited to therapies targeting ALK, BRAF, MET, NTRK, ROS1) as identified by local testing performed after progression to the last line of systemic therapy. 2. Participant with rapid progressive disease eligible to receive a platinum-based chemotherapy. 3. Participant unable ingest or digest tablets. This can be caused by any impaired gastrointestinal function or disease, such as for example: ulcerative diseases, malabsorption syndrome, small bowel resection, ileus, etc. or any condition causing uncontrolled nausea, vomiting or diarrhea. 4. History of a primary malignancy other than NSCLC with the exception of: * Participants with a previous malignancy that completed all anticancer treatment at least 2 years before signing informed consent and with no evidence of residual disease from the prior malignancy at screening. * Malignancies with a negligible risk of metastasis or death (i.e. 5-year overall survival rate \> 90%) that are adequately treated - Examples include, but are not limited to, completely resected basal cell carcinoma and squamous cell carcinoma of skin, melanoma in situ, curatively treated prostate cancer, breast cancer and early gastric cancer cured by endoscopic mucosal resection or endoscopic submucosal dissection. 5. Spinal cord compression or CNS metastases that are associated with progressive neurological symptoms or require increasing doses of corticosteroids to control the CNS disease. If a participant requires corticosteroids for management of CNS disease, the dose must have been stable for 2 weeks prior to enrollment in the trial. 6. History of hypersensitivity to active or inactive ingredients of STX-241, or drugs with a similar chemical structure or from the same class. 7. Active, bacterial, fungal, or viral infection, including, but not limited to: Hepatitis B Virus (HBV), Hepatitis C Virus (HCV), and known Human Immunodeficiency Virus (HIV) or Acquired Immunodeficiency Syndrome (AIDS)-related illness, tuberculosis or an infection requiring systemic therapeutic treatment within 2 weeks prior to Day 1 (first administration of STX-241). Note: Participants with known HIV infection are permitted if they have controlled infection (undetectable viral load \[HIV ribonucleic acid polymerase chain reaction (PCR)\] and CD4 count \>350 either spontaneously or on a stable antiviral regimen). For participants with controlled HIV infection, monitoring will be performed per local standards. 8. Positive SARs-CoV-2 or variants of SARs-CoV2 RT-PCR test or suspected to be infected with SARs-CoV2 or variants of SARsCoV2 with confirmation pending within 2 weeks of first dose of STX-241. 9. Impaired cardiovascular function or clinically significant cardiovascular disease (either active or within 6 months prior to signing informed consent), including any of the following: * Myocardial infarction, acute coronary syndromes including unstable angina, coronary/peripheral artery bypass graft, coronary angioplasty or stenting. * Symptomatic congestive heart failure (New York Heart Association Classification Class ≥ II). * Cerebrovascular accident or transient ischemic attack. * Symptomatic bradycardia, requirement for anti-arrhythmic medication. * Ongoing cardiac dysrhythmias of NCI-CTCAE Grade ≥2. 10. Uncontrolled intercurrent illness including, but not limited to ongoing or active infection or psychiatric illness/social situation that would limit compliance with trial requirements. 11. Past medical history of Interstitial Lung Disease (ILD), drug-induced ILD, radiation pneumonitis that required steroid treatment, or any evidence of clinically active ILD. 12. Past medical history of Stevens-Jonhson Syndrome (SJS) or Toxic epidermal necrolysis (TEN) or any evidence of clinically active SJS/TEN. 13. Women who are breast feeding. 14. Prior anticancer therapy: * EGFR-targeted TKI within 7 days prior to the first dose of STX-241. * Any other systemic anticancer therapy within 28 days or 5 half-lives prior to the first dose of STX-241, whichever is the shortest, but with a minimum of 14 days in all circumstances. * Radiotherapy to a large field or including a vital organ (including whole brain radiotherapy or stereotactic radiosurgery to brain) within 14 days before the first dose of STX-241. 15. Live attenuated vaccine received within 30 days prior to the first dose of STX-241. 16. Any toxicities from prior therapy with a NCI-CTCAE Grade ≥1 at the time of the first dose of STX-241 (C1D1). Exceptions include alopecia (any grade), fatigue with a Grade ≤2, and peripheral neuropathy with a Grade ≤2. 17. Major surgical procedure within 14 days of the first dose of STX-241 (procedures such as central venous catheter placement, tumor needle biopsy, and feeding tube placement are not considered major surgical procedures). Sequelae of surgical procedures must have resolved, including adequate wound healing, prior to the first dose of STX-241. 18. Treatment with a prohibited medication or herbal remedy known to be strong CYP1A2 or CYP3A4 inducers, strong CYP1A2 or CYP3A4 inhibitors, sensitive CYP1A2, CYP2B6 and CYP3A4 substrates, sensitive MATE1 and OATP1B1 substrates and proton pump inhibitors (PPI) and H2 antagonists unless discontinued prior to the first administration of STX-241 within the following timeframe: * At least 5 half-lives plus 14 days for strong CYP inducers. * At least 5 half-lives for CYP inhibitors, CYP/transporter substrates, proton pump inhibitor (PPI) and H2 antagonists. 19. Participation in a clinical trial with administration of an investigational drug within 5 half-lives plus 14 days of the investigational drug, before the first dose of STX-241. 20. Any condition for which, in the opinion of the investigator, participation would not be in the best interest of the participant (e. g, could compromise the participant's well-being) or would prevent, limit, or confound the protocol-specified assessments. 21. Employee or family member of the investigator or site staff. NOTE: Other protocol defined exclusion criteria may apply. | 171 | 54 | 2024-09-17 | 2028-05-17 | 45 | 45 | Protocol eligibility criteria restricted enrollment to 32%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT05655078 | Hemithoracic Irradiation With Proton Therapy in Malignant Pleural Mesothelioma |  | Oncology | Malignant Pleural Mesothelioma | Study design: Randomised phase III clinical trial for patients with unilateral MPM. Primary endpoint: Progression free survival (PFS) and overall survival (OS), defined as the time from randomisation to the date of progression and death from any cause. Secondary Endpoints: Safety and Tolerability, Health related Quality of Life (QOL): EuroQoL EQ-5D-3L, Locoregional Control. Randomisation and stratification: 1:1 randomisation. Patients with be stratified for histology (epithelioid versus non-epithelioid), potential PBT centre (UCLH or The Christie) , laterality (left or right sided) and time since diagnosis (\<1 year or \> 1 year) Treatment: Experimental Arm: Patients in the experimental arm will receive PBT to the hemithorax to a dose of 50Gy in 25 fractions with a boost to 60Gy for the visible tumour (gross tumour volume-GTV). Treatment is given daily Monday-Friday over 5 weeks. Following completion of treatment in the experimental arm patients will have 2 years of follow-up from time of randomisation at the local recruiting/referring centre. Control Arm: The patients in the control arm would be under standard of care surveillance i.e. "watch and wait", with no treatment or other intervention. Patients will have 2 years of follow-up from time of randomisation at the local recruiting/referring centre. If the disease progresses, the patient will receive SOC treatment i.e. immunotherapy with nivolumab and ipilimumab, or chemotherapy at the clinician's discretion. Statistical analysis plan: The sample size is 148 patients (74 patients per arm). This is to detect a OS hazard ratio of 0.58, equivalent to an improvement in 2-year OS from 30% to 50%, with 85% power and 5% two-sided alpha. Recruitment to complete in 3 years across 20 UK centres with 2 years of additional follow-up and up to 5% dropout. Interim analyses for OS efficacy will be performed when 50, 75 and 110 patients have been randomised at around 1.5, 2.0 and 2.5 years respectively. Using a fixed-se | * Patients ≥18 years of age, with biopsy confirmed MPM and histological subtyping (epithelioid or non-epithelioid) * N0 or N1 and M0 disease * Written informed consent * Patient and local/regional MDT opt for active surveillance and deferral of SACT until clinical or radiological progression * WHO Performance Status 0-1 * Disease confined to one hemithorax based on CT assessment * Adequate pulmonary function * ≥ 40% predicted post-FEV1; * ≥ 40% predicted DLCO/TLCO * Agreement to travel to either proton beam therapy centres (i.e. UCLH or The Christie) if randomised to arm 2 * Agreement to be followed up at a local HIT-Meso trial site * Patient likely able to complete PBT planning based on local assessment | * Presence of metastatic or contralateral disease * Cytological diagnosis and/or undetermined histological subtype * Prior thoracic radiotherapy, chemotherapy, immunotherapy for MPM * Prior radical surgery for MPM (extrapleural pneumonectomy or extended pleurectomy decortication or pleurectomy decortication) * Initial systemic therapy or surgery is required and the patient and local/regional MDT do not opt for active surveillance * Involvement of contralateral or supraclavicular lymph nodes * T4 disease with invasion of the myocardium * N2 and/or M1 disease * Presence of new effusion that is not amenable to drainage * WHO Performance Status ≥ 2 * Women who are pregnant or breast feeding * Current or previous malignant disease which may impact on the patient's life expectancy * Patient fitted with a pacemaker or implantable cardioverter-defibrillator (ICD)\\ * Diagnosis of clinically significant interstitial lung disease (ILD), excluding mild fibrosis or incidental findings * Chronic non-malignant disease with an estimated three-year survival rate of less than 20% * Patient with prior thoracic / abdominal radiotherapy for malignancy who was not discussed with sponsor before recruitment | 148 | 43 | 2024-03-28 | 2029-09-30 | 67 | 67 | Protocol eligibility criteria restricted enrollment to 29%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06793189 | A Prospective Study to Evaluate the Efficacy and Safety of MZL-IPI Risk-adapted Targeted Therapy in Patients With Untreated Marginal Zone B-cell Lymphoma | PHASE_II | Oncology | Marginal Zone Lymphoma(MZL) | Marginal zone lymphoma (MZL) is a common type of indolent lymphoma that originates from the marginal zone of lymphoid follicles. This study aims to evaluate targeted therapy based on the prognostic risk stratification of MZL-IPI in newly diagnosed MZL cases requiring systemic treatment, and provides a basis for precision treatment of MZL. | * 1\. Histopathologically confirmed CD20-positive marginal zone lymphoma (according to the 2016 WHO classification). 2\. Age ≥ 18 years old, regardless of gender. 3. MZL patients requiring systemic treatment, including but not limited to: 1. Helicobacter pylori (HP)-positive or HP - negative gastric mucosa extranodal marginal zone lymphoma (MALT) patients with progression/relapse after local treatment (including surgery, radiotherapy, and anti - Helicobacter pylori treatment). 2. Non - gastric MALT patients with Ann Arbor stage I - II who have progression/relapse after local treatment (including surgery, radiotherapy, etc.), or untreated patients with Ann Arbor stage III - IV who meet the GELF criteria recommended by the NCCN guidelines. 3. Splenic marginal zone lymphoma (SMZL) patients with progression/relapse after local treatment (including splenectomy, antiviral treatment for HCV - positive patients, etc.), or untreated patients meeting the criteria of progressive or painful splenomegaly, symptomatic or progressive cytopenia such as HB \< 100g/L, PLT \< 80×10⁹/L, absolute neutrophil count (ANC) \< 1.0×10⁹/L. 4. Nodal marginal zone lymphoma (NMZL) patients with Ann Arbor stage I - II who have progression/relapse after local treatment (including surgery, radiotherapy, etc.), or untreated patients with Ann Arbor stage III - IV who meet the GELF criteria recommended by the NCCN guidelines. 4\. Eastern Cooperative Oncology Group (ECOG) performance status score of 0-2. 5. Life expectancy of at least 3 months. 6. The patient has adequate bone marrow (except those caused by MZL), liver and kidney functions. 7\. Able to comply with the research procedures and cooperate in the implementation of the entire research process; 8. Written informed consent; 9. Women with fertility agree to take appropriate measures to avoid pregnancy during the treatment period until at least one year after the end of treatment; Men agree to maintain abstinence or use barrier contraception. | * 1\. Histologically transformed into high-grade lymphoma. 2. Known central nervous system involvement of MZL. 3. Previous systemic treatment including immunotherapy, chemotherapy or targeted drugs. 4\. Previous autologous stem-cell transplantation or allogeneic tissue/solid organ transplantation. 5\. History of other invasive cancers within the past 3 years that have not received curative treatment or are still receiving anti-cancer treatment (including hormonal therapy for breast or prostate cancer). 6\. Complicated with uncontrolled cardiovascular and cerebrovascular diseases (such as New York Heart Association-defined grade 3 or 4 heart failure, arrhythmia, myocardial infarction, stroke, or intracranial hemorrhage), coagulation - disorder diseases, connective tissue diseases, severe infectious diseases (including active pulmonary tuberculosis), etc. 7\. Known human immunodeficiency virus (HIV) infection, or active hepatitis B or C virus infection (positive result shown by polymerase chain reaction \[PCR\]). Serological antibody - positive is allowed if HBV DNA \< 10³ IU/ml; HCV RNA test must be negative. 8\. Vaccinated with live attenuated vaccines within 4 weeks before starting investigational treatment. During the study, patients are prohibited from receiving live attenuated vaccine inoculations, including influenza vaccines. 9\. Requiring continuous treatment with potent and moderate-effect CYP3A inhibitors or CYP3A inducers. 10\. Unable to swallow capsules or having diseases that significantly affect gastrointestinal function, such as malabsorption syndrome, bariatric surgery, inflammatory bowel disease, or partial or complete intestinal obstruction. 11\. Psychiatric patients or other patients known or suspected to be unable to fully comply with the study protocol. 12\. Pregnant or lactating women. 13. Other concurrent and uncontrolled medical conditions that, in the investigator's opinion, will affect the patient's participation in the study. | 145 | 23 | 2025-01-23 | 2028-12-31 | 48 | 48 | Protocol eligibility criteria restricted enrollment to 16%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT05506410 | A Prospective Clinical Study of Hanlikang and BTK Inhibitors in the Treatment of Newly Diagnosed Mantle Cell Lymphoma |  | Oncology | Newly Diagnosed Mantle Cell Lymphoma | An open-label, single-arm, multicenter, prospective clinical study of Hanlikang and BTK inhibitors in the treatment of newly diagnosed mantle cell lymphoma | 1. Age 18-70, ECOG score 0-2; 2. Estimated survival time \>6 months; 3. Mantle cell lymphoma was confirmed by pathology. 4. Acceptable hematological indexes without chemotherapy contraindications; Neutrophil absolute value ≥1.0×10\^9 /L, PLT≥75×10\^9 /L, hemoglobin ≥80g/L (except patients with lymphoma bone marrow infiltration); 5. At least one measurable lesion. For intrnodal lesions, they were defined as long diameter ≥1.5cm and short diameter ≥1.0cm; For r extranodal lesions, the length should be ≥1.0cm; 7\. Liver function: TBIL≤1.5×ULN; ALT or AST ≤2.5 x ULN; Alkaline phosphatase ≤3×ULN in patients with non-bone invasion; 8\. Kidney function: serum creatinine ≤1.5×ULN; 9\. Excluding other major diseases, the heart function is normal; 10 Women and men of childbearing age and their spouses are willing to use adequate contraception throughout the study period, and women of childbearing age must have a negative serum pregnancy test within 7 days before the first dose; 11 Subjects voluntarily participated in the clinical trial, signed the informed consent form, and cooperated with the follow-up; 12\. There is no other relevant treatment including traditional Chinese medicine (anti-tumor), immunotherapy, biologic therapy (except anti-bone metastasis and other symptoms); | 1. Patients with definite neuropathy or psychosis, including dementia or seizures, a history of psychotropic substance abuse and inability to abstinence, or other substantial lesions that may increase CNS toxicity; 2. Participating in other clinical trials or participating in other clinical investigators 4 weeks before enrollment (except those not receiving treatment); 3. Systemic autoimmune disease or immune deficiency; 4. Refusing to collect blood samples; 5. Allergic to any drug in the protocol; 6. Pregnant and lactating women; 7. Major diseases that can cause test interference and uncontrolled active infected persons; 8. Primary or secondary central tumor; 9. Contraindications to chemotherapy; 10. Not considered suitable for inclusion. 11. Known active bacterial, viral, fungal, mycobacterial, parasitic, or other infections (other than nail bed skin fungal infections) or any major systemic infection event requiring intravenous antibiotic treatment or hospitalization (other than neoplastic fever) within 4 weeks prior to enrollment; 13\. Application of other antitumor therapies (such as radiotherapy, chemotherapy, hormone therapy, biotherapy, immunotherapy); 14\. Other serious medical conditions that may limit the subject's participation in the study, such as uncontrolled diabetes; Severe cardiac insufficiency (NYHA grade II or above); Acute coronary syndrome in the last 6 months; Coronary revascularization such as stenting, cabG, and other cardiac and macrovascular procedures within the last 6 months; Severe arrhythmias include frequent ventricular premature, ventricular tachycardia, rapid atrial fibrillation/flutter, and severe bradycardia. Uncontrolled hypertension: systolic blood pressure \>150mmHg, diastolic blood pressure \>100mmHg. Gastric ulcers (those identified by the investigators as being at risk for perforation); Active autoimmune diseases (e.g. systemic lupus erythematosus, rheumatoid arthritis, multiple sclerosis, Sjogren's syndrome, autoimmune thrombocytopenia, etc.); Severe respiratory diseases (e.g. obstructive pulmonary disease and history of bronchospasm), etc.; 15\. Hemophagocytic cell syndrome; 16\. Hepatitis B surface antigen (HBsAg) or hepatitis B core antibody (HBcAb) was positive, and the peripheral blood hepatitis B virus (HBV) DNA titer was not within the normal reference range; Hepatitis C virus (HCV) antibody positive and HCV RNA positive in peripheral blood; Human immunodeficiency virus (HIV) antibody positive; Cytomegalovirus (CMV) DNA test positive; Who tested positive for syphilis. | 100 | 70 | 2022-08-12 | 2026-12-30 | 53 | 53 | Protocol eligibility criteria restricted enrollment to 70%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06246110 | A Phase 2 Study of EIK1001 in Combination With Pembrolizumab and Chemotherapy in Patients With Stage 4 Non-Small Cell Lung Cancer | PHASE_II | Oncology | NSCLC | This is a multicenter open-label phase 2 trial that aim to assess the safety, tolerability, and efficacy of EIK1001 in combination with standard of care in participants with both confirmed stage 4 squamous and non-squamous NSCLC who have not received prior systemic therapy for the advanced disease. The study includes dose finding and evaluates adverse events and efficacy. | 1. be ≥ 18 years of age on the day of signing of informed consent. 2. confirmed Stage 4 NSCLC (squamous or non-squamous) and be considered for standard of care. 3. have confirmation that mutation-directed therapy is not indicated (documentation of absence of tumor activating mutations/fusions that are approved for first line therapy). 4. have at least 1 lesion with measurable disease at Baseline according to RECIST 1.1 as determined by the local site Investigator/radiology assessment. 5. have not received prior systemic treatment for advanced/metastatic NSCLC. 6. have an ECOG Performance Status of 0 to 1. 7. have adequate organ function. | 1. does not have predominantly squamous cell or non-squamous cell histology NSCLC. Mixed tumors will be categorized by the predominant cell type; if small cell elements are present, the participant is ineligible. 2. is currently participating in or has participated in a study of an investigational agent and received investigational therapy within 4 weeks or 5 half-lives (whichever is shorter) of administration of EIK1001. 3. prior to the first dose of EIK1001, has received prior systemic therapy for metastatic disease, or had major surgery (\< 3 weeks prior to the first dose). 4. has completed palliative radiotherapy within 7 days of the first dose of study drug administration. 5. has a known history of prior malignancy, except if the participant has undergone potentially curative therapy with no evidence of that disease recurrence for 5 years. 6. has an active infection requiring therapy. | 70 | 55 | 2024-02-06 | 2025-11-06 | 21 | 21 | Protocol eligibility criteria restricted enrollment to 79%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06945120 | Efficacy of an Asian Culture-tailored Lung Health (ACT) Intervention on Lung Cancer Screening and Smoking Cessation in Asian Americans |  | Oncology | Smoking Cessation | This two-arm stratified randomized clinical trial is to test a counseling and educational program designed to improve lung health through smoking cessation for Chinese and Korean American smokers at high risk for lung cancer. Participants will be randomized into one of two groups: Group A: ACT Lung Health Intervention versus Group B: Standard Care. Randomization means a participant is placed into a study group by chance. The research study procedures include screening for eligibility, questionnaires, and saliva tests. It is expected participation in this study will last about 6 months. About 50 participants are expected to take part in this research study. The National Cancer Institute is providing funding for this trial. | * Self-identify as either Chinese or Korean * Speak either Korean, Mandarin, or English * Are 18 years of age or older * Are current smokers (i.e., have smoked at least 100 traditional cigarettes ever and have smoked at least one traditional cigarette within the prior 30 days) * Will live in the United States for the next 12 months | * Hospitalization due to a serious mental illness (e.g., psychotic disorders) during the prior 6 months. * We will not include any of the following special populations: * Adults unable to consent. * Adults younger than 50 or older than 80 years * Individuals who are not yet adults (infants, children, teenagers) * Pregnant women * Prisoners | 50 | 0 | 2027-01-18 | 2029-07-18 | 30 | 30
NCT05133843 | Complete Functional Assessment of Intermediate Coronary Artery Stenosis Before and After Transcatheter Aortic Valve Implantation (TAVI) in Patients With Severe Symptomatic Aortic Valve Stenosis |  | Cardiovascular | Coronary Artery Stenosis | Prospective, single center, open-label study to 1. compare coronary flow reserve (CFR), index of microvascular resistance (IMR), fractional flow reserve (FFR) and resting full cycle ratio (RFR) values before TAVI and 6 months after TAVI 2. correlate testing of microcirculatory function (IMR) with measurements of functional testing (FFR and RFR) before and six months after TAVI 3. correlate functional testing (FFR and RFR) with computed tomography (CT) derived fractional flow reserve (CT-FFR) before and six months after TAVI. | * Age \>18 years * Willing to participate and able to understand, read and sign the informed consent document before the planned procedure * Severe symptomatic aortic stenosis with indication for TAVI according to current guidelines deemed by the Heart Team * Patients who have undergone coronary CT angiography before TAVI in which CAD could not be ruled out * CAD in one or more native major epicardial vessels or their branches by coronary angiogram with visually assessed coronary stenosis, in which the physiological severity of the lesion is in question (typically 40-90% diameter stenosis). * Eligible for invasive coronary angiography and functional assessment (FFR, RFR, CFR and IMR) * Eligible for coronary CT-angiography and functional assessment (CT-FFR) | * Patients whose CT-angiography was determined to be non-diagnostic/unreadable during its evaluation * Previous coronary artery bypass grafting with patent grafts to the interrogated vessel * Patients with severe lesions with a diameter stenosis ≥ 90%, flow-limiting lesions, or a significant left main coronary artery stenosis * Critical coronary artery disease deemed by the Heart Team to require immediate revascularization * Contraindication to adenosine (e.g. bronchial asthma) * Chronic renal impairment with severe reduction of glomerular filtration rate (eGFR \<30 ml/min) * Presence of cardiogenic shock * Participation in another interventional study involving the left heart or coronary arteries | 50 | 41 | 2021-09-29 | 2025-09-30 | 49 | 49 | Enrollment reached 82% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06916520 | Prasugrel Monotherapy Reduced Dose in Acute and Chronic Coronary Syndrome Patients After Percutaneous Coronary Intervention | PHASE_IV | Cardiovascular | Coronary Arterial Disease (CAD) | Rationale: Dual antiplatelet therapy, consisting of aspirin and a P2Y12-inhibitor, reduces the risk of stent-related and non-stent-related ischemic events after percutaneous coronary intervention (PCI). However, this therapy is also associated with a higher risk of bleeding. Given the advances in stent technology and pharmacology, it may be possible to treat patients undergoing PCI with low dose prasugrel as single antiplatelet therapy, regardless of medical history, age or body weight. Objective: Assess the feasibility and safety of a single antiplatelet strategy with a reduced dose of prasugrel 5 mg after PCI in acute and chronic coronary syndrome patients (ACS and CCS). Study design: Open-label, single-centre, randomized controlled trial. Study population: Patients undergoing successful PCI due to acute or chronic coronary syndrome. Intervention: A once-daily reduced dose of 5 mg prasugrel for 6 months in CCS patients and for 12 months in ACS patients, preceded by a loading dose of 60 mg prasugrel after PCI, administered without concomitant use of aspirin. Main study parameters/endpoints: The primary endpoint is Net Adverse Clinical Events (NACE), a composite of all-cause death, myocardial infarction, definite stent thrombosis, ischemic stroke, clinically relevant non-major bleeding or major bleeding defined as Bleeding Academic Research Consortium type 2, 3 or 5. | * Acute Coronary Syndrome * Chronic Coronary Syndrome * Successful PCI | * Known allergy or contraindication for prasugrel, including Active pathological bleeding Severe liver disease (defined as Child Pugh class C) * Current indication for oral anticoagulant therapy (OAC) * Indication for ongoing DAPT (e.g. PCI ≤ 6 months for CCS or ACS ≤ 12 months) * Pregnancy or breast-feeding women * Participation in another trial with an investigational drug or device * Recent or ongoing use of CYP2B6 substrates with a narrow therapeutic window (e.g. cyclophosphamide, efavirenz) | 300 | 12 | 2025-11-13 | 2029-06-13 | 44 | 44 | Protocol eligibility criteria restricted enrollment to 4%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06435585 | Responders and Non-responders in the Management of Heart Failure - Significance of Genetic Influence and Identification of Novel Informative Biomarkers |  | Cardiovascular | Heart Failure | The national heart failure quality registry SwedeHF started in 2003. It is the world's largest continuous HF registry enrolling clinician-judged HF (regardless of LVEF) at time of hospital or clinical visit. Eighty variables are entered into an electronic database managed by the Uppsala Clinical Research Center (UCR). There are \>140,000 registrations from \>110,000 unique patients from 70 hospitals in Sweden. University hospitals in Sweden with access to central biobanking will collect a high-quality biobank linked to SwedeHF consisting of blood plasma, whole blood and urine enabling genetic, proteomic and metabolomic analyses as well as analyses of different biomarkers of interest for HF patients. This will provide unique opportunities for future research within the national SwedeHF registry. | 1. Written informed consent 2. Heart failure defined by symptoms and signs of heart failure as judged by the local investigator 3. Registered in SwedeHF | 1. Plasma donation within 1 month of enrolment or any blood donation/blood loss \>500 mL during the 3 months prior to enrolment 2. Previous allogeneic bone marrow transplant (genetics) 3. In the opinion of the investigator, condition/s that may either put the patient at risk on participation or influence the results or the patient's ability to participate in the study. | 5000 | 2480 | 2021-02-17 | 2030-12-31 | 120 | 120 | Protocol eligibility criteria restricted enrollment to 50%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT07286643 | Point-of-care Echocardiogram (POCUS) Guided Resuscitation Versus Conventional Goal- Directed Therapy in the Management of Cirrhosis With Severe Sepsis or Septic Shock: A Randomised Controlled Trial |  | Cardiovascular | Cirrhosis, Liver | * Patients with cirrhosis requiring intensive care for severe sepsis carry a risk of high mortality due to altered hemodynamics with reduced effective arterial volume, portal hypertension, presence of ascites, and risk of complications like acute variceal bleeding (AVB), acute kidney injury (AKI) and circulatory failure(3-5). The main principles for management of severe sepsis include early recognition, control of the source of infection, appropriate and timely administration of antimicrobial agents, and resuscitation with intravenous fluids +/- vasoactive drugs, if needed (6). * Due to portal hypertension, these patients have a hyperdynamic circulation, increased capillary permeability, splanchnic arteriolar vasodilation, and may have latent cirrhotic cardiomyopathy (CCM) (7). Hence assessment of volume status and cardiac reserve using conventional central venous pressure (CVP) or mean arterial pressure (MAP) remains difficult (8). Although inferior vena cava (IVC) dynamics and IVC collapsibility index are reasonable accurate for ventilated patients, their use in spontaneously breathing subjects or those with tense ascites are not defined(9). Even measures like passive leg raising and Valsalva manoeuvre are difficult to perform in cirrhotic patients with tense ascites. * Early goal directed therapy (EGDT) improved outcomes in a randomized trial in patients with severe sepsis(10). Thereafter EGDT was incorporated into the 6-hour resuscitation bundle of the surviving sepsis campaign guidelines, but did not incorporate patients with cirrhosis(11-13). Following the early EGDT trials, studies focussed choice of resuscitation fluid i.e., albumin versus normal saline or balanced salt solution (BSS), concerns about potential risks of volume overload and pulmonary edema and lack of generalisability in subsequent trials showed that there was no associated survival benefit with an aggressive fluid protocol(14, 15). In the ALBIOS study, 1818 patients with severe sepsis or sept | 1. Critically ill patient with cirrhosis of any etiology 2. Sepsis-related Hypotension (MAP \<65mmHg or SBP \<90mmHg) 3. 18-65 yrs of age - | 1. Already on vasopressors/inotropes 2. Severe pre-existing cardiopulmonary disease like porto-pulmonary hypertension (PPH), known coronary artery disease, congenital or valvular heart disease, prosthetic cardiac valves, dilated or restrictive cardiomyopathy. 3. Poor chest wall window due to left pleural effusion, left pneumothorax, small intercostal spaces that restrict performance of a POCUS. 4. Active bleeding like variceal bleed 5. Cerebrovascular events 6. Chronic renal disease - End Stage Renal Disease (ESRD)/ patient on renal replacement therapy 7. Admission to ICU following liver transplantation, burns, cardiac surgery 8. Previous transjugular intra hepatic portosystemic shunt (TIPS), 9. Hepatocellular carcinoma 10. Pregnant or lactating women 11. Informed consent refused by patient or attendants 12. Active COVID-19 infection | 140 | 5 | 2026-01-01 | 2028-12-30 | 36 | 36 | Protocol eligibility criteria restricted enrollment to 4%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06992089 | Pacemaker Implantation in Patients With Heart Failure With Preserved Ejection Fraction, Chronotropic Incompetence and Small Ventricular Volume. The SHOP-HF Trial |  | Cardiovascular | Heart Failure With Preserved Ejection Fraction | This study is designed as a multicenter, prospective, controlled, randomized, two-arms, cross-over, two parallel cohorts, efficacy Clinical research with CE-marked medical device . The crossover trial will be performed in a blind fashion, so each participant will be evaluated during both blinded pacing-on and pacing-off phases, each of which will last 3 months. The population includes patients with the diagnosis of stable HFpEF according to criteria of the European Society of Cardiology and New York Heart Association (NYHA) functional class II-III/IV, left ventricular hypertrophy with small ventricular volume, sinus rhythm with low basal heart rate and chronotropic incompetence (CI). All patients will undergo pacemaker implantation, and computer-generated randomization sequence previously designed will be used to allocate participants (in a 1:1 ratio) to receive: (a) programming of the pacemaker with pacing On followed by pacing Off in two periods of 3 months; or (b) programming of the pacemaker with pacing Off followed by pacing On in two periods of 3 months. The study will be conducted in three centers in Spain. Discounting the time due to staggered entry, the total duration of a patient's follow-up will be 7 months. | * Stable symptomatic heart failure (NYHA functional class ≥II) during the last month. * Diagnosis criteria of HFpEF according to ESC guidelines: 1. symptoms and signs of HF. 2. left ventricular ejection fraction ≥50% by Simpson method. 3. proBNP \>125 pg/mL in the last month. 4. at least one additional criterion: 1. relevant structural heart disease (left ventricular hypertrophy and/or left atrial enlargement); and/or 2. Diastolic dysfunction. * Left ventricular hypertrophy was defined as wall thickness \> 10 mm. * Small ventricular volume was defined as indexed left ventricular end diastolic volume \< 45 ml/m2. * Adults ≥18 years old. * Previous admission for acute heart failure. * Chronotropic incompetence assessed by CPET, defined as: \[(HRmax - HRrest)\]/\[(220 - age) - (HRrest)\] \< 0.62. * Resting heart rate \< 65 bpm in sinus rhythm or 70 bmp in atrial fibrillation. | * Inability to perform a valid baseline exercise test. * Significant primary pulmonary disease; including pulmonary arterial hypertension, chronic thromboembolic pulmonary disease or chronic obstructive pulmonary disease. * Patient with prior history of left ventricular ejection fraction \<50%. * History of an acute coronary syndrome in the previous 12 months. * Effort angina or signs of ischemia during CPET. * RER threshold at \<1.05 at the CPET. * Significant primary moderate to severe valvular disease. * Any other comorbidity with a life expectancy lower than 1 year. * Heart rate at rest \> 75 lpm. * Other pacemaker indication. * Pregnant women. * Baseline rhythm different from sinus rhythm or atrial fibrillation. * Active treatment with beta-blockers, digitalis or non dihidropiridine calcium channel blockers. | 30 | 15 | 2025-06-17 | 2026-12-17 | 18 | 18 | Protocol eligibility criteria restricted enrollment to 50%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT03586518 | Validating the Accuracy of Novel, Non-contrast, Cardiac Magnetic resOnaNce Imaging in Defining Myocardial FIbRosis in Patients With End-stage Renal Disease on haeModialysis: the CONFIRM Study |  | Cardiovascular | End Stage Kidney Disease | Native T1 mapping is a novel, non-contrast, cardiac MRI technique that characterises myocardial tissue by exploiting the different water content of tissues. It correlates well with histo-pathological levels of myocardial fibrosis in diseases of pressure overload such as aortic stenosis. There is growing evidence to demonstrate the potential of native T1 mapping as an imaging biomarker of myocardial fibrosis in patients with ESRD; myocardial native T1 values are higher in patients with ESRD than controls, and associate with measures of myocardial strain and circulating markers of cardiac dysfunction. Although native T1 times are affected by water content of tissues, our group has shown that native T1 times are not influenced by clinical changes in fluid status in HD patients and that the inter-study reproducibility and intra- and inter-observer variability of native T1 are outstanding. Native T1 mapping is a promising, non-invasive imaging biomarker of myocardial fibrosis in patients with advanced renal disease. It is essential that the technique is validated against histology before further use in clinical studies. The aim of this study is to directly assess the relationship between native T1 mapping and levels of MF examined at post-mortem in haemodialysis patients. | * Prevalent haemodialysis patient (more than 3 months) * Active on the supportive care register with anticipated death in the subsequent 12 months * Able to give informed consent * Consent to donation of heart for research following death * Able to understand written and verbal explanations in English | * Contraindication to MRI scan (e.g. pacemaker, incompatible metallic implants, claustrophobia) * Patients with expected or potential infiltrative cardiomyopathy (e.g. amyloidosis) * Unable to give informed consent * Unable to understand written and verbal explanations in English | 9 | 0 | 2026-12-18 | 2029-09-18 | 34 | 34
NCT06906276 | Walking and Thinking - Brain Activity During Complex Walking in Atypical Parkinsonian Syndromes |  | Neurology | Gait Disorders, Neurologic | Every-day life means being part of a complex environment and performing complex tasks that usually involve a combination of motor and cognitive skills. However, the process of aging or the sequelae of neurological diseases such as atypical Parkinson's disease (APD) compromises motor-cognitive interaction necessary for an independent lifestyle. While motor-cognitive performance has been identified as an important goal for sustained health across different clinical populations, little is known about underlying brain function leading to these difficulties and how to best target these motor-cognitive difficulties in the context of rehabilitation and exercise interventions. The challenge of improving treatments of motor-cognitive difficulties (such as dual-tasking and navigation) is daunting, and an important step is arriving at a method that accurately portrays these impairments in an ecologically valid state. The investigators aim therefore to explore brain function during complex walking in healthy and APD by investigating the effects of age and neurological disease on motor-cognitive performance and its neural correlates during three conditions of complex walking (dual-task walking, navigation and a combination of both) using non-invasive measures of brain activity (functional near infrared spectrometry, fNIRS) and advanced gait analysis in real time in older healthy adults and people with APD. | * clinical diagnosis of PSP according to Movement Disorder Society (MDS) (2017) or * MSA according to MDS criteria (2022) * the ability to walk with or without a mobility device for ≤5 minutes continuously | * cognitive difficulties affecting the ability to understand and/or follow verbal/written - instructions * severe freezing of gait * Severe hearing or visual impairments that affect participation in the assessments * Other neurological diseases * Other diseases that can affect gait or balance. | 30 | 8 | 2025-03-14 | 2027-12-31 | 34 | 34 | Protocol eligibility criteria restricted enrollment to 27%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT07213648 | Modification of Threat Interpretation Bias to Reduce Anxiety in Neurodegenerative Movement Disorders (Aim 3) |  | Neurology | Huntington Disease | The investigators will conduct a pilot randomized controlled trial of the MindTrails-Movement CBM-I app in patients with Huntington's disease and Parkinson's disease (N=136). Participants randomly assigned to the intervention group (N=68) will be asked to download the MindTrails-Movement mobile app and to complete daily CBM-I training sessions and nightly surveys, in addition to surveys at baseline and every 2 weeks for the duration of the 6-week intervention and at 4-week follow-up (week 10). Participants assigned to the waitlist control group will download a control version of the app without CBM-I training sessions. They will be asked to complete surveys in the app at baseline and every 2 weeks for the duration of the 6-week intervention and at 4-week follow-up (week 10). After 10 weeks, they will be offered the opportunity to access the version of MindTrails-Movement with CBM-I training content. | * Clinical diagnosis of Huntington's disease or Parkinson's disease (genetic diagnosis of HD also acceptable) * With anxiety symptoms (NeuroQoL Anxiety ≥12) | * Cognitive decline precluding ability to consent or complete the intervention (MoCA 5 min/telephone ≤11) * Unable to read and understand English * Does not have regular access to an internet-connected device, capable of downloading and installing the mobile application (i.e., tablet or iPhone running iOS 10 or later or an Android phone running Android 5.0 or later) * Not located in the USA * \<21 years old * Active suicidality based on the answer "yes" to questions 4, 5, or 6b of the Columbia-Suicide Severity Rating Scale (Screen version) | 136 | 12 | 2025-11-20 | 2028-02-20 | 27 | 27 | Protocol eligibility criteria restricted enrollment to 9%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06893055 | Strength-Endurance Circuit Training in Parkinson's Disease: Effects on Disease Severity, Physical Performance, Blood Biomarkers and Quality of Life. |  | Neurology | Parkinson Disease, Idiopathic | The goal of this clinical trial is to determine whether adding strength training to aerobic training has a comparable or greater effect on the clinical status of Parkinson's disease patients than a standalone aerobic training. \- Does combined strength-endurance circuit training provide added benefits to physical performance, disease severity, blood biomarkers, and quality of life in PD patients compared to standalone aerobic training? Participants will: * undergo outcome measurements before and after the 12-week intervention and a 3-month follow-up measurement, * visit the clinic twice a week for 1-hour training sessions. * selected patients will be given a smartwatch with a pedometer that will count their average number of steps before, during and after the training period | * age ≥18 years * diagnosis of idiopathic Parkinson´s disease * Hoehn-Yahr Scale ≤ 2,5 * stable dopaminergic medication | * age ≥75 years * Hoehn-Yahr Scale ≥ 2,5 * deep brain stimulation * presence of freezing * Camptocormia * inability to walk without support * inability to perform study procedures * limiting co-morbidities * attendance at training sessions below 70% | 90 | 45 | 2025-03-03 | 2027-07-03 | 28 | 28 | Protocol eligibility criteria restricted enrollment to 50%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT07032350 | E-Tailored Pain Management Support for Dementia Family Caregivers |  | Neurology | Care Giving Burden | This randomized controlled trial will assess the feasibility, usability, and preliminary efficacy of the Pain Control Enhancement App (PACE-app), a web-based intervention designed to support family caregivers of persons with dementia in managing pain. The trial will also explore mechanisms through which the PACE-app may affect caregiver and care recipient outcomes. Uncontrolled pain is common in people with dementia and presents unique challenges for caregivers, particularly those with limited access to specialized healthcare services. Family caregivers often lack adequate knowledge, skills, and support to manage pain effectively, contributing to suboptimal outcomes for both caregivers and care recipients. The PACE-app provides tailored, technology-based pain management support that includes: Screening of caregiver-specific challenges in pain management; Personalized pain management strategies based on the screening results; Communication tools to facilitate interactions with healthcare providers; A digital pain diary for tracking care recipients' pain experiences. A total of 60 family caregivers of people with dementia and chronic pain will be randomized 1:1 to either the PACE-app intervention group or a usual-care control group. Participants in the intervention arm will use the app for 1 month and complete outcome assessments at baseline, 1 month (post-intervention), and 2 months (follow-up). Participants in the control arm will continue their usual caregiving practices and complete assessments on the same schedule. Primary outcomes include feasibility (recruitment, retention, adherence to study protocol) and acceptability (measured by app usage analytics and qualitative interviews). Secondary outcomes include changes in caregiver self-efficacy in pain management, adherence to prescribed pain treatments, caregiver burden, stress, depression, and communication with healthcare providers. The study will also examine potential mediators (caregiver knowledge, c | * Be a primary caregiver - (a family member, relative, or friend) of a person with dementia (or cognitive impairment) and chronic pain (lasting \>3 months)' * Be responsible for managing the care recipient's pain and pain treatments (including interpreting verbal or non-verbal pain communication). * Be age 18 - 100. * Be able to read and speak English. * Have regular access to an electronic device (tablet, laptop, or computer) with internet connectivity (for using the app and participating in data collection). * Be accessible by phone or email to schedule meetings. * Be willing to commit to the full study duration and protocol. | * Currently participating in another research study that could interfere with this intervention. | 60 | 8 | 2025-05-22 | 2028-04-22 | 36 | 36 | Protocol eligibility criteria restricted enrollment to 13%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT04786821 | Feasibility Study for a Randomised Control Trial for the Acceptability of Exoskeleton Assisted Walking Compared to Standard Exercise Training for Persons With Mobility Issues Due to Multiple Sclerosis |  | Neurology | Multiple Sclerosis | Multiple sclerosis (MS) is a chronic, inflammatory disease of the central nervous system. Lack of physical activity is common in people with MS (pwMS). This can lead to several comorbid conditions such as obesity, metabolic syndrome, osteoporosis, hypertension, diabetes and worse prognosis. An increasing number of studies suggest that physical exercise can play an important role in managing symptoms, preventing complications and comorbidities in pwMS, and may possibly be neuroprotective. However, doing exercise can be very challenging for pwMS who have moderate/severe mobility disability and who have problems with walking. In this project, the investigators will explore the use of a powered Exoskeleton as an exercise tool for people with moderate to severe difficulty walking due to MS. Powered Exoskeletons are wearable robots that offer opportunity to persons with lower limb weakness to stand and walk. The Exoskeleton-assisted training provides active training with potentially much less intervention needed from therapists. However, it is not clear whether pwMS can walk with a powered Exoskeleton at speeds and intensities sufficient to positively affect health and fitness outcomes. Thus, in this study, the investigators aim to explore whether using an Exoskeleton will enable people with MS to exercise at a moderate intensity and whether people with MS find this acceptable and safe to do on a regular basis. The investigators will also explore whether training with an Exoskeleton can improve walking. The investigators will train 12 patients with MS to walk with an Exoskeleton twice a week for 8 weeks. The investigators will compare the effects with another group of 12 patients who will do exercises with a fitness instructor twice a week for 8 weeks. The investigators will study whether walking with Exoskeleton is better than fitness training in terms of fitness outcomes, walking and cognitive, psychological factors. | * Diagnosis of MS as per the McDonald criteria (Polman et al., 2011). * Age 18 years or older. * Cognitive ability to give consent and participate in the protocol. * Walking limitations with Expanded Disability Status Scale (EDSS) scores ranging from 5.0 to 7.5. * Enough strength in hands and shoulders to support themselves standing and walking using crutches or a walker. * Meet the general requirements to fit with the Phoenix Exoskeleton (160-190.5 cm in height, weight below 80 Kg, hip width no greater than 42.7 cm measured when sitting, healthy skin where it touches Phoenix Exoskeleton). * Able to tolerate exercise twice per week as judged by the PI during screening. | * Any illness, other than MS, affecting walking and exercise performance. * Severe cognitive or behavioral impairment. * Relapses 3 months prior to enrolment. * Change in disease modifying drugs for MS 6 months before enrolment. * Botulin toxin injections for the lower limbs the previous 3 months. * Any medical contraindications to assisted walking (e.g., cardiovascular condition, weight-bearing restrictions, osteoporosis or other fracture risk, pregnancy, uncontrolled seizure). * Significant flexion contractures limited to 35 degrees at the hip and 20 degrees at the knee that precluded Phoenix Exoskeleton fit. * Psychopathology or other health conditions that the physiotherapist, in his or her clinical judgement, considers to be exclusionary to safely use an Exoskeleton. * Living more than 20 miles away from the experiment location to reduce burden on patients due to the number of planned study visits. | 24 | 24 | 2022-06-23 | 2024-10-30 | 29 | 29 | Enrollment exceeded target in Neurology; strong site engagement and pre-screening drove performance. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06426316 | Immune System, Inflammation, Migraine - The Role of Cytokines and Regulatory T Lymphocytes in Migraine Pathophysiology |  | Neurology | Migraine Disorders | Migraine is the 6th most frequent disease (14% of the population) and the second leading cause of disability worldwide. From puberty and onward, migraine is 2 to 3 times more frequent in women, which also suffer from more severe attacks. Migraine is also up to twice as prevalent in patients suffering from autoimmune or inflammatory diseases such as multiple sclerosis (MS), rheumatoid arthritis (RA), Crohn disease (CD), systemic lupus erythematosus (SLE) and endometriosis, whereas patients with long standing type 1 diabetes mellitus (T1DM) - an autoimmune but non inflammatory disease - seem to be less affected compared to the general population. Despite the identification of the role of peptides such as CGRP in migraine pathophysiology and the development of targetted anti-CGRP treatments, many patients remain unresponsive and the mechanisms behind migraine are still unclear. The trigemino-vascular system is involved in the perception of migraine pain. Migraine occurs with trigemino-cervical neuron sensitization, leading to peptide secretion (such as CGRP, PACAP-38 and VIP), which induce neurogenic inflammation that is responsible for vasodilation, capillary leakage, oedema and further sensitization of the trigemino-vascular system, leading to amplified perception of migraine pain. CGRP, PACAP-38 and VIP infusions all induce migraine attacks in migraine patients, and only mild or no headache in healthy volunteers. Sex hormones, prolactin and insulin are also involved in migraine pathophysiology, and the immune system, through cytokine production and immune cell dysregulations seems to also play a role in the pathogenesis of migraine. Both are closely related as sex hormone levels may have an influence on the levels of certain immune cell subtypes. Several pro-inflammatory cytokines (tumor necrosis factor (TNF)-alpha, interferon (IFN)-gamma and interleukin (IL)-6) were shown to be elevated in migraine patients but also inflammatory diseases such as MS and endometri | * female * 18 - 50 years of age * at least 50 kg * autoimmune/inflammatory disease groups : with a diagnosis of multiple sclerosis, systemic lupus erythematous, rheumatoid arthritis, Crohn's disease, type 1 diabetes or endometriosis * migraine group : with a diagnosis of migraine with at least 4 headache days per month | * BMI \< or = 17 ou \> or = 30kg/m² * type 2 diabetes, immune deficit, other chronic autoimmune or inflammatory disease * non-migraine headache, except for tension type headache of less than 4 days/month * pregnancy, delivery, miscarriage, breast-feeding, participation in a medically assisted human reproduction program (ovary stimulation/hormone therapy) \< 3 months before blood sampling * Menopause, hysterectomy, or bilateral oophorectomy * Hormone therapy (besides contraception and treatment of endometriosis) * bone marrow or solid organ transplant * guardianship, curatorship, safeguard of justice or deprivation of liberty * for patients : diagnosis of several autoimmune or inflammatory diseases * for controls : diagnosis of an autoimmune or inflammatory disease * for non-migraine participants : migraine | 396 | 0 | 2027-01-18 | 2029-03-18 | 26 | 26
NCT06106893 | A Single-center Clinical Study Evaluating the Safety and Efficacy of CD19 Universal CAR-γδT Cells in Active Systemic Lupus Erythematosus | PHASE_I | Immunology | Systemic Lupus Erythematosus | The prognosis of patients with active systemic lupus erythematosus (SLE) remains poor, due to two major therapeutic obstacles: (1) current treatment strategies including glucocorticoids, immunosuppressive agents, biological agents, are still difficult to achieve disease control, making the disease condition of some patients continue to be active or even worse; (2) some patients are unable to wean themselves off glucocorticoid and face the risk of numerous adverse effects caused by long-term glucocorticoid dependence, such as glucocorticoid-related diabetes, femoral head necrosis, hypertension, stress ulcers, and infection, etc. Therefore, there is a strong unmet clinical need for more effective treatment for patients suffering from active SLE. Several preclinical studies have shown the efficacy of CAR-T cell treatment in SLE. The aim of this study is to investigate the safety, tolerability, preliminary efficacy, pharmacokinetics (PK), and pharmacodynamics (PD) of CD19 Universal CAR-γδT cells therapy in active SLE. Patients with active SLE will be invited to participate in the study, to receive CD19 Universal CAR-γδT cells intravenous infusion and follow-up visits of up to 2 years after enrollment. | 1. Participants or their guardians understand and voluntarily sign the informed consent form, and be able to complete all the documents, procedures, follow-up examinations and treatments specified in the study protocol, with good compliance; 2. Age range from 18 to 70 years old, regardless of gender; 3. Body weight ≥ 40kg; 4. Participants diagnosed with SLE according to the American College of Rheumatology (ACR) 1997 revised criteria for SLE at least 24 weeks prior to signing the informed consent form; 5. active SLE needs to meet the following criteria at screening: SELENA-SLEDAI score ≥ 6 points; PGA ≥ 1 points; 6. Have received at least 8 weeks of standardized treatment for SLE prior to screening; 7. Female participants need to have a negative pregnancy test, and participants agree to take effective contraceptive measures throughout the study. | 1. Known hypersensitivity to prednisone, immunosuppressive agents; 2. Diagnosis of active severe lupus nephritis within 8 weeks prior to screening, requiring medications prohibited by the research protocol for active nephritis, hemodialysis or prednisone ≥ 100 mg/d, or equivalent glucocorticoid therapy for ≥14 days; 3. Suicidal ideation within the past 6 months based on assessment by Columbia-Suicide Severity Rating Scale (C-SSRS) at screening; or any suicidal behaviors within the past 12 months or recurrent suicidal behaviors during the subject's lifetime; 4. Presence of SLE or non-SLE related central nervous system diseases or pathological changes within 8 weeks prior to screening; 5. Existence of other lupus crisis within 8 weeks prior to screening; 6. Previous or current diagnosis of non-SLE-related inflammatory arthropathy or skin diseases; 7. Previous or current diagnosis of severe vasculitis due to other diseases excluding SLE; 8. History of vital organ transplantation or hematopoietic stem cell/or bone marrow transplantation; 9. Have received plasmapheresis, hemodialysis, intravenous immunoglobulin within 14 days prior to screening; 10. Other autoimmune diseases requiring systemic therapy; 11. Active or latent tuberculosis at screening (can be enrolled if appropriately treated); 12. Any of severe laboratory abnormalities in liver function, renal function, bone marrow function, coagulation function, pulmonary function, cardiac function at screening; 13. History of severe allergy or known hypersensitivity to any of the active ingredients of the drugs, excipients, or rodent-derived products, xenoproteins included in this trial, or subjects with allergic constitution; 14. Severe heart diseases; 15. Severe hepatobiliary disease; 16. Presence of medical conditions that are obviously unstable or not effectively treated; 17. Presence of uncontrollable bacterial, fungal, viral or other infections, requiring antibiotic therapy; 18. Have received live/attenuated vaccination within 4 weeks prior to screening or plan to receive live/attenuated vaccination throughout the study; 19. Have received any commercially available Janus kinase inhibitor or Bruton tyrosine kinase inhibitor within 3 half-lives prior to screening; 20. Have received B-cell targeted therapy prior to screening; 21. Have received a biologic agent other than B-cell targeted therapy within 5 half-lives prior to screening; 22. Previous received therapies with CAR-T cells or other genetically modified T cells; 23. Have received therapeutic dose of corticosteroids within 7 days prior to leukapheresis or within 72 hours prior to infusion; 24. Subjects that have undergone major surgery within 4 weeks prior to lymph depletion or those who are scheduled to undergo major surgery during the study period, or whose surgical wounds have not fully healed prior to enrollment; 25. Subjects that have donated blood for ≥ 400mL or had significant blood loss equivalent to at least 400mL within 4 weeks prior to screening, or have received a blood transfusion within 8 weeks, or plan to donate blood during the study period; 26. History of ≥ grade 2 bleeding within 4 weeks prior to screening or need for long-term continuous anticoagulant therapy; 27. Subjects with severe mental illness; 28. Alcoholics or subjects with a history of drug abuse; 29. Female subjects who are pregnant or lactating, or intend to pursue pregnancy within 2 years after the cell infusion; male patients whose female sexual partners intend to conceive within 2 years after the cell infusion; 30. History of malignancy； 31. Patients that have contraindications to any of the study procedures or have other medical conditions that may expose them to unacceptable risk, in the judgment of the investigators and/or clinical criteria. | 15 | 12 | 2024-01-12 | 2026-09-12 | 32 | 32 | Enrollment reached 80% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT03003572 | Autoreactive Anti-Ro/SSA IgE To Determine Primary SjögRen's Syndrome's Disease Activity |  | Immunology | Primary Sjögren's Syndrome | Primary Sjögren's syndrome (pSS) can affect various organs, sometimes leads to life-threatening conditions and is always responsible for a decreased quality of life. Its evolution is chronic, with flares and relapses, and the need for reliable biomarkers to be carried out routinely is major in patients' follow-up. Because of the existence of autoreactive immunoglobulins E (IgE) in autoimmune diseases, the recently described role for anti-Ro/SSA antibodies in inducing interferon alpha (IFNα) signaling and the specific pharmacologic properties of IgE, anti-Ro/SSA IgE should be an interesting biomarker to determine pSS's activity. The aim of the study is to evaluate whether the proportion of anti-Ro/SSA IgE positive patients is higher in patients with active disease (i.e. Eular Sjögren Syndrome Disease Activity Index≥ 5). All consecutive patients with pSS (new or already known diagnosis) will be included, Anti-Ro/SSA IgE titers will be determined, the disease's features will be collected (including Eular Sjögren Syndrome Disease Activity Index/Eular Sjogren's Syndrome Patient Reported Index). | * Primary Sjögren's syndrome according to the American-European Consensus Criteria) * Informed and having signed the study consent form | * Secondary Sjögren's syndrome * Other systemic autoimmune disease (e.g. rheumatoid arthritis, AntiNeutrophil Antibodies (ANCA) -associated vasculitis, mixed connective tissue disease…) * Incapacity or refusal to sign the informed consent form * Incapacity or refusal to perform the follow-up examinations required by the study * Has received abatacept, sifalimumab, rontalizumab, anifrolumab, belimumab, Tumor Necrosis Factor (TNF) antagonists or interferon during the 6 months prior to the inclusion * Has any current signs or symptoms of active infection | 185 | 185 | 2018-03-27 | 2020-12-27 | 34 | 34 | Enrollment exceeded target in Immunology; strong site engagement and pre-screening drove performance. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06618573 | Study on the Safety of Administering Isoniazid to Systemic Lupus Erythematosus Patients to Prevent Tuberculosis | PHASE_II | Immunology | Tuberculosis | Systemic Lupus Erythematosus (SLE) is a prototypical systemic autoimmune disease characterized by heterogeneity, multisystem involvement, and production of multiple autoantibodies. Clinical features can vary, from mild skin and joint involvement to severe and life-threatening conditions. The course of lupus is highly variable in the form of relapses and remissions, with mild and severe forms that can be life-threatening. Treatments for SLE includes steroids and immunosuppressants to control disease activity. Patients with lupus are more susceptible to infections, in addition to being immunocompromised, and due to the administration of corticosteroid and cytotoxic drugs. The presence of these infections is a cause of death in lupus disease in addition to the activity of the disease itself, especially in Asia-Pacific countries. One infection that often occurs in lupus is Tuberculosis (TB). Tuberculosis is still a problem especially in the Asian region, and Indonesia ranks 2nd with the most cases after India according to World Health Organization in 2019. TB infection is found in 10-11.4% of SLE patients in Asia. The incidence of TB in SLE is reported to range from 150/100,000 patients per year in Turkey to 2,450/100,000 patients per year in India. The annual risk of TB in SLE patients is higher than the normal population. Registry data at Hasan Sadikin Hospital Bandung showed that 11.4% or 93 out of 813 SLE patients were infected with TB after being diagnosed with SLE. Risk factors for increased TB infection in SLE patients, in addition to SLE disease activity itself (SLEDAI score \>12), renal involvement, lymphopenia, and cumulative dose of steroids used by the patient, are also due to long duration of illness and previous history of TB. Tuberculosis is also one of the infections that cause death in SLE patients. Mortality from TB in Asian countries ranged from 5-31%. A study in the Philippines found that 14.8% of SLE patients with TB died, those who died had dis | SLE patients with conditions of : * No signs and symptoms of active TB * Not under TB treatment * No History of TB, malignancy, HIV, liver function test abnormality * Not in pregnancy/lactation * No other active infections * Remission or low to moderate disease activity state * Consented to join the study completely | SLE patients with conditions of : * History of allergy to Isoniazid * Chronic liver disease, including chronic hepatitis B or C virus * Malignancy * Pregnancy | 60 | 60 | 2022-08-15 | 2025-12-01 | 40 | 40 | Enrollment exceeded target in Immunology; strong site engagement and pre-screening drove performance. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT05470569 | Prospective Registry of Patients With Systemic Lupus Erythematosus of the Argentinian Society of Rheumatology |  | Immunology | SLE | A longitudinal and multicenter cohort study of patients with systemic lupus erythematosus (SLE) is planned, with a follow-up of for 5 years. The data will be obtained from the clinical history of each patient. The responsible for data collection will always be a physician with experience in the management of patients with SLE and who has received training for data loading. The data will be collected through the an electronic case report form (eCRF) specially designed for this record and which in turn will facilitate the control of the data and the generation of inquiries to the researchers. STUDY VARIABLES Baseline visit: Sociodemographic data Classification criteria American College of Rheumatology (ACR 1982/1997), Systemic Lupus International Collaborating Clinics (SLICC 2012) and/or European League Against Rheumatism / American College of Rheumatology (EULAR / ACR 2019) History of SLE Access to specialized care Current clinical manifestations Activity and damage Scores Current treatments Patient-Reported Outcomes (PROs): Self-reported quality of life questionnaires EQ-5R; physician global assessment (PGA) and the patient Comorbidities Vaccination Habits Obstetric history Associated antiphospholipid syndrome Hospitalizations for adverse event, infections, or lupus activity Annual clinical follow-up visits Clinical follow-up of the patient Changes in clinical manifestations Changes in treatments Use of health services; hospitalizations; high cost treatments Activity and damage scores PROs Annual global and SLE-related mortality STUDY ENDPOINTS * Number of patients who achieved complete clinical remission or low disease activity status (LDAS) * Impact on the quality of life and working life measured by PROs and PGA * Mortality annual and global during the follow up period * Change in disease activity and damage scores * Health care resources used reported as number of hospitalizations, emergency visits and need of high cost treatment * Accessibility to high c | * Patients ≥ 18 years of age * Classified as SLE (according to the 1982/1997 American College of Rheumatology criteria and/or Systemic Lupus International Collaborating Clinics criteria for SLE) * Less than 5 years from meeting SLE criteria * Informed consent signature | * Diagnosis of other systemic autoimmune diseases or overlap syndromes * Patients who have been transferred to other centers | 1500 | 1270 | 2022-04-01 | 2027-04-01 | 61 | 61 | Enrollment reached 85% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06771427 | Systemic Proteomic Analysis of Plasma Exosomes to Explore the Immunomodulation Reflected to Sjogren's Syndrome and Dry Eye Syndrome |  | Immunology | Dry Eye Syndrome (DES) | Background: A 2015 survey in Taiwan revealed that the prevalence of Dry Eye Syndrome (DES) is 4.87%, with 4.8% of these cases likely to develop into Sjögren's Syndrome (SJS). An American study indicated that 11.6% of DES cases could be diagnosed as SJS, and SJS patients showed significantly more severe conjunctival and corneal staining, Schirmer's test results, clinical symptoms, anti-nuclear antibody, and rheumatoid factor compared to non-SJS patients. Various autoimmune diseases (such as SJS, SLE, RA, SSc, AS, etc.) also affect the severity of dry eye symptoms. Recent studies have employed exosome proteomics to investigate cell-to-cell communication, molecular mechanisms of diseases, and the development of new diagnostic markers and therapeutic targets. While these studies have significant research value for understanding disease mechanisms, diagnosis, and treatment, few have specifically focused on the impact of exosome proteomics in SJS and DES. Objective: By analyzing the differential proteins in exosomes, this study aims to understand the pathological mechanisms of SJS and DES, identify potential diagnostic and therapeutic methods, and advance the diagnosis and treatment of these diseases. Methods: This study will develope on previous research projects conducted at Taipei Veterans General Hospital (TBDESJS，V112C-190) and the National Science and Technology Council (ACUDES). TBDESJS focused on evaluating the use of a herbal tea TBDESJS for relieving dry eye and mouth symptoms in DES and SJS patients, and ACUDES explored the immediate and long-term effects of acupuncture on treating dry eye and mouth symptoms in DES and SJS patients by using the GB20 (Fengchi) and BL2 (Zanzhu) acupuncture points. 1. TBDESJS Study: Included 30 DES patients, 60 SJS patients, and 10 healthy controls (NHC) to evaluate the efficacy of the Traditional Chinese Medicine (TCM) herbal tea in improving dry eye and mouth symptoms. 2. ACUDES Study: Included 50 DES patients, 50 SJS patient | aged between 20 and 75 years Schirmer's test less than 10 mm/5 min | Pregnancy With eye inflammation or infectious eye disease Accepted operation of eye Sjögren's syndrome Inclusion Criteria: primary or secondary SS aged between 20 and 75 years fulfilled the 2002 American-European Consensus Criteria for SS (AECG) had no abnormal findings of immune, liver, kidney, or blood function evaluations. Exclusion Criteria: a history of alcohol abuse, diabetes mellitus, or major life-threatening condition pregnancy or breastfeeding steroid pulse therapy within three months prior to the commencement of our study. non AIDDES Healthy Controls Inclusion Criteria: aged between 20 and 75 years without any Chronic disease Exclusion Criteria: any Sjögren's syndrome or Dry eye syndrome. | 220 | 128 | 2025-01-16 | 2026-12-31 | 24 | 24 | Protocol eligibility criteria restricted enrollment to 58%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06513429 | Clinical Study on Evaluating the Efficacy and Safety of IM19 CAR-T Cell Therapy in Patients With Refractory Systemic Lupus Erythematosus |  | Immunology | Refractory Systemic Lupus Erythematosus | The study is a single-arm, open-label clinical trial intended to recruit 6 refractory SLE subjects who meet the inclusion and exclusion criteria. The subjects will receive IM19 CAR-T cell infusion therapy at a dose of 1×10\^6/kg or 1×10\^8 CAR-T cells . The primary endpoint is to evaluate the improvement in SLE disease activity (SLEDAI-2K) at 90 days and the occurrence of adverse events related to IM19 CAR-T cell infusion within 28 days post-infusion. Additionally, the long-term efficacy was evaluated, including the improvement of SLEDAI-2K score and achieving lupus low disease activity (LLDAS) at day 180 and day 360, and renal response at day 180 and day 360. The persistence and duration of IM19 CAR-T cells in the peripheral blood of subjects will also be evaluated. The study plan includes five phases: screening phase, cell collection phase, lymphodepletion pretreatment phase, cell infusion phase, and follow-up phase. | * 1)The subject was diagnosed with systemic lupus erythematosus and met the classification criteria of EULAR/ACR 2019 SLE (see Annex 2) * 2\) Age ≥ 18 years old, ≤ 65 years old * 3\) Weight ≥ 40 kg * 4\) Meets the current clinical standards for refractory systemic lupus erythematosus: the disease remains active or relapses and progresses after systemic treatment using the current standard treatment regimen, including steroids (sufficient or shock therapy), immunosuppressants (cyclophosphamide or mycophenolate mofetil), and biologics (belizumab or Rituximab) * 5\) Currently, one or more of the following stable dose standard therapies are being used to treat SLE: steroids, antimalarial drugs, immunosuppressants. If the subject is receiving steroids, the following conditions must be met: at screening time and during screening period, the maximum dose of steroids is 30mg/day prednisone (or equivalent dose). Before screening, the dose of steroids should remain stable for ≥ 7 days. During the screening period, the dose of steroids adjustment should not exceed 5mg/day prednisone (or equivalent dose). If the subject is receiving treatment with antimalarial drugs and/or conventional immunosuppressants: the start time of drug treatment must be ≥ 12 weeks before screening. Maintain a stable dose of medication for at least 8 weeks before and during screening. Before the screening period, if biological agents (such as belizumab or Telitacicept) are used, they need to be discontinued for at least 4 weeks before screening. * 6\) Disease activity score (SLEDAI-2K) with a score of 10 or above (refer to Attachment 3) * 7\) Women of childbearing age who tested negative for blood pregnancy before the start of the trial and agreed to take effective contraceptive measures during the trial period until the last follow-up * 8\) Male participants whose partners have fertility agree to take effective contraceptive measures during the trial period until the last follow-up * 9\) Those who voluntarily participate in this experiment and sign an informed consent form. | * 1\) After evaluation by researchers, it is determined that the subject has diseases that are not suitable for participation in this study, such as life-threatening conditions (e.g., catastrophic antiphospholipid syndrome, acute severe renal failure, acute severe central nervous system disease manifestations). * 2\) The research subject has a history of alcohol or drug abuse within the past 24 weeks. * 3\) The research subject has a history of malignant tumors other than B-cell lymphoma. * 4\) Major surgery (including joint surgery) was performed within 24 weeks prior to screening, or surgery is planned within 24 weeks after enrollment in the study. * 5\) The research subject has overlapping mixed connective tissue diseases and other syndromes that affect the judgment of disease activity. * 6\) The research subject has human immunodeficiency virus (HIV) infection, selective IgA deficiency, T-cell deficiency virus infection, chronic hepatitis B or C virus infection, or SARS-CoV-2 \[severe acute respiratory syndrome coronavirus 2\] infections. * 7\) The research subject has a known active tuberculosis (TB) infection or bacterial infection. * 8\) History of myocardial infarction, cardiac angioplasty or stent placement, unstable angina, active arrhythmia, or other clinically significant heart disease within 6 months prior to screening initiation. * 9\) History of symptomatic deep vein thrombosis or pulmonary embolism within 6 months prior to screening initiation. * 10\) The research subject's alanine aminotransferase (ALT), aspartate aminotransferase (AST), or alkaline phosphatase (ALP) levels are ≥3×ULN, or bilirubin \>1.5×ULN, excluding laboratory test abnormalities due to SLE hepatitis. * 11\) The research subject has stage 4 chronic kidney failure, indicated by an estimated glomerular filtration rate (eGFR) \<30 mL/min/1.73 m², or serum creatinine \>2.5 mg/dL. During the screening visit (V1), the research subject presents with any of the following significant hematological abnormalities: a. Hemoglobin \<7.0 g/dL b. CD4+ T lymphocytes \<200/mm³ c. Absolute neutrophil count \<500/mm³ d. CD4+ T lymphocytes \<500/mm³ with a neutrophil count \<1000/mm³ e. Platelets \<25,000/mm³. * 12\) Treatment with CD20 monoclonal antibodies was used within the past 6 months. * 13\) Conditions that the researcher considers unsuitable for inclusion in this clinical trial. | 6 | 0 | 2026-09-18 | 2029-06-18 | 33 | 33
NCT04624490 | Hyperpolarized 129Xe MR Imaging of Lung Function in Healthy Volunteers and Subjects With Pulmonary Disease | PHASE_I | Respiratory | Asthma | This is an unblinded, open-label study with \~160 subjects with diagnosed pulmonary disease and \~100 healthy controls. Subjects to be enrolled will include males and females 18-80 years old. Evaluation will be on an outpatient basis. Imaging will be done on a single day and will involve administration of up to four 1-liter doses of HP 129Xe plus one 129Xe calibration dose (\~300-400mL HP 129Xe). In addition to 129Xe MRI, a series of anatomical conventional 1H MR images will be collected including a localizer scan, breath-hold spin echo image, and breath-hold steady-state free precession image to highlight the vasculature. All subjects will be evaluated at one center: The University of Kansas Medical Center, KS USA. | Healthy Volunteers: * Subject has no diagnosed pulmonary conditions * Ability to read and understand English or Spanish Subjects with Lung Disease: * Subject has a diagnosis of pulmonary dysfunction made by a physician * No acute worsening of pulmonary function in the past 30 days * Ability to read and understand English or Spanish | * MRI is contraindicated based on responses to MRI screening questionnaire * Subject is pregnant or lactating * Subject does not fit into 129Xe vest coil used for MRI * Subject cannot hold his/her breath for 15-16 seconds * Subject deemed unlikely to be able to comply with instructions during imaging * Oxygen saturation \<88% on room air or with supplemental oxygen * Cognitive deficits that preclude ability to provide consent * Institutionalization | 260 | 143 | 2020-11-02 | 2028-10-26 | 97 | 97 | Protocol eligibility criteria restricted enrollment to 55%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT05720325 | Mechanistic Trial of Dupilumab in Adults With House Dust Mite-associated Asthma Using an Aeroallergen Challenge Chamber | PHASE_II | Respiratory | Asthma, Allergic | (i)Intervention #1: HDM exposures in the ACC This trial utilizes exposures to House dust mites (HDM) in the Aeroallergen Challenge Chamber (ACC) as a two-pronged tool for (i) precision phenotyping of HDM+PARC+AA+ persons to identify those with the adaptive and maladaptive phenotypes and (ii) assessment of symptoms intermittently throughout the clinical trial to monitor effects of dupilumab/placebo on symptom severity . (ii) Participants classifying to the adaptive and maladaptive phenotypes are then randomized to 18-weeks dupilumab vs. placebo, with ACC HDM visits during this phase. | 1. Will demonstrate understanding of the study and will provide a signed and dated informed consent. 2. Will be male or female, 18 to 65 years of age at the time of the screening visit. 3. Will have symptoms consistent with perennial nasal allergy for a minimum of 2 years prior to the screening visit. 4. Will have a positive standard skin prick test (SPT) to D. pteronyssinus within 24 months of screening. A positive SPT is defined as a wheal diameter of at least 5 mm larger than the negative control (normal saline). 5. Will have asthma with a documented FEV1 reversibility of ≥10% within 18 months of screening. 6. If a participant manifests symptoms suggestive of COVID-19, the participant must have a negative SARS-CoV-2 rapid antigen nasopharyngeal swab test before each HDM exposure visit. 7. A woman of childbearing potential, must have a negative urine pregnancy test at Visit 1 and prior to each exposure in the ACC. All women of childbearing potential must agree to a medically acceptable form of birth control throughout the study duration and for at least 2 months prior to Visit 1. Acceptable methods of birth control for this study include: 1. oral, patch, or intra-vaginal contraceptives 2. Norplant System® or other implant system 3. Depo-Provera® 4. IUD 5. double barrier method 6. abstinence 7. surgical sterility (hysterectomy, tubal ligation, or uterine ablation) Post-menopausal women defined as women without a menstrual cycle for at least 12 consecutive months qualify as non-childbearing for this study. 8. Will have never smoked or will be an ex-smoker (\<20 pack year history and no cigarette or smokeless tobacco use in the past year). | 1. Have a chronic lung disease other than asthma. 2. Have atopic dermatitis. 3. Have any ocular disease that is not associated with allergic rhinoconjunctivitis. 4. Are on home oxygen requirement. 5. Have a history of rebound nasal congestion (brought on by extended use of topical decongestants), chronic rhinosinusitis with or without nasal polyps, nasal septal perforation, or severe nasal tract malformations noted on physical exam. 6. Have FEV1 \<70% predicted as determined by pre-bronchodilator spirometry at visit 1. 7. Are unwilling/unable to withhold intranasal steroids or asthma medications before specified visits. 8. Are unwilling/unable to abstain from protocol-defined prohibited medications for the protocol-specified times before and during screening/selection and ACC HDM exposure visits. 9. Have received any oral or other form of systemic glucocorticosteroids within 1 month prior to the screening visit. 10. Have received JAK-1 inhibitors within 3 months prior to the screening visit. 11. Have known hypersensitivity to dupilumab or any of its excipients. 12. Have an ongoing helminth infection. 13. Have received a live vaccine within 30 days of screening or are planned to receive one during study participation.Note: Participant can receive a live vaccine \> 30 days after final study investigational product injection (visit 14) 14. Are pregnant or nursing. 15. Have a history of keratoconjunctivitis sicca. 16. Have indoor pet exposure causing upper or lower symptoms. 17. Have received allergen immunotherapy of any form within 12 months of screening visit. 18. Received biologics, other than anti-obesity or diabetes medications (such as tirzepatides, semaglutides), for any indication within 12 months of screening visit. 19. Have participated in a trial with an investigational drug in the past 30 days. 20. Have past or current medical problems or findings from physical examination or laboratory testing that are not listed above, that, in the opinion of the investigator, may pose additional risks from participation in the study, may interfere with the participant's ability to comply with study requirements, or may impact the quality or interpretation of the data obtained from the study. | 88 | 82 | 2023-03-29 | 2026-08-29 | 42 | 42 | Enrollment reached 93% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06903897 | Improving Chronic Disease Outcomes Across the Lifespan by Addressing Structural Racism |  | Respiratory | Hyperlipidemias | With a multidisciplinary team of social determinants of health (SDOH), implementation, antiracism, community-engaged, and practice-based researchers, the investigators will apply an antiracism framework to an existing evidence-based SDOH screening and referral system and develop a holistic implementation toolkit aimed at reducing bias and mitigating unequal treatment for families of color. The investigators will first conduct qualitative interviews with adult patients and caregivers to understand their experiences with racism and discrimination within the context of their experiences with screening and referral for SDOH; the investigators will then share their findings with stakeholders (e.g., clinic directors, community agency leaders, health system leaders, Medicaid leaders) and elicit their ideas on how best to address these issues within the systems they lead. Subsequently, the investigators will refine the WE CARE implementation protocol using this stakeholder input with the guidance of antiracism and implementation experts. The investigators will then implement the refined WE CARE protocol in family medicine clinics since adverse SDOH impact the whole family unit; it will also allow them to examine WE CARE's impact on improving health outcomes for racialized groups across the life course. The investigators will conduct a hybrid effectiveness-implementation study with a stepped wedge cluster RCT design in three large family medicine clinics (including 2 health centers) that serve racially/ethnically diverse low-income families from Worcester, Massachusetts. The specific aims are to: * Aim 1: Refine the WE CARE implementation protocol using an antiracism lens and community engagement approach to: (a) conduct key informant interviews with families to identify racism and discrimination related barriers to SDOH screening/referral; (b) present these barriers to systems-level stakeholders to elicit input on strategies to address patient concerns; and 3) create an an | * Adults and children with diagnosed chronic diseases (hypertension, diabetes mellitus, hyperlipidemia, asthma, or depression) who receive Family Medicine care at one of the study sites. * Children (\<18 years of age) with a diagnosis of asthma. * Adult patients (18 years or older) with a diagnosis of diabetes mellitus, hypertension, hyperlipidemia and/or depression. | * In adults (\>18 years of age), those without one or more of the following diagnoses as recorded by ICD-10 codes in their EHR: hypertension, hyperlipidemia, diabetes mellitus, or depression. * In children (\<18 years of age), those without a diagnosis of asthma. | 68000 | 5228 | 2025-10-08 | 2028-09-30 | 36 | 36 | Protocol eligibility criteria restricted enrollment to 8%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06441812 | A Multicenter, Single-group Phase II Clinical Study to Evaluate the Long-term Safety, Pharmacodynamics and Efficacy of Multiple Subcutaneous Injections of SHR-1703 in Eosinophilic Asthma Patients | PHASE_II | Respiratory | Eosinophilic Asthma Patients | The purpose of this study is to evaluation the long-term Safety, Pharmacodynamics and Efficacy of SHR-1703 in Eosinophilic Asthma Patients | 1. At least 18 years of age, Male or Femal. 2. A minimum weight of 40kg. 3. Subjects with the clinical features of asthma that meets the diagnostic criteria of the "Guidelines for the Prevention and Treatment of Bronchial Asthma (2020 Edition)" and has a medical history of at least 1 year. 4. Documentation of current asthma controller medication \[medium or high dose ICS and at least one of additional controller such as long-acting muscarinic antagonist (LAMA), long-acting beta2-agonist (LABA) and leukotriene receptor antagonist (LTRA)\] for at least 1 stable month before first administration of SHR-1703. 5. At least one confirmed history of exacerbation within one year of initial administration of SHR-1703, occurring during the use of medium and high daily dose ICS. 6. Absolute count of eosinophils must be ≥0.15×109/L at visit 0 and visit 1. 7. A pre-bronchodilator FEV1 \<85% and ≥30% predicted at visit 0 and visit 1. 8. Female subjects with fertility agree to have no plan pregnancy and voluntarily adopt high-efficiency contraception measures from signing the informed consent form to 14 months after the last dose of SHR-1703, and male subjects with fertility as partners agree to have no plan pregnancy and voluntarily adopt high-efficiency contraception measures between the first dose of SHR-1703 and the last visit in the study. 9. Subjects must be able to give written informed consent prior to participation in the study. | 1. Presence of a clinically important lung condition. This includes but is not limited to current infection, bronchiectasis, pulmonary fibrosis or a history of lung cancer. 2. A known immunodeficiency. 3. Presence of a clinically significant and uncontrolled serious cardiovascular and cerebrovascular disease, including but not limited to myocardial infarction, unstable angina, heart failure, stroke, and subarachnoid haemorrhage. 4. Within the first 4 weeks before visit 0, presence of exacerbation of allergic rhinitis or sinusitis, or a history of infections with clinical significance and/or requiring clinical intervention, including but not limited to respiratory infections. 5. A known parasitic infection within the first 6 months before visit 0. 6. A malignancy history within the first 5 years before visit 0 (Subjects that had localized basal carcinoma of the skin or cervical carcinoma in situ which was resected for cure will not be excluded). 7. Blood donation or significant blood loss (≥ 400ml) within the first 4 weeks before visit 0, or infusion of blood products or immunoglobulins. 8. Use systemic immunosuppressants (excluding systemic glucocorticoids used for asthma treatment and for non asthma treatment for less than 3 days) or immunomodulators, or biologics or Th2 cytokine inhibitors, including but not limited to methotrexate, cyclosporine, interferon-α, anti IL-5 monoclonal antibodies (including SHR-1703), anti IL-4R monoclonal antibodies, anti TSLP monoclonal antibodies, anti IgE monoclonal antibodies, metformin, etc., and within 5 half-lives of the drug before the first administration (refer to the longer drug instructions; for those with unknown half-lives, 12 weeks before the first administration shall prevail); 9. Subjects who have previously participated in any study and received Investigational Product within the first 30 days before visit 0. 10. There was a surgical plan or other treatment measures that the researcher believed may affect the subject's evaluation during the study period. 11. Laboratory examination shows obvious abnormalities at visit 0 and visit 1: 1. White blood cell count (WBC) \<3.0×109/L; 2. Hemoglobin≤90g/L； 3. Platelet\<100×109/L； 4. Alanine aminotransferase (ALT)\>2×ULN (upper limit of normal); 5. Aspartate aminotransferase (AST) \>2×ULN； 6. Total bilirubin (TBIL)\>1.5×ULN; 7. Prothrombin time (PT) \>ULN+3s； 8. Creatinin\>1.5×ULN; 9. Active hepatitis B (positive for hepatitis B virus deoxyribonucleic acid (HBV DNA) in peripheral blood), or positive for hepatitis C virus antibody, or positive for human immunodeficiency virus (HIV) antibody, or positive for treponema pallidum antibody； 12. ECG QTc\>450ms or other clinically significant abnormal results that may pose significant safety risks to the subjects at visit 0 or visit 1； 13. A history of drug addicts or substance abuse within 1 years prior to Visit 0； 14. Subjects who are pregnant (positive HCG test at visit 0 or visit 1) or breastfeeding should not be enrolled if they plan to become pregnant during the time of study participation； 15. Subjects with a known allergy or intolerance to anti IL-5 monoclonal antibody or other biologic； 16. Other reasons determined by the researcher as unsuitable for participation in the study. | 200 | 116 | 2024-07-19 | 2026-09-19 | 26 | 26 | Protocol eligibility criteria restricted enrollment to 58%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT07476703 | Expanded Studies of Risk Factors for Pulmonary-, Liver-, and Cardiovascular Disease in the SCAPIS 2 Stockholm Reexamination |  | Respiratory | Coronary Artery Disease | The Swedish CArdioPulmonary bioImage Study (SCAPIS) is a unique, large-scale national research initiative involving 30,000 randomly selected individuals aged 50-64, recruited between 2014 and 2018. The study is a collaborative effort among six university hospitals across Sweden. A follow-up study, SCAPIS 2, is conducted for half of the original participants. In Stockholm, 2,500 individuals will be re-examined at Danderyd University Hospital and Karolinska Institutet. SCAPIS 2 includes a core set of examinations involving blood sampling, questionnaires, and imaging. In addition to these, complementary local investigations are conducted to enable more detailed research questions. This protocol describes the additional studies conducted in the Stockholm cohort: EXTENDED SAMPLING: Saliva and Blood Samples with Blood Cell Isolation Additional blood samples will be collected to isolate blood cells for detailed immune system profiling, red blood cell function nd for lipid profiles and inflammatory markers. Saliva samples will be analyzed for inflammatory markers and microbial composition. EXTENDED QUESTIONNAIRES: Dyspnea, Sleep, Respiratory Infections, and Dental Health Participants will complete detailed questionnaires covering recent food, drink, and medication intake; oral hygiene; breathing and lung function; sleep quality and daytime somnolence; and history of respiratory infections, including COVID-19. EXTENDED IMAGING AND PHYSIOLOGICAL MEASUREMENTS: These investigations will be conducted during a separate visit, coordinated with the main study, and take approximately one hour. 1. Cardiac Ultrasound and Abdominal Aortic Measurements: cardiac structure and function, as well as the diameter of major arteries (e.g., the thoracic and abdominal aorta). 2. Liver Elastography: An ultrasound-based technique used to assess liver stiffness and fat content. 3. Vascular Stiffness: Blood pressure cuff-based pulse wave analysis with automated stiffness calculation. Photopleth | Subjects already included in the main / general SCAPIS reexamination study in Stockholm. | Inability to provide consent. | 1400 | 942 | 2024-04-08 | 2026-08-30 | 29 | 29 | Protocol eligibility criteria restricted enrollment to 67%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT07288554 | A Randomized, Double-Blind, Placebo-controlled, Single- and Multiple-ascending Dose Study to Evaluate the Safety, Tolerability, Pharmacokinetics, Immunogenicity, Pharmacodynamics and Clinical Activity of BBT002 in Healthy Volunteers and Participants With Chronic Obstructive Pulmonary Disease (COPD) | PHASE_I | Respiratory | Chronic Obstructive Pulmonary Disease (COPD) | The study consists of two parts: * Part A (single dose in HVs in sequential ascending dose cohorts, SAD in HVs part) * Part B (two repeated doses in patients with COPD, MAD in patients part) | ( A\&B) 1. Age of 18-65 years (HVs), 35-75 years (patients) 2. Body mass index between 18-32 kg/m², capped at 120 kg 3. Negative pregnancy tests for women of childbearing potential 4. Willingness to refrain from alcohol consumption for 24 hours prior to each study visit 5. Non-smokers, healthy current smokers (≤5 cigarettes/day), or ex-smokers 6. Adequate contraception use (for men and women of childbearing potential) 7. No clinically significant abnormalities or history of relevant diseases Key Inclusion Criteria (Part B only) 1. Documented history of COPD with a post-bronchodilator FEV1/FVC \< 0.70 2. FEV1 ≥ 50% and FEV1\<80% predicted at screening. | ( part A \& B) 1. Positive viral serology for human immunodeficiency virus (HlV), hepatitis C virus (HCV), or hepatitis B (HBV) 2. Immunodeficiencies, autoimmune diseases, or cancer, history of conditions predisposing to infections 3. History of major metabolic, dermatological, liver, kidney, hematological or other significant disorders 4. Clinically relevant abnormal lab results, including low blood counts, liver enzymes, or abnormal kidney function 5. Positive drug/alcohol tests or abnormal vital signs at screening or Day -1 6. Abnormal Electrocardiogram(ECG) findings 7. History of drug/alcohol abuse in the past 2 years 8. History of severe allergic reactions or hypersensitivity Key Exclusion Criteria for (Part B only) 1. Current diagnosis of other significant pulmonary disease 2. Significant or unstable cardiovascular diseases 3. Recent clinically significant infection 4. Inability to perform spirometry | 68 | 0 | 2027-01-18 | 2029-11-18 | 34 | 34
NCT06940531 | Identifying the Causes and Risk Factors of Pulmonary Exacerbations in Cystic Fibrosis |  | Rare Disease | Cystic Fibrosis (CF) | Participants will be recruited by staff within the care of UK CF centres. Initial discussions will occur either during routine outpatient reviews, telephone consultations or during admissions. Consent will take place prior to any other procedures. There will be four separate cohorts of participant 1. Group A participants will be 200 adults with CF (16 years or older) attending a UK adult CF centre taking part in the study 2. Group B participants will be 100 additional adults with CF attending one of the five core CF adult centres: Manchester, Leeds, Newcastle, Cardiff, Liverpool. 3. There will be a pilot study to test the practicalities of running the same protocol in a paediatric population. This will consist of up to 25 children with CF (5-16 years) attending a paediatric clinic in one of the five core centres. 4. In addition, the investigators will recruit up to 40 healthy volunteers to provide samples on a single occasion as controls. Group A participants will have a single in-person visit, at the start of the study. Clinical data, including lung function (spirometry), venous blood draw, sweat chloride, saliva sample and finger-prick dried blood spot sample, sputum, nasal liquid sample and urine sample and demographic data will be collected. The study will run for 12 months. Home sampling kit, consisting of 13 home sampling boxes and 3 additional exacerbation boxes, will be provided for participants to collect in-home sampling for the first 6 months fortnightly. The 3 additional exacerbation boxes will be provided for posting additional set of samples when unwell. There will be questionnaires to complete to remotely monitor the adherence to the protocol. Study app ("Watson") will be set up to provide reminders and aid study adherence and timely return of samples. Group B will only be offered at 5 specialist CF centres (Manchester, Cardiff, Newcastle, Leeds, Liverpool). This follows the same format as Group A but includes additional face to face visits at 1 a | For Adult Participants 1. Confirmed diagnosis of cystic fibrosis (CF), defined as presence of two pathogenic CF-causing CFTR mutations AND clinical features consistent with a diagnosis of CF, OR presence of at least one pathogenic CF-causing CFTR mutation AND sweat chloride (before use of CFTR modulators) \>60mmol/L AND clinical features consistent with a diagnosis of CF. 2. Age ≥ 16 years and receiving care from a UK Adult Cystic Fibrosis Centre for main study. 5-16yrs for Paediatric pilot study (see below). 3. Have had at least 1 previous exacerbation of CF lung disease, treated with oral or intravenous antibiotics, in the previous 12 months. 4. Able to understand the patient information sheet, willing to consent to study protocol and to returning home samples 5. Has a home spirometry device and able to use this For those taking part in Group-B, additional inclusion criteria include 6. Willing to attend for additional face to face visits at 4 weeks, 26 weeks, and if they become unwell For those taking part in home monitoring (as part of Group-B at Manchester) 7. Has wireless internet at home 8. Willing to allow to home access to set up monitoring devices, collect these back in at end of study, and to carry out other visits to perform calibration or intermittent home air sampling. For Paediatric Participants 1. Confirmed diagnosis of cystic fibrosis (CF), defined as presence of two pathogenic CF-causing CFTR mutations AND clinical features consistent with a diagnosis of CF, OR presence of at least one pathogenic CF-causing CFTR mutation AND sweat chloride (before use of CFTR modulators) \>60mmol/L AND clinical features consistent with a diagnosis of CF. 2. Receiving care from an eligible Paediatric CF Centre. 3. Age 5-16 years 4. Have had at least 1 previous exacerbation of CF lung disease, treated with antibiotics. 5. Able to understand the study and/or willing to assent to study protocol. 6. Parents or guardians able to understand the study and willing to consent to take part, including helping with home sampling 7. Has a home spirometry device and able to use this For Healthy Volunteers 1. Healthy subject, male or female, aged 16-65 years 2. No active lung condition, chronic inflammatory disorder or infection 3. Not been on antibiotics or anti-inflammatory agents of any sort (including inhaled or systemic corticosteroids) for at least 90 days. 4. No recent (defined as within the previous 4 weeks) acute viral symptoms 5. Willing to sign the consent form and provide the samples. | 1. Unable to produce sputum, spontaneous or induced, at visit 1. If subject is normally able to produce sputum and still wishes to take part, visit 1 can be repeated on up to two additional occasions if this is needed to obtain sputum sample. 2. For the first visit, participants should be clinically stable at the time of the visit. This is defined as no acute change in their baseline symptoms or presence of new viral symptoms. They should not be on additional antibiotics or anti-viral therapies for any reason (above their usual medications), and should have completed any such additional therapies at least 4 weeks prior to visit 1. 3. Subjects with infection with Mycobacteria tuberculosis 4. Subjects with active ABPA, defined as receiving treatment for ABPA currently or within the last 12 months, or those considered at risk of requiring treatment for ABPA in the next 12 months. 5. Subjects receiving long term oral steroids at an equivalent dose of 10mg or more per day of prednisolone. 6. Subjects receiving any other form of long term immune-suppressant therapy. 7. Subjects with non-tuberculous mycobacteria (NTM) infection who are undergoing active eradication therapy. Subjects with chronic NTM infection who are not on eradication therapy, and not expecting to start this within the next 12 months, are not excluded. 8. Subjects who are unable to complete home spirometry who have previously been shown poor adherence to home monitoring requests 9. Any other condition, co-morbidity or other feature that, in the opinion of the investigator would render the subject unable to complete the protocol or unsuitable for inclusion. 10. For home monitoring, any subject where the investigator or their team has concern about staff safety when performing home visits. Patients taking part in other long term trials or observational studies are eligible to take part in CF-Tracker. Local investigators should judge whether the burden of additional research visits will be manageable. | 300 | 25 | 2025-05-16 | 2029-12-31 | 56 | 56 | Protocol eligibility criteria restricted enrollment to 8%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT05341453 | The Effect of Intensive Hippotherapy on the Psychomotoric Development of Children With Spinal Muscular Atrophy |  | Rare Disease | Spinal Muscular Atrophy | Spinal muscular atrophy is rare neuromuscular disease, it is caused by gene mutation survival motor neuron 1 (SMN1). This gene encodes survival motor neuron(SMN) protein. This protein is most important to survive alfa-motoric neurons in spinal cord. When this protein doesn´t work, no signals go from brain to skeletal muscles and fazic muscles of body. In the end weakening breathing muscles and internal organs muscles. The first treatment is pharmacological treatment. There is a lot of research about medicament treatment, the famous treatment in Czech Republic is medicine Spinraze and from year 2020 medicine Zongelsma. This, however, more often puts more difficulty on complex rehabilitation. An empirical observation has found out that complex rehabilitation has positive effect on progress of disease and on self-sufficiency of people and children with SMA. Physiotherapy is one of the recommended rehabilitation types. The use of rehabilitation procedures is common in clinical practice. In a 2016 study, 105 adults with SMA were asked how many of them used physiotherapy. A total of 86% of respondents received these services, yet the authors of the article conclude that further research is needed to understand the impact of physiotherapy in SMA. Nevertheless, there is a lot of discussion if physiotherapy is really good for people and children with SMA. Some research shows us, that physiotherapy doesn´t worsen this disease. Researchers showed that strength training 3 times a week does not show side effects in children under 10 years of age, in some cases trends in improving muscle strength and motor functions have been observed. Because in physiotherapy therapists work primarily with muscles, and a lot of activity can cause fatigue of skeletal muscles and worsen their function. But from clinical work scientists know that the effect of physiotherapy is extensive. There is a research on mice which shows the effect of physiotherapy on the strength activities and the aerobi | * clinic diagnosis SMA (I, II, and III types) * no changing medicine 6 months at least * without another grave diseases | * hip subluxation * allergies to horses and the environment of horse stables * insurmountable fear of the horse | 16 | 13 | 2022-04-22 | 2025-10-22 | 43 | 43 | Enrollment reached 81% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT05504837 | KB407-02 A Phase 1 Study of Inhaled KB407, a Replication-Defective, Non-Integrating Vector Expressing Human Cystic Fibrosis Transmembrane Conductance Regulator, for the Treatment of Cystic Fibrosis | PHASE_I | Rare Disease | Cystic Fibrosis | This study will evaluate safety and tolerability of ascending doses of nebulized KB407 in adults with cystic fibrosis. | 1. The subject must have read, understood, and signed an Institutional Review Board/Ethics Committee (IRB/IEC) approved Informed Consent Form and must be able to and willing to follow study procedures and instructions 2. Subjects aged 18 years or older at the time of Informed Consent 3. A confirmed diagnosis of CF as defined by clinical signs and symptoms of CF and at least one of the following: * A historical sweat chloride value \>60 mmol/L * Two copies of a disease causing mutation in the CFTR gene 4. Clinically stable in the opinion of the Investigator 5. Percent predicted FEV1 ≥40% and ≤90% of the predicted normal for age, gender, and height at Screening 6. Resting oxygen saturation ≥92% on room air at Screening | 1. Initiation of any new chronic therapy (eg, CFTR modulator, hypertonic saline, inhaled antibiotic) or any change in chronic therapy (excluding pancreatic enzyme replacement therapy) within 28 days prior to the first dose 2. Hospitalization, sinopulmonary infection, CF exacerbation, or other clinically significant infection or illness 14 days prior to the first dose that, in the opinion of the Investigator, may confound study results 3. Treatment for Mycobacterium abscessus within 3 months prior to the first dose or more than two pulmonary exacerbations with a history of Burkholderia cenocepacia infection within 6 months prior to the first dose 4. Participation in another clinical study or treatment with an investigational agent 30 days or 5 half-lives, whichever is longer, prior to the first dose 5. History of or listed for solid organ transplantation 6. Any condition (including a history or current evidence of substance abuse or dependence, uncontrolled asthma, or is considered to be immunocompromised) that, in the opinion of the Investigator, would impact a subject's ability to complete all study-related procedures and/or poses an additional risk to the assessment of safety of KB407 7. An active oral herpes infection 30 days prior to the first dose 8. Women who are pregnant or nursing 9. Subject who is unwilling to comply with contraception requirements per protocol 10. Clinically significant abnormalities of hematology or chemistry testing at Screening that the Investigator believes may interfere with the assessment of safety and/or efficacy of the study treatment 11. Subject has a known hypersensitivity to inhaled glycerol 12. Subject is known to be noncompliant or is unlikely to comply with the requirements of the study protocol in the opinion of the Investigator 13. Bronchoscopy participants only: Unable to tolerate bronchoscopy procedure and airway sampling, in the opinion of the Investigator 14. Cohort 4 participants only: Subjects who are ineligible for, do not tolerate, or do not benefit from modulator therapy | 20 | 17 | 2023-06-30 | 2026-11-30 | 42 | 42 | Enrollment reached 85% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06152302 | Analysis of Mobility in the Bath for Infants Affected With Spinal Muscular Atrophy |  | Rare Disease | Infantile Spinal Muscular Atrophy | This is a multicenter research project coordinated by the Child Neuromuscular Unit at Raymond Poincaré Hospital. Additionally, two other pediatric neurology departments, part of the national neuromuscular network FILNEMUS (https://www.filnemus.fr/), will participate in the study: Necker Children's Hospital and Armand Trousseau Hospital. The study's population will include all infants diagnosed with spinal muscular atrophy (SMA), specifically SMA type 1, who have onset before 6 months of age and have been evaluated by the French Therapeutic Commission. Participation in the study will be contingent on parental or guardian consent during follow-up visits. Spinal muscular atrophy is a genetic neurodegenerative condition that affects spinal motor neurons, causing motor and respiratory paralysis and ultimately leading to death. As groundbreaking therapies emerge, there's an increasing need to refine the methods used to assess motor function, especially in infants with severe hypotonia due to SMA type 1. Traditional reference scales used on examination tables are limited in their accuracy because of gravitational effects. Consequently, there's growing interest in evaluating these children's motor skills in water to detect movements unburdened by gravity. Pediatric neurologists in France (SFNP) have already acknowledged the potential value of parental video recordings during infant baths. However, the lack of standardization in recording conditions, coupled with the subjective nature of video interpretations, underscores the necessity for a more standardized and quantifiable approach. Herein lies the application of our proposed evaluation utilizing inertial sensors. Utilizing inertial sensors to detect subtle movements can highlight still-active yet minimally functional motor neurons. Such detection can be pivotal in identifying children who, despite severe motor skill limitations in traditional settings, still possess developmental potential. Our study seeks to leverage | * Infants with muscle weakness (commonly referred to as floppy babies): * Confirmed diagnosis of SMA through gene mutation or deletion (SMN1 gene). * Receiving standard care. * Age less than 12 years and a height of less than 90 cm at the time of inclusion. * Patients enrolled in a social security scheme. * Informed consent signed by both parents of the child and the investigator. | * Patients presenting with lesions in the spinal cord or conditions affecting the cardiorespiratory system. * Patients covered under the French Aid in Health for Foreign People program (AME). | 15 | 8 | 2025-06-26 | 2027-03-26 | 21 | 21 | Protocol eligibility criteria restricted enrollment to 53%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT05200429 | Canadian Observational Study Evaluating the Long-term IMPACT of CFTR (Can-IMPACT CF) |  | Rare Disease | Cystic Fibrosis | This observational study intends to investigate health trends and data in cystic fibrosis patients all across Canada that are receiving modulator treatment so researchers can determine if CFTR treatments are effective over a long period of time and if so, which treatments work best for each individual. The study will collect clinical data from routine standard of care, patient reported outcomes via survey data and samples for a biobank. | * Prescribed a CFTR modulator therapy and planning to commence modulator therapy within 30 days OR planning to switch modulator therapies within 30 days * Participates in the Canadian Cystic Fibrosis Registry (CCFR) * Informed consent by participant, or parent/legal guardian or assent | * Known contraindications to CFTR modulator therapy | 500 | 413 | 2021-11-01 | 2027-12-31 | 75 | 75 | Enrollment reached 83% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
NCT06528418 | Exploration and Study on the Identification of Various Pulmonary Diseases Using Volatile Organic Compounds Biomarkers in Human Exhaled Breath |  | Rare Disease | Lung Cancer | This is a prospective, cross-sectional, observational cohort study aimed at recruiting 10,000 participants with multiple pulmonary disease, including lung cancer, lung infection, chronic obstructive pulmonary disease (COPD), bronchitis, pulmonary fibrosis, pulmonary embolism, pulmonary arterial hypertension, tuberculosis, lung abscess, emphysema, radioactive lung injury, cystic fibrosis of the lung, Bronchial Asthma, Bronchiectasis, interstitial lung disease (ILD), preserved ratio impaired spirometry (PRISm) etc . Exhaled breath samples from these participants will be collected and analyzed using Gas chromatography-mass spectrometry(GC-MS) and micro Gas Chromatography-photoionisation detector (μGC-PID) system. Upon obtaining the μGC-PID results, a comprehensive evaluation of the diagnostic capabilities of exhaled breath samples in differentiating various pulmonary diseases will be performed, leveraging clinical diagnostic results, CT examination data, and clinical data. | * Males or females, age must be 18 years old or above. * Patients must meet the CT imaging diagnostic criteria for different lung diseases, and patients must be able to provide electronic versions of CT image data. * Patients must have a clear clinical diagnosis. * All participants must sign a written informed consent form. | * Pregnant women. * Individuals with a history of cancer other than lung disease. * Individuals who have undergone organ transplants or non-autologous (allogeneic) bone marrow or stem cell transplants. * Individuals with other severe organic diseases or mental illnesses. * Individuals with metabolic diseases such as diabetes, hyperlipidemia, etc. * Any other condition that researchers deem unsuitable for participation in this clinical trial. | 10000 | 0 | 2026-08-18 | 2028-02-18 | 18 | 18

## Protocol Sites
id | protocol_id | site_id | site_name | country | target_enrollment | actual_enrollment | performance_tier
796 | NCT06567015 | NCT06567015-S01 | Sarah Cannon Research Institute (SCRI) (The SCRI Oncology Research Consortium) | United States | 23 | 8 | Low
797 | NCT06567015 | NCT06567015-S02 | Oncology Consultants (OC) - Texas Medical Center - Cancer Center | United States | 14 | 4 | Low
798 | NCT06567015 | NCT06567015-S03 | Shanghai East Hospital, Tongji University | China | 20 | 6 | Low
799 | NCT06567015 | NCT06567015-S04 | Tianjin Medical University Cancer Institute and Hospital | China | 14 | 5 | Low
800 | NCT06567015 | NCT06567015-S05 | Centre Léon Bérard | France | 35 | 9 | Low
801 | NCT06567015 | NCT06567015-S06 | CHU Hôpital de la Timone | France | 26 | 8 | Low
802 | NCT06567015 | NCT06567015-S07 | Institut de Cancérologie de l'Ouest (ICO) - René Gauducheau | France | 26 | 10 | Low
803 | NCT06567015 | NCT06567015-S08 | Institut Universitaire du Cancer de Toulouse - Oncopole | France | 13 | 4 | Low
804 | NCT05655078 | NCT05655078-S01 | East Sussex Healthcare NHS Trust - Eastbourne Hospital | United Kingdom | 10 | 4 | Low
805 | NCT05655078 | NCT05655078-S02 | East Sussex Healthcare NHS Trust - Conquest Hospital | United Kingdom | 24 | 6 | Low
806 | NCT05655078 | NCT05655078-S03 | Royal Berkshire Hospital | United Kingdom | 30 | 7 | Low
807 | NCT05655078 | NCT05655078-S04 | Southend University Hospital | United Kingdom | 13 | 3 | Low
808 | NCT05655078 | NCT05655078-S05 | Queen Alexandra Hospital | United Kingdom | 20 | 7 | Low
809 | NCT05655078 | NCT05655078-S06 | Queen Elizabeth Hospital, King's Lynn | United Kingdom | 24 | 7 | Low
810 | NCT05655078 | NCT05655078-S07 | Furness General Hospital | United Kingdom | 13 | 5 | Low
811 | NCT05655078 | NCT05655078-S08 | Betsi Cadwaladr University Health Board -Glan Clwyd Hospital | United Kingdom | 14 | 4 | Low
812 | NCT06793189 | NCT06793189-S01 | Shanghai Ruijin Hospital | China | 46 | 7 | Low
813 | NCT06793189 | NCT06793189-S02 | Affiliated First Hospital of China Medical University | China | 59 | 10 | Low
814 | NCT06793189 | NCT06793189-S03 | Peking University Third Hospital | China | 40 | 6 | Low
815 | NCT05506410 | NCT05506410-S01 | Department of Oncology, The First Affiliated Hospital of Zhengzhou University | China | 100 | 70 | Low
816 | NCT06246110 | NCT06246110-S01 | Southern Cancer Care | United States | 13 | 11 | Medium
817 | NCT06246110 | NCT06246110-S02 | Ironwood Cancer and Research Center | United States | 6 | 5 | Medium
818 | NCT06246110 | NCT06246110-S03 | California Cancer Care Associates for Research & Excellence | United States | 9 | 7 | Low
819 | NCT06246110 | NCT06246110-S04 | California Research Institute | United States | 10 | 7 | Low
820 | NCT06246110 | NCT06246110-S05 | University of Southern California, Norris Comprehensive Cancer Center | United States | 8 | 5 | Low
821 | NCT06246110 | NCT06246110-S06 | Providence St Joseph Hospital, Center for Cancer Prevention and Treatment | United States | 8 | 7 | Medium
822 | NCT06246110 | NCT06246110-S07 | Sutter Health Institute for Medical Research | United States | 8 | 6 | Low
823 | NCT06246110 | NCT06246110-S08 | Rocky Mountain Cancer | United States | 8 | 7 | Medium
824 | NCT06945120 | NCT06945120-S01 | Dana-Farber Cancer Institute | United States | 25 | 0 | Low
825 | NCT06945120 | NCT06945120-S02 | University of Massachusetts-Boston | United States | 25 | 0 | Low
826 | NCT05133843 | NCT05133843-S01 | Heart Center Leipzig at University of Leipzig Department of Internal Medicine/Cardiology | Germany | 50 | 41 | Medium
827 | NCT06916520 | NCT06916520-S01 | Amsterdam UMC | Netherlands | 300 | 12 | Low
828 | NCT06435585 | NCT06435585-S01 | Karolinska University hospital | Sweden | 5000 | 2480 | Low
829 | NCT07286643 | NCT07286643-S01 | PGIMER Chandigarh | India | 140 | 5 | Low
830 | NCT06992089 | NCT06992089-S01 | Hospital Clínico de la Comunidad Valenciana | Spain | 30 | 15 | Low
831 | NCT03586518 | NCT03586518-S01 | University Hospitals of Leicester NHS Trust | United Kingdom | 9 | 0 | Low
832 | NCT06906276 | NCT06906276-S01 | Karolinska Institutet | Sweden | 30 | 8 | Low
833 | NCT07213648 | NCT07213648-S01 | Univeristy of Virginia School of Nursing | United States | 136 | 12 | Low
834 | NCT06893055 | NCT06893055-S01 | Department of Neurology and Centre of Clinical Neuroscience First Faculty of Medicine, Charles University and General University Hospital in Prague | Czechia | 90 | 45 | Low
835 | NCT07032350 | NCT07032350-S01 | College of Nursing | United States | 60 | 8 | Low
836 | NCT04786821 | NCT04786821-S01 | sheffield teching hospital NHS foundation trust | United Kingdom | 24 | 24 | High
837 | NCT06426316 | NCT06426316-S01 | CHU de Clermont-Ferrand - Service de Neurologie | France | 396 | 0 | Low
838 | NCT06106893 | NCT06106893-S01 | Wuhan Union Hospital | China | 15 | 12 | Medium
839 | NCT03003572 | NCT03003572-S01 | CH Pierre Oudot | France | 44 | 38 | Medium
840 | NCT03003572 | NCT03003572-S02 | CHU Estaing - Clermont Ferrand | France | 26 | 25 | Medium
841 | NCT03003572 | NCT03003572-S03 | CHU Grenoble Alpes | France | 11 | 14 | High
842 | NCT03003572 | NCT03003572-S04 | Hôpital de la Croix Rousse | France | 12 | 13 | High
843 | NCT03003572 | NCT03003572-S05 | CH Lyon Sud | France | 12 | 15 | High
844 | NCT03003572 | NCT03003572-S06 | Hôpital Edouard Herriot - CHU Lyon | France | 22 | 27 | High
845 | NCT03003572 | NCT03003572-S07 | CHU Reims | France | 39 | 31 | Low
846 | NCT03003572 | NCT03003572-S08 | Chu Saint-Etienne | France | 19 | 22 | High
847 | NCT06618573 | NCT06618573-S01 | Rumah Sakit Dr Hasan Sadikin, Universitas Padjadjaran | Indonesia | 60 | 60 | High
848 | NCT05470569 | NCT05470569-S01 | Lucila Garcia | Argentina | 1500 | 1270 | Medium
849 | NCT06771427 | NCT06771427-S01 | Ching-Mao | Taiwan | 220 | 128 | Low
850 | NCT06513429 | NCT06513429-S01 | Peking Universitiy Third Hospital | China | 6 | 0 | Low
851 | NCT04624490 | NCT04624490-S01 | University of Kansas Medical Center | United States | 260 | 143 | Low
852 | NCT05720325 | NCT05720325-S01 | Biogenics Research Chamber | United States | 52 | 49 | Medium
853 | NCT05720325 | NCT05720325-S02 | University of Texas Health Science Center at San Antonio | United States | 36 | 33 | Medium
854 | NCT06903897 | NCT06903897-S01 | (Benedict) UMass Memorial Medical Center - Adult Primary Care | United States | 21467 | 1370 | Low
855 | NCT06903897 | NCT06903897-S02 | UMass Memorial Medical Center - Hahnemann Campus | United States | 22373 | 1955 | Low
856 | NCT06903897 | NCT06903897-S03 | Family Health Center of Worcester | United States | 24160 | 1903 | Low
857 | NCT06441812 | NCT06441812-S01 | West China Hospital of Sichuan University | China | 200 | 116 | Low
858 | NCT07476703 | NCT07476703-S01 | Cardiovascular Research Lab, Dept Cardiology, Danderyd University Hospital | Sweden | 1400 | 942 | Low
859 | NCT07288554 | NCT07288554-S01 | The Second Hospital of Anhui Medical Univesity | China | 8 | 0 | Low
860 | NCT07288554 | NCT07288554-S02 | The third affiliated hosptial of Guangzhou Medical University | China | 8 | 0 | Low
861 | NCT07288554 | NCT07288554-S03 | The First Affiliated Hospital of Guangdong Medical University | China | 8 | 0 | Low
862 | NCT07288554 | NCT07288554-S04 | Jiangmen Central Hospital | China | 8 | 0 | Low
863 | NCT07288554 | NCT07288554-S05 | Qingyuan People's Hospital | China | 8 | 0 | Low
864 | NCT07288554 | NCT07288554-S06 | The First People's Hospital of Xinxiang City | China | 8 | 0 | Low
865 | NCT07288554 | NCT07288554-S07 | Yichang Central People's Hospital | China | 8 | 0 | Low
866 | NCT07288554 | NCT07288554-S08 | The Affiliated Hospital of Xuzhou Medical University | China | 12 | 0 | Low
867 | NCT06940531 | NCT06940531-S01 | Manchester Adult Cystic Fibrosis Centre | United Kingdom | 23 | 3 | Low
868 | NCT06940531 | NCT06940531-S02 | Birmingham Heartlands Hospital | United Kingdom | 58 | 5 | Low
869 | NCT06940531 | NCT06940531-S03 | Blackpool Teaching Hospitals | United Kingdom | 35 | 3 | Low
870 | NCT06940531 | NCT06940531-S04 | Medical Research Unit, Bristol Royal Infirmary | United Kingdom | 23 | 2 | Low
871 | NCT06940531 | NCT06940531-S05 | Cardiff and Vale University Health Board | United Kingdom | 46 | 3 | Low
872 | NCT06940531 | NCT06940531-S06 | Royal Devon and Exeter Hospital (Wonford) | United Kingdom | 58 | 4 | Low
873 | NCT06940531 | NCT06940531-S07 | NHS Greater Glasgow and Clyde | United Kingdom | 23 | 2 | Low
874 | NCT06940531 | NCT06940531-S08 | Leeds Adult CF Centre | United Kingdom | 34 | 3 | Low
875 | NCT05341453 | NCT05341453-S01 | Kamila Řasová | Czechia | 16 | 13 | Medium
876 | NCT05504837 | NCT05504837-S01 | University of Florida, Gainesville | United States | 2 | 2 | High
877 | NCT05504837 | NCT05504837-S02 | St. Lukes CF Center of Idaho | United States | 4 | 3 | Low
878 | NCT05504837 | NCT05504837-S03 | The Cystic Fibrosis Institute | United States | 2 | 2 | High
879 | NCT05504837 | NCT05504837-S04 | New York Medical College/ Boston Children's Health Physicians | United States | 6 | 4 | Low
880 | NCT05504837 | NCT05504837-S05 | Northwell Health Physicians | United States | 4 | 4 | High
881 | NCT05504837 | NCT05504837-S06 | Atrium Health Wake Forest Baptist Medical Center | United States | 2 | 2 | High
882 | NCT06152302 | NCT06152302-S01 | Infantile neuromuscular unity - Department of paediatric neurological care and intentive care unity, Raymond Poincaré Hospital - APHP | France | 15 | 8 | Low
883 | NCT05200429 | NCT05200429-S01 | British Columbia Children's Hospital | Canada | 348 | 270 | Low
884 | NCT05200429 | NCT05200429-S02 | St Paul's Hospital | Canada | 152 | 143 | Medium
885 | NCT06528418 | NCT06528418-S01 | The First Affiliated Hospital of Guangzhou Medical University | China | 10000 | 0 | Low

## Lessons Learned
id | protocol_id | category | description
215 | NCT06567015 | Operations | Protocol eligibility criteria restricted enrollment to 32%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
216 | NCT05655078 | Operations | Protocol eligibility criteria restricted enrollment to 29%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
217 | NCT06793189 | Operations | Protocol eligibility criteria restricted enrollment to 16%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
218 | NCT05506410 | Operations | Protocol eligibility criteria restricted enrollment to 70%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
219 | NCT06246110 | Operations | Protocol eligibility criteria restricted enrollment to 79%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
220 | NCT05133843 | Operations | Enrollment reached 82% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
221 | NCT06916520 | Operations | Protocol eligibility criteria restricted enrollment to 4%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
222 | NCT06435585 | Operations | Protocol eligibility criteria restricted enrollment to 50%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
223 | NCT07286643 | Operations | Protocol eligibility criteria restricted enrollment to 4%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
224 | NCT06992089 | Operations | Protocol eligibility criteria restricted enrollment to 50%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
225 | NCT06906276 | Operations | Protocol eligibility criteria restricted enrollment to 27%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
226 | NCT07213648 | Operations | Protocol eligibility criteria restricted enrollment to 9%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
227 | NCT06893055 | Operations | Protocol eligibility criteria restricted enrollment to 50%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
228 | NCT07032350 | Operations | Protocol eligibility criteria restricted enrollment to 13%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
229 | NCT04786821 | Operations | Enrollment exceeded target in Neurology; strong site engagement and pre-screening drove performance. Site coordinator training and regular performance reviews were key drivers of patient retention.
230 | NCT06106893 | Operations | Enrollment reached 80% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
231 | NCT03003572 | Operations | Enrollment exceeded target in Immunology; strong site engagement and pre-screening drove performance. Site coordinator training and regular performance reviews were key drivers of patient retention.
232 | NCT06618573 | Operations | Enrollment exceeded target in Immunology; strong site engagement and pre-screening drove performance. Site coordinator training and regular performance reviews were key drivers of patient retention.
233 | NCT05470569 | Operations | Enrollment reached 85% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
234 | NCT06771427 | Operations | Protocol eligibility criteria restricted enrollment to 58%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
235 | NCT04624490 | Operations | Protocol eligibility criteria restricted enrollment to 55%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
236 | NCT05720325 | Operations | Enrollment reached 93% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
237 | NCT06903897 | Operations | Protocol eligibility criteria restricted enrollment to 8%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
238 | NCT06441812 | Operations | Protocol eligibility criteria restricted enrollment to 58%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
239 | NCT07476703 | Operations | Protocol eligibility criteria restricted enrollment to 67%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
240 | NCT06940531 | Operations | Protocol eligibility criteria restricted enrollment to 8%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
241 | NCT05341453 | Operations | Enrollment reached 81% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
242 | NCT05504837 | Operations | Enrollment reached 85% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.
243 | NCT06152302 | Operations | Protocol eligibility criteria restricted enrollment to 53%; recommend broadening at design stage. Site coordinator training and regular performance reviews were key drivers of patient retention.
244 | NCT05200429 | Operations | Enrollment reached 83% of target. Earlier site activation would have closed the gap. Site coordinator training and regular performance reviews were key drivers of patient retention.